## To publish
Customer | Project name | Connection location (substation or circuit) | Max MW | Connection voltage | Technology | Transpower stage |  | Stage % complete | Prior month | Status | Estimated connection livening date
Far North Solar Farm | Solar farm at Waiotahe | Waiotahe | 58 | 33 | Solar | Delivery |  | 90% | 90% | Construction | 2025-04-01
Mercury | Karapiro Runback Scheme | Karapiro | 0 | 110 | Hydro | Delivery |  | 90% | 90% | Livened | 2025-01-01
Manawa Energy | Coleridge runback scheme | Coleridge | 0 | 66 | Hydro | Delivery |  | 80% | 80% | Construction | 2025-06-01
Harmony Energy | Tauhei Solar Farm | Waihou | 200 | 110 | Solar + BESS | Delivery |  | 80% | 80% | Construction | 2025-06-01
Harmony Energy | Waihou Solar Farm | Waihou | 100 | 33 | Solar + BESS | Delivery |  | 80% | 80% | Construction | 2026-07-01
Helios BOP Op LP | Solar farm at Edgecumbe | Edgecumbe | 115 | 33 | Solar | Delivery |  | 60% | 60% | Detailed design | 2026-06-01
Contact Energy | Glenbrook BESS | Glenbrook | 100 | 33 | BESS | Delivery |  | 60% | 50% | Construction | 2025-06-01
Todd Generation | Te Rahui Solar Farm | WRK_WHI | 400 | 220 | Solar | Delivery |  | 50% | 50% | Construction | 2026-03-01
Horizon | FNSF Omeheu Solar farm | Edgecumbe | 29 | 33 | Solar | Delivery |  | 50% | 50% | Construction | 2025-09-01
Far North Solar Farm | The Point Solar Farm | BEN_ISL-A | 300 | 220 | Solar | Delivery |  | 40% | 40% | Detailed design | 2027-06-01
Dannevirke Solar Farm | Solar at Dannevirke | Dannevirke | 25 | 11 | Solar | Delivery |  | 30% | 30% | Detailed design | 2025-12-01
Eastland Generation | TOPP 2 Geothermal | Kawerau | 55 (26)! | 220 | Geothermal | Delivery |  | 10% | 0% | Construction | 2025-08-01
Waikato Solar Farms | Solar Farm at Waerenga | HLY_OTA | 314 | 220 | Solar | Delivery |  | 5% | 5% | Not started | TBC
Waikato Solar Farms | Solar farm at Rangiriri West | OTA_WKM | 214 | 220 | Solar | Delivery |  | 5% | 5% | Not started | TBC
Mainpower | Mt Cass windfarm | Waipara | 93 | 66 | Wind | Delivery |  | 5% | 5% | On hold | TBC
|  | Connection location (substation or circuit) | Max MW | Connection voltage | Technology | Transpower stage |  | Stage % complete | Prior month | Status | Estimated TP scope completion date
|  | Greytown | 158 | 110 | Solar | Investigation |  | 95% | 95% | Contracting | Complete
|  | Masterton | 91 | 33 | Solar + BESS | Investigation |  | 90% | 80% | Contracting | Complete
|  | NMA_TMH_A | 155 | 220 | Wind | Investigation |  | 90% | 90% | Contracting | Complete
|  | Masterton | 100 | 110 | Solar + BESS | Investigation |  | 80% | 80% | Early stage design | TBA
|  | HEN_MDN | 200 | 220 | Solar | Investigation |  | 70% | 70% | Early stage design | TBA
|  | Ohau A | 222 | 220 | Solar | Investigation |  | 70% | 70% | Early stage design | TBA
|  | BPE_LTN | 126 | 220 | Wind | Investigation |  | 70% | 60% | Early stage design | TBA
|  | Huntly | 100 | 220 | BESS | Investigation |  | 70% | 70% | Early stage design | TBA
|  | Te Mihi | 190 (132)! | 220 | Geothermal | Investigation |  | 70% | 70% | Early stage design | TBA
|  | MGM_MST | 90 | 110 | Wind | Investigation |  | 60% | 60% | Early stage design | TBA
|  | Stratford | 32 | 33 | Solar | Investigation |  | 50% | 50% | Early stage design | TBA
|  | Marton | 50 | 110 | Solar + BESS | Investigation |  | 40% | 40% | Early stage design | TBA
|  | Opunake | 77 | 110 | Solar + BESS | Investigation |  | 40% | 40% | Early stage design | TBA
|  | Bunnythorpe | 300 | 220 | Solar + BESS | Investigation |  | 40% | 40% | Early stage design | TBA
|  | Huirangi | 75 | 110 | Solar + BESS | Investigation |  | 40% | 40% | Early stage design | TBA
|  | Huirangi | 68 | 33 | Solar + BESS | Investigation |  | 30% | 30% | Early stage design | TBA
|  | Twizel | 350 | 220 | Solar | Investigation |  | 30% | 30% | Early stage design | TBA
|  | Tangiwai | 110 | 220 | Solar + BESS | Investigation |  | 30% | 30% | Early stage design | TBA
|  | Hinuera | 80 | 33 | Solar + BESS | Investigation |  | 30% | 30% | Early stage design | TBA
|  | Waipawa (South) | 100 | 110 | Solar + BESS | Investigation |  | 30% | 30% | Early stage design | TBA
|  | HOR_ISL | 100 | 66 | Solar + BESS | Investigation |  | 30% | 30% | Early stage design | TBA
|  | Dannevirke | 72 | 110 | Solar + BESS | Investigation |  | 30% | 30% | Early stage design | TBA
|  | CHH_TWZ | 300 | 220 | Solar | Investigation |  | 20% | 20% | Early stage design | TBA
|  | Waipawa (North) | 100 | 110 | Solar + BESS | Investigation |  | 20% | 20% | Early stage design | TBA
|  | BPE_WRK_1, BPE_TNG_1 | 250 | 220 | Wind | Investigation |  | 20% | 15% | Early stage design | TBA
|  | HLY_DEV | 300 | 220 | Solar | Investigation |  | 10% | 10% | Early stage design | TBA
|  | Waipawa (South) | 43 | 33 | Solar | Investigation |  | 10% | 10% | Early stage design | TBA
|  | ROX_ISL_A | 450 | 220 | Solar + BESS | Investigation |  | 10% | 10% | Early stage design | TBA
|  | WHU_WKO | 157 | 110 | Wind | Investigation |  | 10% | 5% | Early stage design | TBA
|  | Argyle | 75 | 110 | Solar | Investigation |  | 10% | 5% | Early stage design | TBA
|  | NMA_TMH_A | 300 | 220 | Wind | Investigation |  | 10% | 10% | Early stage design | TBA
|  | HEN_MDN | 120 | 220 | Solar | Investigation |  | 5% | 5% | Early stage design | TBA
|  | Kikiwa | 100 | 220/110 | Solar | Investigation |  | 0% | 0% | Early stage design | TBA
|  | Marton | 25 | 33 | Solar | Investigation |  | 0% | 0% | Starting this month | TBA
|  | Marton | 29 | 33 | Solar | Investigation |  | 0% | 0% | Starting this month | TBA
|  | ISL_KIK | 200 | 220 | Solar | Investigation |  | 0% | - | New this month | TBA
|  | NMA_TMH_A | 330 | 220 | Wind | Investigation |  | 0% | - | New this month | TBA
|  | Waitaki/ LIV_WTK | 130 | 220/110 | Wind | Investigation |  | 0% | - | New this month | TBA
|  | Naseby | 300 | 220 | Solar + BESS | Investigation |  | 20% | 20% | On hold | TBA
|  | Opunake | 86 | 33 | Solar | Investigation |  | 0% | 0% | On hold | TBA
|  | Connection location (substation or circuit) | Max MW | Connection voltage | Technology | Transpower stage | Sequence number |  |  | Status | Estimated date to progress to investigation
|  | BPE_HAY | 180 | 220 | Solar | Application | 1 |  |  | Confirmed | 2025-04-01
|  | Waipara | 120 | 220/66 | Solar | Application | 2 |  |  | Confirmed | 2025-04-01
|  | Mangamaire | 50 | 33/110 | Wind | Application | 3 |  |  | Confirmed | 2025-04-01
|  | ISL_KIK | 600 | 220 | Solar + BESS | Application | 4 |  |  | Confirmed | 2025-05-01
|  | Whakamaru (North) | 300 | 220 | Solar + BESS | Application | 5 |  |  | Confirmed | 2025-05-01
|  | MGM_MST (110kV) / Linton (220kV) | 100 | 220/110 | Wind | Application | 6 |  |  | Confirmed | 2025-06-01
|  | Wellsford | 88 | 110 | Solar + BESS | Application | 7 |  |  | Confirmed | 2025-06-01
|  | Glenbrook | 280 | 33 | BESS | Application | 8 |  |  | Confirmed | 2025-06-01
|  | ISL_KIK | 200 | 220 | Solar + BESS | Application | 9 |  |  | Confirmed | Jul-Sep 25
|  | Glenbrook | 80 | 33 | Wind | Application | 10 |  |  | Confirmed | Jul-Sep 25
|  | Ohinewai | 300 | 220 | Wind | Application | 11 |  |  | Confirmed | Jul-Sep 25
|  | Mangahao | 30 | 33 | Solar | Application | 12 |  |  | Confirmed | Jul-Sep 25
|  | Edendale | 150 | 110 | Wind | Application | 13 |  |  | Confirmed | Jul-Sep 25
|  | Tangiwai | 120 | 220 | Solar + BESS | Application | 14 |  |  | Confirmed | Jul-Sep 25
|  | BRK_SFD | 750 | 220 | Solar + Wind | Application | 15 |  |  | Confirmed | Jul-Sep 25
|  | BRK_SFD_A | 200 | 220 | Wind | Application | 16 |  |  | Confirmed | Jul-Sep 25
|  | ISL_KIK | 310 | 220 | Solar + BESS | Application | 17 |  |  | Confirmed | Oct-Dec 25
|  | Bunnythorpe | 525 | 220 | Solar + BESS | Application | 18 |  |  | Confirmed | Oct-Dec 25
|  | Piako | 110 | 33 | Solar | Application | 19 |  |  | Confirmed | Oct-Dec 25
|  | MDN_MPE / MSD_HPI | 120 | 110/220 | Wind | Application | 20 |  |  | Confirmed | Oct-Dec 25
|  | BPE_WKM | 500 | 220 | Solar | Application | 21 |  |  | Confirmed | Oct-Dec 25
|  | HLY_TMN / HLY_SFD | 315 | 220 | Wind | Application | 22 |  |  | Confirmed | Oct-Dec 25
|  | HWB_ROX | 165 | 110 | Wind | Application | 23 |  |  | Confirmed | Oct-Dec 25
|  | HLY_SFD, HLY_TWH | 400 | 220 | Wind + BESS | Application | 24 |  |  | Confirmed | Jan-Mar 26
|  | BPE_BRK | 200 | 220 | Solar + BESS | Application | 25 |  |  | Confirmed | Jan-Mar 26
|  | BEN_ISL-A | 180 | 220 | Solar + BESS | Application | 26 |  |  | Confirmed | Jan-Mar 26
|  | ISL-TKB-1, TKB | 250 | 220 | Solar | Application | 27 |  |  | Confirmed | Jan-Mar 26
|  | Kaikohe | 50 | 110 | Various | Application | 28 |  |  | Confirmed | Jan-Mar 26
|  | Linton | 230 | 220 | Wind | Application | 29 |  |  | Confirmed | Jan-Mar 26
|  | Mangamaire | 40 | 33 | Solar | Application | 30 |  |  | Confirmed | Jan-Mar 26
|  | EDG-TRK | 56 | 110/220 | Hydro + Geothermal | Application | 31 |  |  | Confirmed | Apr-Jun 26
|  | NSY_ROX-1 | 220 | 220 | Solar + BESS | Application | 32 |  |  | Received | TBC
Notes
1. The location is given as the substation where a project will connect, or if a new substation is required, the transmission circuit.
2. This list includes generation projects requiring new or upgraded Transpower assets; generation projects connecting to an electricity distribution network and not requiring new or upgraded Transpower assets are not shown.
3. Sequence numbers (for investigations and applications) will be updated as and when projects move to a new stage or are withdrawn; or if a customer with two or more projects with consecutive sequence numbers prioritises a project with a higher number.
4. An Applications sequence number indicates the order in which Transpower will allocate internal resources to new connection investigations and the order in which Transpower will allocate physical assets (spare Transpower transmission assets and land) at the proposed point of connection. An accepted connection application does not guarantee access to transmission capacity beyond the point of connection and does not guarantee the project will proceed to commissioning. For investigations the sequence number indicates the order in which projects entered the investigation stage. Investigations can move into delivery when the investigation is complete, the sequence number will not apply to this transition.
5. Stage % Complete - Approximate progress of the project through the relevant stage based on duration in weeks through the project schedule. Does not accound for effort variance across different tasks. Progress in delivery is progress for the Transpower connection only, not for the associated generation. Timeframes for delivery contracting will vary as they are dependent on bilateral negotiation and each customer's investment decision process. Progress is dependent on both Transpower work and customer decisions at key stage gates. Where customers are unable to make timely decisions progress may stall. Stalled projects may be put on hold so resources can be re-allocated to other waiting projects.
! - Max MW value includes existing generation of () MW as part of the new connection
* - Progressed based on no requirement for new Transpower capital assets for this connection, similar to the treatment of embedded generation connections with no requirement for new Transpower capital assets
^ - Multple applications merged into a single (more efficient) connection