## Sheet1
Customer | Project name | Region | Connection location (substation or circuit) | Type | Transpower stage | Max MW | Status Flag | Stage % complete | Status | Estimated connection livening date | Key
Vector Limited | Amazon Data Centre Connection at Henderson | Auckland | Henderson | New feeder | Delivery | 20 | ● | 100% | Livened | 2025-08-01 | Type | Description
Powerco Limited | Waverley ODID TWA | Taranaki | Waverley | Lifecycle | Delivery | 0 | ● | 95% | Construction | 2025-10-01 | New feeder | New feeder(s) at an existing substation to supply new load or to increase supply resilience
Unison Networks Limited | Additional 33kV Feeders at Whakatu GXP TWA | Hawkes Bay | Whakatu | New feeder | Delivery | 20 | ● | 95% | Construction | 2025-05-01 | New transformer | New or upgraded transformer(s) at an existing to supply new load or to increase supply resilience
MainPower New Zealand Limited | Kaiapoi IDID Upgrade TWA | Canterbury | Kaiapoi | New feeder | Delivery | 0 | ● | 90% | Construction | 2025-11-01 | New GXP | New Grid exit Point (GXP) substation or new load supply point at an existing non GXP substation
Powerco Limited | Te Matai T1 Transformer Replacement | Bay of Plenty | Te Matai | Lifecycle | Delivery | 20 | ● | 90% | Construction | 2025-08-01 | Transmission | New or upgraded transmission assets (overhead transmission lines or underground cables) to increase transmission capacity or resilience
Horizon Networks | Waiotahe 11-33kV Transition TWA | Bay of Plenty | Waiotahe | New feeder | Delivery | 20 | ● | 80% | Construction | 2025-11-01 | Protection and automation | New or replacement protection or automation systems
Powerco Limited | Greytown ODID TWA | Wellington | Greytown | Lifecycle | Delivery | 50 | ● | 80% | Detailed design | 2026-01-01 | Relocation | Relocation of existing transmission assets
Centralines Limited | Waipawa 33kV ODID Conversion TWA | CNI | Waipawa | Lifecycle | Delivery | 0 | ● | 70% | Construction | 2025-07-01 | Lifecycle | Replacement of transmission assets with modern equivalent either at end of life or for policy reasons
Powerco Limited | MTN ODID TWA | CNI | Marton | Lifecycle | Delivery | 0 | ● | 70% | Detailed design | 2026-11-01 | Other | Asset divestments, reconfigurations or other work not included in the above categories
New Zealand Steel Limited | Glenbrook Arc Furnace | Auckland | Glenbrook | New feeder | Delivery | 80 | ● | 70% | Construction | 2025-09-01
Vector Limited | Second 220/33 kV supply transformer at Wairau Road | Auckland | Wairau Road | New transformer | Delivery | 150 | ● | 50% | Detailed design | 2026-12-01 | Max MW | Maximum additional supply capacity enabled by the project (actual demand may step change or grow slowly over many years to utilise this new capacity)
Aurora / Powernet | CML-FKN TTU TWA | Otago | CML-FKN-A | Transmission | Delivery | 20 | ● | 50% | Detailed design | 2026-05-01 |  | Where two or more projects suport the same supply capacity increase some projects Max MW may be set to zero to avoid double counting
PowerNet Limited | Edendale 220kV GXP | Otago-Southland | NMA-TMH / Edendale | New GXP | Delivery | 120 | ● | 30% | Detailed design | 2027-08-01
Drury South Limited | Drury Line Relocation | Auckland | HLY-OTA | Relocation | Delivery | 0 | ● | 20% | Detailed design | 2027-02-01 | Stage % Complete | Approximate progress of the project through the relevant stage based on completed project milestones in the project schedule
Fonterra Co-operative Group Limited | Whareroa Decarbonisation Options | Taranaki | BRK-SFD | New GXP | Delivery | 120 | ● | 20% | Detailed design | 2026-06-01
|  | Region | Connection location (substation or circuit) | Type | Transpower stage | Max MW | Status Flag | Stage % complete | Status | Estimated TP scope completion date | Status flag key
|  | Auckland | MNG-ROS-A | Relocation | Investigation | 0 | ● | 100% | On hold | TBA | ● Progressing normally
|  | Auckland | Huapai | New GXP | Investigation | 30 | ● | 95% | On hold | TBA | ●C Awaiting customer action
|  | Auckland | Takanini | New feeder | Investigation | 20 | ●C | 95% | Contracting | TBA | ●T Awaiting Transpower action
|  | Auckland | Takanini | New feeder | Investigation | 30 | ●C | 95% | Contracting | TBA | ● On hold
|  | Auckland | Henderson | New Feeder | Investigation | 20 | ● | 95% | Contracting | TBA
|  | Sth Canterbury | Timaru | New transformer | Investigation | 40 | ● | 90% | Contracting | TBA
|  | South Canterbury | ROX-ISL-A / Black Point | New GXP | Investigation | 80 | ●C | 85% | Contracting | TBA
|  | Northland | Maungaturoto | Other | Investigation | 0 | ● | 85% | Contracting | TBA
|  | Nelson Marlborough | KIK-STK A | New GXP | Investigation | 60 | ● | 85% | Contracting | TBA
|  | Auckland | Bombay | New transformer | Investigation | 50 | ● | 85% | Early stage design | TBA
|  | CNI | Brunswick | New transformer | Investigation | 30 | ● | 70% | Early stage design | TBA
|  | Wellington | KHD-TKR | Line | Investigation | 0 | ● | 70% | Early stage design | TBA
|  | Wellington | Central Park | New GXP | Investigation | 150 | ●T | 50% | Early stage design | TBA
|  | Auckland | Silverdale | New feeder | Investigation | 36 | ●T | 50% | Contracting | TBA
|  | Auckland | Silverdale | New feeder | Investigation | 30 | ●T | 50% | Contracting | TBA
|  | Waikato | ARI-HAM | Relocation | Investigation | 0 | ●C | 40% | Early stage design | TBA
|  | Auckland | Wiri | New transformer | Investigation | 120 | ● | 39% | Early stage design | TBA
|  | Bay of Plenty | Tarukenga | New transformer | Investigation | 20 | ● | 30% | On hold | TBA
|  | Waikato | Bombay | Other | Investigation | 0 | ● | 30% | Early stage design | TBA
|  | Auckland | Southdown | New GXP | Investigation | 80 | ●C | 30% | Early stage design | TBA
|  | Auckland | HLY-OTA-A | Relocation | Investigation | 0 | ● | 30% | Early stage design | TBA
|  | Canterbury | Ashley | New feeder | Investigation | 40 | ● | 22% | Early stage design | TBA
|  | Auckland | Wellsford | New Transformer | Investigation | 60 | ● | 15% | Early stage design | TBA
|  | Northland | Bream Bay | New GXP | Investigation | 330 | ●C | 14% | Early stage design | TBA
|  | Auckland | Henderson | New Feeder | Investigation | 0 | ● | 14% | Early stage design | TBA
|  | Auckland | Henderson | New Feeder | Investigation | 0 | ● | 14% | Early stage design | TBA
|  | Auckland | Henderson | New Transformer | Investigation | 120 | ● | 14% | Early stage design | TBA
|  | Bay of Plenty | KMO-TRK | New GXP | Investigation | 120 | ● | 14% | Early stage design | TBA
|  | CNI | BPE-WIL | New GXP | Investigation | 120 | ● | 12% | On hold | TBA
|  | Otago-Southland | Cromwell | Protection & Automation | Investigation | 0 | ● | 12% | Early stage design | TBA
|  | Waikato | HAM-MER | Relocation | Investigation | 0 | ● | 11% | On hold | TBA
|  | Waikato | HAM_WHU | Relocation | Investigation | 0 | ● | 11% | Early stage design | TBA
|  | Waikato | Waikino | New feeder | Investigation | 40 | ● | 10% | Early stage design | TBA
|  | Waikato | ARI-HAM | Relocation | Investigation | 0 | ●C | 8% | Early stage design | TBA
|  | Otago-Southland | North Makarewa | New Transformer | Investigation | 60 | ● | 8% | On hold | TBA
|  | Auckland | ALB-WRD | New GXP | Investigation | 120 | ● | 8% | Early stage design | TBA
|  | Bay of Plenty | Edgecumbe | New Feeder | Investigation | 42 | ● | 8% | Early stage design | TBA
|  | Auckland | HOB-WRD | Relocation | Investigation | 0 | ● | 8% | Early stage design | TBA
|  | Otago-Southland | Clyde-Twizel-1 or 2 | New GXP | Investigation | 120 | ● | 8% | Early stage design | TBA
|  | Waikato | Hinuera | Divestment | Investigation | 0 | ● | 8% | Early stage design | TBA
|  | Otago-Southland | Cromwell | Transmission | Investigation | 120 | ● | 8% | Early stage design | TBA
|  | Canterbury | Hororata | Other | Investigation | 0 | ● | 3% | Early stage design | TBA
|  | CNI | Mangamarie | Other | Investigation | 0 | ● | 3% | Early stage design | TBA
|  | Auckland | Takanini | New transformer | Investigation | 150 | ● | 2% | Starting | TBA
|  | Auckland | Penrose | New feeder | Investigation | 30 | ●T | 2% | Starting | TBA
|  | Region | Connection location (substation or circuit) | Type | Transpower stage | Max MW |  |  | Status
|  | Bay of Plenty | Te Matai | New transformer | Investigation Requested | 50 |  |  | Requested
|  | Auckland | Mangere | New transformer | Investigation Requested | 120 |  |  | Requested
|  | Otago-Southland | INV-MAN-A | New GXP | Investigation Requested | 300 |  |  | Requested
|  | Auckland | Silverdale | New Transformer | Investigation Requested | 120 |  |  | Requested
|  | Auckland | Penrose | New GXP | Investigation Requested | 150 |  |  | Requested
|  | Auckland | HEN-OTA | New GXP | Investigation Requested | 200 |  |  | Requested
|  | South Canterbury | CHC-TWZ, ROX-ISL-A | New GXP | Investigation Requested | 120 |  |  | Requested
|  | Canterbury | Hororata | Other | Investigation Requested | 0 |  |  | Requested
|  | West Coast | IGH-WMG / IGH-WPT | Relocation | Investigation Requested | 0 |  |  | Requested
|  | Auckland | Mangere | New feeder | Investigation Requested | 100 |  |  | Requested
|  | Canterbury | ISL-KIK | New GXP | Investigation Requested | 120 |  |  | Requested