## Sheet1
Customer | Project name | Region | Connection location (substation or circuit) | Type | Transpower stage | Max MW | Status Flag | Stage % complete | Status | Estimated connection livening date | Key
Powerco Limited | Waverley ODID | Taranaki | Waverley | Switchboard | Delivery |  | ● | 100% | Construction | 2026-03-31 | Type | Description
Powerco Limited | Te Matai T1 Transformer Replacement | Bay of Plenty | Te Matai | Transformer | Delivery | 20 | ● | 100% | Construction | 2026-03-31 | New feeder | New feeder(s) at an existing substation to supply new load or to increase supply resilience
Unison Networks Limited | Whakatu GXP 2x 33kV Feeders GXP | Hawkes Bay | Whakatu | Feeder | Delivery | 20 | ● | 100% | TP work complete | 2025-05-01 | New transformer | New or upgraded transformer(s) at an existing to supply new load or to increase supply resilience
MainPower New Zealand Limited | Kaiapoi IDID Upgrade | Canterbury | Kaiapoi | Switchboard | Delivery | 0 | ● | 90% | Construction | 2025-11-01 | New GXP | New Grid exit Point (GXP) substation or new load supply point at an existing non GXP substation
New Zealand Steel Limited | Glenbrook Arc Furnace | Auckland | Glenbrook | Process Heat - Other | Delivery | 80 | ● | 90% | TP work complete | 2025-10-30 | Transmission | New or upgraded transmission assets (overhead transmission lines or underground cables) to increase transmission capacity or resilience
Horizon Energy Distribution Limited | Waiotahe 11-33kV Transition | Bay of Plenty | Waiotahe | Switchboard | Delivery | 20 | ● | 85% | Construction | 2025-11-01 | Protection and automation | New or replacement protection or automation systems
Centralines Limited | Waipawa 33kV ODID Conversion | Central North Island | Waipawa | Switchboard | Delivery | 0 | ● | 80% | Construction | 2026-03-31 | Relocation | Relocation of existing transmission assets
Powerco Limited | Greytown ODID | Wellington | Greytown | Switchboard | Delivery | 50 | ● | 80% | Detailed Design | 2026-01-01 | Lifecycle | Replacement of transmission assets with modern equivalent either at end of life or for policy reasons
Powerco Limited | MTN ODID | Central North Island | Marton | Switchboard | Delivery | 0 | ● | 80% | Detailed Design | 2026-11-01 | Other | Asset divestments, reconfigurations or other work not included in the above categories
Aurora Energy Limited | CML-FKN Line TTU (Aurora) | Otago-Southland | CML-FKN-A | Conductor | Delivery | 20 | ● | 70% | Detailed Design | 2026-05-01
PowerNet Limited | CML-FKN Line TTU | Otago-Southland | CML-FKN-A | Conductor | Delivery | 20 | ● | 70% | Detailed Design | 2026-05-01 | Max MW | Maximum additional supply capacity enabled by the project (actual demand may step change or grow slowly over many years to utilise this new capacity)
Vector Limited | Wairau Road T9 Transformer | Auckland | Wairau Road | Transformer | Delivery | 150 | ● | 50% | Detailed Design | 2026-12-01 |  | Where two or more projects suport the same supply capacity increase some projects Max MW may be set to zero to avoid double counting
Network Tasman Limited | Brightwater GXP | Nelson-Marlborough | KIK-STK A | Substation | Delivery | 60 | ● | 40% | Detailed Design | 2028-05-31
PowerNet Limited | Puna Awa 220kV GXP | Otago-Southland | NMA-TMH / Edendale | Substation | Delivery | 120 | ● | 40% | Detailed Design | 2027-08-01 | Stage % Complete | Approximate progress of the project through the relevant stage based on completed project milestones in the project schedule
Fonterra Co-operative Group Limited | Whareroa Electrification (Ohangai Sub) | Taranaki | BRK-SFD | Process Heat - Dairy | Delivery | 120 | ● | 30% | Detailed Design | 2026-06-01
Vector Limited | Takanini 1x 33kV Feeder | Auckland | Takanini | Feeder | Delivery | 20 | ● | 30% | Detailed Design | 2026-04-09
Drury South Limited | Drury Line Relocation | Auckland | HLY-OTA | Non-Connected | Delivery | 0 | ● | 20% | Detailed Design | 2027-02-01
|  | Region | Connection location (substation or circuit) | Type | Transpower stage | Max MW | Status Flag | Stage % complete | Status | Estimated TP scope completion date
|  | Auckland | Takanini | Feeder | Investigation | 30 | ● | 98% | Investment Contract Negotiation | TBA | Status flag key
|  | South-Canterbury | Timaru | Transformer | Investigation | 40 | ● | 95% | Investment Contract Negotiation | TBA | ● Progressing normally
|  | Auckland | Huapai | Non-Connected | Investigation | 30 | ● | 95% | Investment Contract Negotiation | TBA | ●C Awaiting customer action
|  | Auckland | Henderson | Feeder | Investigation | 20 | ● | 95% | Investment Contract Negotiation | TBA | ●T Awaiting Transpower action
|  | Northland | Maungaturoto | Transaction | Investigation | 0 | ● | 94% | Investment Contract Negotiation | TBA | ● On hold
|  | Wellington | KHD-TKR | Conductor | Investigation | 0 | ● | 94% | Investment Contract Negotiation | TBA
|  | Bay of Plenty | Edgecumbe | Transformer | Investigation | 42 | ● | 92% | Investment Contract Negotiation | TBA
|  | Auckland | Silverdale | Feeder | Investigation | 36 | ● | 90% | Investment Contract Negotiation | TBA
|  | Canterbury | Ashley | Feeder | Investigation | 40 | ● | 90% | Investment Contract Negotiation | TBA
|  | Auckland | Silverdale | Feeder | Investigation | 30 | ●T | 90% | Investment Contract Negotiation | TBA
|  | Central North Island | Brunswick | Transformer | Investigation | 30 | ● | 90% | Investment Contract Negotiation | TBA
|  | South-Canterbury | ROX-ISL-A / Black Point | Substation | Investigation | 80 | ● | 85% | Early Stage Design | TBA
|  | Otago-Southland | Cromwell | Special Protection Scheme | Investigation | 30 | ● | 85% | Investment Contract Negotiation | TBA
|  | Auckland | Bombay | Switchboard | Investigation | 50 | ● | 85% | Early Stage Design | TBA
|  | Auckland | Wellsford | Transformer | Investigation | 60 | ● | 60% | Early Stage Design | TBA
|  | Waikato | Hinuera | Transaction | Investigation | 0 | ● | 50% | Early Stage Design | TBA
|  | Waikato | HAM_WHU | Non-Connected | Investigation | 0 | ● | 50% | Early Stage Design | TBA
|  | Auckland | Southdown | Substation | Investigation | 80 | ●C | 50% | Early Stage Design | TBA
|  | Auckland | Henderson | Transformer | Investigation | 120 | ● | 50% | Early Stage Design | TBA
|  | Auckland | HLY-OTA-A | Non-Connected | Investigation | 0 | ● | 50% | Early Stage Design | TBA
|  | Wellington | Central Park | Substation | Investigation | 150 | ●T | 50% | Early Stage Design | TBA
|  | Waikato | ARI-HAM | Non-Connected | Investigation | 0 | ●C | 40% | Early Stage Design | TBA
|  | Auckland | Wiri | Transformer | Investigation | 120 | ● | 39% | Early Stage Design | TBA
|  | Waikato | Waikino | Feeder | Investigation | 40 | ● | 38% | Early Stage Design | TBA
|  | Waikato | Bombay | Transaction | Investigation | 0 | ●C | 35% | Early Stage Design | TBA
|  | Bay of Plenty | Tarukenga | Transformer | Investigation | 20 | ● | 30% | Early Stage Design | TBA
|  | Auckland | HOB-WRD | Non-Connected | Investigation | 0 | ● | 20% | Early Stage Design | TBA
|  | Otago-Southland | Cromwell | Substation | Investigation | 120 | ● | 20% | Early Stage Design | TBA
|  | Central North Island | Mangamarie | Switchboard | Investigation | 0 | ● | 20% | Early Stage Design | TBA
|  | Otago-Southland | Cromwell | Conductor | Investigation | 120 | ● | 15% | Early Stage Design | TBA
|  | Bay of Plenty | KMO-TRK | Substation | Investigation | 120 | ● | 14% | Early Stage Design | TBA
|  | Auckland | Henderson | Feeder | Investigation | 30 | ● | 14% | Early Stage Design | TBA
|  | Auckland | Henderson | Feeder | Investigation | 30 | ● | 14% | Early Stage Design | TBA
|  | Auckland | Henderson | Feeder | Investigation | 30 | ● | 14% | Early Stage Design | TBA
|  | Auckland | Henderson | Feeder | Investigation | 30 | ● | 14% | Early Stage Design | TBA
|  | Auckland | ALB-WRD | Substation | Investigation | 120 | ● | 12% | Early Stage Design | TBA
|  | Auckland | Silverdale | Transformer | Investigation | 120 | ● | 12% | Early Stage Design | TBA
|  | Otago-Southland | Clyde-Twizel-1 or 2 | Substation | Investigation | 120 | ● | 11% | Early Stage Design | TBA
|  | Auckland | Penrose | Data Centre | Investigation | 150 | ● | 10% | Early Stage Design | TBA
|  | Auckland | Penrose | Feeder | Investigation | 30 | ● | 10% | Starting | TBA
|  | Bay of Plenty | Edgecumbe | Special Protection Scheme | Investigation | 30 | ● | 10% | Starting | TBA
|  | Otago-Southland | INV-MAN-A | Data Centre | Investigation | 300 | ● | 8% | Early Stage Design | TBA
|  | Canterbury | Hororata | Switchboard | Investigation | 0 | ● | 8% | Early Stage Design | TBA
|  | Bay of Plenty | Te Matai | Transformer | Investigation | 50 | ● | 8% | Early Stage Design | TBA
|  | Waikato | ARI-HAM | Non-Connected | Investigation | 0 | ● | 8% | Early Stage Design | TBA
|  | Auckland | Takanini | Transformer | Investigation | 150 | ● | 8% | Starting | TBA
|  | Northland | Bream Bay | Hydrogen - eSAF | Investigation | 330 | ● | 5% | Starting | TBA
|  | Otago-Southland | North Makarewa | Transformer | Investigation | 60 | ● | 0% | Starting | TBA
|  | Auckland | BHL_PAK | Non-Connected | Investigation | 0 | ● |  | Starting | TBA
|  | Region | Connection location (substation or circuit) | Type | Transpower stage | Max MW |  |  | Status
|  | Canterbury | ISL-KIK | Substation | Application | 120 |  |  | Requested
|  | Otago-Southland | Cromwell | Transformer | Application | 60 |  |  | Requested
|  | Northland | HEN_MDN | Non-Connected | Application | 0 |  |  | Requested
|  | Auckland | HEN_MDN / HEN_MPE | Non-Connected | Application | 0 |  |  | Requested
|  | Auckland | Mangere | Transformer | Application | 120 |  |  | Requested
|  | Auckland | HEN-OTA | Data Centre | Application | 200 |  |  | Requested
|  | Auckland | Wairau Road GXP | Transformer | Application | 120 |  |  | Requested
|  | Auckland | HEN_OTA | Non-Connected | Application | 0 |  |  | Requested
|  | Auckland | GLN-DEV-A | Non-Connected | Application | 0 |  |  | Requested