## Sheet1
Project ID | Parent Project ID | Customer | Project name | Region | Connection location (substation or circuit) | Type | Transpower stage | Max MW | Status Flag | Stage % complete | Status | Estimated connection livening date | Key
38310 | 0 | Vector Limited | Albany 2x New 33kV Feeders | Auckland | Albany | Feeder | Delivery | 30 | ● | 100% | Livened | 2026-02-14 | Type | Description
38123 | 0 | Powerco Limited | Waverley ODID | Taranaki | Waverley | Switchboard | Delivery | 0 | ● | 100% | Livened | 2026-03-31 | New feeder | New feeder(s) at an existing substation to supply new load or to increase supply resilience
38124 | 0 | Powerco Limited | Te Matai T1 Transformer Replacement | Bay of Plenty | Te Matai | Transformer | Delivery | 20 | ● | 100% | Livened | 2026-03-31 | New transformer | New or upgraded transformer(s) at an existing to supply new load or to increase supply resilience
38125 | 0 | Powerco Limited | Greytown ODID | Wellington | Greytown | Switchboard | Delivery | 50 | ● | 100% | Livened | 2026-01-01 | New GXP | New Grid exit Point (GXP) substation or new load supply point at an existing non GXP substation
38126 | 0 | Powerco Limited | MTN ODID | Central North Island | Marton | Switchboard | Delivery | 0 | ● | 100% | Transpower scope complete | 2026-11-01 | Transmission | New or upgraded transmission assets (overhead transmission lines or underground cables) to increase transmission capacity or resilience
38155 | 0 | Unison Networks Limited | Whakatu GXP 2x 33kV Feeders GXP | Hawkes Bay | Whakatu | Feeder | Delivery | 20 | ● | 100% | Livened | 2025-05-24 | Protection and automation | New or replacement protection or automation systems
38112 | 0 | New Zealand Steel Limited | Glenbrook Arc Furnace | Auckland | Glenbrook | Process Heat - Other | Delivery | 80 | ● | 92% | Livened | 2025-10-11 | Relocation | Relocation of existing transmission assets
38094 | 0 | Horizon Energy Distribution Limited | Waiotahe 11-33kV Transition | Bay of Plenty | Waiotahe | Switchboard | Delivery | 20 | ● | 91% | Livened | 2025-11-01 | Lifecycle | Replacement of transmission assets with modern equivalent either at end of life or for policy reasons
38072 | 0 | Aurora Energy Limited | CML-FKN Line TTU (Aurora) | Otago-Southland | CML-FKN-A | Conductor | Delivery | 20 | ● | 60% | Construction | 2026-05-01 | Other | Asset divestments, reconfigurations or other work not included in the above categories
38084 | 0 | Centralines Limited | Waipawa 33kV ODID Conversion | Central North Island | Waipawa | Switchboard | Delivery | 0 | ● | 60% | Construction | 2026-03-31
38089 | 0 | Fonterra Co-operative Group Limited | Whareroa Electrification (Ohangai Sub) | Taranaki | BRK-SFD | Process Heat - Dairy | Delivery | 120 | ● | 60% | Construction | 2026-06-01 | Max MW | Maximum additional supply capacity enabled by the project (actual demand may step change or grow slowly over many years to utilise this new capacity)
38105 | 0 | MainPower New Zealand Limited | Kaiapoi IDID Upgrade | Canterbury | Kaiapoi | Switchboard | Delivery | 0 | ● | 60% | Construction | 2025-11-01 |  | Where two or more projects suport the same supply capacity increase some projects Max MW may be set to zero to avoid double counting
38136 | 0 | PowerNet Limited | CML-FKN Line TTU | Otago-Southland | CML-FKN-A | Conductor | Delivery | 20 | ● | 60% | Construction | 2026-05-01
38142 | 0 | PowerNet Limited | Edendale 220kV GXP | Otago-Southland | NMA-TMH / Edendale | Substation | Delivery | 120 | ● | 60% | Detailed Design | 2027-08-01 | Stage % Complete | Approximate progress of the project through the relevant stage based on completed project milestones in the project schedule
38163 | 0 | Vector Limited | Wairau Road T9 Transformer | Auckland | Wairau Road | Transformer | Delivery | 150 | ● | 60% | Detailed Design | 2026-12-01
38087 | 0 | Drury South Limited | Drury Line Relocation | Auckland | HLY-OTA | Non-Connected | Delivery | 0 | ● | 22% | Detailed Design | 2027-02-01 | Status flag key
38110 | 0 | Network Tasman Limited | Brightwater GXP | Nelson-Marlborough | KIK-STK A | Substation | Delivery | 60 | ● | 13% | Detailed Design | 2028-05-31 | ● Progressing normally
38173 | 0 | Vector Limited | Henderson 1x 33kV Feeder (Microsoft 1/2) | Auckland | Henderson | Feeder | Delivery | 20 | ● | 12% | Detailed Design | 2027-11-01 | ●C Awaiting customer action
38340 | 0 | Horizon Energy Distribution Limited | Edgecumbe Capacity Increase SPS | Bay of Plenty | Edgecumbe | Special Protection Scheme | Delivery | 30 | ● | 5% | Detailed Design | 2026-06-30 | ●T Awaiting Transpower action
38106 | 0 | MainPower New Zealand Limited | ASY 66kV Coldstream Feeder | Canterbury | Ashley | Feeder | Delivery | 40 | ● | 1% | Detailed Design | 2027-05-31 | ● On hold
38164 | 0 | Vector Limited | Takanini 1x 33kV Feeder | Auckland | Takanini | Feeder | Delivery | 20 | ● | 0% | Detailed Design | 2026-04-09
38165 | 0 | Vector Limited | Takanini 2x 33kV Feeders (Spark) | Auckland | Takanini | Feeder | Delivery | 30 | ● | 0% | Detailed Design | 2026-03-01
38181 | 0 | Waka Kotahi New Zealand Transport Agency | C2P Project Stage 1 (Online) | Auckland | ARI-HAM | Non-Connected | Delivery | 0 | ● | 0% | Detailed Design | 2026-05-19
38189 | 0 | Wellington Electricity Lines Limited | KHD-TKR Uprating | Wellington | KHD-TKR | Conductor | Delivery | 0 | ● | 0% | Detailed Design | 2026-06-01
Project ID | Parent Project ID |  |  | Region | Connection location (substation or circuit) | Type | Transpower stage | Max MW | Status Flag | Stage % complete | Status | Estimated TP scope completion date
38096 | 0 |  |  | Auckland | Huapai | Non-Connected | Investigation | 30 | ● | 100% | Investment Contract Negotiation | TBA
38174 | 0 |  |  | Northland | Wellsford | Transformer | Investigation | 60 | ● | 100% | Investment Contract Negotiation | TBA
38166 | 0 |  |  | Auckland | Silverdale | Feeder | Investigation | 30 | ●T | 98% | Investment Contract Negotiation | TBA
38065 | 0 |  |  | South-Canterbury | Timaru | Transformer | Investigation | 40 | ●C | 95% | Investment Contract Negotiation | TBA
38113 | 0 |  |  | Northland | Maungaturoto | Transaction | Investigation | 0 | ● | 95% | Investment Contract Negotiation | TBA
38182 | 0 |  |  | Auckland | HLY-OTA-A | Non-Connected | Investigation | 0 | ● | 95% | Investment Contract Negotiation | TBA
38077 | 0 |  |  | Otago-Southland | Cromwell | Special Protection Scheme | Investigation | 30 | ● | 92% | Investment Contract Negotiation | TBA
38167 | 0 |  |  | Auckland | Wiri | Transformer | Investigation | 120 | ● | 90% | Investment Contract Negotiation | TBA
38097 | 0 |  |  | Auckland | Bombay | Switchboard | Investigation | 50 | ● | 85% | Early Stage Design | TBA
38127 | 0 |  |  | Taranaki | Brunswick | Transformer | Investigation | 30 | ● | 85% | Investment Contract Negotiation | TBA
38129 | 0 |  |  | Waikato | Waikino | Feeder | Investigation | 40 | ● | 77% | Early Stage Design | TBA
38149 | 0 |  |  | Waikato | HAM_WHU | Non-Connected | Investigation | 0 | ● | 77% | Early Stage Design | TBA
38150 | 0 |  |  | Waikato | ARI-HAM | Non-Connected | Investigation | 0 | ● | 53% | Early Stage Design | TBA
38130 | 0 |  |  | Waikato | Hinuera | Transaction | Investigation | 0 | ● | 50% | Early Stage Design | TBA
38168 | 0 |  |  | Auckland | Southdown | Substation | Investigation | 80 | ●C | 50% | Early Stage Design | TBA
38188 | 0 |  |  | Wellington | Central Park | Substation | Investigation | 150 | ● | 50% | Early Stage Design | TBA
38175 | 0 |  |  | Auckland | Henderson | Feeder | Investigation | 30 | ● | 39% | Early Stage Design | TBA
38176 | 0 |  |  | Auckland | Henderson | Feeder | Investigation | 30 | ● | 39% | Early Stage Design | TBA
38177 | 0 |  |  | Auckland | Henderson | Transformer | Investigation | 120 | ● | 39% | Early Stage Design | TBA
38344 | 38177 |  |  | Auckland | Henderson | Feeder | Investigation | 0 | ● | 39% | Early Stage Design | TBA
38186 | 0 |  |  | Waikato | Bombay | Transaction | Investigation | 0 | ● | 35% | Investment Contract Negotiation | TBA
38336 | 0 |  |  | Waikato | Meremere | Transaction | Investigation | 0 | ● | 35% | Investment Contract Negotiation | TBA
38086 | 0 |  |  | Otago-Southland | INV-MAN-A | Data Centre | Investigation | 300 | ●C | 32% | Early Stage Design | TBA
38156 | 0 |  |  | Bay of Plenty | Tarukenga | Transformer | Investigation | 20 | ● | 30% | Early Stage Design | TBA
38178 | 0 |  |  | Auckland | Silverdale | Transformer | Investigation | 120 | ● | 22% | Early Stage Design | TBA
38090 | 0 |  |  | Northland | Bream Bay | Hydrogen - eSAF | Investigation | 330 | ● | 15% | Early Stage Design | TBA
38171 | 0 |  |  | Auckland | Penrose | Feeder | Investigation | 30 | ● | 15% | Early Stage Design | TBA
38128 | 0 |  |  | Bay of Plenty | KMO-TRK | Substation | Investigation | 120 | ● | 14% | Early Stage Design | TBA
38183 | 0 |  |  | Auckland | HOB-WRD | Non-Connected | Investigation | 0 | ●C | 14% | Early Stage Design | TBA
38098 | 0 |  |  | Auckland | Silverdale | Feeder | Investigation | 36 | ● | 13% | Early Stage Design | TBA
38073 | 0 |  |  | Otago-Southland | Cromwell | Substation | Investigation | 120 | ● | 12% | Early Stage Design | TBA
38131 | 0 |  |  | Central North Island | Mangamarie | Switchboard | Investigation | 0 | ●C | 12% | Early Stage Design | TBA
38137 | 0 |  |  | Otago-Southland | Cromwell | Conductor | Investigation | 120 | ● | 12% | Early Stage Design | TBA
38169 | 0 |  |  | Auckland | ALB-WRD | Substation | Investigation | 120 | ●C | 12% | Early Stage Design | TBA
38116 | 0 |  |  | Canterbury | Hororata | Switchboard | Investigation | 0 | ● | 11% | Early Stage Design | TBA
38078 | 0 |  |  | Otago-Southland | Clyde-Twizel-1 or 2 | Substation | Investigation | 120 | ● | 10% | Early Stage Design | TBA
38079 | 0 |  |  | Otago-Southland | Cromwell | Transformer | Investigation | 60 | ● | 10% | Early Stage Design | TBA
38395 | 38079 |  |  | Otago-Southland | Cromwell | Transformer | Investigation | 60 | ● | 10% | Early Stage Design | TBA
38132 | 0 |  |  | Bay of Plenty | Te Matai | Transformer | Investigation | 50 | ● | 10% | Early Stage Design | TBA
38309 | 0 |  |  | South-Canterbury | ROX-ISL-A / Black Point | Substation | Investigation | 80 | ● | 8% | Early Stage Design | TBA
38091 | 0 |  |  | Auckland | Penrose | Data Centre | Investigation | 150 | ● | 8% | Early Stage Design | TBA
38143 | 0 |  |  | Otago-Southland | North Makarewa | Transformer | Investigation | 60 | ● | 8% | Early Stage Design | TBA
38170 | 0 |  |  | Auckland | Takanini | Transformer | Investigation | 150 | ● | 8% | Early Stage Design | TBA
38355 | 38070 |  |  | Auckland | BHL_PAK | Non-Connected | Investigation | 0 | ● | 8% | Early Stage Design | TBA
38326 | 0 |  |  | Northland | HEN_MDN | Non-Connected | Investigation | 0 | ● | 8% | Early Stage Design | TBA
38335 | 0 |  |  | Auckland | HEN_MDN / HEN_MPE | Non-Connected | Investigation | 0 | ● | 8% | Early Stage Design | TBA
38338 | 0 |  |  | Auckland | HEN_OTA | Non-Connected | Investigation | 0 | ● | 8% | Early Stage Design | TBA
38107 | 0 |  |  | Canterbury | ISL-KIK | Substation | Investigation | 120 | ● | 2% | Starting | TBA
38198 | 0 |  |  | Otago-Southland | CYD | Switchboard | Investigation | 0 | ● | 1% | Starting | TBA
38435 | 0 |  |  | Otago-Southland | CML-FKN-A 110 kV | Non-Connected | Investigation | 0 | ● | 1% | Starting | TBA
Project ID | Parent Project ID |  |  | Region | Connection location (substation or circuit) | Type | Transpower stage | Max MW |  | Ready to proceed 3 | Status
00038172 | 0 |  |  | Auckland | Mangere | Transformer | Application | 120 |  | Y | Requested
00038323 | 0 |  |  | Auckland | Wairau Road GXP | Transformer | Application | 120 |  |  | Requested
00038092 | 0 |  |  | Auckland | HEN-OTA | Data Centre | Application | 200 |  |  | Requested
Notes
1. The location is given as the substation where a project will connect, or if a new substation is required, the transmission circuit.
2. Stage % Complete - Approximate progress of the project through the relevant stage based project milestones completed in the project schedule. Progress in delivery is progress for the Transpower connection only, not for the associated customer assets. Timeframes for delivery contracting will vary as they are dependent on bilateral negotiation and each customer's investment decision process. Progress is dependent on both Transpower work and customer decisions at key stage gates. Where customers are unable to make timely decisions progress may stall. Stalled projects may be put on hold so resources can be re-allocated to other waiting projects.
3. Applications are deemed ready to proceed to investigation where Transpower has had confirmation the applicant: is ready to sign the associated services agreement, has FID for the residual application fee and the investigation costs, maintains a need date which justifies an investigation in the near term, and plans for securing property rights and consenting remain on track.