| Item Category | Description of Item | Transpower Supplier | Requisition via Maximo with work order | Order via FMIS No work order | Supporting information |
| --- | --- | --- | --- | --- | --- |
| Concrete Poles | Standard & High Strength Concrete Poles | Hynds | ✓ |  | 04.04 Procure High Level Materials |
| Cathodic Protection | Bentonite and Anodes | Corrosion Control Engineering (CCE) | ✓ |  |  |
| Cut to length Conductor (under 1000mtrs) | Butterfly, Centipede, Cicada | Prysmian | ✓ |  |  |
| HMI License | Electronic License | Eaton Electrical Australia | ✓ |  |  |
| Battery Banks |  | Enersys Australia Ltd | ✓ |  |  |
| Medium Voltage (MV) Cables |  | Nexans |  | ✓ |  |
| Terminations |  | Gridworks / Hiko |  | ✓ |  |

Some materials are stored and overseen by a Transpower approved supplier under a supply agreement. The Inventory and Purchasing team monitor demand requirements and coordinate with the supplier to ensure materials are dispatched to the project site in alignment with the Required on Site date. The team will provide Grid Delivery Project Managers (PM) with order status updates as required. The PM should reference and adhere to the material lead-times outlined in Appendix A, when specifying the Required on Site date.

Concrete Poles and Cathodic Protection (Bentonite and Anodes) are managed at the programme level. Asset Planning provides seasonal forecasts, which are confirmed and time-phased by Programme Planning. Grid Delivery personnel in conjunction with Inventory Management and Senior Category Management are responsible for monitoring actuals against forecasts throughout the season to ensure alignment and monitor variances. Suppliers produce and hold stock based on the forecasts provided by Transpower.

The purchase of Terminations and Cables is managed outside of Maximo. The PM provides the Senior Category Manager and Purchasing Coordinator with the MV cable and terminations schedule (in Excel) prepared by the Project Engineer or Engineering Consultant. This schedule is sent to the supplier to confirm lengths, drum sizes and weights. The PM confirms this information and forwards it to the Purchasing Coordinator (PC) who will raise a purchase order in FMIS based on these requirements; the PC will monitor the purchase order dates in order to provide the Service Provider notice of dispatch to site.