## Design Deliverables
Checklist for Cable Project Design Deliverables - V1
Project Description: |  | Design Completion Date:
FMIS Project Code:
Site:
Transpower Project Manager: |  | Review Date:
EC Design Manager:
11/22/33/50/66/110/220kV Cable Design - Deliverables
The EC is to confirm the following has been undertaken and submit status with monthly reports All items to be priced for at the tender stage . All provisional sums should be within 15% of total |  | Transpower's expected durations | Completed by EC with actual dates | Accepted (YES - N/A)
Deliverable | Description
Monthly Reports & Update Stationware | On a case by case, report by exceptions. Monthly Reports - The Design Project Manager shall report the progress on the Services at monthly intervals for the duration of the Contract. The report shall be in the hands of Transpower by the 5th working day of the following month. | Monthly (By 5th of each month)
Invoicing | Claims need to be made by the 10th of each month for TP approval The Claim sheet is to match your pricing schedule layout (or otherwise as directed by the PM). Once approved please submit the invoice by the 20th of the month. All variations must be notified early in advance of works to the Transpower Project Manager. This variation notification must include the anticipated scope of work, reasoning for changes and have a accurate price estimate (+/- 10%). Variations must have Transpower approval before work can progress. | Monthly (By the 10th for the Claim Sheet) (By the 20th for the Invoice)
Environmental and consenting Where applicable / to be confirmed by PM | For cable works that require excavation within Transpower Stations the Consultant shall provide: • A soil testing location report- mark out on a site layout drawing all possible locations where any excavation or soil disturbance may be carried out, e.g. new ducting, foundation modifications, etc. • A total volume amount of soil that will be disturbed. • Any possible consenting requirements or anything that could require Environmental Impact Assessment (EIA) / Resource Management Assessment (RMA). • Any constraints/requirements to secure a Permit to Dig | As per the project programme
Geotechnical Report & Thermal Resistivity (TR) Testing Where applicable / to be confirmed by PM | Geotechnical (Required for cable termination foundations), the Consultant shall perform: • Geotechnical testing to assess the soil types at the proposed location to the depth necessary for the design of all civil works required. (incl. soil contamination). • In situ soil sample collection and TR Testing. • If required, i.e. for a ducted or direct buried cable system identifiation of trench backfill and TR testing to confirm suitability. • Secure a Permit to Dig to undertake the above geotechnical testing. | As per the project programme
Seismic Hazard Assessment Where applicable / to be confirmed by PM | Seismic Hazard Assessment - Transpower’s current seismic design practice shall be followed for all new plant installation (including replacement plant), stands and re-use of foundations. | As per the project programme
EIA and RMA (Environmental and consenting) Where applicable / to be confirmed by PM | Environmental Impact Assessment (EIA) / Resource Management Assessment (RMA) - The Consultant shall investigate and report back on the requirements of (and compliance to) all legal, statutory, Local Body Zonings, Regulations and the Resource Management Act with respect to the Detail Design. | As per the project programme
Engineering Study Reports | The Consultant shall prepare an Engineering Study’ Report for each of the following: 110kV and 220kV •Current Rating •Sheath Bonding, Induced Voltage and Earth Potential Rise Study •Magnetic Field Study •Mechanical Strength and Seismic Study •Thermo-Mechanical, Gravitational and Traffic Induced Forces Study 11kV and 33kV •Current Rating •Sheath Bonding, Induced Voltage and Earth Potential Rise Study | As per the project programme
Materials list PM to provide template spreadsheet(s) | •The Consultant shall identify and confirm, in a materials / procurement list, all the materials that are required to be purchased or relocated. This list is to include the appropriate Transpower Maximo inventory/part number. If any of items do not have a TP part number, they must have the necessary Technical Specifications. •This Material List shall be prepared and submitted for review at the earliest possible time, otherwise at same time as the Tender Doc’s become available. The list shall be reviewed and finalised prior to the construction drawings being issued. •The completed material list must include where the equipment will be delivered, e.g. Transpower stores, Contractor, Site. •Any non-inventory materials must recommend a suitable supplier and where possible this equipment should be supplied locally. •The Technical Specifications, including schedules and specification drawings, shall be sufficiently completed to enable Transpower to call tenders without further design input. •The Consultant shall list and verify redundant equipment disposals i.e. return to store, re-use on existing / alternative site or scrapped. (Note this is sometimes recorded in the Delivery Business Case (DBC) •The Materials List is to provide the Maximo Device locations for all new assets (Process to be confirmed) | As per the project programme
Material Drawing Packs | Where appropriate the EC shall provide Tender drawing packages with material schedules for issue to specific suppliers. | As per the project programme
Population of (Maximo) Asset Changes Plan (ACI data) | Complete the appropriate asset location update spreadsheet . On completion send spreadsheet to Project Manager who will forward the information to Asset Information to create assets in Maximo After commissioning the SP completes the template with details such as install date and installation contractor | As per the project programme
Asset Changes Plan (ACI data) | Prior to commissioning the Consultant shall verify or otherwise the current rating (in the Current Rating Study) and complete the template for submission to ACI. | As per the project programme
SCORED Workshop Where applicable / to be confirmed by PM | (Safety, Constructability, Operability & Maintenance, Risk, Environment and Design) Allow for attendance to 2 SCORED Workshops: 1 at commencement for Design and 1 for commencement of Installation works) for identifying, documenting and elimination / mitigating risks and engineering problems. | As per the project programme
BIM Modelling Where applicable and to be confirmed by Digital Engineering. | Provide BIM digitised updates – the extent will be confirmed for each project, scope could include: • Pre-construction LIDAR scan. • LIDAR/drone scan of 110/220kV cable joint bays. • Uploading to Project Wise. | As per the project programme
Constructability Review Maybe omitted if covererd in SCOREd Workshop to be confirned by PM | A Constructability Review and report detailing construction concerns, timing/outage, access issues, resources etc. and recommended courses of action. The Constructability Review is to determine the practicality and feasibility of carrying out project work in the Detailed Design Report and should; • Highlight any shortcomings in the proposals and where necessary recommend alternative courses of actions required to meet the Design objectives detailed above. • Particular areas of interest include cable pulling & joint bay locations. • The Constructability review will be conducted in conjunction with the Contractor (Installer) and the Site Maintenance Contractor. | As per the project programme
Certificate(s) of Suitability for Purpose | Completion and signing of: • CSP1 – Certificate of Design • CSP4 - Certificate of Construction Monitoring To be duplicated as required for staged works. CSP3 – Certificate of Design review or Verification may be required and will be confirmed by the PM | As per the project programme
Construction Monitoring To be confirmed by PM | The appropriate level of construction monitoring will be identified by the Project Manager, it is anticipated that CM3 or CM4 (as per Appendix 4 of ACE/Engineers Guideline on the Briefing & Engagement for Consulting Services) will be the minimum requirement.
System Project Overview (SPO) Draft (1-2 pages) | The draft System Project Overview is intended to give an overview of all the stages of the project, indicating the construction method and sequence, including any sequential protection settings requirements, system release outages and commissioning programme requirements. (Including (esp. SPS schemes) a basic Scheme description and operation along with SPO) For larger projects stage drawings will be required. | As per the project programme
"For Tender Drawings" (IFT) package and associated works (For contractor estimating purposes) | All Tender Drawings (issue for Tender package) will need to be sent to Transpower for review. These will include technical specifications required for the completion of the whole of the works including; •A scope of the works including a description of the Works (with drawings) to be constructed. •A list and explanation of all interfaces and protocols that the Contractor will have to comply, liaise, cooperate with or manage with during the Works. •Copies of all Resource Consents and any other Resource Management or Building Act, permits or approvals issued to allow the Contractor to carry out the Works. •A copy of the Materials list. •A list and description of the minimum testing and commissioning requirements. •Any installation and/or testing and commissioning requirements that are specified by a Supplier of the Plant. Provision of electronic versions of installation tender packages for the site works contract as follows; • Instructions on the dismantling / disposal of Plant or any redundant Transpower equipment. • For larger projects a pricing schedule for the installation tender will be required, please confirm with the TP PM. | As per the project programme
Project Close-out | The Scope of Services includes the production of “As Built” drawings post Construction. This includes; • Assisting with the Pre & Post Commissioning Checklists TP590 (primarily) & TP 593 respectively. • Assisting with the collation of the Operation & Maintenance Manual: scope to be advised by the PM. • Provision of Geographical Information to Transpower for AssetMap and beforeudig updates. • Uploading BIM models and underground “point features” | As per the project programme
Design handover to Contractor (OPTIONAL) (includes tactical engineering feedback and design amendment/further details) | A meeting with the Contractor (on site or over Teams) before construction for with the Contractor to explain the characteristics of the project. This meeting is an opportunity for the Contractor to understand how the completed project will work, and allows them an opportunity to ask questions of the EC. | As per the project programme
Issue for Construction Package | The "Issue for Construction Package" must include; •Installation specifications •Finalised Material List •SPO •Construction & route drawings. | As per the project programme
New Project Operating Information (TP582) To be confirmed by PM | Provision of form TP582 "New project operating information" (technical information for NGOC) both the PM or the Projects Construction Contractor for loading into CAT. | Along with Construction Drawings (IFC)
Cable Circuit Information Folder Updates | Collating & updating Operation & Maintenance Manuals. | Along with Construction Drawings (IFC)
Installation Tender Services Support | • The answering of questions raised by Transpower during the tendering period. • Provision of clarification for site queries as required during the construction period. • Provision of Operator and Technician Training requirement to cover the modifications to preparation and maintenance of the Station. | Ongoing
CSP (s) | Completion and signing of CSP4 (s) To be duplicated as required for staged works | 2 weeks after construction
Site Monitoring
PC Sum review for As Building | Review the quantities of as build drawings and update the fixed sum accordingly | Along with Construction Drawings (IFC)
Drawings updates | All drawing updates should be labelled correctly. Any updates must be updated in the complete drawing package (Master Drawing list) with the superseded drawings being replaced. Each issue of drawings should include all drawings. Larger drawing set transmittals are to include quick reference codes. Included in the Master Drawing list should be sub-drawing packages for material suppliers (This should align with the material list items). Cable schedules and drawing registers to be provided in excel format. Supply Redeye-Drawings team with a Final transmittal drawings list | As per the project programme
‘As Built’ Drawing updates / BIM Models Close out | ‘As Built’ Drawing updates – Costs to be confirmed on receipt of installation contractor’s mark ups upon submission, scope anticipated to include: • Uploading the appropriate manufacture’s drawings as well as manufacturers as-built drawings. • The EC is to ensure the correct project code is linked to the drawings being submitted into RedEye. • The cancellation / removal of all identified superseded/’no-longer appropriate’ drawings relating to this site. • where appropriate will include A&O drawings with drafts to be approved by the Customer before final submission. | As per the project programme

## Version Log
Current Published Version
Revision Log - Checklist
| Changes made | Changes made by | Date
Version 4 Row 26 27 | Added Accurate PC Sum for as build works, with drawing quantities, categories/groupings; Row 26 | Robyn Boyd | 2022-06-20
Version 5 Row 13 | Variation notification requirements | Robyn Boyd | 2022-06-29
Version 5 Row 26 27 | Minor modifications | Robyn Boyd | 2022-06-29
Version 5 Row 32 33 | Inclusion of quick reference drawing codes | Robyn Boyd | 2022-06-29
Version 5 Row 41 42 | Tender Support Services provisional sums modification | Robyn Boyd | 2022-06-29
Version 5 Row 47 48 | Updated to include A&O drawing preparation and submission | Robyn Boyd | 2022-06-29
Version 6 Row 48 49 | Population of Network Services Support Protection Signalling Requirements Table. | Garry Lamb | 2022-09-06
Version 6 Row 49 50 | Transformer protection CID Files | Garry Lamb | 2022-09-06
Version 6 Row 50 51 | Submit Designs in Modelling Integrator Tool . | Garry Lamb | 2022-09-06
Version 6 Row 51 52 | Supply Redeye-Drawings team with a Final transmittal drawings list | Garry Lamb | 2022-09-06
Version 7 Row 29 30 | Included Updated IED IP addressing schedule and Submit to SCADA Engineering e-mail account. (If not yet integrated to Modelling Integrator Tool) | Sean Fletcher-Garry Lamb | 2022-09-09
Version 8 Row 16 | Added Device locations to the Materials list | Robyn Boyd | 2022-12-08
Version 8 Row 26 | Inserted new row "IST Design" | Robyn Boyd | 2022-12-09
Version 9 Row 17 | Material Drawing Packs | Robyn Boyd & Garry Lamb | 2024-02-25
Version 9 Row 18-24 | RTS Updates and other support systems | Jeff Adams, RB & GL | 2024-02-26
Version 10 | Updated some comments and slightly re-arranged the order into a more practical timeline. | RB, GL, Lynette Bell, Darryl York | 2024-03-11
Version 11 (Proposed) | Clarify Metering requirements from updated Metering page based on Ian Martin input. Capture Telco Requirements from Mike Salisbury. Incorporate Lines EC requirements from Armi. Incorporate changes to asset registration process | GL/JM | Proposed