## Title
Integrated Transmission Plan 2026
Expenditure and Performance Schedules
September 2026

## Contents
Contents
1 | Expenditure summary
Sets out the actual and forecast base capex and opex on a constant basis.
2 | Operating expenditure
Sets out operating expenditure by expenditure category on a constant.
3 | Base capital expenditure
Sets out Base Capex by asset grouping on a constant basis including interest during construction.
4 | Major capex and Listed projects expenditure
Sets out Major Capital and Listed projects: approved, under development and both listed and other reconductoring.
5 | Major capex - outputs
Describes the approved capex outputs, major capex allowances and indicative commissioning dates
6 | Grid Performance targets
Measures (GP1 and GP2) measuring the number and average duration of unplanned interruptions.
7 | Asset Performance and Health
Asset performance caps, collars, targets, quality standards and incentive summary for our revenue linked performance measures (AP1 and AP2), and asset health targets for asset classes with an AHI of 8 or higher.

## 1. Expenditure summary
1. Expenditure summary
This schedule presents an overview of all forecast expenditure during regulatory control periods four, five and six (RCP4, RCP5 and RCP6). All figures are presented in constant 2025/26 dollars. For capital expenditure (capex) we include the forecast cost of interest during construction. This approach is consistent with the way our base capex allowances are set. Major projects are enhancement and development (E&D) projects with a value in in excess of $30 million. Listed projects are base capex projects for which we need to apply during RCP4 for an increase in our base capex allowance.
Summary of RCP4 expenditure, constant 2025/26 $m |  | RCP4 | [5 empty] | RCP5 | [5 empty] | RCP6
This sheet sets out base capex and opex actuals and forecast |  | Actual | Forecast | Forecast | Forecast | Forecast |  | Forecast | [5 empty] | Forecast
|  | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | RCP4 Total | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | RCP5 Total | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | RCP6 Total
Opex | Network opex | 254036822.5802 | 248821722.2887 | 254567153.9258 | 250871240.2879 | 251222118.6062 | 1259519057.6888 | 244149654.7584 | 240961444.1787 | 245872265.3242 | 245158129.3076 | 239969597.0939 | 1216111090.6627 | 239970258.0032 | 239970258.0032 | 239970258.0032 | 239970258.0032 | 239970258.0032 | 1199851290.0159
| Non-Network opex | 164563476.1168 | 191677860.5324 | 184720084.269 | 173569067.3418 | 169386256.7836 | 883916745.0437 | 175976215.1571 | 178466456.432 | 182297417.5542 | 184057134.544 | 187018171.8003 | 907815395.4877 | 187129580.5683 | 187130300.0382 | 187271104.5583 | 187427803.6845 | 187601243.6809 | 936560032.5302
| Total opex | 418600298.697 | 440499582.8211 | 439287238.1949 | 424440307.6297 | 420608375.3898 | 2143435802.7325 | 420125869.9155 | 419427900.6107 | 428169682.8783 | 429215263.8516 | 426987768.8942 | 2123926486.1504 | 427099838.5715 | 427100558.0413 | 427241362.5615 | 427398061.6877 | 427571501.6841 | 2136411322.5461
Base Capex
Renewal | Substations | 85183334.5549 | 86309794.3786 | 120817516.9917 | 151040827.8336 | 99000097.9503 | 542351571.7091 | 114641797.6563 | 199155020.3034 | 145955113.5164 | 158972120.8181 | 96405461.1933 | 715129513.4875 | 92331617.0456 | 153048375.9901 | 142453025.735 | 113833711.2591 | 100279984.6915 | 601946714.7213
| Buildings & Grounds | 17502087.0888 | 28308369.1452 | 19108525.3986 | 12310297.0351 | 12385102.7461 | 89614381.4137 | 8054560.4661 | 10583970.5649 | 12078538.5085 | 9699566.5422 | 11974341.7228 | 52390977.8045 | 12838201.7171 | 10632411.4022 | 9620975.0808 | 9617897.2624 | 9030620.4493 | 51740105.9118
| Transmission Lines | 147796306.3612 | 155732197.3496 | 174002747.151 | 173516345.6618 | 137643083.7657 | 788690680.2894 | 137482297.3981 | 138047714.9604 | 181666085.4716 | 197057645.123 | 208878889.9495 | 863132632.9026 | 180888455.2414 | 187760726.3262 | 197977463.7637 | 257943865.4684 | 240587649.2626 | 1065158160.0624
| HVDC & reactive assets | 30233252.7131 | 28559333.8845 | 51155661.2149 | 59352161.6407 | 33948559.025 | 203248968.4783 | 27709221.5203 | 53776458.0503 | 46528124.0465 | 29241934.5353 | 20651087.0935 | 177906825.2458 | 17215864.4862 | 24719339.1503 | 30974583.7856 | 23932005.063 | 30827267.5117 | 127669059.9968
| Secondary Assets | 45967919.0472 | 65525224.6019 | 75284165.7234 | 59048792.6731 | 47350135.8487 | 293176237.8943 | 77327365.0647 | 76438678.4867 | 72862902.3152 | 71397763.527 | 60592767.9433 | 358619477.3369 | 52880712.3242 | 83492292.2082 | 40423131.447 | 28589054.4103 | 44777083.5113 | 250162273.901
Other | E&D | 43857545.1794 | 34234164.2758 | 29311132.5734 | 24319044.9683 | 2987295.599 | 134709182.5958 | 54962943.1707 | 28796710.2129 | 28783908.8601 | 30348683.6248 | 37333330.9337 | 180225576.8023 | 37028749.3015 | 52813717.9597 | 42248781.7873 | 23834163.4105 | 22677391.6886 | 178602804.1476
| Resilience | 4647267.7508 | 19432923.2901 | 48197347.6073 | 54938081.8462 | 42200299.714 | 169415920.2084 | 40197590.3841 | 41040639.9306 | 41603688.7065 | 39202715.4547 | 39248088.6052 | 201292723.081 | 38623726.2529 | 38698141.0645 | 38778738.1614 | 38861203.0405 | 38915671.4663 | 193877479.9856
| ICT | 68205075.2901 | 51301449.0644 | 51598984.223 | 18365636.568 | 19008068.09 | 208479213.2353 | 36504674.2227 | 41013293.6924 | 41019092.1605 | 41016692.9672 | 41023569.5087 | 200577322.5515 | 40835635.1089 | 40829338.1073 | 40821462.5825 | 40813686.2834 | 40866452.3315 | 204166574.4135
| Business support capex | 7045748.8062 | 10324272.2087 | 11822500.7578 | 6275723.3507 | 6350958.2587 | 41819203.3822 | 6645002.1315 | 5912008.9849 | 5857649.5396 | 5806676.9438 | 6115009.0692 | 30336346.669 | 5926640.9008 | 5926640.6556 | 5926641.4579 | 5926641.127 | 5926640.2189 | 29633204.3602
| Total base capex | 450438536.7917 | 479727728.1988 | 581298581.6411 | 559166911.5775 | 400873600.9974 | 2471505359.2065 | 503525452.0145 | 594764495.1865 | 576355103.1249 | 582743799.536 | 522222546.0192 | 2779611395.8811 | 478569602.3786 | 597920982.8642 | 549224803.8011 | 543352227.3245 | 533888761.1317 | 2702956377.5001
Major Capex | Approved Major Capex | 121179498.6117 | 159061088.9899 | 123114391.5004 | 207696874.1851 | 200741838.9996 | 811793692.2867 | 407498088.7139 | 190128052.1783 | 374183.1616 | 330021.4878 | 337603.7352 | 598667949.2767 | 142118.5932 | 0 | 0 | 0 | 0 | 142118.5932
| Unallocated adjustments | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
| Capex spend including adjustments | [5 empty] | 0 | [5 empty] | 0 | [5 empty] | 0
| Under development | 66436.6976 | 11842719.3128 | 82440765.1011 | 249669626.7988 | 370961581.3119 | 714981129.2223 | 371930917.118 | 486491209.7432 | 642883182.2657 | 541263116.1146 | 576453549.011 | 2619021974.2525 | 200498673.689 | 78266842.1472 | 389131186.2854 | 432117973.8499 | 402123144.8714 | 1502137820.8428
| Total Major Capex | 121245935.3093 | 170903808.3027 | 205555156.6015 | 457366500.9839 | 571703420.3115 | 1526774821.509 | 779429005.8319 | 676619261.9215 | 643257365.4272 | 541593137.6024 | 576791152.7461 | 3217689923.5292 | 200640792.2822 | 78266842.1472 | 389131186.2854 | 432117973.8499 | 402123144.8714 | 1502279939.436
check
Listed projects | Total listed and other conductor replacement expenditure | 0 | 11438055.6388 | 33122378.4308 | 30789600.8881 | 48769444.2112 | 124119479.1689 | 137291791.845 | 132200732.227 | 202624189.537 | 53064910.0412 | 167803663.1503 | 692985286.8005 | 0 | 23751035.4153 | 72434353.149 | 29955846.8999 | 113840029.4678 | 239981264.9321
| Proposed capex and opex | 990284770.7981 | 1102569174.9614 | 1259263354.8683 | 1471763321.0792 | 1441954840.9099 | 6265835462.6169 | 1840372119.6069 | 1823012389.9458 | 1850406340.9674 | 1606617111.0312 | 1693805130.8098 | 8814213092.3612 | 1106310233.2323 | 1127039418.468 | 1438031705.797 | 1432824109.762 | 1477423437.155 | 6581628904.4142

## 2. Operating expenditure
| 2. Operating expenditure, constant 2025/26 $m | RCP4 |  |  |  |  | RCP5 |  |  |  |  | RCP6 | [5 empty] | RCP Totals
| This sheet sets out base opex actuals and forecast | Actual | Forecast | Forecast | Forecast | Forcast | Forecast |  |  |  |  | Forecast |  |  |  |  | RCP4 | RCP5 | RCP6
| Expenditure Category | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | RCP4 Total | RCP5 Total | RCP6 Total
Network opex | Preventive Maintenance | 53132023.1133 | 52221095.1525 | 52336772.7683 | 52715408.9107 | 52605212.2497 | 53768891.866 | 53768891.866 | 53768891.866 | 53768891.866 | 53768891.866 | 53768891.866 | 53768891.866 | 53768891.866 | 53768891.866 | 53768891.866 | 263010512.1945 | 268844459.3301 | 268844459.3301
| Predictive Maintenance | 95601002.2389 | 92030737.0916 | 98375884.9876 | 96567430.6993 | 97048556.8755 | 88500978.1517 | 85916270.659 | 89468821.2071 | 89264040.9091 | 84924420.4872 | 84792654.6308 | 84792657.7178 | 83298564.6911 | 83858853.3062 | 83858853.3062 | 479623611.8929 | 438074531.4141 | 420601583.6523
| Corrective Maintenance | 6461874.24 | 5184697.0629 | 4527156 | 4527156 | 4527156 | 4527156 | 4527156 | 4527156 | 4527156 | 4527156 | 4527156 | 4527156 | 4527156 | 4527156 | 4527156 | 25228039.3029 | 22635780 | 22635780
| Proactive Maintenance | 1087784.07 | 1173894.4683 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 1200000 | 5861678.5383 | 6000000 | 6000000
| Resilience | 2370105.1634 | 2920760.7295 | 3323752.7363 | 1769869.276 | 1306816.0035 | 1324313.9611 | 1324310.8741 | 2682581.4715 | 2173225.7529 | 1324313.9611 | 1456740.7267 | 1456737.6398 | 2950830.6664 | 2390542.0513 | 2390542.0513 | 11691303.9087 | 8828746.0206 | 10645393.1356
| Asset Management and Operations | 94698429.5247 | 94582848.4575 | 94078446.8837 | 93366234.8518 | 93809236.9275 | 94103174.2296 | 93499674.2296 | 93499674.2296 | 93499674.2296 | 93499674.2296 | 93499674.2296 | 93499674.2296 | 93499674.2296 | 93499674.2296 | 93499674.2296 | 470535196.6452 | 468101871.1479 | 467498371.1479
| Sustainability | 685604.23 | 707689.3264 | 725140.55 | 725140.55 | 725140.55 | 725140.55 | 725140.55 | 725140.55 | 725140.55 | 725140.55 | 725140.55 | 725140.55 | 725140.55 | 725140.55 | 725140.55 | 3568715.2064 | 3625702.75 | 3625702.75
Non-network opex | Business Support | 71861434.067 | 73743754.9696 | 76613972.8992 | 75540106.0032 | 75246229.9525 | 75234561.5588 | 75234561.5588 | 75234561.5588 | 75234561.5588 | 75234561.5588 | 75234561.5588 | 75109561.5588 | 75109561.5588 | 75109561.5588 | 75109561.5588 | 373005497.8915 | 376172807.794 | 375672807.794
| ICT Opex | 47623963.9298 | 49286162.7051 | 54320706.594 | 56863859.5508 | 55092859.1009 | 55761359.8555 | 56523356.7363 | 58390974.4536 | 57802846.853 | 58537859.5719 | 58537859.5723 | 58537859.5723 | 58537859.5723 | 58537859.5723 | 58537859.5723 | 263187551.8807 | 287016397.4703 | 292689297.8616
| ICT Software as a Service | 14083799.66 | 37956614.6662 | 20933361.8995 | 6929069.4816 | 3384996.2245 | 7811836.6784 | 7947637.546 | 8097410.5606 | 8261799.4714 | 8441471.6171 | 8552880.3848 | 8678599.8546 | 8819404.3747 | 8976103.5009 | 9149543.4973 | 83287841.9318 | 40560155.8736 | 44176531.6123
| Insurance | 30994278.46 | 30691328.1915 | 32852042.8763 | 34236032.3061 | 35662171.5057 | 37168457.0644 | 38760900.591 | 40574470.9811 | 42757926.6608 | 44804279.0525 | 44804279.0525 | 44804279.0525 | 44804279.0525 | 44804279.0525 | 44804279.0525 | 164435853.3396 | 204066034.3498 | 224021395.2623
| Total Opex | 418600298.697 | 440499582.8211 | 439287238.1949 | 424440307.6297 | 420608375.3898 | 420125869.9155 | 419427900.6107 | 428169682.8783 | 429215263.8516 | 426987768.8942 | 427099838.5715 | 427100558.0413 | 427241362.5615 | 427398061.6877 | 427571501.6841 | 2143435802.7325 | 2123926486.1504 | 2136411322.5461
| Capitalised Leases (Cash flow/expenditure value) | [15 empty] | 0 | 0 | 0 | 10370106.4875 | 11564393.7365 | 17007233.9113 | 10316690.98 | 9396863.6279 | 9387437.4689 | 9232899.0649 | 9206944.2471 | 9179125.4872 | 9011181.6683 | 9011181.6683 | 9011181.6683 | 9011181.6683 | 9011181.6683 | 9011181.6683

## 3. Base capital expenditure
3. Base capital expenditure, including IDC, constant 2025/26 $m |  |  | RCP4 |  |  |  |  | RCP5 |  |  |  |  | RCP6 | [5 empty] | RCP Totals
This sheet sets out base capex actuals and forecast |  |  | Actual | Forecast | Forecast | Forecast | Forcast | Forecast |  |  |  |  | Forecast
Expenditure Category | Asset Category | Asset Class | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | RCP4 Total | RCP5 Total | RCP6 Total
| AC Substations | Power Transformers | 19586974.9086 | 19154716.1437 | 43415911.6687 | 77257803.7006 | 49635489.5292 | 34631498.1431 | 102609206.5574 | 73608090.405 | 82124287.1565 | 32554811.9523 | 15915002.3017 | 66456407.8361 | 57985723.1652 | 51069246.3642 | 32225140.6336 | 209050895.9508 | 325527894.2143 | 223651520.3009
|  | Indoor Switchgear | 6589520.0574 | 6909427.5138 | 10899910.13 | 8199300.6589 | 5740947.508 | 7354741.6263 | 10305345.7275 | 6739445.2981 | 8163232.7045 | 8119086.4179 | 30865185.9648 | 31905311.5971 | 34041970.2996 | 24286830.4966 | 26735247.8959 | 38339105.8681 | 40681851.7744 | 147834546.2539
|  | Outdoor Switchgear | 14882764.1988 | 26493219.937 | 31557476.122 | 30114114.5504 | 24460544.8436 | 39652454.2237 | 23354320.9594 | 25181719.4492 | 26774662.5695 | 36702102.3812 | 30383796.2172 | 41066471.2226 | 34927825.6906 | 19874365.6974 | 24007036.4994 | 127508119.6518 | 151665259.5829 | 150259495.3272
|  | Structures & Buswork | 3624634.2246 | 6857481.269 | 10442974.9642 | 15777950.3 | 9776498.9901 | 11374598.3465 | 15421553.1045 | 5100284.3885 | 6155816.9695 | 5726464.3335 | 8039724.7458 | 6342387.0999 | 7857699.8226 | 10980481.7222 | 9586696.312 | 46479539.7479 | 43778717.1425 | 42806989.7025
|  | Power Cables | 29043272.9309 | 15526830.2185 | 7494337.1651 | 7253678.4246 | 4257845.4755 | 7445096.4317 | 22943695.7292 | 26896591.0397 | 26538476.6562 | 2435651.9712 | 257676.3122 | 474249.4527 | 1158066.2747 | 1163198.4701 | 613922.4251 | 63575964.2146 | 86259511.8279 | 3667112.9349
|  | Other AC Substation Equipment | 5722866.4452 | 9835667.4857 | 12984034.6256 | 8522977.2323 | 5126439.9013 | 8758769.7464 | 9118561.7797 | 7662850.0251 | 7712274.9178 | 6915141.7506 | 6870231.5039 | 6803548.7816 | 6481740.4824 | 6459588.5085 | 7111940.9254 | 42191985.6901 | 40167598.2195 | 33727050.2018
|  | Outdoor 33kV switchyards: Outdoor to Indoor Conversion | 5733301.7896 | 1532451.8108 | 4022872.3161 | 3915002.9668 | 2331.7026 | 5424639.1387 | 15402336.4457 | 766132.9109 | 1503369.844 | 3952202.3867 | 0 | 0 | 0 | 0 | 0 | 15205960.5858 | 27048680.726 | 0
Renewal | ACS Buildings & Grounds | Buildings & Grounds | 17502087.0888 | 28308369.1452 | 19108525.3986 | 12310297.0351 | 12385102.7461 | 8054560.4661 | 10583970.5649 | 12078538.5085 | 9699566.5422 | 11974341.7228 | 12838201.7171 | 10632411.4022 | 9620975.0808 | 9617897.2624 | 9030620.4493 | 89614381.4137 | 52390977.8045 | 51740105.9118
| Transmission Lines | Structures & Insulators | 100671590.3563 | 107081106.1938 | 108620917.8964 | 117022264.8575 | 117203763.9404 | 114771238.2966 | 118154702.7801 | 119815526.7223 | 120461951.023 | 121562840.8985 | 122273450.6177 | 123597693.8807 | 126870759.8414 | 127080423.7241 | 130252384.328 | 550599643.2444 | 594766259.7204 | 630074712.3919
|  | Conductor & hardware | 20185423.595 | 21689674.7403 | 47432988.8445 | 42822750.694 | 7676783.5083 | 8177835.333 | 6210277.4224 | 46515884.1645 | 61408667.0597 | 73257264.0093 | 45569738.7505 | 51117086.0295 | 58060307.2944 | 117816588.872 | 97288205.261 | 139807621.382 | 195569927.9889 | 369851926.2074
|  | Grillage | 10849350.2874 | 11983721.576 | 9939954.1917 | 10321097.8662 | 9894264.3064 | 9820474.2894 | 10417042.3826 | 12068904.5264 | 11921253.3435 | 10793004.5814 | 9360961.7831 | 9361556.7544 | 9361987.1956 | 9362425.7355 | 9362695.4816 | 52988388.2276 | 55020679.1233 | 46809626.9503
|  | Foundation and Access | 16089942.1225 | 14977694.8396 | 8008886.2185 | 3350232.2442 | 2868272.0107 | 4712749.4792 | 3265692.3753 | 3265770.0584 | 3265773.6967 | 3265780.4604 | 3684304.0901 | 3684389.6615 | 3684409.4324 | 3684427.1369 | 3684364.1921 | 45295027.4354 | 17775766.07 | 18421894.5128
| HVDC & reactive assets | HVDC | 14618613.1763 | 13699334.7992 | 20553531.2778 | 26784387.6459 | 9608683.9895 | 10717215.2163 | 17118121.2258 | 23542634.324 | 25172099.3222 | 12544486.7492 | 13298453.6785 | 20761822.3285 | 27775750.5221 | 16461866.6682 | 20979940.1446 | 85264550.8886 | 89094556.8374 | 99277833.3418
|  | Reactive Assets | 15614639.5368 | 14859999.0853 | 30602129.9372 | 32567773.9948 | 24339875.0355 | 16992006.304 | 36658336.8245 | 22985489.7225 | 4069835.2131 | 8106600.3443 | 3917410.8078 | 3957516.8218 | 3198833.2636 | 7470138.3948 | 9847327.3671 | 117984417.5896 | 88812268.4084 | 28391226.655
| Secondary Assets | Protection, battery systems and Revenue Meters | 41856919.8782 | 60784395.2415 | 67364202.3339 | 46647764.2422 | 44051627.5991 | 65772231.2823 | 70879397.4291 | 62343265.5021 | 62709932.8732 | 49770583.575 | 44901371.4083 | 69090107.351 | 34336850.9513 | 22713815.3374 | 42175333.6595 | 260704909.295 | 311475410.6617 | 213217478.7074
|  | Substation Management Systems | 4110999.1689 | 4740829.3604 | 7919963.3895 | 12401028.4309 | 3298508.2496 | 11555133.7824 | 5559281.0577 | 10519636.8131 | 8687830.6538 | 10822184.3683 | 7979340.9159 | 14402184.8572 | 6086280.4957 | 5875239.0729 | 2601749.8519 | 32471328.5993 | 47144066.6752 | 36944795.1936
Enhancement and Development | Grid E&D | Grid E&D | 43857545.1794 | 34234164.2758 | 29311132.5734 | 24319044.9683 | 2987295.599 | 54962943.1707 | 28796710.2129 | 28783908.8601 | 30348683.6248 | 37333330.9337 | 37028749.3015 | 52813717.9597 | 42248781.7873 | 23834163.4105 | 22677391.6886 | 134709182.5958 | 180225576.8023 | 178602804.1476
Resilience | Resilience | Resilience | 4647267.7508 | 19432923.2901 | 48197347.6073 | 54938081.8462 | 42200299.714 | 40197590.3841 | 41040639.9306 | 41603688.7065 | 39202715.4547 | 39248088.6052 | 38623726.2529 | 38698141.0645 | 38778738.1614 | 38861203.0405 | 38915671.4663 | 169415920.2084 | 201292723.081 | 193877479.9856
ICT capex | ICT | ICT including XaaS | 68205075.2901 | 51301449.0644 | 51598984.223 | 18365636.568 | 19008068.09 | 36504674.2227 | 41013293.6924 | 41019092.1605 | 41016692.9672 | 41023569.5087 | 40835635.1089 | 40829338.1073 | 40821462.5825 | 40813686.2834 | 40866452.3315 | 208479213.2353 | 200577322.5515 | 204166574.4135
Business support Capex | Business support | Business support | 7045748.8062 | 10324272.2087 | 11822500.7578 | 6275723.3507 | 6350958.2587 | 6645002.1315 | 5912008.9849 | 5857649.5396 | 5806676.9438 | 6115009.0692 | 5926640.9008 | 5926640.6556 | 5926641.4579 | 5926641.127 | 5926640.2189 | 41819203.3822 | 30336346.669 | 29633204.3602
Total capex |  |  | 450438536.7917 | 479727728.1988 | 581298581.6411 | 559166911.5775 | 400873600.9974 | 503525452.0145 | 594764495.1865 | 576355103.1249 | 582743799.536 | 522222546.0192 | 478569602.3786 | 597920982.8642 | 549224803.8011 | 543352227.3245 | 533888761.1317 | 2471505359.2065 | 2779611395.8811 | 2702956377.5001
Summary Base Capex
Renewal | Substations |  | 85183334.5549 | 86309794.3786 | 120817516.9917 | 151040827.8336 | 99000097.9503 | 114641797.6563 | 199155020.3034 | 145955113.5164 | 158972120.8181 | 96405461.1933 | 92331617.0456 | 153048375.9901 | 142453025.735 | 113833711.2591 | 100279984.6915 | 542351571.7091 | 715129513.4875 | 601946714.7213
| Buildings & Grounds |  | 17502087.0888 | 28308369.1452 | 19108525.3986 | 12310297.0351 | 12385102.7461 | 8054560.4661 | 10583970.5649 | 12078538.5085 | 9699566.5422 | 11974341.7228 | 12838201.7171 | 10632411.4022 | 9620975.0808 | 9617897.2624 | 9030620.4493 | 89614381.4137 | 52390977.8045 | 51740105.9118
| Transmission Lines |  | 147796306.3612 | 155732197.3496 | 174002747.151 | 173516345.6618 | 137643083.7657 | 137482297.3981 | 138047714.9604 | 181666085.4716 | 197057645.123 | 208878889.9495 | 180888455.2414 | 187760726.3262 | 197977463.7637 | 257943865.4684 | 240587649.2626 | 788690680.2894 | 863132632.9026 | 1065158160.0624
| HVDC & reactive assets |  | 30233252.7131 | 28559333.8845 | 51155661.2149 | 59352161.6407 | 33948559.025 | 27709221.5203 | 53776458.0503 | 46528124.0465 | 29241934.5353 | 20651087.0935 | 17215864.4862 | 24719339.1503 | 30974583.7856 | 23932005.063 | 30827267.5117 | 203248968.4783 | 177906825.2458 | 127669059.9968
| Secondary Assets |  | 45967919.0472 | 65525224.6019 | 75284165.7234 | 59048792.6731 | 47350135.8487 | 77327365.0647 | 76438678.4867 | 72862902.3152 | 71397763.527 | 60592767.9433 | 52880712.3242 | 83492292.2082 | 40423131.447 | 28589054.4103 | 44777083.5113 | 293176237.8943 | 358619477.3369 | 250162273.901
Total Renewal |  |  | 326682899.7652 | 364434919.3599 | 440368616.4796 | 455268424.8443 | 330326979.3357 | 365215242.1055 | 478001842.3657 | 459090763.8581 | 466369030.5455 | 398502547.9024 | 356154850.8145 | 459653145.0771 | 421449179.812 | 433916533.4632 | 425502605.4264 | 1917081839.7848 | 2167179426.7773 | 2096676314.5932
Other | E&D |  | 43857545.1794 | 34234164.2758 | 29311132.5734 | 24319044.9683 | 2987295.599 | 54962943.1707 | 28796710.2129 | 28783908.8601 | 30348683.6248 | 37333330.9337 | 37028749.3015 | 52813717.9597 | 42248781.7873 | 23834163.4105 | 22677391.6886 | 134709182.5958 | 180225576.8023 | 178602804.1476
| Resilience |  | 4647267.7508 | 19432923.2901 | 48197347.6073 | 54938081.8462 | 42200299.714 | 40197590.3841 | 41040639.9306 | 41603688.7065 | 39202715.4547 | 39248088.6052 | 38623726.2529 | 38698141.0645 | 38778738.1614 | 38861203.0405 | 38915671.4663 | 169415920.2084 | 201292723.081 | 193877479.9856
| ICT |  | 68205075.2901 | 51301449.0644 | 51598984.223 | 18365636.568 | 19008068.09 | 36504674.2227 | 41013293.6924 | 41019092.1605 | 41016692.9672 | 41023569.5087 | 40835635.1089 | 40829338.1073 | 40821462.5825 | 40813686.2834 | 40866452.3315 | 208479213.2353 | 200577322.5515 | 204166574.4135
| Business support capex |  | 7045748.8062 | 10324272.2087 | 11822500.7578 | 6275723.3507 | 6350958.2587 | 6645002.1315 | 5912008.9849 | 5857649.5396 | 5806676.9438 | 6115009.0692 | 5926640.9008 | 5926640.6556 | 5926641.4579 | 5926641.127 | 5926640.2189 | 41819203.3822 | 30336346.669 | 29633204.3602
Total Base Capex |  |  | 450438536.7917 | 479727728.1988 | 581298581.6411 | 559166911.5775 | 400873600.9974 | 503525452.0145 | 594764495.1865 | 576355103.1249 | 582743799.536 | 522222546.0192 | 478569602.3786 | 597920982.8642 | 549224803.8011 | 543352227.3245 | 533888761.1317 | 2471505359.2065 | 2779611395.8811 | 2702956377.5001

## 4. MCP and Listed projects Exp.
4. Major capex and listed projects, including IDC, constant 2025/26 $m |  | RCP4 |  |  |  |  | RCP5 |  |  |  |  | RCP6 |  |  |  |  | RCP Totals
This sheet sets out major capex and listed projects actuals and forecast |  | Actual | Forecast | Forecast | Forecast | Forcast | Forecast |  |  |  |  | Forecast
Spend basis $m | Expenditure Category | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | 2036/37 | 2037/38 | 2038/39 | 2039/40 | RCP4 Total | RCP5 Total | RCP6 Total
Approved Major Capex | Waikato & Upper North Island (WUNI) Voltage mgt Stage 1 Statcom | 7730665.7404 | 434929.2026 | 108514.622 | 111871.3597 | 110792.3871 | 53865.162 | 55104.2487 | 51580.0824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8496773.3119 | 160549.493 | 0
| Net Zero Grid Pathways - Stage 1.1 | 72695980.7861 | 90114897.7582 | 45121980.8803 | 40161380.4296 | 6049080.6162 | 435270.3567 | 315361.2118 | 322603.0792 | 330021.4878 | 337603.7352 | 142118.5932 | 0 | 0 | 0 | 0 | 254143320.4703 | 1740859.8707 | 142118.5932
| Western Bay of Plenty Capacity | 1514366.1391 | 12878180.4568 | 15944534.7372 | 26897627.9695 | 4811489.0857 | 1318166.6474 | 64911.001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62046198.3884 | 1383077.6484 | 0
| Redclyffe 220 kV Rebuild | 3010206.4292 | 21739121.6772 | 26054679.1257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50804007.2321 | 0 | 0
| NZGP 1.2 HVDC Capacity increase & cable replacement stg1 | 36222239.817 | 33893959.8951 | 35884682.1352 | 140525994.4264 | 189770476.9105 | 405690786.5478 | 189692675.7167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 436297353.1842 | 595383462.2646 | 0
| Other approved major capex | 6039.6998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6039.6998 | 0 | 0
| Total approved major capital projects expenditure | 121179498.6117 | 159061088.9899 | 123114391.5004 | 207696874.1851 | 200741838.9996 | 407498088.7139 | 190128052.1783 | 374183.1616 | 330021.4878 | 337603.7352 | 142118.5932 | 0 | 0 | 0 | 0 | 811793692.2867 | 598667949.2767 | 142118.5932
Major capex under development | Upper South Island upgrade - Stage 2 | 0 | 8322986.0883 | 27843598.1485 | 86223165.3572 | 59444775.8499 | 15121769.2884 | 20761970.1739 | 44380163.8654 | 8524611.4922 | 11672188.5323 | 0 | 0 | 0 | 0 | 0 | 181834525.4438 | 100460703.3521 | 0
| NZGP 1.2 HVDC Capacity increase & cable replacement stg2 | 0 | 0 | 39419584.2805 | 49521178.7014 | 51972916.0429 | 53195005.8832 | 123987984.1495 | 98464730.2306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 140913679.0248 | 275647720.2633 | 0
| Waikato and Upper North Island voltage management stage 2 | 0 | 3519733.2245 | 10330082.5394 | 45822349.2976 | 101348979.9283 | 111239187.4463 | 86488936.3359 | 62741957.6536 | 13203666.7255 | 32785022.4274 | 26918458.3351 | 0 | 29852340.305 | 96435355.0007 | 66900708.9828 | 161021144.9899 | 306458770.5886 | 220106862.6236
| Waikato regional interconnecting capacity | 0 | 0 | 3517508.4591 | 16029211.0004 | 23547327.4775 | 5031802.8553 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43094046.937 | 5031802.8553 | 0
| NZGP Wairakei Ring transmission constraint | 0 | 0 | 0 | 0 | 55533725.7339 | 103609808.8412 | 71799393.3779 | 80895045.2353 | 94899720.9634 | 73426963.729 | 0 | 0 | 0 | 0 | 0 | 55533725.7339 | 424630932.1468 | 0
| Tararua Regional Upgrade | 0 | 0 | 751631.9497 | 19003103.5512 | 32389382.4788 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52144117.9798 | 0 | 0
| Southland Regional Capacity | 0 | 0 | 578359.7239 | 33070618.8909 | 32762922.1379 | 3691602.5654 | 6105556.8275 | 11226167.0374 | 25562886.1607 | 24273405.4524 | 14477075.7747 | 0 | 0 | 0 | 0 | 66411900.7527 | 70859618.0434 | 14477075.7747
| North Canterbury Capacity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13160831.2967 | 23076644.7554 | 0 | 0 | 0 | 0 | 36237476.0521
| NZGP2 Central NI New Line | 66436.6976 | 0 | 0 | 0 | 13961551.6627 | 80041740.2382 | 177347368.8785 | 345175118.2434 | 399072230.7729 | 434295968.8699 | 159103139.5792 | 65106010.8505 | 336202201.2249 | 335682618.8492 | 335222435.8886 | 14027988.3604 | 1435932427.003 | 1231316406.3923
| ENC Regional capacity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total major capital projects expenditure under development | 66436.6976 | 11842719.3128 | 82440765.1011 | 249669626.7988 | 370961581.3119 | 371930917.118 | 486491209.7432 | 642883182.2657 | 541263116.1146 | 576453549.011 | 200498673.689 | 78266842.1472 | 389131186.2854 | 432117973.8499 | 402123144.8714 | 714981129.2223 | 2619021974.2525 | 1502137820.8428
Listed projects | RCP4 Listed HLY-OTA reconductor | 0 | 0 | 0 | 10200628.4198 | 30208304.3881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40408932.8079 | 0 | 0
| Haywards bus rationalisation | 0 | 0 | 4644927.1823 | 11189007.8143 | 18561139.8231 | 10147318.0256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 34395074.8198 | 10147318.0256 | 0
| RCP4 Listed OTA-WKM reconductor | 0 | 11438055.6388 | 28477451.2485 | 9399964.654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 49315471.5412 | 0 | 0
| RCP5 and 6 reconductoring | 0 | 0 | 0 | 0 | 0 | 127144473.8194 | 132200732.227 | 202624189.537 | 53064910.0412 | 167803663.1503 | 0 | 23751035.4153 | 72434353.149 | 29955846.8999 | 113840029.4678 | 0 | 682837968.7749 | 239981264.9321
| Total listed and other conductor replacement expenditure | 0 | 11438055.6388 | 33122378.4308 | 30789600.8881 | 48769444.2112 | 137291791.845 | 132200732.227 | 202624189.537 | 53064910.0412 | 167803663.1503 | 0 | 23751035.4153 | 72434353.149 | 29955846.8999 | 113840029.4678 | 124119479.1689 | 692985286.8005 | 239981264.9321
Total Major, Listed and Other projects |  | 121245935.3093 | 182341863.9415 | 238677535.0323 | 488156101.872 | 620472864.5227 | 916720797.6769 | 808819994.1485 | 845881554.9642 | 594658047.6436 | 744594815.8964 | 200640792.2822 | 102017877.5625 | 461565539.4344 | 462073820.7498 | 515963174.3392 | 1650894300.6779 | 3910675210.3297 | 1742261204.3681

## 5. Major capex - outputs
5. Major capital expenditure - outputs
This schedule presents outputs for both approved and under development major capex projects as of April 2026
Projects | Outputs | Status | Estimated cost (nominal) | Commissioning date (estimate)
Approved MCP
Waikato and Upper North Island Voltage Management (WUNI) Stage 1 | 1) one dynamic reactive device in the Upper North Island capable of delivering (within 10%) 150 Mvar capacitive to 150 Mvar inductive at nominal voltage 2) one dynamic reactive device in the Waikato capable of delivering (within 10%) 150 Mvar capacitive to 150 Mvar inductive at nominal voltage 3) a post-fault demand management scheme for the Waikato Upper North Island region 4) preparatory works for Stage 2, including additional investigation, consultation, obtaining property rights and environmental approvals, design work and non-binding tendering for future series capacitors and installation works on the BrownhillWhakamaru 1&2 transmission lines (BHL-WKM lines) | In progress | $173m | 2028-12-01
Net Zero Grid Pathways Stage 1 | 1) HVDC upgrade: installing reactive plant, filter banks and associated equipment to upgrade inter-island HVDC link north transfer availability from 1071 MW to closer to 1200 MW; 2) Central North Island upgrade: increasing transfer capacity north from Bunnythorpe by between 60% to 90% by installing variable line rating and tactical thermal upgrade of Tokaanu-Whakamaru lines and to Bunnythorpe-Tokaanu circuits; duplexing Tokaanu-Whakamaru circuits with Goat conductor; upgrading protection on Huntly-Stratford circuit; replacing the special protection scheme at Tokaanu; and splitting the Bunnythorpe-Ongarue circuit; 3) Wairakei ring upgrade: increasing transmission capacity by 25% (300 MW) under typical operating conditions by installing tactical thermal upgrading on both circuits of Wairakei-Whakamaru C line and the Edgecumbe-Kawerau 3 circuit on the Ohakuri-Edgecumbe A and Kawerau-Deviation lines; and splitting the Edgecumbe-Kawerau circuit; 4) Preparedness projects: carry out the investigation and design of a number of possible stage two projects. | In progress | $392.9m | 2028-06-01
Western Bay of Plenty | 1 install a new 220kV/110kV interconnecting transformer at Kaitemako; 2 reconductor the interconnection section of the Kaitemako-Tauranga 110kV line to a rating of 200MVA; 3 reconductor the Okere-Te Matai, Okere-Tarukenga, and Kaitemako-Te Matai 110kV lines to a rating of 195 MVA; and 4 fund a development NTS | In progress | $86.1m | 1938-06-01
Redclyffe 220 kV Rebuild | 1) Raising critical HV plant using equipment stands & access platforms 2) Supply and installation of new 220 kV electrical equipment 3) Install digital substation control building | In progress | $44m | 2027-12-01
NZGP 1.2 HVDC Capacity increase & cable replacement Stage 1 | 1) Installing four new undersea electricity cables – with the addition of a fourth cable boosting electricity transfer capacity to 1400 MW 2) New cable termination stations on either side of Cook Strait 3) Spare cable storage 4) A filter bank upgrade at Benmore 5) A scheme to raise the overload capacity of Pole 2. | Approved | $128m | Early 2030s
Unapproved MCP – under consideration by Commerce Commission
Upper South Island voltage stability | 1) Switching station at Orari 2) Switching station at Rangitaha 3) Lines turn ins to switching stations 4) Thermal upgrades of the Norwood-Rangitata circuit to 90°C and Orari-Rangitata circuit to 100°C 5) A total of 150 Mvar shunt capacitor banks at Orari 220kV 6) Automatic over-voltage shunt capacitor and shunt reactor switching scheme | Under consideration by Commerce Commission | $155m | TBC
Unapproved MCP – under investigation
NZGP 1.2 HVDC Capacity increase & cable replacement Stage 2 | Possible capacity increase, risk-based replacement of existing cables, and improve link reliability. | Investigation currently underway | $120m (Enhancement cost for fourth cable only. Cost for condition-based cable replacement is included in our Asset Management Plan.) | Early 2030's
Waikato and Upper North Island Voltage Management (WUNI) Stage2 | Addressing thermal and voltage constraints following on from the WUNI (stage 1) investments. Solution is costed as a series capacitor on the Brownhill– Whakamaru circuits | Investigation currently underway | $90m | 2030-2036
Waikato 220/110 kV interconnection capacity | Evaluate options to resolve n-1 constraints on the 220/110 kV interconnecting transformers at Hamilton, particularly during low generation on the Waikato 110 kV network. Additionally, this presents an opportunity to look at increasing security of supply to the Waikato region as it is currently supplied on n- security during outages on 220 kV circuits and 220/110 kV interconnectors. | Investigation currently underway | $48m | 2030
Wairakei-Whakamaru capacity | New 220 kV line between Whakamaru and the Taupō area | Investigation currently underway | $266m | 2030-2035 (or earlier), generation development dependent
Tararua Regional Upgrade | Long list consultation feedback published | Investigation currently underway | $25m | Generation dependent
Cross-Auckland transmission capacity | Install a fourth 220 kV transmission circuit across Auckland | Investigation currently underway | $800m | Mid-2030's
Lower South Island transmission capacity | Potential future transmission constraint modelled, awaiting MCP investigation | Needs identification | TBC | TBC
Unapproved Major Capex Projects – investigation scheduled for options analysis
Brunswick-Stratford | Reconductor A line with higher capacity conductor, dismantle B line | Needs identification | $113m | 2026-2030
Unapproved Major Capex Projects – investigation scheduled to confirm need
Northland 220kV transmission capacity | TBC | Needs identification | TBC | TBC

## 6. Grid Performance Targets
6. RCP4 Grid Performance targets
The RCP4 determination contains two revenue-linked grid performance measures: GP1 measures the total number of unplanned interruptions experienced by each point of service sub-category during a disclosure year. GP2 measures the average duration of unplanned interruptions experienced by each point of service sub-category during a disclosure year. Together, these measures indicate the reliability of the transmission grid from a customer perspective: GP1 measures how often customers experience transmission interruptions. GP2 measures how long those interruptions last. Compliance occurs when interruption frequency (GP1) and interruption duration (GP2) remain below the applicable quality collar (limit) for the relevant customer categories, taking account of the Determination's assessment methodology. Non-compliance occurs when the GP1 or GP2 quality standard is not met. In practical terms, this means customers experienced either: More unplanned interruptions than allowed under the quality standards (GP1); or Longer interruption durations than allowed under the quality standards (GP2). Green cell shading - grid performance assessed value falls below collar (limit). Red cell shading - grid performance assessed value exceeds collar (limit).
This schedule presents our RCP4 targets for the two grid performance measures (GP1 and GP2) measuring the number and average duration of unplanned interruptions.
|  |  | Quality Standards |  |  | FY25/26 Performance |  |  | FY26/27 Performance |  |  | FY27/28 Performance |  |  | FY28/29 Performance |  |  | FY29/30 Performance
|  | Measure | Cap | Target | Collar | Assessed value | Incentive rate | Output adjustment | Assessed value | Incentive rate | Output adjustment | Assessed value | Incentive rate | Output adjustment | Assessed value | Incentive rate | Output adjustment | Assessed value | Incentive rate | Output adjustment
| GP1: number of interruptions (per annum) | [5 empty] | $ per interruption |  |  | $ per interruption |  |  | $ per interruption |  |  | $ per interruption |  |  | $ per interruption
|  | N-1 Security High Economic Consequence | 0 | 4 | 8 | 4 | 789666 | 0 |  | 789666 |  |  | 789666 |  |  | 789666 |  |  | 789666
|  | N-1 Security Material Economic Consequence | 4 | 21 | 38 | 18 | 170537 | 511611 |  | 170537 |  |  | 170537 |  |  | 170537 |  |  | 170537
|  | N Security High Economic Consequence | 0 | 2 | 4 | 2 | 185592 | 0 |  | 185592 |  |  | 185592 |  |  | 185592 |  |  | 185592
|  | N Security Material Economic Consequence | 4 | 15 | 26 | 9 | 57795 | 346770 |  | 57795 |  |  | 57795 |  |  | 57795 |  |  | 57795
|  | N-1 Security Generator | 4 | 9 | 14 | 6 | 50000 | 150000 |  | 50000 |  |  | 50000 |  |  | 50000 |  |  | 50000
|  | N Security Generator | 4 | 7 | 10 | 13 | 83333 | -249999 |  | 83333 |  |  | 83333 |  |  | 83333 |  |  | 83333
|  | Total output adjustment ($) | [5 empty] | 758382
| GP2: average duration of interruptions (mins) | [5 empty] | $ per minute |  |  | $ per minute |  |  | $ per minute |  |  | $ per minute |  |  | $ per minute
|  | N-1 Security High Economic Consequence | 23 | 73 | 123 | 105 | 63173 | -2021536 |  | 63173 |  |  | 63173 |  |  | 63173 |  |  | 63173
|  | N-1 Security Material Economic Consequence | 27 | 74 | 121 | 80.8 | 61683 | -419444.4 |  | 61683 |  |  | 61683 |  |  | 61683 |  |  | 61683
|  | N Security High Economic Consequence | 15 | 66 | 117 | 90 | 7278 | -174672 |  | 7278 |  |  | 7278 |  |  | 7278 |  |  | 7278
|  | N Security Material Economic Consequence | 0 | 104 | 208 | 395.6 | 6113 | -635752 |  | 6113 |  |  | 6113 |  |  | 6113 |  |  | 6113
|  | N-1 Security Generator | 30 | 225 | 420 | 84.8 | 1282 | 179736.4 |  | 1282 |  |  | 1282 |  |  | 1282 |  |  | 1282
|  | N Security Generator | 0 | 123 | 246 | 193.3 | 2033 | -142919.9 |  | 2033 |  |  | 2033 |  |  | 2033 |  |  | 2033
|  | Total output adjustment ($) | [5 empty] | -3214587.9

## 7. Asset Performance & Health
7. Asset performance and Health targets
Asset performance
AP1 (HVDC Energy Availability) measures the annual availability of the HVDC system (primarily Pole 2 and Pole 3) as a percentage of its total capacity over the disclosure year. AP2 (HVAC Asset Availability) measures the percentage availability of specified HVAC transmission assets over the disclosure year. Transpower is required to achieve annual availability above the regulatory quality standards specified in the RCP4 determination. Compliance occurs when the reported annual availability exceeds the applicable quality standard. Non-compliance occurs when annual availability falls below the relevant quality standard, indicating that asset performance has not met the minimum reliability level required by the Commerce Commission. Green cell shading - asset availability performance exceeds collar. Yellow cell shading - asset availability performance equals collar. Red cell shading - asset availability performance does not exceed collar.
This schedule presents the asset performance caps, collars, targets, quality standards and incentive summary.
| Measure | Cap | Target | Collar | Quality standard | Incentive rate | $ at risk per year | DY 2026 Performance | DY 2026 Output | DY 2027 Performance | DY 2027 Output | DY 2028 Performance | DY 2028 Output | DY 2029 Performance | DY 2029 Output | DY 2030 Performance | DY 2030 Output
| AP1: HVDC availability (%) |  |  |  |  | $ per 1%
| HVDC availability | 99% | 98% | 97% | 96% | 1000000 | 1000000 | 98.22% | 220000
| AP2: HVAC availability (%) |  |  |  |  | $ per 1%
| HVAC availability (selected assets) | 98.62% | 98.25% | 97.87% | 97.45% | 5320564 | 2021814 | 98.5% | 1330141
| AP1 - Performance Compliant? | [6 empty] | Compliant
| AP2 - Performance Compliant? | [6 empty] | Compliant
Asset health
The purpose of asset health measures is to provide an indication of whether Transpower is effectively managing asset condition and preventing deterioration of critical transmission assets over time. Rather than measuring service availability, it measures the underlying health and condition of the asset fleet. To comply with the AH assessment, the assessed value for four or more asset health measure asset classes must not exceed their specified quality limits for the relevant disclosure year. Certain asset classes (conductors, insulators, power transformers, and outdoor circuit breakers) are weighted by asset criticality when calculating the assessed value. Green cell shading - asset health measure actual does not exceed limit. Yellow cell shading - asset health measure actual equals limit. Red cell shading - asset health measure actual exceeds limit.
This schedule presents the asset health targets for asset classes with an AHI of 8 or higher for RCP4.
*Criticality weighted
| Asset Class Target | DY 2026 Standard | DY 2026 Actual | DY 2027 Standard | DY 2027 Actual | DY 2028 Standard | DY 2028 Actual | DY 2029 Standard | DY 2029 Actual | DY 2030 Standard | DY 2030 Actual
|  | % | % | % | % | % | % | % | % | % | %
| Tower grillage foundations | 4.26 | 5.84 | 3.51 |  | 3.9 |  | 4.04 |  | 3.99
| Tower protective coatings | 13.98 | 9.11 | 15.89 |  | 17.79 |  | 20.02 |  | 22.09
| Insulators* | 2.79 | 1.88 | 3.14 |  | 3.85 |  | 4.76 |  | 5.98
| Conductors* | 1.76 | 2.36 | 1.97 |  | 2.18 |  | 2.37 |  | 2.61
| Protection Relays | 7.56 | 7.82 | 6.92 |  | 6.37 |  | 8.12 |  | 8.61
| Power transformers* | 5.17 | 3.85 | 9.15 |  | 11.53 |  | 12.18 |  | 13.35
| Outdoor circuit breakers* | 1.24 | 0.3 | 1.45 |  | 2.46 |  | 3.19 |  | 4.27
| Asset Health - Performance Compliant? |  | Compliant