## outage-windows-2026-05-14-13-52
Outage Block Name | Description of Work | Planned Start | Planned Finish | Timeframe | Region | Nature | Status | Window ID
MAT_RTU_1 | Outage required for LAN switch replacement as part of the Substation LAN Lifecycle Refresh project | 2026-07-01 08:00 | 2026-07-02 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1162627
HKK_C7C8C9 | OTI-HKK Protection Replacement. Relocate HKK Capacitor Bank VT I/O to new panel, re-establish VT supplies. | 2026-07-01 08:00 | 2026-07-03 17:30 | Continuous | SI | RS - Removal from Service | Approved | OW1162650
CCT_8310_CYD_ROX | CYD - SMR Internal Plant Works | 2026-07-01 08:00 | 2026-07-01 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1163142
WHU_RTU_1 | WHU Bus Extension Project - Project SCADA config & Testing WHU Bus Extension Project - Project SCADA config & Testing | 2026-07-01 10:00 | 2026-07-01 14:00 | Daily | NNI | RS - Removal from Service | Approved | OW2005365
WKM_CB_562 | Affected equipment with OHW_WKM_2 and for the reconnection of PAK_WKM_2 | 2026-07-02 07:00 | 2026-07-04 10:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162808
OHW_WKM_2 | Decommission CCT | 2026-07-02 07:00 | 2026-07-02 17:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162707
WKM_CB_572 | Affected equipment with OHW_WKM_2 and for the reconnection of PAK_WKM_2 | 2026-07-02 07:00 | 2026-07-04 10:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162811
WTU_FDR_2162 | Assurance of Isolated & Earthed requested by UNN | 2026-07-02 07:30 | 2026-07-02 13:30 | Daily | SNI | RS - Removal from Service | Approved | OW2006399
BEN_220BZ | BEN 220BZ - T27 Migration | 2026-07-02 07:30 | 2026-07-02 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160228
MCH_RTU_1 | SMS & GPS Replacements inc n-1 Improvements 25/27 (RSA5) | 2026-07-02 07:30 | 2026-07-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161030
PAK_CB_512 | Siemens relay replacement | 2026-07-02 07:30 | 2026-07-04 10:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1162721
BEN_220CBF | BEN 220BZ - T27 Migration | 2026-07-02 07:30 | 2026-07-02 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160245
DRY_GLN_2 | New GLN anti-islanding scheme install and test | 2026-07-02 07:30 | 2026-07-09 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1163450
DRY_220BS_A | New GLN Anti-islanding scheme install and test | 2026-07-02 07:30 | 2026-07-09 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1163451
DRY_CB_412 | Affected Equipment New GLN Anti-islanding scheme install and test | 2026-07-02 07:30 | 2026-07-09 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1163452
PAK_220BS_B | Reconnect and commission PAK-WKM 2 | 2026-07-02 07:30 | 2026-07-04 10:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1162708
PAK_R582 | Affected Equipment Reconnect and commission PAK-WKM 2 | 2026-07-02 07:30 | 2026-07-04 10:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1162714
PAK_CB_432 | Affected Equipment Reconnect and commission PAK-WKM 2 | 2026-07-02 07:30 | 2026-07-04 10:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1162710
PAK_CB_462 | Affected Equipment Reconnect and commission PAK-WKM 2 | 2026-07-02 07:30 | 2026-07-04 10:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1162711
PAK_CB_522 | Siemens relay replacement | 2026-07-02 07:30 | 2026-07-04 10:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1162713
PAK_CB_492 | Affected Equipment Reconnect and commission PAK-WKM 2 | 2026-07-02 07:30 | 2026-07-04 10:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1162712
MTR_RTU_1 | Replace Cisco 2520 switches with Moxa PT-G7728 switches | 2026-07-02 08:00 | 2026-07-03 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005067
CCT_5205_MTO_WEL | Outage block to cover site build preparation for external fibreworks. Note this will impact both ends of the CCT circut in MOTand WEL with crews at both ends. | 2026-07-02 08:00 | 2026-07-02 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1162920
HWA_OHG_1 | OHG GXP PJ. Maintenance and TTU work. Optimised. HWA_OHG_1 HWA-PTA TTU Works | 2026-07-02 08:00 | 2026-07-30 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1159185
WRD_220BS_C | GIS mtce by GE Vernova | 2026-07-02 08:00 | 2026-07-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1159275
WRD_CB_178 | Affected Equipment GIS mtce by GE Vernova | 2026-07-02 08:00 | 2026-07-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1159276
HOB_WRD_1 | GIS mtce by GE Vernova | 2026-07-02 08:00 | 2026-07-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1159277
WRD_T7 | GIS mtce by GE Vernova | 2026-07-02 08:00 | 2026-07-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1159278
BEN_220BZ | BZ project | 2026-07-03 08:00 | 2026-07-03 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1162070
BEN_220CBF | BZ project | 2026-07-03 08:00 | 2026-07-03 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1162071
HOR_KBY_ISL_2 | ISL Cable Project -remake jumpers ISL_KBT_2 | 2026-07-04 06:30 | 2026-07-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2006212
KBY_CB_4902 | Affected Equipment of HOR_KBY_ISL_2 ISL Cable Project -remake jumpers ISL_KBT_2 | 2026-07-04 06:30 | 2026-07-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2006213
WRD_220BS_A | GIS mtce by GE Vernova | 2026-07-05 08:00 | 2026-07-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1159279
WRD_CB_138 | Affected Equipment GIS mtce by GE Vernova | 2026-07-05 08:00 | 2026-07-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1159280
WRD_CB_112 | GIS mtce by GE Vernova | 2026-07-05 08:00 | 2026-07-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1159281
ALB_WRD_4 | GIS mtce by GE Vernova | 2026-07-05 08:00 | 2026-07-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1159282
WRD_T7 | GIS mtce by GE Vernova | 2026-07-05 08:00 | 2026-07-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1159283
DOB_RFN_IGH_1 | BWR-IGH-A0398, BWR-IGH-A0420, BWR-IGH-A0472 IGH 110 kV CB412 Line Protection Replacement | 2026-07-06 06:30 | 2026-07-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161895
DRY_220CBF_A_PROT1 | New GLN Anti-islanding scheme install and test | 2026-07-06 07:30 | 2026-07-06 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1163456
DRY_220BZ_A_PROT1 | New GLN Anti-islanding scheme install and test | 2026-07-06 07:30 | 2026-07-06 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1163455
BOB_T4 | Affected Equipment New GLN Anti-islanding scheme install and test | 2026-07-06 07:30 | 2026-07-06 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1163454
DRY_BOB_HLY_1 | New GLN Anti-islanding scheme install and test | 2026-07-06 07:30 | 2026-07-06 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1163453
DOB_T12 | Affected Equipment of DOB_RFN_IGH_1 BWR-IGH-A0398 | 2026-07-06 07:30 | 2026-07-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161898
TWI_CB_468 | TWI-P-CB-468 | 2026-07-06 07:30 | 2026-07-06 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161733
LFD_RTU_1 | SMS Replacements inc n-1 Improvements 25/27 (RSA2) | 2026-07-06 07:30 | 2026-07-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161012
KAI_FDR_7 | KAI-CB-7, KAI IDID CP_KAI_84_00_00. CP_KAI_87_00_00 KAI-CB-7 | 2026-07-06 07:30 | 2026-07-06 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1149199
ARI_HAM_2 | Reinsulation | 2026-07-06 07:30 | 2026-07-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005340
ARI_HAM_1 | Reinsulation | 2026-07-06 07:30 | 2026-07-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160163
CST_T2 | CST-M-CT2132, CST-M-VT2132. CST-P-TF-T2 [CP_CST_00Q_0_00]. | 2026-07-06 07:30 | 2026-07-08 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160416
EDN_T1 | EDN-CB-2052, EDN-M-CT2052, EDN-M-VT5 | 2026-07-06 07:30 | 2026-07-08 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160490
TWI_CB_478 | TWI-P-CB-478 | 2026-07-07 07:30 | 2026-07-07 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161734
WEL_AUVLS | WEL-P-UVLS | 2026-07-07 07:30 | 2026-07-08 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161771
GLN_220BZ | New GLN Anti-islanding scheme install and test | 2026-07-07 07:30 | 2026-07-07 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1163457
GLN_220CBF | New GLN Anti-islanding scheme install and test | 2026-07-07 07:30 | 2026-07-07 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1163458
FHL_T3 | FHL-TF-T3 | 2026-07-07 07:30 | 2026-07-07 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160498
FHL_RTU_1 | SMS replacements [CP_RA4_03E_0_00] | 2026-07-07 07:30 | 2026-07-07 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160496
WRD_220BS_A | GIS mtce by GE Vernova | 2026-07-07 08:00 | 2026-07-08 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1159292
WRD_CB_138 | Affected Equipment GIS mtce by GE Vernova | 2026-07-07 08:00 | 2026-07-08 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1159293
WRD_CB_112 | GIS mtce by GE Vernova | 2026-07-07 08:00 | 2026-07-08 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1159297
WPW_RTU_1 | Download new config for T1 protection changes | 2026-07-07 08:00 | 2026-07-07 16:00 | Daily | SNI | SCA - SCADA Interrupt Request | Approved | OW1157855
KBY_RTU_1 | Outage required for LAN switch replacement as part of the Substation LAN Lifecycle Refresh project | 2026-07-07 08:00 | 2026-07-08 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1162628
HOB_WRD_1 | GIS mtce by GE Vernova | 2026-07-07 08:00 | 2026-07-08 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1159298
TWZ_220BZ_A_PROT1 | TWZ-P-BZ-220-A-P1 | 2026-07-08 07:30 | 2026-07-08 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161736
TWI_CB_518 | TWI-P-CB-518 | 2026-07-08 07:30 | 2026-07-08 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161735
BPE_RTU_1 | Post first circuit outage | 2026-07-08 08:00 | 2026-07-08 11:00 | Daily | SNI | RS - Removal from Service | Approved | OW1162423
BPD_RTU_1 | RTU config download. | 2026-07-08 10:00 | 2026-07-08 15:00 | Daily | SI | RS - Removal from Service | Approved | OW2005336
MTN_RTU_1 | Post first circuit outage | 2026-07-08 13:00 | 2026-07-08 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW1162430
TWI_CB_428 | TWI-P-CB-428 | 2026-07-09 07:30 | 2026-07-09 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161732
TWZ_220BZ_A_PROT2 | TWZ-P-BZ-220-A-P2 | 2026-07-09 07:30 | 2026-07-09 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161737
TWZ_220BZ_B_PROT1 | TWZ-P-BZ-220-B-P1 | 2026-07-09 07:30 | 2026-07-09 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161738
TWZ_220BZ_B_PROT2 | TWZ-P-BZ-220-B-P2 | 2026-07-09 07:30 | 2026-07-09 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161739
WGN_RTU_1 | Post first circuit outage | 2026-07-09 08:00 | 2026-07-09 11:00 | Daily | SNI | RS - Removal from Service | Approved | OW1162435
OTI_67_46_56 | OTI-VT-VT67 OTI 66 kV CB/CT/VT Repl 27/28 | 2026-07-13 06:30 | 2026-07-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161351
COL_OTI_2 | Affected Equipment of OTI_67_46_56 OTI-VT-VT67 | 2026-07-13 06:30 | 2026-07-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160393
WRK_DIS_117 | CLO for the duration of WRK_77_97, to maintain a solid 220kV bus. | 2026-07-13 07:30 | 2026-07-13 18:30 | Daily | SNI | CLO - Close | Approved | OW1161857
HKK_OTI_2 | OTI-CB-52 Pole Replacement and Affected Equipment of OTI_67_46_56 OTI-VT-VT67 | 2026-07-13 07:30 | 2026-07-17 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005484
WRK_CB_108 | Affected equipment of WRK_77_97. | 2026-07-13 07:30 | 2026-07-13 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161851
TMU_FDR_24 | Affected equipment TMU_11BS_A1 & TMU_FDR_23 | 2026-07-13 07:30 | 2026-07-15 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161671
TMU_FDR_22 | Affected equipment TMU_11BS_A1 & TMU_FDR_23 | 2026-07-13 07:30 | 2026-07-15 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161669
TMU_CB_38 | Affected equipment TMU_11BS_A1 & TMU_FDR_23 | 2026-07-13 07:30 | 2026-07-15 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161668
WRK_77_97 | WRK-DS-87, WRK-DS-194 (NAP_2) | 2026-07-13 07:30 | 2026-07-13 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161849
TMU_CB_37 | Affected equipment TMU_11BS_A1 & TMU_FDR_23 | 2026-07-13 07:30 | 2026-07-15 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161667
TMU_11BS_A1 | TMU-BS-11-A1 | 2026-07-13 07:30 | 2026-07-15 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161662
OTA_PEN_2 | Replace OTA CT152. | 2026-07-13 07:30 | 2026-07-18 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1163435
NAP_WRK_2 | OKI-ES-309, OKI-P-CB-302, WRK-CB-192, WRK-CVT-192, WRK-DS-196, WRK-ES-199, WRK-P-CB-192. Affected equipment of WRK_77_97. | 2026-07-13 07:30 | 2026-07-15 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161197
BRB_RTU_1 | BRB T2, T3 TOPS Scheme Project | 2026-07-13 09:00 | 2026-07-13 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162988
WPW_LST_31 | Decommissioning this asset | 2026-07-14 07:00 | 2026-07-20 17:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1157826
FHL_WPW_2 | For safety while working around WPW T1 | 2026-07-14 07:00 | 2026-07-20 17:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1157825
WPW_214_267 | Affected Equipment Cut over from outdoor CB 292 to new CB in CNL switchroom | 2026-07-14 07:00 | 2026-07-20 17:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1157836
WPW_DIS_36B | Affected Equipment Relocation and divestment of this asset to CNL | 2026-07-14 07:00 | 2026-07-19 16:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1157823
WPW_DIS_36A | Affected Equipment Relocation and divestment of this asset to CNL | 2026-07-14 07:00 | 2026-07-19 16:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1157822
WPW_T1 | Cut over from outdoor CB 292 to new CB in CNL switchroom | 2026-07-14 07:00 | 2026-07-20 17:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1163338
WPW_T33 | Relocation and divestment of this asset to CNL | 2026-07-14 07:00 | 2026-07-19 16:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1157821
WPW_FDR_222 | Affected Equipment Affected Equipment Cut over from outdoor CB 292 to new CB in CNL switchroom | 2026-07-14 07:00 | 2026-07-20 17:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1157837
WPW_FDR_302 | Affected Equipment Affected Equipment Cut over from outdoor CB 292 to new CB in CNL switchroom | 2026-07-14 07:00 | 2026-07-20 17:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1157854
WPW_FDR_282 | Affected Equipment Affected Equipment Cut over from outdoor CB 292 to new CB in CNL switchroom | 2026-07-14 07:00 | 2026-07-20 17:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1157853
WPW_FDR_242 | Affected Equipment Affected Equipment Cut over from outdoor CB 292 to new CB in CNL switchroom | 2026-07-14 07:00 | 2026-07-20 17:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1157838
WPW_247_304_314 | Affected Equipment Cut over from outdoor CB 292 to new CB in CNL switchroom | 2026-07-14 07:00 | 2026-07-20 17:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1157852
ABY_TIM_1 | Affected Equipment TIM-CSA-98 | 2026-07-14 07:30 | 2026-07-15 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1163385
TIM_CB_98 | Affected Equipment TIM-CSA-98 | 2026-07-14 07:30 | 2026-07-15 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1163386
TIM_T8 | Affected Equipment of TIM_97_114_134 TIM-CSA-98 | 2026-07-14 07:30 | 2026-07-15 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161619
CST_T4 | CST-M-CT2262, CST-M-VT2262. CST-P-TF-T4 [CP_CST_00Q_0_00]. | 2026-07-14 07:30 | 2026-07-16 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160417
TMK_TIM_2_TMK_T2 | Affected Equipment TIM-CSA-98 | 2026-07-14 07:30 | 2026-07-15 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1163387
TIM_T6 | Affected Equipment of TIM_97_114_134 TIM-CSA-98 | 2026-07-14 07:30 | 2026-07-15 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161617
TIM_CB_2752 | Affected Equipment of TIM_97_114_134 TIM-CSA-98 | 2026-07-14 07:30 | 2026-07-15 18:30 | Daily | SI | CLO - Close | Approved | OW1161611
TIM_97_114_134 | TIM-CSA-98 | 2026-07-14 07:30 | 2026-07-15 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161610
EDN_T2 | EDN-CB-2112, EDN-M-CT2112, EDN-M-VT6 | 2026-07-14 07:30 | 2026-07-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160491
GFD_CB_2188 | GFD-CBL-2188-2217 | 2026-07-14 07:30 | 2026-07-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160509
PAO_RTU_1 | SMS Replacements inc n-1 Improvements 25/27 (RSA2) | 2026-07-14 07:30 | 2026-07-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161366
STK_RTU_3 | STK-P-SMS-A. NOC IP Team Switch work - JSD-12072 | 2026-07-14 08:00 | 2026-07-14 13:00 | Daily | SI | RS - Removal from Service | Approved | OW1163356
KOE_MPE_1 | Attachment points, re-insulation and steel and bolts. | 2026-07-14 08:00 | 2026-07-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005212
STK_RTU_2 | STK-P-SMS-A. NOC IP Team Switch work - JSD-12072 | 2026-07-14 08:00 | 2026-07-14 13:00 | Daily | SI | RS - Removal from Service | Approved | OW1163355
STK_RTU_1 | STK-P-SMS-A. NOC IP Team Switch work - JSD-12072 | 2026-07-14 08:00 | 2026-07-14 13:00 | Daily | SI | RS - Removal from Service | Approved | OW1163354
GYT_RTU_1 | Outage required for LAN switch replacement as part of the Substation LAN Lifecycle Refresh project | 2026-07-14 08:00 | 2026-07-15 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1162629
CCT_1090_HRP_WRK | Fibre Access cables for TRU | 2026-07-14 08:30 | 2026-07-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005300
CCT_1070_HRP_WHI | TRU SMR Access Fibre Cables | 2026-07-14 08:30 | 2026-07-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005301
MLG_CB_38 | MLG-CB-38, MLG-P-CB-38 | 2026-07-15 07:00 | 2026-07-15 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161059
TGA_110BZ | TGA-P-BZ-110-A | 2026-07-15 07:30 | 2026-07-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161594
TGA_110CBF | TGA-P-BS-110 | 2026-07-15 07:30 | 2026-07-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161595
PEN_STC_1 | Power supply replacement | 2026-07-15 07:30 | 2026-07-16 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW2006406
PEN_LS1 | Affected Equipment of PEN_STC_1 Power supply replacement | 2026-07-15 07:30 | 2026-07-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006407
FHL_110BZ | FHL-P-BZ-110 | 2026-07-15 07:30 | 2026-07-15 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160492
FHL_110CBF | Affected equipment of FHL_110BZ, for FHL-P-BZ-110 | 2026-07-15 07:30 | 2026-07-15 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160493
OTA_TIE_5 | OTA-CT-552, OTA-DS-556, OTA-ES-559, OTA-P-CB-1302-CZP, OTA-P-CB-552 | 2026-07-15 07:30 | 2026-07-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161348
ARG_RTU_1 | ARG-P-SMS-A. NOC IP Team Switch work - JSD-12080 | 2026-07-15 12:00 | 2026-07-15 17:00 | Daily | SI | RS - Removal from Service | Approved | OW1163357
TKR_33BZ_K | TKR-P-BZ-33 | 2026-07-16 07:30 | 2026-07-17 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161626
TKR_33BZ_L | TKR-P-BZ-33 | 2026-07-16 07:30 | 2026-07-17 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161627
TKR_33CBF | Affected equipment of TKR_33BZ_K/L, for TKR-P-BZ-33 | 2026-07-16 07:30 | 2026-07-17 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161628
MCH_RTU_1 | MCH-P-SMS-A. NOC IP Team Switch work - JSD-12118 | 2026-07-16 08:00 | 2026-07-16 13:00 | Daily | SI | RS - Removal from Service | Approved | OW1163359
NMA_220CBF | Work Description: Project Works - NMA Protection Project - Decommission Old RTU. | 2026-07-16 08:00 | 2026-07-16 17:00 | Daily | SI | RS - Removal from Service | Approved | OW2006026
NMA_220BZ | Work Description: Project Works - NMA Protection Project - Decommission Old RTU. | 2026-07-16 08:00 | 2026-07-16 17:00 | Daily | SI | RS - Removal from Service | Approved | OW2006025
NMA_RTU_1 | Work Description: Project Works - NMA Protection Project - Decommission Old RTU. | 2026-07-16 08:00 | 2026-07-16 17:00 | Daily | SI | RS - Removal from Service | Approved | OW2006028
OTA_110CBF | Stability testing OTA CT162 v CT152 | 2026-07-17 07:30 | 2026-07-17 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1163438
OTA_110BZ | Stability testing OTA CT162 v CT152 | 2026-07-17 07:30 | 2026-07-17 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1163437
OTA_ROS_1 | Stability testing OTA CT162 v CT152 | 2026-07-17 07:30 | 2026-07-17 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1163436
SBK_FDR_152 | SBK-CB-152 | 2026-07-17 07:30 | 2026-07-17 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161526
IGH_RTU_1 | Adding a point to the SMS JSD-9066 | 2026-07-17 08:00 | 2026-07-17 13:00 | Daily | SI | RS - Removal from Service | Approved | OW1163838
ISL_CB_688 | Corroding SF6 pipework | 2026-07-20 07:00 | 2026-07-24 17:00 | Continuous | SI | RS - Removal from Service | Approved | OW1163297
HUI_FDR_1262 | HUI-CB-1262 | 2026-07-20 07:00 | 2026-07-20 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160738
MNI_CB_808 | MNI-P-CB-808 | 2026-07-20 07:00 | 2026-07-20 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161085
HUI_MNI_1 | HUI-CVT-892, HUI-DS-896, HUI-ES-899, HUI-P-CB-892, MNI-BU-832, MNI-CVT-832, MNI-P-CB-832 | 2026-07-20 07:00 | 2026-07-21 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160740
STU_66_77 | Affected Equipment of STU_77_66_T6 STU-TF-T6B, STU-TF-T6R, STU-TF-T6Y | 2026-07-20 07:30 | 2026-07-24 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005928
HAY_STC_31 | S4.10F31-R1, S4.10J01-C1, S4.10J01-L1, S4.10J01-Q15, S4.10J01-Q2, S4.10J01-Q2-R1, S4.10J01-STC31, S4.10J01-T7, S4.10T31 | 2026-07-20 07:30 | 2026-07-24 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160626
ASB_FDR_82 | Affected Equipment of ASB_T10 ASB-NCDT-T10 | 2026-07-20 07:30 | 2026-07-27 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005042
WRD_CB_112 | WRD T9 Installation PJ - New GIS duct and wall bushing installation to WRD CB 112. | 2026-07-20 07:30 | 2026-08-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006458
WDV_T1 | WDV-M-CT2632, WDV-M-VT2632 | 2026-07-20 07:30 | 2026-07-21 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161770
BRB_CB_148 | Affected Equipment of BRB_220BS_B Repair BRB DS143 indication, fleeting mid-pos alarms | 2026-07-20 07:30 | 2026-07-20 17:00 | Daily | NNI | RS - Removal from Service | Approved | OW2005234
OTA_TIE_4 | OTA-DS-405, OTA-DS-413, OTA-ES-419, OTA-P-CB-1222-CZP, OTA-CT-412, OTA-P-CB-412, OTA-CT-402, OTA-P-CB-402 | 2026-07-20 07:30 | 2026-07-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161347
BRB_220BS_B | Repair BRB DS143 indication, fleeting mid-pos alarms | 2026-07-20 07:30 | 2026-07-20 17:00 | Daily | NNI | RS - Removal from Service | Approved | OW2005233
GLN_CB_658 | Affected Equipment of GLN_220BS_A GLN DS613 motor drive retrofit | 2026-07-20 07:30 | 2026-07-23 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW2005369
ASB_T10 | ASB-NCDT-T10 | 2026-07-20 07:30 | 2026-07-27 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005041
MGM_MST_1 | Pole replacements x11 (inc. 4x tagged poles). PDM-L AGS conductor clamp replacement and other PDM works | 2026-07-20 07:30 | 2026-07-24 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161049
ROS_110BZ | ROS-P-BZ-110 | 2026-07-20 07:30 | 2026-07-21 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161476
ROS_110CBF | ROS-P-BZ-110 | 2026-07-20 07:30 | 2026-07-21 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161477
TMI_RTU_1 | SMS Replacements inc n-1 Improvements 25/27 (RSA2) | 2026-07-20 07:30 | 2026-07-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161650
GLN_220BS_A | GLN DS613 motor drive retrofit | 2026-07-20 07:30 | 2026-07-23 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW2005368
ROT_33BZ | ROT-P-BZ-33 | 2026-07-20 07:30 | 2026-07-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161492
BRB_CB_158 | Affected Equipment of BRB_220BS_B Repair BRB DS143 indication, fleeting mid-pos alarms | 2026-07-20 07:30 | 2026-07-20 17:00 | Daily | NNI | RS - Removal from Service | Approved | OW2005235
TKR_CB_92_ITRIP | TKR-P-ITRP-CB-92-172 | 2026-07-20 07:30 | 2026-07-20 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161630
ROT_33CBF | Affected equipment | 2026-07-20 07:30 | 2026-07-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161493
DRY_GLN_2 | GLN DS613 motor drive retrofit | 2026-07-20 07:30 | 2026-07-23 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW2005366
STU_77_66_T6 | STU-TF-T6B, STU-TF-T6R, STU-TF-T6Y | 2026-07-20 07:30 | 2026-07-24 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161565
BRB_T2 | BRB T2, T3 TOPS Scheme Project | 2026-07-20 07:30 | 2026-07-21 17:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1162989
BRB_FDR_2232 | BRB T2, T3 TOPS Scheme Project | 2026-07-20 07:30 | 2026-07-21 17:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1162990
EDG_OWH_2 | RC attachment points | 2026-07-20 08:00 | 2026-07-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005668
WRK_DIS_117 | Affected equipment. WRK_47_44_197 | 2026-07-20 08:00 | 2026-07-22 18:30 | Continuous | SNI | CLO - Close | Approved | OW1162044
OHW_OTA_1 | Sub-conductor spacer project | 2026-07-20 08:00 | 2026-07-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005683
WRK_47_44_197 | Replace strung Conductors with tubular bus Replace 220kV Bus Hardware - WRK T30 Upgrade Project | 2026-07-20 08:00 | 2026-07-22 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1159857
HOB_WRD_1 | HOB-WRD-A-CBL-SHEATH, WRD-CBL-182-R182 | 2026-07-20 08:00 | 2026-08-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1149890
WRK_CB_198 | Affected Equipment Replace strung Conductors with tubular bus Replace 220kV Bus Hardware - WRK T30 Upgrade Project | 2026-07-20 08:00 | 2026-07-22 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1159858
WRK_T30 | Replace strung Conductors with tubular bus Replace 220kV Bus Hardware - WRK T30 Upgrade Project | 2026-07-20 08:00 | 2026-07-22 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1159859
INV_707_604 | INV-DS-604 | 2026-07-21 07:30 | 2026-07-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160772
INV_CB_632 | Affected equipment INV_707_604 | 2026-07-21 07:30 | 2026-07-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160773
HUI_FDR_1282 | HUI-CB-1282 | 2026-07-21 07:30 | 2026-07-21 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160739
INV_T1 | Affected equipment INV_707_604 Invercargill Protection Replacements - x3 Transformer, Feeder, 33kV Bus Zone Protection & Arc flash | 2026-07-21 07:30 | 2026-07-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160789
EDN_INV_1 | Affected equipment INV_707_604 | 2026-07-21 07:30 | 2026-07-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160488
MNI_CB_848 | MNI-P-CB-848 | 2026-07-21 07:30 | 2026-07-21 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161086
PTS_270598_MAN_ROX | MAN-C-PTSG-270598, ROX-C-PTSG-270598 | 2026-07-21 07:30 | 2026-07-21 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161464
PTS_2182_HWB_SDN | HWB-C-PTSG-2182, SDN-C-PTSG-2182 | 2026-07-21 07:30 | 2026-07-21 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1161462
PTS_1800_OTA_WIR | OTA-C-PTSG-1800A, WIR-C-PTSG-1800A | 2026-07-21 07:30 | 2026-07-21 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161458
DOB_GYM_1 | AHA-DOB-A0243-00 RSA5 TL Pole 26-27 | 2026-07-21 07:30 | 2026-07-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160435
BPE_110BZ | Modifications to the BZ/CBF system | 2026-07-21 08:00 | 2026-07-21 18:00 | Daily | SNI | RS - Removal from Service | Approved | OW1163514
BPE_110CBF | Affected equipment for the BZ outage | 2026-07-21 08:00 | 2026-07-21 18:00 | Daily | SNI | RS - Removal from Service | Approved | OW1163515
BRY_RTU_MULTI | BRY-P-SMS-A. NOC IP Team Switch work - JSD-12112 | 2026-07-21 08:30 | 2026-07-21 13:30 | Daily | SI | RS - Removal from Service | Approved | OW1163360
CST_MNI_1 | MNI-DEV-A0169-10, MNI-DEV-A0170-10 | 2026-07-22 07:30 | 2026-07-24 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160413
MDN_STC_5 | Replacement of Power supplies. | 2026-07-22 07:30 | 2026-07-22 17:00 | Daily | HVDC | RS - Removal from Service | Approved | OW2005241
MNI_CB_858 | MNI-CB-858, MNI-P-CB-858 | 2026-07-22 07:30 | 2026-07-22 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161087
MNG_CB_248 | MNG-P-CB-248 | 2026-07-22 07:30 | 2026-07-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161075
MNG_110CBF | Affected equipment | 2026-07-22 07:30 | 2026-07-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161072
MNG_110BZ_B | MNG-P-BZ-110 | 2026-07-22 07:30 | 2026-07-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161071
MNG_110BZ_A | MNG-P-BZ-110 | 2026-07-22 07:30 | 2026-07-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161070
PTS_1517_ALB_HEN | ALB-C-PTSG-1517C, HEN-C-PTSG-1517C | 2026-07-22 07:30 | 2026-07-22 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161454
WGN_110BZ | Modifications to the BZ/CBF system | 2026-07-22 08:00 | 2026-07-22 18:00 | Daily | SNI | RS - Removal from Service | Approved | OW1163516
WGN_110CBF | Affected equipment for the BZ outage | 2026-07-22 08:00 | 2026-07-22 18:00 | Daily | SNI | RS - Removal from Service | Approved | OW1163517
CCT_4900_MTI_WKM | WKM - SMR Internal Plant Works | 2026-07-22 08:00 | 2026-07-22 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1157220
CCT_2048_TKU_WKM | WKM - SMR Internal Plant Works | 2026-07-22 08:00 | 2026-07-22 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1157221
CCT_2039_WKN_WKM | WKM - SMR Internal Plant Works | 2026-07-22 08:00 | 2026-07-22 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1157223
ASY_RTU_1 | ASY-P-SMS-A. NOC IP Team Switch work - JSD-12081 | 2026-07-22 09:00 | 2026-07-22 13:00 | Daily | SI | RS - Removal from Service | Approved | OW1163361
MNI_CB_898 | MNI-CB-898, MNI-P-CB-898 | 2026-07-23 07:30 | 2026-07-23 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161088
MDN_STC_6 | Replacement of Power supplies. | 2026-07-23 07:30 | 2026-07-23 17:00 | Daily | HVDC | RS - Removal from Service | Approved | OW2005242
PEN_FDR_2512 | PEN-CB-2512, PEN-P-CB-2512 | 2026-07-23 07:30 | 2026-07-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161420
PTS_1290_HEN_MTO | MPE-C-PTSG-1290B | 2026-07-23 07:30 | 2026-07-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161453
CCT_2035_WKN_WKM | WKM - SMR Internal Plant Works | 2026-07-23 08:00 | 2026-07-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1157239
CCT_2037_ATI_WKM | WKM - SMR Internal Plant Works | 2026-07-23 08:00 | 2026-07-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1157222
ISL_RTU_MULTI | ISL-P-SMS-A. NOC IP Team Switch work - JSD-14080 | 2026-07-23 08:30 | 2026-07-23 13:30 | Daily | SI | RS - Removal from Service | Approved | OW1163362
PEN_FDR_2352 | PEN-CB-2352, PEN-P-CB-2352 | 2026-07-24 07:30 | 2026-07-24 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161413
PTS_1605_MPE_MTO | MPE-C-PTSG-1605A, MTO-C-PTSG-1605A | 2026-07-24 07:30 | 2026-07-24 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161456
PEN_FDR_2342 | PEN-CB-2342, PEN-P-CB-2342 | 2026-07-26 07:30 | 2026-07-26 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161412
BRB_T3 | BRB T2, T3 TOPS Scheme Project | 2026-07-27 07:00 | 2026-07-28 17:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1162991
BRB_FDR_2332 | BRB T2, T3 TOPS Scheme Project | 2026-07-27 07:00 | 2026-07-28 17:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1162992
BRB_220BS_A | BRB DIS 133 repairs | 2026-07-27 07:00 | 2026-07-27 17:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162993
BRB_CB_138 | Affected equipment with bus A | 2026-07-27 07:00 | 2026-07-27 17:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162994
BRB_CB_168 | Affected equipment with bus A | 2026-07-27 07:00 | 2026-07-27 17:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162996
BPE_WDV_1 | Re-insulation x13 | 2026-07-27 07:00 | 2026-07-31 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160347
KAW_MAT_2 | KAW-MAT-A0003-0004-20 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160902
HAY_SC_1 | HAY-SC1, HAY-SC1-CB-1A, HAY-SC1-EXC, HAY-SC1-NER | 2026-07-27 07:30 | 2026-08-07 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160618
BEN_CB_418 | BEN-CT-CT418 BEN 220BZ - CB418 Migration | 2026-07-27 07:30 | 2026-08-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160266
KAW_CB_78 | Affected equipment KAW_77_87_107 & KAW_MAT_2 & KAW_T5 & KAW_T6 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160897
KAW_T14 | Affected equipment KAW_77_87_107 & KAW_MAT_2 & KAW_T5 & KAW_T6 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160906
KAW_77_87_107 | KAW-DS-87, KAW-VT-97 . | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160892
GLN_220BS_B | GLN DS615 motor drive retrofit | 2026-07-27 07:30 | 2026-07-29 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW2005374
DRY_GLN_2 | GLN DS615 motor drive retrofit | 2026-07-27 07:30 | 2026-07-29 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW2005371
KAW_T5 | Affected equipment KAW_77_87_107 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160909
MNI_11BS_K | Affected equipment MNI_T4 | 2026-07-27 07:30 | 2026-07-28 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161081
GLN_CB_658 | Affected Equipment of GLN_220BS_B GLN DS615 motor drive retrofit | 2026-07-27 07:30 | 2026-07-29 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW2005375
STU_67_76_T5 | AP Maint OLTC | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1162074
MNI_CB_2732 | Affected equipment MNI_T4 | 2026-07-27 07:30 | 2026-07-28 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161083
PEN_FDR_2322 | PEN-P-CB-2322 | 2026-07-27 07:30 | 2026-07-27 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161411
KMO_127_137 | KMO-CB-138, KMO-P-CB-138 | 2026-07-27 07:30 | 2026-07-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160956
MNI_T4 | MNI-NCT-4, MNI-P-TF-T4, MNI-RES-ER4, MNI-TF-ET4, MNI-TF-T4 | 2026-07-27 07:30 | 2026-07-28 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161095
KMO_CB_138 | KMO-CB-138, KMO-P-CB-138 | 2026-07-27 07:30 | 2026-07-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160960
MNI_FDR_2712 | Affected equipment MNI_T4 | 2026-07-27 07:30 | 2026-07-28 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161089
MNI_FDR_2722 | Affected equipment MNI_T4 | 2026-07-27 07:30 | 2026-07-28 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161090
INV_647_776_755 | INV-DS-774 | 2026-07-27 08:00 | 2026-07-31 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160771
INV_CB_752 | Affected equipment INV_727_776_755 & INV_NMA_1 | 2026-07-27 08:00 | 2026-07-31 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160779
INV_CB_762 | Affected equipment INV_727_776_755 & INV_NMA_1 | 2026-07-27 08:00 | 2026-07-31 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160780
INV_CB_772 | Affected equipment INV_727_776_755 & INV_NMA_1 | 2026-07-27 08:00 | 2026-07-31 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160781
BEN_220CBF | BEN 220BZ - AVI_BEN_1 CCT Migration CP_BEN_AZ_00_00 BEN 220BZ - CB418 Migration | 2026-07-27 08:00 | 2026-07-27 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2006245
INV_NMA_1 | INV-DS-775, INV-DS-776, NMA-CT-CT642 | 2026-07-27 08:00 | 2026-07-31 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160784
INV_CB_692 | Affected Equipment of INV_647_776_755 INV-DS-774 | 2026-07-27 08:00 | 2026-07-31 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005929
BEN_220BZ | BEN 220BZ - AVI_BEN_1 CCT Migration CP_BEN_AZ_00_00 BEN 220BZ - CB418 Migration | 2026-07-27 08:00 | 2026-07-27 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2006244
INV_T3 | INV-DS-775, INV-DS-776, NMA-CT-CT642 Invercargill Protection Replacements - x3 Transformer, Feeder, 33kV Bus Zone Protection &Arc flash | 2026-07-27 08:00 | 2026-07-31 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160791
OHW_OTA_2 | Sub-conductor spacer project | 2026-07-27 08:00 | 2026-07-31 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005685
NMA_C_1 | SI-STNS NMA-CT-CT652 2017657, 2017656, 2017655 | 2026-07-28 07:30 | 2026-07-28 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1162156
PEN_CB_2498 | PEN-CB-2498, PEN-P-CB-2498 | 2026-07-28 07:30 | 2026-07-28 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161386
ISL_220BS_E | ISL_DS_6527 | 2026-07-28 07:30 | 2026-07-29 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160800
ISL_CB_658 | Affected Equipment of ISL_220BS_E ISL_DS_6527 | 2026-07-28 07:30 | 2026-07-29 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160825
ISL_CB_688 | Affected Equipment of ISL_220BS_E ISL_DS_6527 | 2026-07-28 07:30 | 2026-07-29 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160832
NMA_TWI_CAP_ITRIP_1 | Work Description: Project Works - NMA Protection Project - Decommission Old RTU. | 2026-07-28 08:00 | 2026-07-29 17:00 | Continuous | SI | RS - Removal from Service | Approved | OW2006030
NMA_RTU_1 | Work Description: Project Works - NMA Protection Project - Decommission Old RTU. | 2026-07-28 08:00 | 2026-07-31 17:00 | Daily | SI | RS - Removal from Service | Approved | OW2006032
CCT_8041_BDE_GOR | BDE - SMR Internal Plant Works Cancelled due to Fibre Outages in Area. BDE - SMR Internal Plant Works | 2026-07-28 08:00 | 2026-07-28 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160052
CCT_8050_BDE_EDN | BDE - SMR Internal Plant Works Cancelled due to Fibre Outages in Area. BDE - SMR Internal Plant Works | 2026-07-28 08:00 | 2026-07-28 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160051
NMA_TWI_CAP_ITRIP_2 | Work Description: Project Works - NMA Protection Project - Decommission Old RTU. | 2026-07-28 08:00 | 2026-07-29 17:00 | Continuous | SI | RS - Removal from Service | Approved | OW2006029
IGH_ROB_2 | Structure Replacements WMG-WPT-A0135, WMG-WPT-A0160 | 2026-07-29 06:30 | 2026-07-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1163104
MNI_11BS_L | Affected equipment MNI_T3 | 2026-07-29 07:30 | 2026-07-30 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161082
MNI_CB_2822 | Affected equipment MNI_T3 | 2026-07-29 07:30 | 2026-07-30 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161084
MNI_FDR_2832 | Affected equipment MNI_T3 | 2026-07-29 07:30 | 2026-07-30 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161091
MNI_T3 | MNI-NCT-3, MNI-P-TF-T3, MNI-RES-ER3, MNI-TF-ET3, MNI-TF-T3 | 2026-07-29 07:30 | 2026-07-30 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161094
MNI_FDR_2842 | Affected equipment MNI_T3 | 2026-07-29 07:30 | 2026-07-30 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161092
BEN_RTU_MULTI | BEN 220BZ - AVI_BEN_1 CCT Migration CP_BEN_AZ_00_00 | 2026-07-29 08:00 | 2026-07-29 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005403
CCT_2049_RPO_TKU | TKU - SMR Internal Plant Works | 2026-07-29 08:00 | 2026-07-29 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1157208
WPW_RTU_1 | Tidy up configuration | 2026-07-29 08:00 | 2026-07-29 16:00 | Daily | SNI | SCA - SCADA Interrupt Request | Approved | OW1157856
WHU_RTU_1 | WHU Bus Extension Project - Post Outage SCADA config Tidy up WHU Bus Extension Project - Post Outage SCADA config Tidy up | 2026-07-29 10:00 | 2026-07-29 14:00 | Daily | NNI | RS - Removal from Service | Approved | OW2005367
PEN_FDR_2422 | PEN-CB-2422, PEN-P-CB-2422 | 2026-07-30 07:30 | 2026-07-30 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161415
ISL_220BS_D | ISL-DS-425 | 2026-07-30 07:30 | 2026-07-31 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160799
ISL_C_21 | Affected equipment ISL_220BS_D & ISL_CB_658 | 2026-07-30 07:30 | 2026-07-31 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160815
ISL_CB_608 | Affected equipment ISL_220BS_D & ISL_CB_658 | 2026-07-30 07:30 | 2026-07-31 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160822
ISL_CB_658 | ISL-CT-CT658, ISL-DS-6517, ISL-DS-6527 | 2026-07-30 07:30 | 2026-07-31 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160826
NMA_RPC | Work Description: Project Works - NMA Protection Project - Decommission Old RTU. | 2026-07-30 08:00 | 2026-07-31 17:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW2006031
CCT_2048_TKU_WKM | TKU - SMR Internal Plant Works TKU - SMR Internal Plant Works | 2026-07-30 08:00 | 2026-07-30 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1157209
CCT_1095_TRU_WRK | Fibre Access cables TRU | 2026-07-30 08:30 | 2026-07-30 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005310
CCT_1085_HRP_TRU | TRU SMR Fibre Access Cables | 2026-07-30 08:30 | 2026-07-30 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005309
BRB_RTU_1 | BRB T2, T3 TOPS Scheme Project | 2026-07-30 09:00 | 2026-07-30 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162997
HWB_SDN_GXP_TIE | Transfer 1 MW from HWB 2522 to SDN 2252 | 2026-07-31 07:30 | 2026-07-31 08:30 | Daily | SI | OTH - Other Work Nature | Approved | OW2005047
BPE_WDV_2 | Re-insulation x13 | 2026-08-03 06:30 | 2026-08-07 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160349
GLN_220BS_A | GLN DS653 motor drive retrofit | 2026-08-03 07:30 | 2026-08-06 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW2005377
KAW_T14 | Affected equipment KAW_587_674_657 & KAW_CB_608 & KAW_OHK_1 | 2026-08-03 07:30 | 2026-08-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160907
KAW_OHK_1 | KAW-CT-622, KAW-CVT-622, KAW-DS-626, KAW-ES-629, OHK-DS-1316, OHK-DS-86, OHK-ES-89. Tower Painting | 2026-08-03 07:30 | 2026-08-07 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160903
KUM_OTI_1 | Lines Maintenance -Lines Maintenance AHA-OTI-A0098-00, AHA-OTI-A0099-00 Includes Stev D request to extend to 14.08 | 2026-08-03 07:30 | 2026-08-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160997
KAW_DIS_617 | Closed for the duration of KAW bus outage | 2026-08-03 07:30 | 2026-08-05 18:30 | Continuous | NNI | CLO - Close | Approved | OW1160898
RDF_T1 | RDF-TF-T1. Corrosive sulphur work. 12-hour heat soak on last day. | 2026-08-03 07:30 | 2026-08-17 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161469
KAW_CB_608 | KAW-CT-608, KAW-P-CB-608 | 2026-08-03 07:30 | 2026-08-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160895
KAW_587_674_657 | KAW-BS-220-627-647 | 2026-08-03 07:30 | 2026-08-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160891
ISL_FDR_112 | ISL-CB-112, ISL-P-CB-112 | 2026-08-03 07:30 | 2026-08-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160848
PEN_FDR_2432 | PEN-CB-2432, PEN-CBL-2342-SP2, PEN-P-CB-2432 | 2026-08-03 07:30 | 2026-08-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161416
HWB_FDR_2612 | HWB-CBL-2612 | 2026-08-03 07:30 | 2026-08-03 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160758
OTA_PAK_3 | OTA-PAK-A0003-00 | 2026-08-03 07:30 | 2026-08-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161337
HKK_OTI_2 | Lines Maintenance | 2026-08-03 07:30 | 2026-08-07 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160693
GLN_CB_658 | Affected Equipment of GLN_220BS_A GLN DS653 motor drive retrofit | 2026-08-03 07:30 | 2026-08-06 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW2005378
HOR_KBY_ISL_2 | HOR-CB-102 66 KV CB Replacement | 2026-08-03 07:30 | 2026-08-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1154528
HPI_CB_342 | HPI-CB-342 Pole replacement project | 2026-08-03 07:30 | 2026-08-07 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160725
OHW_OTA_1 | Sub-conductor spacer project | 2026-08-03 08:00 | 2026-08-07 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005684
BPE_MTN_WGN_1 | MTN-T1 dual differential protection and BPE-MTN-WGN-1 line protection upgrade. Aligns with MTN ODID. | 2026-08-03 08:00 | 2026-09-03 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1159599
MTN_T1 | MTN-T1 dual differential protection and BPE-MTN-WGN-1 line protection upgrade. Aligns with MTN ODID. | 2026-08-03 08:00 | 2026-09-03 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1159598
ONG_FDR_192 | ONG SPS Changeover Project | 2026-08-03 08:00 | 2026-08-06 15:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2005772
CCT_1160_MGM_MST | Rearrangement of Fibre Bearers | 2026-08-03 08:00 | 2026-08-03 12:00 | Daily | SNI | RS - Removal from Service | Approved | OW2006105
BPE_110CBF | Affected equipment for the BZ outage | 2026-08-03 08:00 | 2026-08-03 11:00 | Daily | SNI | RS - Removal from Service | Approved | OW1163519
BPE_110BZ | Modifications to the BZ/CBF system | 2026-08-03 08:00 | 2026-08-03 11:00 | Daily | SNI | RS - Removal from Service | Approved | OW1163518
INV_MAN_2 | INV-MAN-A0337-00, INV-MAN-A0355-00, INV-MAN-A0354-00, INV-MAN-A0344-00, INV-MAN-A0122-00, INV-MAN-A0034-00, INV-MAN-A0123-00, INV-MAN-A0283-00, INV-MAN-A0033-00, INV-MAN-A0280-00, INV-MAN-A0028-00, INV-MAN-A0119-00, INV-MAN-A0036-00, INV-MAN-A0037-00, INV-MAN-A0035-00, INV-MAN-A0032-00, INV-MAN-A0120-00, INV-MAN-A0029-00, INV-MAN-A0282-00, INV-MAN-A0030-00, INV-MAN-A0031-00, INV-MAN-A0121-00, INV-MAN-A0279-00, INV-MAN-A0281-00 | 2026-08-03 08:30 | 2026-08-07 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160782
WGN_110CBF | Affected equipment for the BZ outage | 2026-08-03 09:30 | 2026-08-03 11:30 | Daily | SNI | RS - Removal from Service | Approved | OW1163521
WGN_110BZ | Modifications to the BZ/CBF system | 2026-08-03 09:30 | 2026-08-03 11:30 | Daily | SNI | RS - Removal from Service | Approved | OW1163520
HAY_RTU_1 | HAY_110BZ Stage 1A; RTU config updates [CP_HAY_IN_00_00] | 2026-08-03 10:00 | 2026-08-03 14:00 | Daily | SNI | RS - Removal from Service | Approved | OW1162195
HAY_RTU_2 | HAY_110BZ Stage 1A; RTU config updates [CP_HAY_IN_00_00] | 2026-08-03 10:00 | 2026-08-03 14:00 | Daily | SNI | RS - Removal from Service | Approved | OW1162196
HAY_RTU_3 | HAY_110BZ Stage 1A; RTU config updates [CP_HAY_IN_00_00] | 2026-08-03 10:00 | 2026-08-03 14:00 | Daily | SNI | RS - Removal from Service | Approved | OW1162197
HOR_RTU_1 | HOR CB102 CB Replacement RTU Config changes | 2026-08-03 10:30 | 2026-08-03 12:30 | Daily | SI | RS - Removal from Service | Approved | OW1163070
CCT_1170_MST_UHT | Rearrangement of Fibre Bearers 1170 | 2026-08-03 13:00 | 2026-08-03 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2006109
HWB_FDR_2552 | HWB-CBL-2552 | 2026-08-04 07:30 | 2026-08-05 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160755
NMA_RTU_1 | Work Description: Project Works - NMA Protection Project - Decommission Old RTU. | 2026-08-04 08:00 | 2026-08-05 17:00 | Daily | SI | RS - Removal from Service | Approved | OW2006019
BEN_220BS_B | BEN-CT-CT418 BEN 220BZ - CB418 Migration | 2026-08-04 08:00 | 2026-09-08 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160225
HWB_FDR_2532 | HWB-CBL-2532 | 2026-08-05 07:30 | 2026-08-05 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160754
BEN_220CBF | BEN 220BZ - AVI_BEN_1 CCT Migration CP_BEN_AZ_00_00 BEN 220BZ - CB418 Migration | 2026-08-05 08:00 | 2026-08-06 18:00 | Continuous | SI | RS - Removal from Service | Approved | OW2006247
BEN_220BZ | BEN 220BZ - AVI_BEN_1 CCT Migration CP_BEN_AZ_00_00 BEN 220BZ - CB418 Migration | 2026-08-05 08:00 | 2026-08-06 18:00 | Continuous | SI | RS - Removal from Service | Approved | OW2006246
OTA_T14 | OTA-TF-T14 | 2026-08-06 07:30 | 2026-08-07 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161345
HWB_FDR_2602 | HWB-CBL-2602 | 2026-08-06 07:30 | 2026-08-07 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160757
ARI_HTI_ONG_1 | ONG SPS Changeover Project | 2026-08-06 08:00 | 2026-08-06 15:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005773
HWB_FDR_2592 | HWB-CBL-2592 | 2026-08-07 07:30 | 2026-08-07 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160756
NMA_220BS_A3 | MAN-P-CB-272, MAN-TWI-A0010-10, MAN-TWI-A0216-0217-00, MAN-TWI-A0220-0221-00, MAN-TWI-A0258-0259-00, MAN-TWI-A0259-0260-00, MAN-TWI-A0260-0261-00, MAN-TWI-A0294-10, MAN-TWI-A0296-00, MAN-TWI-A0296-10, MAN-TWI-A0299-00, MAN-TWI-A0299-10, MAN-TWI-A0300-00, MAN-TWI-A0300-10, MAN-TWI-A0308-10, MAN-TWI-A0311-0312-10, MAN-TWI-A0313-0314-10, MAN-TWI-A0314-0315-10 | 2026-08-10 07:30 | 2026-08-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161200
NMA_CB_708 | Affected Equipment of NMA_220BS_A3 MAN-P-CB-272, MAN-TWI-A0010-10, MAN-TWI-A0216-0217-00, MAN-TWI-A0220-0221-00, MAN-TWI-A0258-0259-00, MAN-TWI-A0259-0260-00, MAN-TWI-A0260-0261-00, MAN-TWI-A0294-10, MAN-TWI-A0296-00, MAN-TWI-A0296-10, MAN-TWI-A0299-00, MAN-TWI-A0299-10, MAN-TWI-A0300-00, MAN-TWI-A0300-10, MAN-TWI-A0308-10, MAN-TWI-A0311-0312-10, MAN-TWI-A0313-0314-10, MAN-TWI-A0314-0315-10 | 2026-08-10 07:30 | 2026-08-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161219
NMA_CB_718 | Affected Equipment of NMA_220BS_A3 MAN-P-CB-272, MAN-TWI-A0010-10, MAN-TWI-A0216-0217-00, MAN-TWI-A0220-0221-00, MAN-TWI-A0258-0259-00, MAN-TWI-A0259-0260-00, MAN-TWI-A0260-0261-00, MAN-TWI-A0294-10, MAN-TWI-A0296-00, MAN-TWI-A0296-10, MAN-TWI-A0299-00, MAN-TWI-A0299-10, MAN-TWI-A0300-00, MAN-TWI-A0300-10, MAN-TWI-A0308-10, MAN-TWI-A0311-0312-10, MAN-TWI-A0313-0314-10, MAN-TWI-A0314-0315-10 | 2026-08-10 07:30 | 2026-08-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161226
GLN_CB_658 | Affected Equipment of GLN_220BS_B GLN DS655 motor drive retrofit | 2026-08-10 07:30 | 2026-08-13 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW2005380
GLN_220BS_B | GLN DS655 motor drive retrofit | 2026-08-10 07:30 | 2026-08-13 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW2005379
HKK_OTI_2 | Lines Maintenance AHA-OTI-A0098-00, AHA-OTI-A0099-00 | 2026-08-10 07:30 | 2026-08-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160694
IGH_ROB_1 | Tower Painting-GH-P-CB-342, ROB-P-CB-522 IGH-WPT-B0027-00, IGH-WPT-B0034-00, IGH-WPT-B0032-00, IGH-WPT-B0037-00, IGH-WPT-B0030-00, IGH-WPT-B0033-00, IGH-WPT-B0029-00, IGH-WPT-B0031-00, IGH-WPT-B0035-00, IGH-WPT-B0028-00, IGH-WPT-B0036-00 | 2026-08-10 07:30 | 2026-08-15 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143091
KAW_DIS_617 | Closed for the duration of KAW_547_587_627 | 2026-08-10 07:30 | 2026-08-12 18:30 | Continuous | NNI | CLO - Close | Approved | OW1160899
MAN_NMA_1 | MAN-P-CB-272, MAN-TWI-A0010-10, MAN-TWI-A0216-0217-00, MAN-TWI-A0220-0221-00, MAN-TWI-A0258-0259-00, MAN-TWI-A0259-0260-00, MAN-TWI-A0260-0261-00, MAN-TWI-A0294-10, MAN-TWI-A0296-00, MAN-TWI-A0296-10, MAN-TWI-A0299-00, MAN-TWI-A0299-10, MAN-TWI-A0300-00, MAN-TWI-A0300-10, MAN-TWI-A0308-10, MAN-TWI-A0311-0312-10, MAN-TWI-A0313-0314-10, MAN-TWI-A0314-0315-10 | 2026-08-10 07:30 | 2026-08-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161023
KAW_CB_608 | KAW-CT-608, KAW-P-CB-608 | 2026-08-10 07:30 | 2026-08-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160896
KAW_547_587_627 | KAW-DS-584, KAW-DS-587 | 2026-08-10 07:30 | 2026-08-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160890
EDG_FDR_2202 | Affected Equipment New EDG 33kV CB 2152 Interlocking & BZ Stability | 2026-08-10 07:30 | 2026-08-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162848
EDG_FDR_2182 | Affected Equipment New EDG 33kV CB 2152 Interlocking & BZ Stability | 2026-08-10 07:30 | 2026-08-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162847
EDG_FDR_2172 | Affected Equipment New EDG 33kV CB 2152 Interlocking & BZ Stability | 2026-08-10 07:30 | 2026-08-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162846
EDG_KAW_3 | EDG-CB-502, KAW-CB-582, KAW-DEV-A0307-00 | 2026-08-10 07:30 | 2026-08-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160477
EDG_CB_2198 | Affected Equipment New EDG 33kV CB 2152 Interlocking & BZ Stability | 2026-08-10 07:30 | 2026-08-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162845
EDG_33BS_K | New EDG 33kV CB 2152 Interlocking & BZ Stability | 2026-08-10 07:30 | 2026-08-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162844
EDG_T4 | New EDG 33kV CB 2152 Interlocking & BZ Stability | 2026-08-10 07:30 | 2026-08-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162840
OTA_PEN_2 | Tower Painting, Cable sheath tests | 2026-08-10 08:00 | 2026-08-15 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142921
TAK_T5 | Affected Equipment Tower Painting | 2026-08-10 08:00 | 2026-08-15 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142879
DRY_TAK_OTA_1 | Tower Painting | 2026-08-10 08:00 | 2026-08-15 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142878
BPE_MTR_1 | ONG SPS Changeover Project | 2026-08-10 08:00 | 2026-08-14 15:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2005767
OHW_OTA_2 | Sub-conductor spacer project | 2026-08-10 08:00 | 2026-08-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005686
DRY_CB_442 | Affected equipment with bus A | 2026-08-10 08:00 | 2026-08-10 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1162927
DRY_220BS_A | DRY CB 412, 422 Siemens relay replacement | 2026-08-10 08:00 | 2026-08-10 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1162926
HOR_T8 | HOR-CT-NCT8 | 2026-08-11 07:30 | 2026-08-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160724
WIL_33BZ_K | WIL-P-BZ-33 | 2026-08-11 07:30 | 2026-08-12 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161798
WIL_33BZ_L | WIL-P-BZ-33 | 2026-08-11 07:30 | 2026-08-12 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161799
WIL_33CBF | Affected equipment of WIL_33BZ_K/L, for WIL-P-BZ-33 | 2026-08-11 07:30 | 2026-08-12 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161800
OTA_404_437_507 | Access OTA GDR 60 directly above DS 453, 455 detach falling bird proofing | 2026-08-11 07:30 | 2026-08-11 16:30 | Daily | NNI | RS - Removal from Service | Approved | OW2005347
OTA_CB_478 | Replace CB 478 Siemens relays | 2026-08-11 07:30 | 2026-08-11 16:30 | Daily | NNI | RS - Removal from Service | Approved | OW2005349
OTA_CB_402 | Affected Equipment of OTA_404_437_507 Access OTA GDR 60 directly above DS 453, 455 detach falling bird proofing | 2026-08-11 07:30 | 2026-08-11 16:30 | Daily | NNI | RS - Removal from Service | Approved | OW2005348
CCT_9994_RDF_WHI | Outage block to cover site build preparation for external fibreworks. Note this will impact both ends of the CCT circuit in RDFand WHI with crews at both ends. | 2026-08-11 08:00 | 2026-08-11 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005972
KUM_RTU_1 | Stage 5 - Load RTU Configuration Changes | 2026-08-11 08:30 | 2026-08-11 11:30 | Daily | SI | RS - Removal from Service | Approved | OW1163365
OTI_RTU_1 | Stage 5 - Load RTU Configuration Changes | 2026-08-11 13:30 | 2026-08-11 16:30 | Daily | SI | RS - Removal from Service | Approved | OW1163364
NMA_CB_738 | Affected Equipment of NMA_687_835 MAN-P-CB-272, MAN-TWI-A0010-10, MAN-TWI-A0216-0217-00, MAN-TWI-A0220-0221-00, MAN-TWI-A0258-0259-00, MAN-TWI-A0259-0260-00, MAN-TWI-A0260-0261-00, MAN-TWI-A0294-10, MAN-TWI-A0296-00, MAN-TWI-A0296-10, MAN-TWI-A0299-00, MAN-TWI-A0299-10, MAN-TWI-A0300-00, MAN-TWI-A0300-10, MAN-TWI-A0308-10, MAN-TWI-A0311-0312-10, MAN-TWI-A0313-0314-10, MAN-TWI-A0314-0315-10 | 2026-08-12 07:30 | 2026-08-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161235
EDG_RTU_1 | RTU config | 2026-08-12 07:30 | 2026-08-12 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1162841
NMA_687_835 | MAN-P-CB-272, MAN-TWI-A0010-10, MAN-TWI-A0216-0217-00, MAN-TWI-A0220-0221-00, MAN-TWI-A0258-0259-00, MAN-TWI-A0259-0260-00, MAN-TWI-A0260-0261-00, MAN-TWI-A0294-10, MAN-TWI-A0296-00, MAN-TWI-A0296-10, MAN-TWI-A0299-00, MAN-TWI-A0299-10, MAN-TWI-A0300-00, MAN-TWI-A0300-10, MAN-TWI-A0308-10, MAN-TWI-A0311-0312-10, MAN-TWI-A0313-0314-10, MAN-TWI-A0314-0315-10 | 2026-08-12 07:30 | 2026-08-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161210
HLY_220BZ_A | HLY-P-BZ-220-A | 2026-08-12 07:30 | 2026-08-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160698
HLY_220CBF | Affected equipment HLY-P-BZ-220-A | 2026-08-12 07:30 | 2026-08-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160699
KMO_TGA_1 | KMO-MTM-TGA line protection upgrade | 2026-08-12 07:30 | 2026-08-12 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1162247
MTM_CB_52 | OPE system split as per OB info | 2026-08-12 07:30 | 2026-08-12 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1162264
KAI_FDR_4 | KAI-CB-4, KAI IDID CP_KAI_84_00_00 KAI-CB-4 | 2026-08-13 06:30 | 2026-08-13 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1150182
WIL_110BS_A_PROT1 | WIL-P-SPS-SPLIT | 2026-08-13 07:30 | 2026-08-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161791
WIL_110BS_C_PROT2 | WIL-P-SPS-SPLIT | 2026-08-13 07:30 | 2026-08-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161794
WIL_110BS_C_PROT1 | WIL-P-SPS-SPLIT | 2026-08-13 07:30 | 2026-08-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161793
WIL_110BS_A_PROT2 | WIL-P-SPS-SPLIT | 2026-08-13 07:30 | 2026-08-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161792
NAP_220CBF | Affected equipment of NAP_220BZ, for NAP-P-BZ-220. | 2026-08-13 07:30 | 2026-08-13 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161195
KMO_MTM_TGA_2 | KMO-MTM-TGA line protection upgrade | 2026-08-13 07:30 | 2026-08-13 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1162248
NAP_220BZ | NAP-P-BZ-220 | 2026-08-13 07:30 | 2026-08-13 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161194
OTA_CB_488 | OTA-CT-488 | 2026-08-13 08:00 | 2026-08-13 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161330
EDG_33CBF | EDG 33kV CB 2152 BZ Stability Check | 2026-08-13 08:00 | 2026-08-13 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163034
EDG_33BZ_K | EDG 33kV CB 2152 BZ Stability Check | 2026-08-13 08:00 | 2026-08-13 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163033
EDG_33CBF | EDG 33kV CB 2152 to CBFail Initiate Connection | 2026-08-14 08:00 | 2026-08-14 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163035
EDG_33BZ_K | EDG 33kV CB 2152 to CBFail Initiate Connection | 2026-08-14 08:00 | 2026-08-14 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163036
MAN_NMA_3 | INV-MAN-A0289-20, INV-MAN-A0292-20, INV-MAN-A0297-20, INV-MAN-A0298-20, MAN-P-CB-222 | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161026
HAM_T8 | CT replacement. HAM-CT-1532 | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160574
NMA_CB_708 | Affected Equipment of NMA_220BS_A1 INV-MAN-A0289-20, INV-MAN-A0292-20, INV-MAN-A0297-20, INV-MAN-A0298-20, MAN-P-CB-222 | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161220
NMA_CB_688 | Affected Equipment of NMA_220BS_A1 INV-MAN-A0289-20, INV-MAN-A0292-20, INV-MAN-A0297-20, INV-MAN-A0298-20, MAN-P-CB-222 | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161215
HAM_CB_1522 | Place T7 into service for duration of T8 | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | NNI | CLO - Close | Approved | OW1160550
HAM_347_364_407 | Headgear replacement HAM-DS-367 | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160544
NMA_220BS_A1 | INV-MAN-A0289-20, INV-MAN-A0292-20, INV-MAN-A0297-20, INV-MAN-A0298-20, MAN-P-CB-222 | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161198
KMO_TGA_1 | KMO-TGA-1 110KV line protection upgrade | 2026-08-17 07:30 | 2026-08-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1149146
EDG_FDR_2262 | Affected Equipment New EDG 33kV CB2282 Interlocking & BZ Stability | 2026-08-17 07:30 | 2026-08-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1163200
MTM_CB_52 | System split for duration of KMO_TGA_1 | 2026-08-17 07:30 | 2026-08-25 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1149147
ISL_CB_708 | ISL-CB-708 Pole Replacement | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005043
EDG_FDR_2252 | Affected Equipment New EDG 33kV CB2282 Interlocking & BZ Stability | 2026-08-17 07:30 | 2026-08-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1163199
EDG_FDR_2242 | Affected Equipment New EDG 33kV CB2282 Interlocking & BZ Stability | 2026-08-17 07:30 | 2026-08-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1163198
APS_OTI_1 | Lines Maintenance | 2026-08-17 07:30 | 2026-08-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160141
EDG_33BS_L | New EDG 33kV CB2282 Interlocking & BZ Stability | 2026-08-17 07:30 | 2026-08-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1163197
EDG_FDR_2232 | Affected Equipment New EDG 33kV CB2282 Interlocking & BZ Stability | 2026-08-17 07:30 | 2026-08-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1163196
EDG_FDR_2212 | Affected Equipment New EDG 33kV CB2282 Interlocking & BZ Stability | 2026-08-17 07:30 | 2026-08-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1163195
EDG_CB_2198 | Affected Equipment New EDG 33kV CB2282 Interlocking & BZ Stability | 2026-08-17 07:30 | 2026-08-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1163194
EDG_T7 | Affected Equipment New EDG 33kV CB2282 Interlocking & BZ Stability | 2026-08-17 07:30 | 2026-08-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1163201
COL_OTI_2 | Lines Maintenance | 2026-08-17 07:30 | 2026-08-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160394
OHW_OTA_2 | Sub-conductor spacer project | 2026-08-17 08:00 | 2026-08-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005687
DRY_TAK_OTA_2 | Tower Painting | 2026-08-17 08:00 | 2026-08-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142882
TAK_T8 | Affected Equipment Tower Painting | 2026-08-17 08:00 | 2026-08-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142883
OTA_ROS_1 | Tower Painting | 2026-08-17 08:00 | 2026-08-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142923
KMO_110BZ | 110KV protection upgrade | 2026-08-18 07:00 | 2026-08-18 11:00 | Daily | NNI | RS - Removal from Service | Approved | OW1155527
KMO_110CBF | 110KV protection upgrade | 2026-08-18 07:00 | 2026-08-18 11:00 | Daily | NNI | RS - Removal from Service | Approved | OW1155530
MNG_ROS_1 | MNG-ROS-A0034-10, MNG-ROS-A0037-10 | 2026-08-18 07:30 | 2026-08-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161079
MNG_OTA_1 | Affected equipment MNG_227_VT1 & MNG_ROS_1 | 2026-08-18 07:30 | 2026-08-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161077
MNG_227_VT1 | MNG-M-VT1, MNG-VT-1 | 2026-08-18 07:30 | 2026-08-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161073
CCT_2102_NAP_TAB | Outage block to cover site build preparation for external fibreworks. Note this will impact both ends of the CCT circuit in NAPand TAB with crews at both ends. | 2026-08-18 08:00 | 2026-08-18 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005331
TGA_110CBF | 110KV protection upgrade | 2026-08-18 11:30 | 2026-08-18 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW1155535
TGA_110BZ | 110KV protection upgrade | 2026-08-18 11:30 | 2026-08-18 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW1155531
ARI_STH_RNBACK_PROT1 | ARI-P-SPS-SOUTH-OL | 2026-08-19 07:30 | 2026-08-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160175
EDG_RTU_1 | RTU Config | 2026-08-19 08:00 | 2026-08-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163202
CCT_5100_ATI_OHK | ATI - SMR Internal Plant Works | 2026-08-19 08:00 | 2026-08-19 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1157212
CCT_2037_ATI_WKM | ATI - SMR Internal Plant Works | 2026-08-19 08:00 | 2026-08-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1157211
BPE_RTU_1 | Pre-outage second circuit config | 2026-08-20 08:00 | 2026-08-20 11:00 | Daily | SNI | RS - Removal from Service | Approved | OW1162427
EDG_33BZ_L | EDG 33kV CB2282 BZ Stability Check | 2026-08-20 08:00 | 2026-08-20 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163203
EDG_33CBF | EDG 33kV CB2282 BZ Stability Check | 2026-08-20 08:00 | 2026-08-20 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163204
CCT_2112_ATI_KIN | ATI - SMR Internal Plant Works | 2026-08-20 08:00 | 2026-08-20 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1157215
CCT_1060_ATI_PPI | ATI - SMR Internal Plant Works | 2026-08-20 08:00 | 2026-08-20 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1157214
CCT_2111_ATI_WRK | ATI - SMR Internal Plant Works | 2026-08-20 08:00 | 2026-08-20 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1157213
MTN_RTU_1 | Pre-outage second circuit config | 2026-08-20 13:00 | 2026-08-20 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW1162432
EDG_33BZ_L | EDG 33kV CB2282 CBFail Initiate Connection | 2026-08-21 08:00 | 2026-08-21 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163206
EDG_33CBF | EDG 33kV CB2282 CBFail Initiate Connection | 2026-08-21 08:00 | 2026-08-21 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163205
WGN_RTU_1 | Pre-outage second circuit config | 2026-08-21 08:00 | 2026-08-21 11:00 | Daily | SNI | RS - Removal from Service | Approved | OW1162436
ARG_KIK_1 | Lines Maintenance | 2026-08-24 06:30 | 2026-08-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160149
TGA_T3 | KMO-MTM-TGA 110KV line prot upgrade | 2026-08-24 07:30 | 2026-08-24 12:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155716
RDF_T2 | RDF-CBL-ET2-NER2, RDF-CBL-T2-2462, RDF-CBL-T2-ET2, RDF-NCT-2, RDF-RES-NER2, RDF-TF-ET2, RDF-TF-T2. 12-hour heat soak on last day. | 2026-08-24 07:30 | 2026-09-09 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161470
KPU_WKO_1 | Affected equipment KPU_357_VT367 & KPU_T4 | 2026-08-24 07:30 | 2026-08-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160993
KPU_T4 | Reinhausen tap changer maintenance | 2026-08-24 07:30 | 2026-08-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160992
KPU_357_VT367 | KPU-VT-VT367 | 2026-08-24 07:30 | 2026-08-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160986
KIN_T7 | KIN-M-CT2742, KIN-M-VT2742 | 2026-08-24 07:30 | 2026-08-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160949
TNG_220BS_A | TNG-DS-253 (T11) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-220. Optimised | 2026-08-24 07:30 | 2026-08-25 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161674
INV_NMA_1 | Inv_ds_776 Headgear | 2026-08-24 07:30 | 2026-08-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160785
KIK_CB_398 | Affected equipment KIK_220BS_A includes SF6 repair | 2026-08-24 07:30 | 2026-08-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160924
KIK_CB_358 | Affected equipment KIK_220BS_A includes SF6 repair | 2026-08-24 07:30 | 2026-08-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160921
TNG_CB_288 | Affected equipment of TNG_220BS_A, for TNG-DS-253 (T11), TNG-ES-220 | 2026-08-24 07:30 | 2026-08-25 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161688
TNG_T11 | BPE-TNG prot upgrade Stage 1: Installation of CT-252 at Bay 250[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-08-24 07:30 | 2026-08-28 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1162036
KIK_220BS_A | KIK-DS-367, KIK-DS-373, KIK-DS-393 includes SF6 repair | 2026-08-24 07:30 | 2026-08-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160916
CUL_FDR_1222 | CUL-CB-1222, CUL-P-CB-1222 | 2026-08-24 07:30 | 2026-08-26 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160423
OTA_C_29 | OTA-CB-5812, OTA-DS-5814 | 2026-08-24 08:00 | 2026-08-27 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161320
TAK_T5 | Affected equipment TAK-BS-220-302-T5, TAK-CB-2162A, TAK-CB-2162B, TAK-TF-T5 | 2026-08-24 08:00 | 2026-08-27 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161592
OTA_537_597_587 | OTA-CB-5812, OTA-DS-5814 | 2026-08-24 08:00 | 2026-08-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162885
OTA_CB_538 | Affected equipment | 2026-08-24 08:00 | 2026-08-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162895
OTA_CB_598 | Affected equipment | 2026-08-24 08:00 | 2026-08-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162896
DRY_TAK_OTA_1 | HLY-OTA-A0150-10, HLY-OTA-A0164-10, HLY-OTA-A0167-10, HLY-OTA-A0172-10, HLY-OTA-A0178-10, HLY-OTA-A0190-10, HLY-OTA-A0196-10, HLY-OTA-A0203-10, HLY-OTA-A0204-10, HLY-OTA-A0207-10, HLY-OTA-A0208-10, HLY-OTA-A0210-10, HLY-OTA-A0213-10 | 2026-08-24 08:00 | 2026-08-27 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160450
ISL_T8 | Affected Equipment of ISL_WPR_CUL_KIK_2 ISL-CB-562 Corroding SF6 pipework - P3 | 2026-08-24 08:00 | 2026-08-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005912
WPR_T12 | Affected Equipment of ISL_WPR_CUL_KIK_2 ISL-CB-562 Corroding SF6 pipework - P3 | 2026-08-24 08:00 | 2026-08-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005074
HEP_CB_218 | Hep Mimic Panel Decommissioning | 2026-08-24 08:00 | 2026-08-24 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW2005916
ISL_WPR_CUL_KIK_2 | ISL-CB-562 Corroding SF6 pipework - P3 | 2026-08-24 08:00 | 2026-08-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005072
CUL_T22 | Affected Equipment of ISL_WPR_CUL_KIK_2 ISL-CB-562 Corroding SF6 pipework - P3 | 2026-08-24 08:00 | 2026-08-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005073
HKK_RTU_1 | Tidy Up RTU Configuration | 2026-08-25 12:30 | 2026-08-25 15:00 | Daily | SI | RS - Removal from Service | Approved | OW1162648
TGA_110BZ | 110KV line protection upgrade | 2026-08-26 07:30 | 2026-08-26 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW1155727
TGA_110CBF | 110KV line protection upgrade | 2026-08-26 07:30 | 2026-08-26 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW1155728
RDF_TUI_1 | RSA4 conductor repair [MP_RA4_03N_0_00]. | 2026-08-26 07:30 | 2026-08-27 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161472
BRB_CB_138 | BRB-CB-138 | 2026-08-26 07:30 | 2026-08-27 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160351
TNG_220BS_B | BPE-TNG prot upgrade Stage 1: Installation of CT-252 at Bay 250[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. TNG-ES-230 | 2026-08-26 07:30 | 2026-08-28 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161681
TNG_CB_288 | Affected equipment of TNG_220BS_B, for BPE-TNG prot upgrade Stage 1, TNG-ES-230 | 2026-08-26 07:30 | 2026-08-28 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161689
TNG_FDR_2802 | TNG-CB-2802, TNG-P-CB-2802 (TENTATIVE OW - asset may be decommissioned). | 2026-08-26 07:30 | 2026-08-26 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161698
TUI_110BZ | TUI-P-BZ-110 | 2026-08-26 07:30 | 2026-08-26 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161713
TUI_110CBF | Affected equipment of TUI_110BZ, for TUI-P-BZ-110 | 2026-08-26 07:30 | 2026-08-26 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161714
TGA_C_11 | OC/EF(HV) relay input 110KV line protection upgrade | 2026-08-26 08:00 | 2026-08-26 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW1157368
KUM_RTU_1 | Tidy Up RTU Configuration | 2026-08-26 08:00 | 2026-08-26 11:00 | Daily | SI | RS - Removal from Service | Approved | OW1162649
OTI_RTU_1 | Tidy Up RTU Configuration | 2026-08-26 12:30 | 2026-08-26 15:30 | Daily | SI | RS - Removal from Service | Approved | OW1162647
TNG_T12 | BPE-TNG prot upgrade Stage 1: Installation of CT-252 at Bay 250[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-08-27 07:30 | 2026-08-27 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005754
TNG_220CBF | Affected equipment of TNG_220BZ, for BPE-TNG prot upgrade Stage1 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-08-27 08:00 | 2026-08-27 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005571
TNG_220BZ | BPE-TNG prot upgrade Stage 1: Installation of CT-252 at Bay 250[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-08-27 08:00 | 2026-08-27 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005558
TGA_110CBF | 110KV protection upgrade | 2026-08-28 07:30 | 2026-08-28 12:00 | Daily | NNI | RS - Removal from Service | Approved | OW1155534
TGA_110BZ | 110KV protection upgrade | 2026-08-28 07:30 | 2026-08-28 12:00 | Daily | NNI | RS - Removal from Service | Approved | OW1155532
KMO_110CBF | 110KV protection upgrade | 2026-08-28 07:30 | 2026-08-28 11:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155529
KMO_110BZ | 110KV protection upgrade | 2026-08-28 07:30 | 2026-08-28 11:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155528
KIK_T1 | KIK-TF-T1B, KIK-TF-T1R, KIK-TF-T1Y | 2026-08-28 07:30 | 2026-08-28 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160935
BPE_TNG_1 | BPE-TNG prot upgrade Stage 1: Installation of CT-252 at Bay 250[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-08-28 11:30 | 2026-08-28 17:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005559
EDG_OWH_2 | Affected Equipment of EDG_227_254_274 SRG-Gantry Painting | 2026-08-31 07:30 | 2026-09-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006187
EDG_KAW_1 | Affected Equipment of EDG_227_254_274 SRG-Gantry Painting | 2026-08-31 07:30 | 2026-09-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006186
KPU_WKO_2 | Affected equipment KPU_T3 | 2026-08-31 07:30 | 2026-09-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160994
KPU_T3 | SF6 CB pole replacement. | 2026-08-31 07:30 | 2026-09-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160990
KPU_367_VT10 | Affected equipment KPU_T3 | 2026-08-31 07:30 | 2026-09-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160987
ISL_TKB_1 | Tower Painting | 2026-08-31 07:30 | 2026-09-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143086
FHL_TUI_1 | FHL-CT-62, FHL-DS-66, FHL-ES-69, TUI-DS-146, TUI-VT-142. Last day for testing. NO LINES WORK. | 2026-08-31 07:30 | 2026-09-01 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160499
MNG_287_VT2 | CT/VT replacement project MNG-M-VT2, MNG-VT-2 | 2026-08-31 07:30 | 2026-09-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161074
EDG_T5 | Affected Equipment of EDG_227_254_274 SRG-Gantry Painting | 2026-08-31 07:30 | 2026-09-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006188
ROS_117_147 | ROS 110kV Gantry Refurb Project | 2026-08-31 07:30 | 2026-09-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162112
ROS_T4 | Affected Equipment ROS 110kV Gantry Refurb Project | 2026-08-31 07:30 | 2026-09-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162114
MNG_OTA_2 | Seimens relay replacement | 2026-08-31 07:30 | 2026-09-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161078
MNG_ROS_2 | MNG-ROS-A0034-20, ROS-CT-122, ROS-DS-126, ROS-ES-129, ROS-P-CB-122 | 2026-08-31 07:30 | 2026-09-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161080
EDG_227_254_274 | SRG-Gantry Painting | 2026-08-31 07:30 | 2026-09-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006184
BEN_OHB_1 | BEN 220BZ - BEN_OHB_1 CCT Migration | 2026-08-31 07:30 | 2026-09-10 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2006287
ISL_FDR_92 | ISL-CB-92, ISL-DS-96, ISL-P-CB-92 | 2026-08-31 07:30 | 2026-08-31 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160859
ISL_FDR_322 | ISL-P-CB-322 | 2026-08-31 07:30 | 2026-08-31 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160858
ARG_KIK_1 | Lines Maintenance | 2026-08-31 07:30 | 2026-09-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160150
MTR_OKN_1 | ONG SPS Changeover Project | 2026-08-31 08:00 | 2026-09-04 15:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2005768
GOR_ROX_1 | GOR-ROX COPS SPS Scheme Project. | 2026-08-31 08:00 | 2026-09-04 17:30 | Continuous | SI | RS - Removal from Service | Approved | OW1162683
BEN_220CBF | BEN-CT-CT418 BEN 220BZ - CB418 Migration BEN 220BZ - AVI_BEN_1 CCT Migration CP_BEN_AZ_00_00 | 2026-08-31 08:00 | 2026-08-31 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160248
MDN_MPE_1 | Tower Painting | 2026-08-31 08:00 | 2026-09-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142912
BEN_220BZ | BEN-CT-CT418 BEN 220BZ - CB418 Migration BEN 220BZ - AVI_BEN_1 CCT Migration CP_BEN_AZ_00_00 | 2026-08-31 08:00 | 2026-08-31 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160231
MPE_CB_252 | system split for the duration of MDN_MPE_1 | 2026-08-31 08:00 | 2026-08-31 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1143152
MPE_CB_292 | system split for the duration of MDN_MPE_1 | 2026-08-31 08:00 | 2026-08-31 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1143153
GOR_RTU_1 | GOR-ROX-1 COPS Protection Project | 2026-08-31 09:00 | 2026-08-31 16:00 | Daily | SI | RS - Removal from Service | Approved | OW2005346
MPE_CB_292 | system split for the duration of MDN_MPE_1 | 2026-09-01 06:00 | 2026-09-03 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161131
MPE_CB_252 | system split for the duration of MDN_MPE_1 | 2026-09-01 06:00 | 2026-09-03 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161096
OTA_CB_1462 | Affected equipment OTA_220BS_N & OTA_CB_1412 & OTA_CB_1422 | 2026-09-01 07:30 | 2026-09-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006018
KMO_T2 | 110KV line protection upgrade | 2026-09-01 07:30 | 2026-09-01 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW1157369
ASB_ISL_1 | insulator and earth wire | 2026-09-01 07:30 | 2026-09-01 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160186
WPR_T12 | Affected Equipment of WPR_127_134_174 WPR Project-Mt Cass Connections, upgrade DIS | 2026-09-01 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161827
WPR_127_134_174 | WPR Project-Mt Cass Connections, upgrade DIS | 2026-09-01 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161816
OTA_220BS_N | OTA-CT-CT1448A, OTA-DS-1415, OTA-DS-1425, OTA-DS-1447, OTA-ES-1420, OTA-ES-1449, OTA-P-CB-1448 | 2026-09-01 07:30 | 2026-09-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161310
OTA_C_30 | OTA-CB-1422 | 2026-09-01 07:30 | 2026-09-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161321
OTA_C_31 | OTA-CB-1412 | 2026-09-01 07:30 | 2026-09-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161323
ASY_WPR_1 | Affected Equipment of WPR_127_134_174 WPR Project-Mt Cass Connections, upgrade DIS | 2026-09-01 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160195
OTA_CB_1448 | Affected equipment OTA_220BS_N & OTA_CB_1412 & OTA_CB_1422 | 2026-09-01 07:30 | 2026-09-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161326
BPE_110CBF | Affected equipment for the BZ outage | 2026-09-01 08:00 | 2026-09-01 18:00 | Daily | SNI | RS - Removal from Service | Approved | OW1163523
BPE_110BZ | Modifications to the BZ/CBF system | 2026-09-01 08:00 | 2026-09-01 18:00 | Daily | SNI | RS - Removal from Service | Approved | OW1163522
BEN_RTU_MULTI | BEN 220BZ - BEN_OHB_1 CCT Migration | 2026-09-01 08:00 | 2026-09-01 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2006288
KAW_RTU_1 | RSA2 Battery & Charger work | 2026-09-01 08:00 | 2026-09-01 16:30 | Daily | NNI | RS - Removal from Service | Approved | OW2005722
ROX_RTU_1 | GOR-ROX-1 COPS Protection Project | 2026-09-01 09:00 | 2026-09-01 16:00 | Daily | SI | RS - Removal from Service | Approved | OW2005350
STK_RTU_1 | Stage 0 - STK T7 Transformer Protection Replacement RTU Config Load | 2026-09-01 11:30 | 2026-09-01 16:30 | Daily | SI | RS - Removal from Service | Approved | OW1162751
STK_RTU_2 | Stage 0 - STK T7 Transformer Protection Replacement RTU Config Load | 2026-09-01 11:30 | 2026-09-01 16:30 | Daily | SI | RS - Removal from Service | Approved | OW1162752
STK_RTU_3 | Stage 0 - STK T7 Transformer Protection Replacement RTU Config Load | 2026-09-01 11:30 | 2026-09-01 16:30 | Daily | SI | RS - Removal from Service | Approved | OW1162753
KMO_T4 | 110KV line protection upgrade | 2026-09-02 07:30 | 2026-09-02 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW1157370
WGN_110CBF | Affected equipment for the BZ outage | 2026-09-02 08:00 | 2026-09-02 18:00 | Daily | SNI | RS - Removal from Service | Approved | OW1163525
WGN_110BZ | Modifications to the BZ/CBF system | 2026-09-02 08:00 | 2026-09-02 18:00 | Daily | SNI | RS - Removal from Service | Approved | OW1163524
BEN_RTU_1 | BEN 220BZ - BEN_OHB_1 CCT Migration | 2026-09-02 08:00 | 2026-09-02 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2006289
IGH_110BZ | IGH CBF Isolation for safety to isolate CBF to IGH 412 | 2026-09-03 07:30 | 2026-09-03 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005495
DOB_RFN_IGH_1 | Protection project RFN CB332, IGH CB412 Line Protection Replacement CP_RFN_06_00_00, CP_IGH_40_00_00 | 2026-09-03 07:30 | 2026-09-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160437
IGH_110CBF | IGH CBF Isolation for safety to isolate CBF to IGH 412 | 2026-09-03 07:30 | 2026-09-03 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005494
IGH_RTU_1 | IGH SMS Config Load | 2026-09-03 07:30 | 2026-09-03 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005497
DOB_66BZ_CBF | IGH CBF Isolation for safety to isolate CBF to IGH 412 | 2026-09-03 07:30 | 2026-09-03 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005496
DOB_T12 | Affected Equipment of DOB_RFN_IGH_1 Protection project RFN CB332, IGH CB412 Line Protection Replacement CP_RFN_06_00_00, CP_IGH_40_00_00 | 2026-09-03 07:30 | 2026-09-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160442
MPE_CB_252 | system split for the duration of MDN_MPE_1 | 2026-09-04 06:00 | 2026-09-04 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161097
MPE_CB_292 | system split for the duration of MDN_MPE_1 | 2026-09-04 06:00 | 2026-09-04 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161132
PTS_1604_MPE_MTO | MPE-C-PTSG-1604A, MTO-C-PTSG-1604A | 2026-09-04 07:30 | 2026-09-04 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161455
RFN_RTU_1 | RFT SMS Config Load | 2026-09-04 07:30 | 2026-09-04 12:30 | Daily | SI | RS - Removal from Service | Approved | OW2005498
DOB_RTU_1 | RFT SMS Config Load | 2026-09-04 12:30 | 2026-09-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005499
KIK_STK_3 | Under clearance works | 2026-09-07 06:30 | 2026-09-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1151080
KMO_2157_2184 | Affected equipment | 2026-09-07 07:30 | 2026-09-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160959
BRK_CB_572 | BRK-P-CB-572. Affected equipment of BRK_SFD_3. | 2026-09-07 07:30 | 2026-10-09 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160359
WPR_T3 | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161834
WPR_LST_30 | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161826
WPR_FDR_82 | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161824
NMA_GOR_TMH_2 | GOR-CVT-VT712, GOR-ES-719, NMA-DS-813, NMA-TMH-A0153-20, NMA-TMH-A0177-20, NMA-TMH-A0178-20, NMA-TMH-A0186-20, NMA-TMH-A0189-20, NMA-TMH-A0192-20, NMA-TMH-A0225-20, NMA-TMH-A0227-20, NMA-TMH-A0230-20, NMA-TMH-A0236-20, NMA-TMH-A0239-0240-20, NMA-TMH-A0240-0241-20 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161246
WPR_FDR_132 | WPR-P-CB-132 moved fr GXP outage from July 2026 Affected Equipment of WPR_127_134_174 WPR Project-Mt Cass Connections, upgrade DIS | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161823
WPR_FDR_1192 | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161821
TNG_220BS_A | TNG-DS-273 (T12) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-220 | 2026-09-07 07:30 | 2026-09-08 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161675
BRK_SFD_3 | SFD-DS-653, SFD-DS-665. Tower steel replacements. [CP_760_005_0_00]. Optimised. | 2026-09-07 07:30 | 2026-10-09 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160370
WPR_FDR_1172 | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161820
WPR_FDR_1132 | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161818
GOR_T12 | GOR-CB-712, GOR-CBL-T12-ET12, GOR-CT-CT592, GOR-CT-CT712, GOR-CT-NCT12, GOR-DCB-592, GOR-DS-716, GOR-NCTD-T12, GOR-P-CB-712, GOR-P-TF-T12, GOR-TF-ET12, GOR-TF-T12 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160531
WPR_33BS | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161817
TNG_CB_288 | Affected equipment of TNG_220BS_A, for TNG-DS-273 (T12), TNG-ES-220 | 2026-09-07 07:30 | 2026-09-08 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161690
ISL_NWD_1 | Tower Painting | 2026-09-07 07:30 | 2026-09-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143123
KMO_CB_2158 | KMO-CB-2158, KMO-P-CB-2158 | 2026-09-07 07:30 | 2026-09-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160964
TNG_T12 | BPE-TNG prot upgrade Stage 2: Installation of CT-272 at Bay 270[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1162037
WPR_104_137 | WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161815
KUM_OTI_1 | Lines Maintenance | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1162030
KMO_FDR_2172 | KMO-CB-2172, KMO-P-CB-2172 | 2026-09-07 07:30 | 2026-09-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160967
KMO_FDR_2182 | KMO-CB-2182, KMO-P-CB-2182 | 2026-09-07 07:30 | 2026-09-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160968
SBK_WPR_1 | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161528
HKK_OTI_2 | Lines Maintenance | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1162026
WPR_T13 | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161830
KMO_MTM_TGA_2 | KMO-MTM-TGA line protection upgrade | 2026-09-07 07:30 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162246
MDN_MPE_2 | Tower Painting | 2026-09-07 08:00 | 2026-09-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142914
MPE_CB_252 | System split for the duration MDN_MPE_2 | 2026-09-07 08:00 | 2026-09-07 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1143154
OTA_ROS_2 | Tower Painting. ROS 82 corroded bolts repair and Siemens relay replacement | 2026-09-07 08:00 | 2026-09-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142925
MPE_CB_292 | System split for the duration MDN_MPE_2 | 2026-09-07 08:00 | 2026-09-07 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1143155
MPE_CB_292 | System split for the duration MDN_MPE_2 | 2026-09-08 06:00 | 2026-09-10 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161133
MPE_CB_252 | System split for the duration MDN_MPE_2 | 2026-09-08 06:00 | 2026-09-10 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161098
CML_FDR_1102 | CML-DS-1106, CML-ES-1109, CML-P-CB-1102 | 2026-09-08 07:30 | 2026-09-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160386
TGA_T4 | KMO-MTM-TGA 110KV line prot upgrade | 2026-09-08 07:30 | 2026-09-08 16:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155717
KMO_110BZ | 110KV line protection upgrade | 2026-09-08 07:30 | 2026-09-08 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155725
KMO_110CBF | 110KV line protection upgrade | 2026-09-08 07:30 | 2026-09-08 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155726
TGA_110CBF | 110KV line protection upgrade | 2026-09-08 07:30 | 2026-09-08 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155776
TGA_110BZ | 110KV line protection upgrade | 2026-09-08 07:30 | 2026-09-08 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155777
WGN_RTU_1 | Post second circuit outage tidyup | 2026-09-08 08:00 | 2026-09-08 11:00 | Daily | SNI | RS - Removal from Service | Approved | OW1162437
MTN_RTU_1 | Post second circuit outage tidyup | 2026-09-08 13:00 | 2026-09-08 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW1162433
TNG_220BS_B | BPE-TNG prot upgrade Stage 2: Installation of CT-272 at Bay 270[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. TNG-DS-275 (T12) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-230 | 2026-09-09 07:30 | 2026-09-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161682
TNG_CB_288 | Affected equipment of TNG_220BS_B, for TNG-DS-275 (T12), TNG-ES-230 | 2026-09-09 07:30 | 2026-09-10 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161691
SVL_FDR_2822 | SVL-CBL-2822 | 2026-09-09 07:30 | 2026-09-09 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161579
TNG_FDR_2772 | TNG-CB-2772, TNG-P-CB-2772 (TENTATIVE OW - asset may be decommissioned). | 2026-09-09 07:30 | 2026-09-09 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161696
BEN_220CBF | BEN-CT-CT418 BEN 220BZ - CB418 Migration BEN 220BZ - AVI_BEN_1 CCT Migration CP_BEN_AZ_00_00 | 2026-09-09 08:00 | 2026-09-10 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160249
PEN_CB_848 | Affected equipment | 2026-09-09 08:00 | 2026-09-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161398
BPE_RTU_1 | Post second circuit outage tidyup | 2026-09-09 08:00 | 2026-09-09 11:00 | Daily | SNI | RS - Removal from Service | Approved | OW1162428
BEN_220BZ | BEN-CT-CT418 BEN 220BZ - CB418 Migration BEN 220BZ - AVI_BEN_1 CCT Migration CP_BEN_AZ_00_00BEN 220BZ - AVI_BEN_1 CCT MigrationCP_BEN_AZ_00_00 | 2026-09-09 08:00 | 2026-09-10 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160232
PEN_CB_698 | Affected equipment | 2026-09-09 08:00 | 2026-09-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161387
PEN_697_847 | PEN-CBL-698-848, | 2026-09-09 08:00 | 2026-09-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161374
CML_FDR_1052 | , CML-P-CB-1052 | 2026-09-10 07:30 | 2026-09-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005894
KMO_FDR_2132 | KMO-CB-2132, KMO-P-CB-2132 | 2026-09-10 07:30 | 2026-09-10 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160966
TNG_FDR_2792 | TNG-CB-2792, TNG-P-CB-2792 (TENTATIVE OW - asset may be decommissioned). | 2026-09-10 07:30 | 2026-09-10 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161697
HEP_FDR_2222 | HEP-CB-2222, HEP-P-CB-2222 | 2026-09-10 07:30 | 2026-09-10 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160679
TNG_T11 | BPE-TNG prot upgrade Stage 2: Installation of CT-272 at Bay 270[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-09-10 07:30 | 2026-09-10 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005756
TNG_220CBF | Affected equipment of TNG_220BZ, for BPE-TNG prot upgrade Stage2 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-09-10 08:00 | 2026-09-10 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005572
TNG_220BZ | BPE-TNG prot upgrade Stage 2: Installation of CT-272 at Bay 270[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-09-10 08:00 | 2026-09-10 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005560
MPE_CB_292 | System split for the duration MDN_MPE_2 | 2026-09-11 06:00 | 2026-09-11 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161134
MPE_CB_252 | System split for the duration MDN_MPE_2 | 2026-09-11 06:00 | 2026-09-11 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161099
KMO_FDR_2122 | KMO-CB-2122, KMO-P-CB-2122 | 2026-09-11 07:30 | 2026-09-11 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160965
BPE_TNG_1 | BPE-TNG prot upgrade Stage 2: Installation of CT-272 at Bay 270[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-09-11 11:30 | 2026-09-11 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005562
ISL_SBK_1 | ISL-SBK A line reconductoring | 2026-09-14 06:30 | 2026-10-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1157428
ISL_SBK_2 | ISL-SBK A line reconductoring | 2026-09-14 06:30 | 2026-10-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1157430
KPU_367_VT10 | Affected equipment KPU_T3 | 2026-09-14 07:00 | 2026-09-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160988
KPU_T3 | KPU-CB-342, KPU-CT-342, KPU-TF-T3, KPU-VT-VT1062 | 2026-09-14 07:00 | 2026-09-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160991
KPU_WKO_2 | Affected Equipment of KPU_367_VT10 | 2026-09-14 07:00 | 2026-09-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160995
WTU_T4 | WTU-P-TF-T4 [CP_WTU_009_0_00]. Affected equipment of RDF_WTU_1. | 2026-09-14 07:30 | 2026-09-18 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161879
ROX_T10_573_575_584 | ROX-CT-CT572, ROX-NCTD-T10 | 2026-09-14 07:30 | 2026-09-18 18:00 | Continuous | SI | RS - Removal from Service | Approved | OW1161519
TNG_CB_288 | Affected equipment of TNG_220BS_A, for TNG-DS-223 (T2), TNG-ES-220 | 2026-09-14 07:30 | 2026-09-15 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161692
MNG_ROS_1 | Affected Equipment ROS 110kv Gantry Refurb PJ | 2026-09-14 07:30 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006044
TNG_T2 | BPE-TNG prot upgrade Stage 3: Installation of CT-222 at Bay 220[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. TNG-CT-1562, TNG-DS-1566, TNG-ES-1569, TNG-SA-2, TNG-TF-T2, TNG-VT-1562. TNG-TF-T2 [CP_TNG_BG_00_00]. Reinhausen work. | 2026-09-14 07:30 | 2026-09-18 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1162038
RDF_WTU_1 | RDF-CB-652, RDF-CT-652, RDF-CVT-652, RDF-DS-653, RDF-DS-655, RDF-DS-656, RDF-ES-659, RDF-P-CB-652, WTU-CVT-4, WTU-DS-846, WTU-ES-849. RDF-CB-652 line protection & ODJB [CP_RDF_00E_0_00]. | 2026-09-14 07:30 | 2026-09-18 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161474
ROS_T3 | Affected Equipment ROS 110kV Gantry Refurb PJ | 2026-09-14 07:30 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162111
INV_ROX_1 | INV-P-CB-692/722, INV-ROX-A0001-00, INV-ROX-A0009-00, INV-ROX-A0010-00, INV-ROX-A0027-00, INV-ROX-A0028-00, INV-ROX-A0029-00, INV-ROX-A0031-00, INV-ROX-A0032-00, INV-ROX-A0033-00, INV-ROX-A0035-00, INV-ROX-A0050-00, INV-ROX-A0078-00, INV-ROX-A0087-00, ROX-P-CB-492 | 2026-09-14 07:30 | 2026-09-18 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160787
ROS_97_127 | ROS 110kV Gantry Refurb PJ ROS 110kv Gantry Refurbishment Project | 2026-09-14 07:30 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162110
TNG_220BS_A | TNG-DS-223 (T2) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-220 | 2026-09-14 07:30 | 2026-09-15 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161676
TGA_T3 | 110KV line protection upgrade | 2026-09-14 07:30 | 2026-09-14 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW1157371
ISL_KIK_1 | Tower Painting - ISL-KIK-A0276 ISL-KIK-A0296 ISL-KIK-A0303 ISL-KIK-A0312 ISL-KIK-A0342. | 2026-09-14 07:30 | 2026-09-18 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143100
OHW_OTA_1 | Spacer replacement project. OTA-WKM-C0310-0311-10 | 2026-09-14 07:30 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161282
ISL_TKB_1 | BEN-ISL-A0393-10, BEN-ISL-A0678-10 | 2026-09-14 07:30 | 2026-09-18 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005913
MPE_CB_252 | System split for the duration of HEN_HPI_1 | 2026-09-14 08:00 | 2026-09-14 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1143525
MPE_CB_292 | System split for the duration of HEN_HPI_1 | 2026-09-14 08:00 | 2026-09-14 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1143526
DRY_TAK_OTA_1 | Tower Painting | 2026-09-14 08:00 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142880
EDG_207_217_237 | SRG-Gantry Painting | 2026-09-14 08:00 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006190
TAK_T5 | Affected Equipment Tower Painting | 2026-09-14 08:00 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142881
BEN_220BZ | BEN 220BZ - AVI_BEN_1 CCT Migration CP_BEN_AZ_00_00 | 2026-09-14 08:00 | 2026-09-14 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2006291
BRB_HPI_1 | Affected Equipment Tower Painting | 2026-09-14 08:00 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1143182
HEN_HPI_1 | Tower Painting | 2026-09-14 08:00 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1143181
EDG_DIS_214 | CLO for the duration of EDG_207_217_227 | 2026-09-14 08:00 | 2026-09-18 18:30 | Continuous | NNI | CLO - Close | Approved | OW2006285
EDG_CB_222 | Affected Equipment of EDG_207_217_237 SRG-Gantry Painting | 2026-09-14 08:00 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006191
BEN_220CBF | BEN 220BZ - AVI_BEN_1 CCT Migration CP_BEN_AZ_00_00 | 2026-09-14 08:00 | 2026-09-14 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2006292
AVI_BEN_1 | BEN 220BZ - AVI_BEN_1 CCT Migration CP_BEN_AZ_00_00 | 2026-09-14 08:00 | 2026-09-24 18:00 | Continuous | SI | RS - Removal from Service | Approved | OW2005402
KAW_CB_112 | CLO for the duration of EDG_207_217_227 outage | 2026-09-14 08:00 | 2026-09-18 18:30 | Continuous | NNI | CLO - Close | Approved | OW2006286
MPE_CB_292 | System split for the duration of HEN_HPI_1 | 2026-09-15 06:00 | 2026-09-17 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161135
MPE_CB_252 | System split for the duration of HEN_HPI_1 | 2026-09-15 06:00 | 2026-09-17 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161100
WTK_11BS_B | Affected equipment WTK_T22 | 2026-09-15 07:30 | 2026-09-17 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161866
WTK_FDR_28 | Affected equipment WTK_T22 | 2026-09-15 07:30 | 2026-09-17 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161869
TGA_T4 | 110KV line protection upgrade | 2026-09-15 07:30 | 2026-09-15 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW1157372
WTK_LST_32 | Affected equipment WTK_T22 | 2026-09-15 07:30 | 2026-09-17 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161871
WTK_T22 | WTK-CBL-T22-ET32, WTK-CBL-T22-T32, WTK-CT-CT22, WTK-CT-CT462, WTK-ES-290, WTK-P-AVR-T32, WTK-P-TF-T22, WTK-RES-T22-N, WTK-TF-ET32, WTK-TF-T22, WTK-TF-T32, WTK-VT-VT22, WTK-VT-VT32 | 2026-09-15 07:30 | 2026-09-17 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161873
CUL_T22 | CUL-CBL-LS22, CUL-CBL-NER22, CUL-CBL-T22, CUL-P-TF-T22, CUL-RES-NER22, CUL-TF-LS22, CUL-TF-T22 | 2026-09-16 06:30 | 2026-09-18 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160427
MTM_110CBF | 110KV line upgrade project | 2026-09-16 08:00 | 2026-09-16 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1157376
MTM_110BZ | 110KV line upgrade project | 2026-09-16 08:00 | 2026-09-16 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1157375
MTM_C_1 | OC/EF(HV) relay input 110KV line protection upgrade | 2026-09-16 08:00 | 2026-09-16 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW1157373
CCT_2031_OWH_TMI | OWH - SMR Internal Plant Works | 2026-09-16 08:00 | 2026-09-16 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1156327
CCT_2108_OWH_TRK | OWH - SMR Internal Plant Works | 2026-09-16 08:00 | 2026-09-16 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1156326
BEN_RTU_MULTI | BEN 220BZ - AVI_BEN_1 CCT Migration CP_BEN_AZ_00_00 | 2026-09-16 08:00 | 2026-09-16 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2006290
TNG_T11 | BPE-TNG prot upgrade Stage 3: Installation of CT-222 at Bay 220[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-09-17 07:30 | 2026-09-17 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005760
MPE_FDR_242 | Revenue metering. MPE-M-CT242 | 2026-09-17 07:30 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161166
KPU_LST_1 | KPU-TF-LS | 2026-09-17 07:30 | 2026-09-17 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160989
TNG_220CBF | Affected equipment of TNG_220BZ, for BPE-TNG prot upgrade Stage3 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-09-17 08:00 | 2026-09-17 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005573
TNG_220BZ | BPE-TNG prot upgrade Stage 3: Installation of CT-222 at Bay 220[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-09-17 08:00 | 2026-09-17 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005563
MPE_CB_252 | System split for the duration of HEN_HPI_1 | 2026-09-18 06:00 | 2026-09-18 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161101
MPE_CB_292 | System split for the duration of HEN_HPI_1 | 2026-09-18 06:00 | 2026-09-18 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161136
TNG_CB_288 | Affected equipment of TNG_220BS_B, for BPE-TNG prot upgrade Stage 3, TNG-ES-230 | 2026-09-18 07:30 | 2026-09-18 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161693
TNG_220BS_B | BPE-TNG prot upgrade Stage 3: Installation of CT-222 at Bay 220[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. TNG-ES-230 | 2026-09-18 07:30 | 2026-09-18 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161683
KMO_110BZ | 110KV line protection upgrade | 2026-09-18 07:30 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1155774
KMO_110CBF | 110KV line protection upgrade | 2026-09-18 07:30 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1155775
MTM_110BZ | 110KV line protection upgrade | 2026-09-18 07:30 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1155778
MTM_110CBF | 110KV line protection upgrade | 2026-09-18 07:30 | 2026-09-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1155779
TGA_110CBF | 110KV line upgrade project | 2026-09-18 08:00 | 2026-09-18 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1157378
TGA_110BZ | 110KV line upgrade project | 2026-09-18 08:00 | 2026-09-18 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1157377
BPE_TNG_1 | BPE-TNG prot upgrade Stage 3: Installation of CT-222 at Bay 220[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-09-18 11:30 | 2026-09-18 17:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005564
ISL_NWD_1 | Tower Painting | 2026-09-21 06:30 | 2026-09-26 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143130
TMH_CB_538 | Affected equipment TMH_220BS_A3 | 2026-09-21 07:30 | 2026-09-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161647
TMH_220BS_A3 | TMH-DS-553, TMH-DS-603 | 2026-09-21 07:30 | 2026-09-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161645
EDG_217_207_324 | SRG-Gantry Painting | 2026-09-21 07:30 | 2026-09-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006192
OHW_OTA_1 | Sub conductor spacers project | 2026-09-21 07:30 | 2026-09-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161283
RDF_703_627_673 | RDF-BS-220-587-627, RDF-BS-220-617-673. | 2026-09-21 07:30 | 2026-09-21 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161467
RDF_CB_628 | Affected equipment RDF_587_617_627 | 2026-09-21 07:30 | 2026-09-21 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161468
RDF_WTU_2 | RDF-CB-672 line protection & ODJB [CP_RDF_00E_0_00]. | 2026-09-21 07:30 | 2026-09-25 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161475
OTA_ROS_1 | Affected Equipment ROS 110kv Gantry Refurb PJ | 2026-09-21 07:30 | 2026-09-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006067
ROX_TMH_2 | ROX-ES-639, ROX-TMH-A0078-0079-20, TMH-CB-552, TMH-CT-CT552, TMH-CVT-VT9, TMH-DS-555, TMH-DS-556, TMH-ES-559 | 2026-09-21 07:30 | 2026-09-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161521
ROX_644_635_633_636 | ROX-DS-636 | 2026-09-21 07:30 | 2026-09-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161514
ROS_137_167 | ROS 110kV Gantry Refurb PJ | 2026-09-21 07:30 | 2026-09-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162361
HAY_F_8 | S4.10E22-FB8, S4.10E22.B-C1A, S4.10E22.B-C1B, S4.10E22.B-C1C, S4.10E22.B-L1A, S4.10E22.B-L1B, S4.10E22.B-L1C, S4.10E22.B-R1A, S4.10E22.B-R1B, S4.10E22.B-R1C | 2026-09-21 07:30 | 2026-09-25 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160615
EDG_KAW_2 | Affected Equipment of EDG_217_207_324 SRG-Gantry Painting | 2026-09-21 07:30 | 2026-09-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006193
WTU_T3 | WTU-CBL-LS3, WTU-CBL-T3-2152, WTU-NER-3, WTU-SA-3A, WTU-TF-LS3,WTU-TF-T3. WTU-P-TF-T3 [CP_WTU_009_0_00]. Affected equipment ofRDF_WTU_2. | 2026-09-21 07:30 | 2026-09-25 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161878
ROS_FDR_142 | Affected Equipment ROS 110kV Gantry Refurb PJ | 2026-09-21 07:30 | 2026-09-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162118
HEP_FDR_2232 | HEP-CB-2232, HEP-P-CB-2232 | 2026-09-21 07:30 | 2026-09-21 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160680
BEN_220BZ | BEN 220BZ - CB408 Migration CP_BEN_AZ_00_00 | 2026-09-21 08:00 | 2026-09-21 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005415
MPE_CB_292 | System split for the duration of MDN_MPE_1 | 2026-09-21 08:00 | 2026-09-21 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1143157
MPE_CB_252 | System split for the duration of MDN_MPE_1 | 2026-09-21 08:00 | 2026-09-21 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1143156
DRY_TAK_OTA_2 | Tower Painting | 2026-09-21 08:00 | 2026-09-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142884
TAK_T8 | Affected Equipment Tower Painting | 2026-09-21 08:00 | 2026-09-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142885
BEN_220CBF | BEN 220BZ - CB408 Migration CP_BEN_AZ_00_00 | 2026-09-21 08:00 | 2026-09-21 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005416
MDN_MPE_1 | Tower Painting | 2026-09-21 08:00 | 2026-09-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142913
MPE_CB_252 | System split for the duration of MDN_MPE_1 | 2026-09-22 06:00 | 2026-09-24 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161102
MPE_CB_292 | System split for the duration of MDN_MPE_1 | 2026-09-22 06:00 | 2026-09-24 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161137
OTA_CB_1438 | Affected equipment OTA_220BS_M & OTA_CB_1412 & OTA_CB_1422 | 2026-09-22 07:30 | 2026-09-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161325
OTA_C_31 | OTA-CB-1412 | 2026-09-22 07:30 | 2026-09-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161324
OTA_C_30 | OTA-CB-1422 | 2026-09-22 07:30 | 2026-09-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161322
OTA_220BS_M | OTA-CT-CT1438A, OTA-DS-1413, OTA-DS-1423, OTA-DS-1437, OTA-ES-1410, OTA-ES-1439, OTA-P-CB-1438 | 2026-09-22 07:30 | 2026-09-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161309
RDF_597_703 | RDF-BS-220-587-703 | 2026-09-22 07:30 | 2026-09-22 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161466
OTA_CB_1472 | Affected equipment OTA_220BS_M & OTA_CB_1412 & OTA_CB_1422 | 2026-09-22 07:30 | 2026-09-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006027
SVL_FDR_2782 | SVL-CBL-2782 | 2026-09-22 07:30 | 2026-09-22 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161577
OHW_C_2 | OWH-NER-2 | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161280
RDF_220BS_B | RDF-BS-220-627-705 | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161465
HAY_11BS_F | Affected equipment HAY_T22 | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160599
HAY_11BS_G | Affected equipment HAY_T22 | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160600
HAY_T37 | Affected equipment HAY_T22 | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160631
HAY_T34 | Affected equipment HAY_T22 | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160629
HAY_T22 | HAY-CT-822 | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160627
MTM_110CBF | 110KV line protection upgrade | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155729
MTM_110BZ | 110KV line protection upgrade | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155730
BEN_220CBF | BEN 220BZ - AVI_BEN_1 CCT Migration CP_BEN_AZ_00_00 | 2026-09-23 08:00 | 2026-09-23 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2006293
TMH_220BS_B | TMH-DS-605 | 2026-09-24 07:30 | 2026-09-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161646
TMH_CB_538 | Affected equipment TMH_220BS_B | 2026-09-24 07:30 | 2026-09-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161648
PEN_FDR_2232 | PEN-CB-2232, PEN-P-CB-2232 | 2026-09-24 07:30 | 2026-09-24 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161406
MPE_CB_292 | System split for the duration of MDN_MPE_1 | 2026-09-25 06:00 | 2026-09-25 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161138
MPE_CB_252 | System split for the duration of MDN_MPE_1 | 2026-09-25 06:00 | 2026-09-25 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161103
RFN_RTU_1 | RFT SMS Config Load | 2026-09-25 07:30 | 2026-09-25 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005500
TGA_C_11 | OC/EF(HV) relay input 110KV line protection upgrade | 2026-09-25 08:00 | 2026-09-25 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW1157374
OTI_CB_1062 | Affected equipment OTI_T6 | 2026-09-26 07:30 | 2026-09-27 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161352
OTI_LST_1 | Affected equipment OTI_T6 | 2026-09-26 07:30 | 2026-09-27 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161353
OTI_T6 | OTI-M-CT1062, OTI-M-VT1062, OTI-TF-T6 | 2026-09-26 07:30 | 2026-09-27 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161354
CML_T8 | Affected equipment CYD_CML_TWZ_2 | 2026-09-28 07:30 | 2026-10-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160390
CML_FKN_2 | Affected Equipment of CML_T8 Affected equipment CYD_CML_TWZ_2 | 2026-09-28 07:30 | 2026-10-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160388
DOB_RTU_1 | RFT SMS Config Load | 2026-09-28 07:30 | 2026-09-28 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005502
KMO_MTM_1 | 110KV line protection upgrade | 2026-09-28 07:30 | 2026-10-30 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1157384
TNG_220BS_A | TNG-DS-343 (T3) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-220 | 2026-09-28 07:30 | 2026-09-28 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161677
ISL_KIK_1 | Tower Painting | 2026-09-28 07:30 | 2026-10-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143099
ISL_LST_8 | Affected Equipment of ISL_T2 ISL-M-CT2112, ISL-M-VT2112, ISL-NCTD-T2 | 2026-09-28 07:30 | 2026-10-03 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005076
CYD_CML_TWZ_2 | ROX-TWZ-A0143-20, ROX-TWZ-A0145-20, ROX-TWZ-A0146-20, ROX-TWZ-A0147-20, ROX-TWZ-A0148-20, ROX-TWZ-A0149-20, ROX-TWZ-A0150-20, ROX-TWZ-A0151-20, ROX-TWZ-A0152-20, ROX-TWZ-A0153-20, ROX-TWZ-A0154-20, ROX-TWZ-A0155-20, ROX-TWZ-A0156-20, ROX-TWZ-A0157-20 | 2026-09-28 07:30 | 2026-10-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160433
TNG_CB_288 | Affected Equipment of TNG_220BS_A TNG-DS-343 (T3), TNG-ES-220 | 2026-09-28 07:30 | 2026-09-28 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161694
TNG_T3 | BPE-TNG prot upgrade Stage 4: Installation of CT-342 at Bay 340[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. TNG-CT-1572, TNG-CT-342, TNG-DS-1576, TNG-ES-1579, TNG-TF-T3, TNG-VT-1572. | 2026-09-28 07:30 | 2026-10-02 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161699
FKN_T3 | Affected equipment CYD_CML_TWZ_2 | 2026-09-28 07:30 | 2026-10-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160505
ISL_C_22 | Affected equipment ISL_T2 | 2026-09-28 07:30 | 2026-10-03 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160816
HEP_ROS_2 | Affected Equipment ROS 110kV Gantry Refurb PJ | 2026-09-28 07:30 | 2026-09-30 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162116
ROS_157_164_174 | ROS 110kV Gantry Refurb PJ | 2026-09-28 07:30 | 2026-09-30 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162362
ISL_T2 | ISL-M-CT2112, ISL-M-VT2112, ISL-NCTD-T2 | 2026-09-28 07:30 | 2026-10-03 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160868
ROS_FDR_162 | Affected Equipment with ROS 137 164 174 | 2026-09-28 07:30 | 2026-09-30 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162119
DOB_66BZ_CBF | DOB 66 CBF reinstate CBF to DOB T12 and DOB 562 and mods | 2026-09-28 07:30 | 2026-09-28 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005501
ISL_LST_4 | Affected Equipment of ISL_T2 ISL-M-CT2112, ISL-M-VT2112, ISL-NCTD-T2 | 2026-09-28 07:30 | 2026-10-03 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005075
MDN_MPE_2 | Tower Painting | 2026-09-28 08:00 | 2026-10-02 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142915
OTA_PEN_2 | Tower Painting | 2026-09-28 08:00 | 2026-10-02 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142922
MPE_CB_252 | System split for the duration of MDN_MPE_2 | 2026-09-28 08:00 | 2026-10-02 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1143158
MPE_CB_292 | System split for the duration of MDN_MPE_2 | 2026-09-28 08:00 | 2026-10-02 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1143159
IGH_RTU_1 | IGH SMS Config Load | 2026-09-29 07:30 | 2026-09-29 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005506
IGH_110CBF | IGH CBF Reinstate CBF to IGH 412 and CBF Mods | 2026-09-29 07:30 | 2026-09-29 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005503
MTM_T1 | 110KV line protection upgrade | 2026-09-29 07:30 | 2026-09-29 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW1157379
IGH_110BZ | IIGH CBF Reinstate CBF to IGH 412 and CBF Mods | 2026-09-29 07:30 | 2026-09-29 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005504
ALB_WRD_4 | ALB-WRD-C-CBL-SHEATH, WRD-VT-VT152. MP_ALB_01F_0_00 | 2026-09-29 07:30 | 2026-10-02 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160137
CLH_11BS | Affected Equipment of CLH_T1 CLH-TF-RT1 | 2026-09-30 07:30 | 2026-10-02 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160381
CLH_FDR_672 | Affected Equipment of CLH_T1 CLH-TF-RT1 | 2026-09-30 07:30 | 2026-10-02 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160383
CLH_FDR_692 | Affected Equipment of CLH_T1 CLH-TF-RT1 | 2026-09-30 07:30 | 2026-10-02 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160384
MTM_T3 | 110KV line protection upgrade | 2026-09-30 07:30 | 2026-09-30 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW1157380
PEN_CB_8612 | Open for the duration of OTA_PEN_5 & PEN_T10 to place PEN REA into service | 2026-09-30 07:30 | 2026-10-02 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1161401
CLH_T1 | CLH-TF-RT1 | 2026-09-30 07:30 | 2026-10-02 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160385
OTA_PEN_5 | OTA-CVT-1192, OTA-P-CB-1192/1202 | 2026-09-30 07:30 | 2026-10-02 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161339
PEN_T10 | Open whilst PEN REA is in service | 2026-09-30 07:30 | 2026-10-02 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1161425
TNG_T12 | BPE-TNG prot upgrade Stage 4: Installation of CT-342 at Bay 340[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-10-01 07:30 | 2026-10-01 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005761
TNG_220CBF | Affected equipment of TNG_220BZ, for BPE-TNG prot upgrade Stage4 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-10-01 08:00 | 2026-10-01 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005574
TGA_FDR_11 | 110KV line protection project | 2026-10-01 08:00 | 2026-10-02 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1157385
BEN_220BZ | BEN 220BZ - CB428 Migration | 2026-10-01 08:00 | 2026-10-02 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160234
BEN_220CBF | BEN 220BZ - CB428 Migration BEN 220BZ - CB408 Migration CP_BEN_AZ_00_00 | 2026-10-01 08:00 | 2026-10-02 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160251
TNG_220BZ | BPE-TNG prot upgrade Stage 4: Installation of CT-342 at Bay 340[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-10-01 08:00 | 2026-10-01 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005565
TNG_220BS_B | BPE-TNG prot upgrade Stage 4: Installation of CT-342 at Bay 340[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. TNG-ES-230 | 2026-10-02 07:30 | 2026-10-02 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161684
TNG_CB_288 | Affected equipment of TNG_220BS_B, for BPE-TNG prot upgrade Stage 4, TNG-ES-230 | 2026-10-02 07:30 | 2026-10-02 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161695
BPE_TNG_1 | BPE-TNG prot upgrade Stage 4: Installation of CT-342 at Bay 340[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-10-02 11:30 | 2026-10-02 17:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005566
KIN_CB_2222 | Open for the duration of KIN T9 | 2026-10-04 01:30 | 2026-10-05 07:29 | Continuous | NNI | OPE - Open Ended | Approved | OW1160941
KIN_CB_2232 | Closed for the duration of KIN T9 | 2026-10-04 01:30 | 2026-10-11 02:00 | Continuous | NNI | CLO - Close | Approved | OW1160942
MCH_T1 | MCH-TF-T1 | 2026-10-04 06:30 | 2026-10-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161031
KIK_MCH_1 | KIK-CB-82 | 2026-10-04 06:30 | 2026-10-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160926
MCH_CB_32 | Affected Equipment of MCH_T1 Affected equipment MCH_110BS & KIK_MCH_1 & MCH_T1 | 2026-10-04 06:30 | 2026-10-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161029
MCH_11BS | Affected equipment MCH_110BS & KIK_MCH_1 & MCH_T1 | 2026-10-04 06:30 | 2026-10-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161028
MCH_110BS | MCH-DS-64 | 2026-10-04 06:30 | 2026-10-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161027
IGH_MCH_1 | Affected equipment MCH_110BS & KIK_MCH_1 & MCH_T1 | 2026-10-04 06:30 | 2026-10-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160767
CML_FKN_1 | Affected equipment CYD_CML_TWZ_1 & CML_T5 | 2026-10-05 06:30 | 2026-10-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160387
CML_T5 | CML-TF-T5A, CML-TF-T5B | 2026-10-05 06:30 | 2026-10-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160389
FKN_T1 | Affected equipment CYD_CML_TWZ_1 & CML_T5 | 2026-10-05 06:30 | 2026-10-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160504
CYD_CML_TWZ_1 | ROX-TWZ-A0143-10, ROX-TWZ-A0145-10, ROX-TWZ-A0146-10, ROX-TWZ-A0147-10, ROX-TWZ-A0148-10, ROX-TWZ-A0149-10, ROX-TWZ-A0150-10, ROX-TWZ-A0151-10, ROX-TWZ-A0152-10, ROX-TWZ-A0153-10, ROX-TWZ-A0154-10, ROX-TWZ-A0155-10, ROX-TWZ-A0156-10, ROX-TWZ-A0157-10 | 2026-10-05 06:30 | 2026-10-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160432
ISL_SBK_2 | ISL-SBK A line reconductoring | 2026-10-05 06:30 | 2026-10-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1157429
ISL_SBK_1 | ISL-SBK A line reconductoring | 2026-10-05 06:30 | 2026-10-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1157431
WPW_T2 | WPW-P-TF-T2 [CP_WPW_00L_0_00]. Affected equipment of DVK_WPW_1. | 2026-10-05 07:00 | 2026-10-09 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161840
MLG_T1 | SS pipework replacement. 12-hour soak on last day. | 2026-10-05 07:00 | 2026-10-16 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161067
RPO_TNG_1 | RPO-DS-333 (bus A), RPO-DS-335 (bus B). RPO-CBL-626-639. BPE-TNG prot upgrade Stage 6: Connect to new TNG 220kV selection scheme (TBC) [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. Affected equipmentof TNG_220BS_A/B. | 2026-10-05 07:00 | 2026-10-09 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161523
DVK_WPW_1 | Tower works x7 (A244, A246, A258, A273, A286, A302, A315). | 2026-10-05 07:00 | 2026-10-09 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160467
ROS_FDR_162 | Protection replacement project, ROS-P-CB-162 | 2026-10-05 07:00 | 2026-10-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161482
CPK_T3 | Affected equipment of CPK_WWD_WIL_3. No cable works. | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160402
ASB_397_427 | ASB-DS-404 | 2026-10-05 07:30 | 2026-10-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160178
INV_TWI_1 | Tower Painting and Lines | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1157289
HAM_T6 | HAM T6 CCC and WTI replacement project. HAM-TF-T6 | 2026-10-05 07:30 | 2026-10-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160572
TGA_FDR_12 | Modify & commission 11 kV CB12 relay settings for COPS trip | 2026-10-05 07:30 | 2026-10-05 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155797
TKR_WIL_2 | Re-insulation x2. Attachment points. Affected equipment of WIL_128_VT57. | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161635
PEN_T10 | PEN-CBL-T10-LV-N, PEN-CT-782, PEN-CT-NCT10, PEN-P-TF-T10, PEN-TF-T10 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161426
ISL_FDR_262 | ISL-CB-262 | 2026-10-05 07:30 | 2026-10-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160856
ASB_FDR_62 | Affected equipment ASB_397_427 | 2026-10-05 07:30 | 2026-10-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160184
NMA_220BS_A4 | MAN-P-CB-252, MAN-TWI-A0010-20, MAN-TWI-A0038-20, MAN-TWI-A0039-20, MAN-TWI-A0042-20, MAN-TWI-A0043-20, MAN-TWI-A0046-20, MAN-TWI-A0049-20, MAN-TWI-A0056-20, MAN-TWI-A0060-20, MAN-TWI-A0061-20, MAN-TWI-A0062-20, MAN-TWI-A0063-20, MAN-TWI-A0294-20, MAN-TWI-A0296-20, MAN-TWI-A0299-20, MAN-TWI-A0300-20, MAN-TWI-A0308-20,MAN-TWI-A0311-0312-20, MAN-TWI-A0313-0314-20, MAN-TWI-A0314-0315-20, NMA-CT-CT762 | 2026-10-05 07:30 | 2026-10-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161205
MAN_NMA_2 | MAN-P-CB-252, MAN-TWI-A0010-20, MAN-TWI-A0038-20, MAN-TWI-A0039-20, MAN-TWI-A0042-20, MAN-TWI-A0043-20, MAN-TWI-A0046-20, MAN-TWI-A0049-20, MAN-TWI-A0056-20, MAN-TWI-A0060-20, MAN-TWI-A0061-20, MAN-TWI-A0062-20, MAN-TWI-A0063-20, MAN-TWI-A0294-20, MAN-TWI-A0296-20, MAN-TWI-A0299-20, MAN-TWI-A0300-20, MAN-TWI-A0308-20,MAN-TWI-A0311-0312-20, MAN-TWI-A0313-0314-20, MAN-TWI-A0314-0315-20, NMA-CT-CT762 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161024
NMA_CB_738 | Affected Equipment of NMA_220BS_A4 MAN-P-CB-252, MAN-TWI-A0010-20, MAN-TWI-A0038-20, MAN-TWI-A0039-20, MAN-TWI-A0042-20, MAN-TWI-A0043-20, MAN-TWI-A0046-20, MAN-TWI-A0049-20, MAN-TWI-A0056-20, MAN-TWI-A0060-20, MAN-TWI-A0061-20, MAN-TWI-A0062-20, MAN-TWI-A0063-20, MAN-TWI-A0294-20, MAN-TWI-A0296-20, MAN-TWI-A0299-20, MAN-TWI-A0300-20, MAN-TWI-A0308-20, MAN-TWI-A0311-0312-20, MAN-TWI-A0313-0314-20, MAN-TWI-A0314-0315-20, NMA-CT-CT762 | 2026-10-05 07:30 | 2026-10-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161236
ASB_T9 | Affected equipment ASB_397_427 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160190
KPO_TMU_1 | System split for the duration of HAM T6 | 2026-10-05 07:30 | 2026-10-11 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1160981
NMA_CB_718 | Affected Equipment of NMA_220BS_A4 MAN-P-CB-252, MAN-TWI-A0010-20, MAN-TWI-A0038-20, MAN-TWI-A0039-20, MAN-TWI-A0042-20, MAN-TWI-A0043-20, MAN-TWI-A0046-20, MAN-TWI-A0049-20, MAN-TWI-A0056-20, MAN-TWI-A0060-20, MAN-TWI-A0061-20, MAN-TWI-A0062-20, MAN-TWI-A0063-20, MAN-TWI-A0294-20, MAN-TWI-A0296-20, MAN-TWI-A0299-20, MAN-TWI-A0300-20, MAN-TWI-A0308-20, MAN-TWI-A0311-0312-20, MAN-TWI-A0313-0314-20, MAN-TWI-A0314-0315-20, NMA-CT-CT762 | 2026-10-05 07:30 | 2026-10-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161227
ARI_HAM_2 | System split for the duration of HAM T6 | 2026-10-05 07:30 | 2026-10-11 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1160165
WIL_128_VT57 | WIL-DCB-118, WIL-DCB-52 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161796
CPK_WWD_WIL_3 | WWD-TEE-A0111-WWDG1-10 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160410
ARI_HAM_1 | System split for the duration of HAM T6 | 2026-10-05 07:30 | 2026-10-11 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1160160
HAY_F_7 | Scheduled Maintenance | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW2006468
ISL_CB_658 | Affected Equipment of ISL_220BS_D ISL-DS-445 Headgear Replacement | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005080
DRY_GLN_1 | Tower Painting | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142835
DRY_BOB_HLY_1 | Tower Painting | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142870
BOB_T4 | Affected Equipment Tower Painting | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142871
DRY_CB_432 | Affected equipment with bus B | 2026-10-05 08:00 | 2026-10-05 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1162925
ALB_HEN_3 | Tower Painting | 2026-10-05 08:00 | 2026-10-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1143180
DRY_220BS_B | DRY CB 462 Siemens relay replacement | 2026-10-05 08:00 | 2026-10-05 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1162924
ISL_220BS_D | ISL-DS-445 Headgear Replacement | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005078
KIN_11BS_D | KIN-VT-2057, SM KIN 2042, 2052, 2072 | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160937
KIN_317_368 | KIN-DCB-338 | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160938
OTA_ROS_1 | Tower Painting | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142927
KIN_CB_2042 | KIN-CB-2042 | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160940
KIN_CB_338 | Affected equipment KIN_317_368 | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160943
KIN_FDR_2052 | KIN-NER-2052 | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160944
KIN_FDR_2062 | Affected equipment KIN_CB_2042 & KIN_FDR_2052 | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160945
ISL_C_21 | Affected Equipment of ISL_220BS_D ISL-DS-445 Headgear Replacement | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005081
ASB_ISL_1 | ISL-DS-445 Headgear Replacement | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005077
KIN_T9 | KIN-CBL-2072-ET9A, KIN-CBL-ET9B-NER9, KIN-CBL-T9-2072, KIN-CBL-T9-2222, KIN-CBL-T9-ET9B, KIN-CT-322, KIN-RES-NER9, KIN-TF-ET9A,KIN-TF-ET9B, KIN-TF-T9. KIN-M-VT2222 | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160951
ISL_CB_608 | Affected Equipment of ISL_220BS_D ISL-DS-445 Headgear Replacement | 2026-10-05 08:00 | 2026-10-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005079
TNG_220BS_B | TNG-DS-335 (RPO-1) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-350 | 2026-10-06 07:30 | 2026-10-06 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161686
TGA_FDR_13 | Modify & commission 11 kV CB13 relay settings for COPS trip | 2026-10-06 07:30 | 2026-10-06 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155798
BLN_CB_2108 | Affected equipment BLN_33BS_B & BLN_C_2 & BLN_C_4 | 2026-10-07 06:30 | 2026-10-08 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160297
BLN_C_4 | BLN-CAPS-C4, BLN-CB-2132, BLN-CBL-C4, BLN-REA-C4-1, BLN-REA-C4-3, BLN-VT-C4-2 | 2026-10-07 06:30 | 2026-10-08 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160295
BLN_C_2 | BLN-CAPS-C2, BLN-CB-2122, BLN-CBL-C2, BLN-REA-C2-1, BLN-REA-C2-3, BLN-VT-C2-2 | 2026-10-07 06:30 | 2026-10-08 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160293
BLN_FDR_2152 | Affected equipment BLN_33BS_B & BLN_C_2 & BLN_C_4 | 2026-10-07 06:30 | 2026-10-08 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160302
BLN_33BS_B | 1 yrs, BLN-VT-VT2147 | 2026-10-07 06:30 | 2026-10-08 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160289
BLN_FDR_2162 | Affected equipment BLN_33BS_B & BLN_C_2 & BLN_C_4 | 2026-10-07 06:30 | 2026-10-08 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160303
BLN_FDR_2172 | Affected equipment BLN_33BS_B & BLN_C_2 & BLN_C_4 | 2026-10-07 06:30 | 2026-10-08 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160304
BLN_T1 | Affected equipment BLN_33BS_B & BLN_C_2 & BLN_C_4 | 2026-10-07 06:30 | 2026-10-08 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160305
TNG_220BS_A | TNG-DS-333 (RPO-1) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-220 | 2026-10-07 07:30 | 2026-10-07 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161679
WHU_110CBF | Affected equipment | 2026-10-07 07:30 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161787
NMA_687_835 | MAN-P-CB-252, MAN-TWI-A0010-20, MAN-TWI-A0038-20, MAN-TWI-A0039-20, MAN-TWI-A0042-20, MAN-TWI-A0043-20, MAN-TWI-A0046-20, MAN-TWI-A0049-20, MAN-TWI-A0056-20, MAN-TWI-A0060-20, MAN-TWI-A0061-20, MAN-TWI-A0062-20, MAN-TWI-A0063-20, MAN-TWI-A0294-20, MAN-TWI-A0296-20, MAN-TWI-A0299-20, MAN-TWI-A0300-20, MAN-TWI-A0308-20,MAN-TWI-A0311-0312-20, MAN-TWI-A0313-0314-20, MAN-TWI-A0314-0315-20, NMA-CT-CT762 | 2026-10-07 07:30 | 2026-10-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161211
WHU_110BZ | WHU-P-BZ-110-A | 2026-10-07 07:30 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161786
TGA_FDR_14 | Modify & commission 11 kV CB14 relay settings for COPS trip | 2026-10-07 07:30 | 2026-10-07 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155801
NMA_CB_738 | Affected Equipment of NMA_687_835 MAN-P-CB-252, MAN-TWI-A0010-20, MAN-TWI-A0038-20, MAN-TWI-A0039-20, MAN-TWI-A0042-20, MAN-TWI-A0043-20, MAN-TWI-A0046-20, MAN-TWI-A0049-20, MAN-TWI-A0056-20,MAN-TWI-A0060-20, MAN-TWI-A0061-20, MAN-TWI-A0062-20, MAN-TWI-A0063-20, MAN-TWI-A0294-20, MAN-TWI-A0296-20, MAN-TWI-A0299-20, MAN-TWI-A0300-20, MAN-TWI-A0308-20, MAN-TWI-A0311-0312-20, MAN-TWI-A0313-0314-20, MAN-TWI-A0314-0315-20, NMA-CT-CT762 | 2026-10-07 07:30 | 2026-10-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161237
TRK_407_417_437 | TRK-BS-220-417-437, TRK-DS-417 | 2026-10-07 07:30 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161707
ISL_T8 | ISL-TF-T8 | 2026-10-08 06:30 | 2026-10-08 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160873
TGA_FDR_15 | Modify & commission 11 kV CB15 relay settings for COPS trip | 2026-10-08 07:30 | 2026-10-08 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155799
OTA_220BZ_K_PROT2 | OTA-P-BZ-2-220-K | 2026-10-08 07:30 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161312
OTA_220CBF_K_PROT2 | Affected equipment. OTA-P-BZ-2-220-K | 2026-10-08 07:30 | 2026-10-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161314
TGA_FDR_16 | Modify & commission 11 kV CB16 relay settings for COPS trip | 2026-10-09 07:30 | 2026-10-09 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155800
BPE_TKU_2 | Tower painting x21 (B53-B54, B55A, B56-B73) [CP_718_004_0_00]. Completion of outstanding 25-26 BPE-WKM-B TTU works [CP_VAR_1DE_0_00]. Affected equipment of TKU_64_67_107. | 2026-10-12 06:30 | 2026-10-23 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160344
ISL_CB_648 | ISL-CB-648 Corroding SF6 pipework - P3 | 2026-10-12 06:30 | 2026-10-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005083
TKR_WIL_2 | Attachment point replacements. | 2026-10-12 07:00 | 2026-10-16 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW2006230
GFD_T5 | GFD-CBL-2242-LS5, GFD-CBL-T5-2242, GFD-CBL-T5-NER5, GFD-CBL-TS-T5, GFD-RES-NER5, GFD-TF-LS-LS5, GFD-TF-T5, GFD-VT-72 | 2026-10-12 07:00 | 2026-10-16 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1161903
WHI_WRK_1 | WRK-CB-172, WRK-CT-172. WHI-DS-516 headgear refurbishment [CP_RA4_03K_0_00]. Tower works x14 (A12, A63-A64, A68, A100-A101, A104-A105, A122, A155-A156, A158-A160). RSA4 re-insulation x1. | 2026-10-12 07:00 | 2026-10-16 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161784
WHI_T1 | Affected equipment of WHI_514_524_537 | 2026-10-12 07:00 | 2026-10-14 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161783
GFD_HAY_2 | Maintenance | 2026-10-12 07:00 | 2026-10-16 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1161902
PEN_CB_828 | PEN-CB-828 | 2026-10-12 07:00 | 2026-10-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161396
PEN_CB_812 | Affected equipment PEN_220BS_C & PEN_CB_798 & PEN_CB_828 & PEN_T11 | 2026-10-12 07:00 | 2026-10-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161395
WHI_514_524_537 | WHI-DS-514 headgear refurbishment [CP_RA4_03K_0_00]. | 2026-10-12 07:00 | 2026-10-14 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161774
PEN_CB_798 | PEN-CT-798, PEN-P-CB-798 | 2026-10-12 07:00 | 2026-10-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161393
PEN_CB_2332B | Place T8 into service for the duration of PEN_T11 | 2026-10-12 07:00 | 2026-10-14 18:30 | Continuous | NNI | CLO - Close | Approved | OW1161384
PEN_T11 | PEN-TF-ET11 | 2026-10-12 07:00 | 2026-10-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161431
PEN_CB_2332A | Place T8 into service for the duration of PEN_T11 | 2026-10-12 07:00 | 2026-10-14 18:30 | Continuous | NNI | CLO - Close | Approved | OW1161382
PEN_220BS_C | PEN-DS-804, PEN-DS-807, PEN-DS-814, PEN-DS-827, PEN-ES-810, PEN-ES-820 | 2026-10-12 07:00 | 2026-10-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161372
TNG_220BS_B | TNG-DS-285 (BC) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-230 | 2026-10-12 07:30 | 2026-10-13 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161685
TNG_CB_288 | BPE-TNG prot upgrade Stage 5: Installation of CT-288 at Bay 280[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-10-12 07:30 | 2026-10-16 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1162035
CYD_ROX_1 | ROX-CVT-VT69, ROX-DS-556, ROX-DS-564, ROX-ES-559 | 2026-10-12 07:30 | 2026-10-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160434
HAY_F_3 | 8 yrs, S4.WA-Z2.Q1, S4.WA-Z2.Z1.Q1, S4.WA-Z2.Z1.R1A, S4.WA-Z2.Z1.R1B, S4.WA-Z2.Z1.R1C, S4.WA-Z2.Z2.Q1, S4.WA-Z2.Z2.R1A, S4.WA-Z2.Z2.R1B, S4.WA-Z2.Z2.R1C, HVDC HAY-DC Pole 2 Era AC Disconnector/Earth Switch Refurbishments | 2026-10-12 07:30 | 2026-10-23 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160610
INV_TWI_2 | Tower Painting | 2026-10-12 07:30 | 2026-10-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1157290
KIK_STK_1 | Stage 2 - STK_KIK_1 Secondary Cabling Modifications excluding STK T7 Intetrip connections | 2026-10-12 07:30 | 2026-10-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1162754
TGA_FDR_17 | Modify & commission 11 kV CB17 relay settings for COPS trip | 2026-10-12 07:30 | 2026-10-12 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155803
ROX_220BS_B | ROX-DS-553, ROX-DS-555 | 2026-10-12 07:30 | 2026-10-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161510
ROX_564_555_553_556 | ROX-DS-553, ROX-DS-555 | 2026-10-12 07:30 | 2026-10-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161512
ROX_CB_698 | Affected Equipment of ROX_220BS_B ROX-DS-553, ROX-DS-555 | 2026-10-12 07:30 | 2026-10-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161516
TNG_T11 | BPE-TNG prot upgrade Stage 5: Installation of CT-288 at Bay 280[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-10-12 07:30 | 2026-10-16 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW2005567
ROX_CB_708 | Affected Equipment of ROX_220BS_B ROX-DS-553, ROX-DS-555 | 2026-10-12 07:30 | 2026-10-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161517
MPE_CB_292 | System split for HEN_HPI_1 | 2026-10-12 08:00 | 2026-10-12 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161139
BEN_220BZ | BEN 220BZ - Filter 3 Migration BEN 220BZ - CB428 Migration CP_BEN_AZ_00_00 | 2026-10-12 08:00 | 2026-10-12 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160235
NPK_T1 | Affected Equipment of OKN_NPK_ONG_1 ONG SPS Changeover Project | 2026-10-12 08:00 | 2026-10-19 15:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2005770
OTA_ROS_2 | Tower Painting | 2026-10-12 08:00 | 2026-10-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142928
NMA_GOR_TMH_2 | pdm maint includes Lines | 2026-10-12 08:00 | 2026-10-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161247
BEN_F_3 | BEN 220BZ - Filter 3 Migration | 2026-10-12 08:00 | 2026-10-22 18:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160269
NMA_CB_738 | Affected Equipment of NMA_220BS_A4 pdm maint. | 2026-10-12 08:00 | 2026-10-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161238
BEN_CB_408 | BEN 220BZ - CB408 Migration CP_BEN_AZ_00_00 | 2026-10-12 08:00 | 2026-10-21 18:00 | Continuous | SI | RS - Removal from Service | Approved | OW2005410
NMA_CB_718 | Affected Equipment of NMA_220BS_A4 pdm maint. | 2026-10-12 08:00 | 2026-10-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161228
BEN_220CBF | BEN 220BZ - CB408 Migration | 2026-10-12 08:00 | 2026-10-12 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160252
MPE_CB_252 | System split for HEN_HPI_1 | 2026-10-12 08:00 | 2026-10-12 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161104
OKN_NPK_ONG_1 | ONG SPS Changeover Project | 2026-10-12 08:00 | 2026-10-19 15:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2005769
HEN_HPI_1 | Tower Painting | 2026-10-12 08:00 | 2026-10-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1143184
BRB_HPI_1 | Affected Equipment Tower Painting | 2026-10-12 08:00 | 2026-10-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1143185
NMA_220BS_A4 | pdm maint. | 2026-10-12 08:00 | 2026-10-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161206
DRY_GLN_2 | Tower Painting | 2026-10-12 08:00 | 2026-10-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142836
DRY_BOB_HLY_2 | Tower Painting. HLY DS 463 headgear refurbishment | 2026-10-12 08:00 | 2026-10-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142874
GOR_T12 | Affected Equipment of NMA_GOR_TMH_2 pdm maint | 2026-10-12 08:00 | 2026-10-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160532
BOB_T5 | Affected Equipment DRY_BOB_HLY_2 | 2026-10-12 08:00 | 2026-10-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142875
MPE_CB_292 | System split for HEN_HPI_1 | 2026-10-13 06:00 | 2026-10-15 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161140
MPE_CB_252 | System split for HEN_HPI_1 | 2026-10-13 06:00 | 2026-10-15 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161105
HAY_CB_58 | Affected equipment of HAY_27_VT47, for HAY_110BZ Stage 1B; VT47JB replacement [CP_HAY_IN_00_00] | 2026-10-13 06:30 | 2026-10-14 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1162199
HAY_27_VT47 | HAY_110BZ Stage 1B; VT47 JB replacement [CP_HAY_IN_00_00] | 2026-10-13 06:30 | 2026-10-14 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1162198
HAM_T2 | Revenue metering HAM-M-CT2872 | 2026-10-13 07:30 | 2026-10-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160570
TGA_FDR_18 | Modify & commission 11 kV CB18 relay settings for COPS trip | 2026-10-13 07:30 | 2026-10-13 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155804
HTI_CB_2188 | HTI-CBL-2188-2217 | 2026-10-13 07:30 | 2026-10-15 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160729
TKU_64_67_107 | TKU-DS-64 (BPE_2) | 2026-10-13 07:30 | 2026-10-13 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161637
TKU_WKM_2 | Affected equipment of TKU_64_67_107. | 2026-10-13 07:30 | 2026-10-13 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161644
ROX_CB_708 | Affected Equipment of ROX_220BS_C ROX-DS-553, ROX-DS-555 | 2026-10-14 07:30 | 2026-10-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161518
MAN_220BZ | MAN-P-BZ-220 | 2026-10-14 07:30 | 2026-10-14 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161019
TNG_220BS_A | BPE-TNG prot upgrade Stage 5: Installation of CT-288 at Bay 280[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. TNG-DS-283 (BC) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-220 | 2026-10-14 07:30 | 2026-10-16 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161678
HAM_KPO_2 | CBG-DS-206, CBG-ES-209, CBG-ES-239, HAM-ES-139, HAM-KPO-A2-Z-CBL-SHEATH, HAM-P-CB-132 | 2026-10-14 07:30 | 2026-10-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160564
KPO_TMU_1 | KPO-TMU-A0019-00, KPO-TMU-A0070-00, TMU-VT-92 | 2026-10-14 07:30 | 2026-10-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006080
KPO_CB_198 | Affected equipment | 2026-10-14 07:30 | 2026-10-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160980
KPO_BUS_A1 | KPO-DCB-198, KPO-VT-VT187 | 2026-10-14 07:30 | 2026-10-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160979
TGA_FDR_19 | Modify & commission 11 kV CB19 relay settings for COPS trip | 2026-10-14 07:30 | 2026-10-14 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155805
NMA_220BS_A3 | pdm maint. | 2026-10-14 07:30 | 2026-10-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161201
NMA_CB_718 | Affected Equipment of NMA_220BS_A3 pdm maint. | 2026-10-14 07:30 | 2026-10-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161229
CBG_T3 | Affected equipment CBG_206_224_236 & HAM_KPO_2 | 2026-10-14 07:30 | 2026-10-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160379
ROX_220BS_C | ROX-DS-553, ROX-DS-555 | 2026-10-14 07:30 | 2026-10-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161511
ROX_CB_658 | Affected Equipment of ROX_220BS_C ROX-DS-553, ROX-DS-555 | 2026-10-14 07:30 | 2026-10-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161515
NMA_CB_708 | Affected Equipment of NMA_220BS_A3 pdm maint. | 2026-10-14 07:30 | 2026-10-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161221
CBG_206_224_236 | CBG-DS-224, CBG-DS-236 | 2026-10-14 07:30 | 2026-10-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160378
BEN_RTU_MULTI | BEN 220BZ - CB408 Migration CP_BEN_AZ_00_00 | 2026-10-14 08:00 | 2026-10-14 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005413
HAY_37_VT57 | HAY_110BZ Stage 1C; VT57 JB replacement | 2026-10-15 06:30 | 2026-10-16 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1162000
TGA_FDR_20 | Modify & commission 11 kV CB20 relay settings for COPS trip | 2026-10-15 07:30 | 2026-10-15 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155806
PEN_FDR_2252 | PEN-CB-2252, PEN-P-CB-2252 | 2026-10-15 07:30 | 2026-10-15 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161408
TNG_220CBF | Affected equipment of TNG_220BZ, for BPE-TNG prot upgrade Stage5 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-10-15 08:00 | 2026-10-15 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005575
TNG_220BZ | BPE-TNG prot upgrade Stage 5: Installation of CT-288 at Bay 280[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-10-15 08:00 | 2026-10-15 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005568
ONG_RTU_1 | ONG SPS Changeover Project | 2026-10-15 10:00 | 2026-10-15 14:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005771
MPE_CB_292 | System split for HEN_HPI_1 | 2026-10-16 06:00 | 2026-10-16 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161141
MPE_CB_252 | System split for HEN_HPI_1 | 2026-10-16 06:00 | 2026-10-16 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161106
HAY_CB_2622 | HAY-CBL-CB2622-ST10 | 2026-10-16 07:30 | 2026-10-16 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160606
PEN_FDR_2502 | PEN-CB-2502, PEN-P-CB-2502 | 2026-10-16 07:30 | 2026-10-16 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161419
TGA_FDR_21 | Modify & commission 11 kV CB21 relay settings for COPS trip | 2026-10-16 07:30 | 2026-10-16 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155807
BPE_TNG_1 | BPE-TNG prot upgrade Stage 5: Installation of CT-288 at Bay 280[CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-10-16 11:30 | 2026-10-16 17:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005569
KIK_CB_37 | KIK-P-TF-RT1, KIK-TF-RT1 | 2026-10-18 06:30 | 2026-10-18 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160923
ISL_FDR_92 | Affected equipment ISL-DS-95. CY4 Re-planned. | 2026-10-19 06:30 | 2026-10-19 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1159816
ISL_CB_728 | Affected Equipment ISL-DS-95, ISL-DS-145. CY4 Re-planned. | 2026-10-19 06:30 | 2026-10-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159812
ISL_CB_708 | Affected Equipment ISL-DS-95, ISL-DS-145. CY4 Re-planned. | 2026-10-19 06:30 | 2026-10-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159811
ISL_66BS_D | ISL-DS-95, ISL-DS-145. CY4 Re-planned. | 2026-10-19 06:30 | 2026-10-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159810
HAY_WIL_LTN_2 | Strain attachment point replacements | 2026-10-19 07:00 | 2026-10-23 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2006228
HAY_CB_982A | S4.10DC98.A-C1A, S4.10DC98.A-C1B, S4.10DC98.A-C1C, S4.10DC98.A-C2A, S4.10DC98.A-C2B, S4.10DC98.A-C2C, S4.10DC98.A-C3A, S4.10DC98.A-C3B, S4.10DC98.A-C3C, S4.10DC98.A-L1A, S4.10DC98.A-L1B, S4.10DC98.A-L1C, S4.10DC98.A-L2A, S4.10DC98.A-L2B, S4.10DC98.A-L2C, S4.10DC98.A-L3A, S4.10DC98.A-L3B, S4.10DC98.A-L3C, S4.10DC98.A-Q0, S4.10DC98.A-R2A, S4.10DC98.A-R2B, S4.10DC98.A-R2C, S4.10DC98.A-R3A, S4.10DC98.A-R3B, S4.10DC98.A-R3C | 2026-10-19 07:30 | 2026-10-23 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160609
PEN_110BS_A | PEN-DS-44, PEN-DS-54, PEN-DS-64, PEN-DS-94, PEN-DS-97, PEN-VT-47 | 2026-10-19 07:30 | 2026-10-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161367
TWH_33BS_A | Protection replacement project. TWH-P-BZ-33-A | 2026-10-19 07:30 | 2026-10-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161715
MAN_NMA_2 | MAN-TWI-A0038-20 MAN-TWI-A0039-20 MAN-TWI-A0042-20 MAN-TWI-A0043-20 MAN-TWI-A0046-20 MAN-TWI-A0049-20 MAN-TWI-A0056-20 MAN-TWI-A0060-20 MAN-TWI-A0061-20 MAN-TWI-A0062-20 MAN-TWI-A0063-20 MAN-TWI-A0294-20 MAN-TWI-A0296-20 MAN-TWI-A0299-20 MAN-TWI-A0300-20 MAN-TWI-A0308-20 | 2026-10-19 07:30 | 2026-10-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161025
BOB_T5 | Affected Equipment of DRY_BOB_HLY_2 Lines maintenance | 2026-10-19 07:30 | 2026-10-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160313
PEN_C_11 | PEN-CB-52 | 2026-10-19 07:30 | 2026-10-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161376
WHI_567_634_644 | WHI-DS-584 headgear refurbishment [CP_RA4_03K_0_00]. | 2026-10-19 07:30 | 2026-10-21 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161775
TWH_CB_2808 | TWH-P-CB-2808 | 2026-10-19 07:30 | 2026-10-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161718
TWH_FDR_2722 | TWH-P-CB-2722 | 2026-10-19 07:30 | 2026-10-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161721
PEN_C_13 | Affected equipment PEN_110BS_A & PEN_C_11 & PEN_FDR_62 | 2026-10-19 07:30 | 2026-10-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161378
HAY_F_5 | S4.10DC98-FB5, S4.10DC98.B-Q0 | 2026-10-19 07:30 | 2026-10-23 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160612
PEN_CB_118 | Affected equipment PEN_110BS_A & PEN_C_11 & PEN_FDR_62 | 2026-10-19 07:30 | 2026-10-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161379
TWH_FDR_2742 | TWH-P-CB-2742 | 2026-10-19 07:30 | 2026-10-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161722
TWH_FDR_2762 | TWH-P-CB-2762 | 2026-10-19 07:30 | 2026-10-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161723
TWH_FDR_2782 | TWH-P-CB-2782 | 2026-10-19 07:30 | 2026-10-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161724
PEN_T6 | Affected equipment PEN_110BS_A & PEN_C_11 & PEN_FDR_62 | 2026-10-19 07:30 | 2026-10-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161433
CPK_T4 | Affected equipment of CPK_WWD_WIL_2 | 2026-10-19 07:30 | 2026-10-23 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160404
TWH_T1 | TWH-P-TF-T1, TWH-TF-T1 | 2026-10-19 07:30 | 2026-10-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161729
KIK_STK_2 | Stage 3 - STK_KIK_1 Secondary Cabling Modifications excluding STK T7 Intetrip connections | 2026-10-19 07:30 | 2026-10-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005487
EDG_T4 | EDG-CB-412, EDG-CBL-ET4-NER4, EDG-CBL-T4-2162, EDG-CBL-TS-ET4, EDG-CT-412, EDG-NCT-4, EDG-RES-NER4, EDG-TF-ET4, EDG-TF-T4 | 2026-10-19 07:30 | 2026-10-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160479
DRY_BOB_HLY_2 | Lines maintenance | 2026-10-19 07:30 | 2026-10-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160446
ISL_CB_768 | ISL-P-CB-768 | 2026-10-19 07:30 | 2026-10-20 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160842
CPK_WWD_WIL_2 | WWD-CB-242, WWD-CT-242, WWD-CVT-242, WWD-DS-246, WWD-ES-249. WWD-TEE-A0108-0109-00, WWD-TEE-A0109-0110-00, WWD-TEE-A0111-WWDG2-10 | 2026-10-19 07:30 | 2026-10-23 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160408
PEN_FDR_62 | PEN-CT-62, PEN-DS-66, PEN-ES-69, PEN-P-CB-62 | 2026-10-19 07:30 | 2026-10-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161422
RDF_WHI_1 | Affected equipment of WHI_567_634_644, for DS headgear refurbishment | 2026-10-19 07:30 | 2026-10-21 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161473
TGA_FDR_2162 | Modify & commission 33 kV CB2162 protection wiring and relay settings for COPS trip | 2026-10-19 07:30 | 2026-10-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1155808
HEN_WEL_2 | Attachment point, re-insulation and steel and bolts | 2026-10-19 08:00 | 2026-10-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005178
HEN_WEL_1 | Attachment point, re-insulation and steel and bolts | 2026-10-19 08:00 | 2026-10-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005177
HAY_247_295 | HAY_110BZ Stage 1D; VT267 JB replacement | 2026-10-20 06:30 | 2026-10-21 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161998
ISL_FDR_142 | ISL-CB-142, ISL-CT-CT142, ISL-DS-146, ISL-DS-143, ISL-DS-145. CY4 Re-planned. | 2026-10-20 06:30 | 2026-10-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159817
ROX_624_615_613_616 | ROX-DS-616 | 2026-10-20 07:30 | 2026-10-22 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161513
ROX_TMH_1 | ROX-TMH-A0078-0079-10 | 2026-10-20 07:30 | 2026-10-22 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161520
HIN_T2 | Affected Equipment of HIN_KPO_1 replace RC tagged pole HIN-KPO-A0091 | 2026-10-20 07:30 | 2026-10-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005682
HEP_FDR_2202 | HEP-CB-2202, HEP-P-CB-2202 | 2026-10-20 07:30 | 2026-10-20 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160678
HIN_44_64_124 | Affected Equipment of HIN_KPO_1 replace RC tagged pole HIN-KPO-A0091 | 2026-10-20 07:30 | 2026-10-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005680
TIM_CB_2752 | Affected equipment TIM_T6 | 2026-10-20 07:30 | 2026-10-22 18:30 | Continuous | SI | CLO - Close | Approved | OW1161612
TIM_T6 | TIM-CBL-T6-CB2932, TIM-CBL-T6-LS6, TIM-CBL-T6-NER6, TIM-RES-NER6, TIM-TF-LS6, TIM-TF-T6, TIM-VT-VT2932 | 2026-10-20 07:30 | 2026-10-22 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161618
WEL_1044_1054_1067 | WEL DS1047 and DS1067 insulator replacements & repairs | 2026-10-20 07:30 | 2026-10-20 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163754
WEL_T1 | Affected Equipment WEL DS1047 and DS1067 insulator replacements& repairs | 2026-10-20 07:30 | 2026-10-20 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163755
WEL_1047_1064_1097 | WEL DS1047 and DS1067 insulator replacements and repairs | 2026-10-20 07:30 | 2026-10-20 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163756
WEL_LST_1 | Affected Equipment WEL DS1047 and DS1067 insulator replacementsand repairs | 2026-10-20 07:30 | 2026-10-20 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163757
HIN_T1 | Affected Equipment of HIN_KPO_1 replace RC tagged pole HIN-KPO-A0091 | 2026-10-20 07:30 | 2026-10-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005681
HIN_KPO_1 | replace RC tagged pole HIN-KPO-A0091 | 2026-10-20 07:30 | 2026-10-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005679
BEN_220BZ | BEN 220BZ - CB408 Migration | 2026-10-20 08:00 | 2026-10-21 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160236
BEN_220CBF | BEN 220BZ - CB408 Migration | 2026-10-20 08:00 | 2026-10-21 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160253
BEN_220BS_A | BEN 220BZ - CB408 Migration CP_BEN_AZ_00_00 | 2026-10-20 08:00 | 2026-10-20 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005412
TNG_RTU_1 | BPE-TNG prot upgrade Stage 0: Pre-outage installation works andsite establishment [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-10-20 08:00 | 2026-10-20 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005762
ISL_CB_768 | Affected Equipment ISL-DS-143. CY4 Re-planned. | 2026-10-21 06:30 | 2026-10-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159815
ISL_CB_708 | Affected Equipment ISL-DS-143. CY4 Re-planned. | 2026-10-21 06:30 | 2026-10-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159814
ISL_66BS_A | ISL-DS-143. CY4 Re-planned. | 2026-10-21 06:30 | 2026-10-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159813
HAM_STC_3 | HAM-BU-STC3, HAM-COOL-STC3, HAM-STC-3 | 2026-10-21 07:30 | 2026-10-23 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160567
TGA_FDR_2422 | • Modify & commission 33 kV CB2422 protection wiring and relay settings for COPS trip | 2026-10-21 07:30 | 2026-10-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1155810
WEL_1047_1064_1097 | WEL DS1077 and DS1097 insulator replacements and repairs | 2026-10-21 07:30 | 2026-10-21 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163758
WEL_LST_1 | Affected Equipment WEL DS1077 and DS1097 insulator replacementsand repairs | 2026-10-21 07:30 | 2026-10-21 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163759
WEL_1077_1084_1094 | WEL DS1077 and DS1087 insulator replacements and repairs | 2026-10-21 07:30 | 2026-10-21 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163760
WEL_T2 | Affected Equipment WEL DS1077 and DS1087 insulator replacementsand repairs | 2026-10-21 07:30 | 2026-10-21 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163761
BPE_RTU_1 | BPE-TNG prot upgrade Stage 0: Pre-outage installation works andsite establishment [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-10-21 08:00 | 2026-10-21 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005556
HAY_37_VT297 | HAY_110BZ Stage 1E; VT297 JB replacement | 2026-10-22 06:30 | 2026-10-23 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161999
HAY_CB_258 | Affected equipment of HAY_37_VT297 HAY_110BZ Stage 1E; VT297 JBreplacement | 2026-10-22 06:30 | 2026-10-23 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1162001
SVL_FDR_2882 | SVL-CBL-2882 | 2026-10-22 07:30 | 2026-10-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161585
KMO_RTU_1 | 110KV line protection upgrade | 2026-10-23 07:00 | 2026-10-23 10:00 | Daily | NNI | RS - Removal from Service | Approved | OW1155756
PTS_2027_ARI_HTI | ARI-C-PTSG-2027, HTI-C-PTSG-2027 | 2026-10-23 07:30 | 2026-10-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161461
TGA_RTU_2 | 110KV line protection upgrade | 2026-10-23 10:30 | 2026-10-23 13:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155762
TGA_RTU_1 | 110KV line protection upgrade | 2026-10-23 10:30 | 2026-10-23 13:30 | Daily | NNI | RS - Removal from Service | Approved | OW1155761
MTM_RTU_1 | 110KV line protection upgrade | 2026-10-23 14:00 | 2026-10-23 17:00 | Daily | NNI | RS - Removal from Service | Approved | OW1155760
GFD_T6 | Reinhausen work. Affected equipment of GFD_HAY_1, for HAY_110BZStage 3F; Bay 260 - Gracefield cct 1. No other HAY work on days2, 3, 6. | 2026-10-26 07:00 | 2026-10-30 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1161905
GFD_HAY_1 | Maintenance. HAY_110BZ Stage 1F; Integrate/commission referenceCT to CT_262 | 2026-10-26 07:00 | 2026-10-30 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1161900
ISL_CB_628 | Affected Equipment of ISL_220BS_C ISL-DS-443 Headgear Replacement-ISL-CB-628 Corroding SF6 pipework - P3, Affected equipment ISL-DS-443 Headgear Replacement | 2026-10-27 06:30 | 2026-10-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005090
TKR_WIL_1 | Attachment point replacements. | 2026-10-27 07:00 | 2026-10-30 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW2006229
ASB_ISL_1 | ISL-DS-443 Headgear Replacement | 2026-10-27 07:30 | 2026-10-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005086
ISL_CB_608 | Affected Equipment of ISL_220BS_C ISL-DS-443 Headgear Replacement | 2026-10-27 07:30 | 2026-10-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005089
ISL_220BS_C | ISL-DS-443 Headgear Replacement | 2026-10-27 07:30 | 2026-10-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005088
NMA_GOR_TMH_2 | includes Lines | 2026-10-27 07:30 | 2026-10-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161248
OWH_97_104_114 | OWH-BS-110-107-114, OWH-DS-104, OWH-DS-107, OWH-DS-114, OWH-VT-VT107 | 2026-10-27 07:30 | 2026-10-31 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161358
OWH_T2 | OWH-TF-T2 | 2026-10-27 07:30 | 2026-10-31 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161360
OWH_TMI_TRK_1 | ARI-EDG-B0268-00, ARI-EDG-B0279-00, ARI-EDG-B0302-00, TRK-CT-142, TRK-DS-146, TRK-ES-149, TRK-P-CB-142 | 2026-10-27 07:30 | 2026-10-31 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161361
HTI_TMU_1 | Affected equipment HTI_97_87_VT57 | 2026-10-27 07:30 | 2026-10-28 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160733
HTI_DIS_54 | Affected equipment HTI_97_87_VT57 | 2026-10-27 07:30 | 2026-10-28 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160730
HTI_97_87_VT57 | HTI-M-VT57, HTI-M-CT52 | 2026-10-27 07:30 | 2026-10-28 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160728
MLG_T2 | SS pipework replacement. 12-hour soak on last day. | 2026-10-27 07:30 | 2026-11-06 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161069
BEN_CB_428 | BEN 220BZ - CB428 Migration CP_BEN_AZ_00_00 | 2026-10-27 07:30 | 2026-11-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005419
GOR_T12 | Affected Equipment of NMA_GOR_TMH_2 includes Lines | 2026-10-27 07:30 | 2026-10-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160533
BEN_220BZ | BEN 220BZ - CB428 Migration CP_BEN_AZ_00_00 | 2026-10-27 08:00 | 2026-10-27 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2006295
BEN_220CBF | BEN 220BZ - CB428 Migration CP_BEN_AZ_00_00 | 2026-10-27 08:00 | 2026-10-27 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2006296
OTA_PEN_6 | Tower Painting | 2026-10-27 08:00 | 2026-10-31 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142931
PEN_CB_8612 | Place PEN REA into service for the duration of OTA_PEN_6 | 2026-10-27 08:00 | 2026-10-31 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1143516
PEN_T10 | Open for duration of OTA_PEN_6 | 2026-10-27 08:00 | 2026-10-28 07:59 | Continuous | NNI | OPE - Open Ended | Approved | OW1143517
HEN_287_297_334 | HEN-DS-294, HEN-DS-297, HEN-DS-304, HEN-DS-314, HEN-DS-324, HEN-VT-2 | 2026-10-28 07:30 | 2026-10-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160645
RPO_WRK_1 | RPO-CBL-526-539. Affected equipment of WRK_97_127_164. | 2026-10-28 07:30 | 2026-10-30 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161524
HEN_CB_288 | Affected equipment HEN_287_297_334 | 2026-10-28 07:30 | 2026-10-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160649
HEN_HEP_3 | Affected equipment HEN_287_297_334 | 2026-10-28 07:30 | 2026-10-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160657
HEN_HEP_4 | Affected equipment HEN_287_297_334 | 2026-10-28 07:30 | 2026-10-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160658
HEN_T5 | Affected equipment HEN_287_297_334 | 2026-10-28 07:30 | 2026-10-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160669
HEN_WEL_1 | Affected equipment HEN_287_297_334 | 2026-10-28 07:30 | 2026-10-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160671
HEN_WEL_2 | Affected equipment HEN_287_297_334 | 2026-10-28 07:30 | 2026-10-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160672
ABY_TKA_1 | TKA-TIM-A0191-00 | 2026-10-28 07:30 | 2026-10-29 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160120
WHI_WRK_1 | Additional outage for tower works x14 (A12, A63-A64, A68, A100-A101, A104-A105, A122, A155-A156, A158-A160). RSA4 re-insulation x1. WHI-DS-516, WRK-CB-172, WRK-CT-172. | 2026-10-28 07:30 | 2026-10-30 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161785
ABY_TIM_1 | ABY-CB-72, TIM-P-CB-132, TKA-TIM-A0314-00, TKA-TIM-A0320-00, TKA-TIM-A0386-00, TKA-TIM-A0399-00, TKA-TIM-A0410-00, TKA-TIM-A0450-00, TKA-TIM-A0454-00, TKA-TIM-A0463-10 | 2026-10-28 07:30 | 2026-10-29 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160117
ABY_FDR_2742 | ABY-CB-2742, ABY-P-CB-2742, ABY-VT-VT2742 | 2026-10-28 07:30 | 2026-10-29 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160115
ABY_FDR_2732 | ABY-CB-2732, ABY-P-CB-2732, ABY-VT-VT2732 | 2026-10-28 07:30 | 2026-10-29 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160114
ABY_FDR_2722 | Affected Equipment of ABY_11BS Affected equipment ABY_T2 | 2026-10-28 07:30 | 2026-10-29 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160113
ABY_11BS | Affected equipment ABY_T2 | 2026-10-28 07:30 | 2026-10-29 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160112
ABY_T2 | Affected equipment - LOS ABY_T2 | 2026-10-28 07:30 | 2026-10-29 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1162593
TAB_WRK_1 | WRK-CB-162, WRK-CT-162, WRK-DS-166, WRK-ES-169. Tower work x1 (A20). Affected equipment of WRK_97_127_164. | 2026-10-28 07:30 | 2026-10-29 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161591
WRK_97_127_164 | WRK-DS-107 (bus), WRK-DS-164 (TAB-1). | 2026-10-28 07:30 | 2026-10-29 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161850
BEN_RTU_MULTI | BEN 220BZ - CB428 Migration CP_BEN_AZ_00_00 | 2026-10-29 08:00 | 2026-10-29 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2006294
PEN_T10 | Open for duration of OTA_PEN_6 | 2026-10-30 18:30 | 2026-10-31 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1163429
WKM_WRK_1 | WRK-DS-114 (WKM_1). Affected equipment of WRK_47_57_197 | 2026-10-31 07:30 | 2026-11-01 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161812
WRK_44_57_197 | WRK-DS-47 (bus). Aligned with WKM_WRK_1. | 2026-10-31 07:30 | 2026-10-31 12:59 | Daily | SNI | RS - Removal from Service | Approved | OW1161846
WRK_CB_112 | WRK-CB-112 (WKM_1) pole replacement [CP_WRK_00U_0_00]. Affectedequipment of WKM_WRK_1. | 2026-10-31 07:30 | 2026-11-01 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161853
WRK_CB_198 | Affected equipment of WRK_44_57_197, for WRK-DS-47 (bus) | 2026-10-31 07:30 | 2026-10-31 12:59 | Daily | SNI | RS - Removal from Service | Approved | OW1161855
WRK_T30 | WRK-TF-T30R. Affected equipment of WRK_44_57_197 | 2026-10-31 07:30 | 2026-10-31 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161864
WRK_47_67 | WRK-DS-57 (bus). Aligned with WKM_WRK_1. | 2026-10-31 13:00 | 2026-10-31 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005203
WRK_47_57 | WRK-DS-114 (WKM_1). Aligned with WKM_WRK_1. | 2026-11-01 07:30 | 2026-11-01 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2006219
ISL_SVC_3 | ISL-CAPS-C1, ISL-CAPS-C3, ISL-CWU-SVC3, ISL-SVC-3 | 2026-11-02 06:30 | 2026-11-06 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160865
ISL_T3 | ISL-CB-162, ISL-TF-T3B, ISL-TF-T3R | 2026-11-02 06:30 | 2026-11-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160870
CLH_COL_1 | COL-OTI-A0031-00, COL-OTI-A0045-00 | 2026-11-02 06:30 | 2026-11-07 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161893
COL_OTI_2 | COL-OTI-A0031-00, COL-OTI-A0045-00 | 2026-11-02 06:30 | 2026-11-07 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161894
TWH_CB_2808 | TWH-P-CB-2808 | 2026-11-02 07:00 | 2026-11-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161719
CPK_T5 | Reinhausen work. Affected equipment of CPK_WIL_1, for line works | 2026-11-02 07:00 | 2026-11-06 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160406
TWH_33BS_B | Transformer, feeder and BZ protection replacement. TWH-P-BZ-33-B | 2026-11-02 07:00 | 2026-11-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161716
CPK_WIL_1 | CPK-WIL-A0001-00, CPK-WIL-A0001-0002-10, CPK-WIL-A0002-0003-10,CPK-WIL-A0004-0005-00, CPK-WIL-A0004-0005-10, CPK-WIL-A0007-00,CPK-WIL-A0007-0008-00, CPK-WIL-A0007-0008-10, CPK-WIL-A0008-0009-10, CPK-WIL-A0009-00, CPK-WIL-A0009-0010-10, CPK-WIL-A0014-0015-00, CPK-WIL-A0014-0015-10, CPK-WIL-B0027-0028-00, CPK-WIL-B0028-0029-00 | 2026-11-02 07:00 | 2026-11-06 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160407
KWA_WIL_2 | KWA-CBL-62-WIL2, KWA-ES-69, WIL-CT-CT222, WIL-P-CB-222 | 2026-11-02 07:00 | 2026-11-06 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161009
KWA_T3 | KWA-P-TF-T3. Affected equipment of KWA_WIL_2. | 2026-11-02 07:00 | 2026-11-06 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161006
TWH_FDR_2822 | TWH-P-CB-2822 | 2026-11-02 07:00 | 2026-11-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161725
KWA_CB_14 | Affected equipment KWA_T3 & KWA_WIL_2 | 2026-11-02 07:00 | 2026-11-06 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161001
TWH_FDR_2842 | TWH-P-CB-2842 | 2026-11-02 07:00 | 2026-11-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161726
TWH_FDR_2862 | TWH-P-CB-2862 | 2026-11-02 07:00 | 2026-11-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161727
TWH_FDR_2882 | TWH-DS-2884 | 2026-11-02 07:00 | 2026-11-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161728
TWH_T2 | Protection replacement TWH-P-TF-T2, TWH-TF-T2 | 2026-11-02 07:00 | 2026-11-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161730
WIL_178_VT217 | WIL-DCB-188, WIL-DCB-192, WIL-DCB-202, WIL-DCB-222, WIL-VT-VT217 | 2026-11-02 07:00 | 2026-11-06 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161797
WIL_T8 | Reinhausen work. WIL CB, CBL, CT, NCT, NER and TF mtce. Affected equipment of WIL_178_VT217. | 2026-11-02 07:00 | 2026-11-07 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161803
EDG_KAW_1 | Affected Equipment EDG-CB-252 SF6 pole replacement | 2026-11-02 07:30 | 2026-11-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1157723
EDG_227_254_274 | EDG-CB-252 SF6 pole replacement | 2026-11-02 07:30 | 2026-11-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1157722
HEP_FDR_2262 | HEP-CB-2262, HEP-P-CB-2262 | 2026-11-02 07:30 | 2026-11-02 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160682
PEN_FDR_2452 | PEN-CB-2452, PEN-P-CB-2452 | 2026-11-02 07:30 | 2026-11-03 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161418
HAY_F_6 | S4.10DC96-FB6, S4.10DC96.A-L1A, S4.10DC96.A-L1B, S4.10DC96.A-L1C, S4.10DC96.A-L2A, S4.10DC96.A-L2B, S4.10DC96.A-L2C, S4.10DC96.A-Q0, S4.10DC96.A-Q1, S4.10DC96.A-Q8 | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160613
HAY_CB_962 | S4.10DC96-Q0 | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160608
OTA_110CBF | OTA-P-BS-110 | 2026-11-02 07:30 | 2026-11-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161306
OTA_110BZ | OTA-P-BZ-110 | 2026-11-02 07:30 | 2026-11-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161305
SFD_TMN_1 | RSA3 lines works. | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161552
OTA_CB_188 | OTA-P-CB-188 | 2026-11-02 07:30 | 2026-11-03 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161328
EDG_OWH_2 | , EDG-CT-252, EDG-DS-256, EDG-P-CB-252, EDG-ES-259, SF6 CB Proactive Pole Repl RSA2 25/26 EDG-CB-252 MP_RA2_02S_0_00 | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1150685
TMN_T5 | Affected Equipment of SFD_TMN_1 RSA3 lines works. | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161659
TMN_CB_458 | Affected Equipment of SFD_TMN_1 RSA3 lines works. | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161657
TAK_T5 | T5 midlife refurbishment project T5 midlife refurbishment project | 2026-11-02 07:30 | 2026-11-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006425
TMN_396_457 | Affected Equipment of SFD_TMN_1 RSA3 lines works. | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161655
HWB_ROX_1 | HWB-ROX-A0135-00, HWB-ROX-A0145A-00, HWB-ROX-A0150-00, HWB-ROX-A0153-00, HWB-ROX-A0160-00, HWB-ROX-A0173-00, HWB-ROX-A0312-10, HWB-ROX-A0344-10, HWB-ROX-A0346-10, HWB-ROX-A0347-10 | 2026-11-02 07:30 | 2026-11-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160759
KMO_110BZ | KMO-P-BZ-110-C | 2026-11-02 07:30 | 2026-11-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160954
KMO_110CBF | Affected equipment | 2026-11-02 07:30 | 2026-11-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160955
STK_T10 | Stage 4 - T10 Secondary Cabling Modifications and retesting | 2026-11-02 07:30 | 2026-11-06 17:30 | Continuous | SI | RS - Removal from Service | Approved | OW1162756
HWB_ROX_2 | HWB-ROX-A0201-20, HWB-ROX-A0203A-10, HWB-ROX-A0204A-10, | 2026-11-02 07:30 | 2026-11-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160760
HEN_WEL_1 | Attachment point, re-insulation and steel and bolts | 2026-11-02 08:00 | 2026-11-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005179
HEN_WEL_2 | Attachment point, re-insulation and steel and bolts | 2026-11-02 08:00 | 2026-11-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005180
BEN_F_4 | BEN 220BZ - Filter 4 Migration | 2026-11-02 08:00 | 2026-11-12 18:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160271
BEN_220CBF | BEN 220BZ - Filter 4 Migration | 2026-11-02 08:00 | 2026-11-02 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160254
BEN_220BZ | BEN 220BZ - Filter 4 Migration | 2026-11-02 08:00 | 2026-11-02 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160237
PEN_T10 | Open for duration of OTA_PEN_5 | 2026-11-02 08:00 | 2026-11-07 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1143514
PEN_CB_8612 | Place PEN REA into service for the duration of OTA_PEN_5 | 2026-11-02 08:00 | 2026-11-07 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1143513
HTU_T1 | Affected equipment | 2026-11-02 08:00 | 2026-11-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160734
OTA_HTU_WKM_1 | Tower Painting and Recoat CP_661_005_0_00 | 2026-11-02 08:00 | 2026-11-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142953
OTA_PEN_5 | Tower Painting | 2026-11-02 08:00 | 2026-11-07 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142930
DRY_GLN_1 | Tower Painting | 2026-11-02 08:00 | 2026-11-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142837
ARI_HTI_ONG_1 | Tower painting x10 (B231-B240) [CP_708_002_0_00] | 2026-11-02 08:00 | 2026-11-07 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1142833
KOE_MPE_2 | Replace KOE DS104, DS106, ES109 bellcrank | 2026-11-04 07:30 | 2026-11-04 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163032
ARG_BLN_1 | Affected Equipment of BLN_64_74_87 BLN-DS-64 BLN-DS-67 | 2026-11-04 07:30 | 2026-11-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160147
KAW_T12 | KAW-CT-592, KAW-NCT-12 | 2026-11-04 07:30 | 2026-11-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160904
BEN_220BS_C | BEN 220BZ - CB428 Migration CP_BEN_AZ_00_00 | 2026-11-04 07:30 | 2026-11-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005420
OHC_TWZ_4 | Affected equipment TWZ_2616_2417 & TWZ_T19 | 2026-11-04 07:30 | 2026-11-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161274
TWZ_2616_2417 | TWZ-DS-2564 | 2026-11-04 07:30 | 2026-11-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161740
TWZ_CB_2442 | Affected equipment TWZ_2616_2417 & TWZ_T19 | 2026-11-04 07:30 | 2026-11-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161742
TWZ_CB_2562 | Affected equipment TWZ_2616_2417 & TWZ_T19 | 2026-11-04 07:30 | 2026-11-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161745
BLN_T1 | Affected Equipment of BLN_64_74_87 BLN-DS-64 BLN-DS-67 | 2026-11-04 07:30 | 2026-11-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160306
TWZ_T19 | TWZ-CBL-LS19-2162, TWZ-CBL-T19-2162, TWZ-CBL-T19-NER19, TWZ-RES-NER-19, TWZ-TF-LS19 | 2026-11-04 07:30 | 2026-11-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161747
BLN_64_74_87 | BLN-DS-64 BLN-DS-67 | 2026-11-04 07:30 | 2026-11-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160290
OTA_CB_178 | OTA-P-CB-178 | 2026-11-04 07:30 | 2026-11-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161327
SVL_FDR_2902 | SVL-CBL-2902 | 2026-11-05 07:30 | 2026-11-05 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161587
BEN_220BS_D | BEN 220BZ - CB428 Migration CP_BEN_AZ_00_00 | 2026-11-05 08:00 | 2026-11-05 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005421
BEN_220CBF | BEN 220BZ - CB428 Migration CP_BEN_AZ_00_00 | 2026-11-05 08:00 | 2026-11-05 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2006298
PEN_CB_2388 | PEN-CB-2388 WO2075282 | 2026-11-05 08:00 | 2026-11-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162440
PEN_CB_2378 | PEN-CB-2378 WO2075281 | 2026-11-05 08:00 | 2026-11-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162439
BEN_220BZ | BEN 220BZ - CB428 Migration CP_BEN_AZ_00_00 | 2026-11-05 08:00 | 2026-11-05 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2006297
HAY_SC_7_T7 | HAY-SC7, HAY-SC7-EXC, HAY-SC7-NCT-7, HAY-SC7-NER, HAY-TF-T7 | 2026-11-06 07:30 | 2026-11-17 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160622
HLY_SFD_1 | RSA2 Attachment points and reinsulation | 2026-11-07 07:30 | 2026-11-13 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1153420
EDG_WAI_2 | Annual shut | 2026-11-08 07:30 | 2026-11-08 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160485
WAI_104_114 | Annual shut | 2026-11-08 07:30 | 2026-11-08 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161750
WAI_964_2726 | WAI-DS-2726, WAI-DS-961, WAI-DS-962, WAI-DS-963, WAI-DS-964, WAI-VT-5 | 2026-11-08 07:30 | 2026-11-08 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161751
WAI_CB_1362 | Affected Equipment of WAI_T2 Annual shut | 2026-11-08 07:30 | 2026-11-08 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161752
WAI_CB_2722 | WAI-CB-2722, WAI-CBL-2722 | 2026-11-08 07:30 | 2026-11-08 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161754
WAI_T1 | WAI-CB-102, WAI-CT-102, Annual shut | 2026-11-08 07:30 | 2026-11-08 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161755
WAI_T2 | Annual shut | 2026-11-08 07:30 | 2026-11-08 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161756
WAI_T5 | WAI-CB-2752, WAI-CB-92, WAI-CBL-2752-2756, WAI-CBL-2752-T5, WAI-DS-2756, WAI-DS-96, WAI-TF-T5, WAI-VT-92 | 2026-11-08 07:30 | 2026-11-08 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161758
MLG_T2 | MLG-CB-37, MLG-CBL-37, MLG-NCT-T2, MLG-TF-T2, MLG-VT-37. Affected equipment of HAY_MLG_2, for Tower works x3 (B16, B19, B30) | 2026-11-09 07:00 | 2026-11-13 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162032
HAY_WIL_LTN_1 | Strain attachment point replacements | 2026-11-09 07:00 | 2026-11-13 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2006223
WIL_T5 | Reinhausen work. WIL-CBL-852 (T5). Testing 18th + 19th, 12-hourheat soak on 20th. | 2026-11-09 07:30 | 2026-11-20 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161802
MTM_C_1 | Repaint MTM REA 1 | 2026-11-09 07:30 | 2026-11-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161178
FHL_RDF_1 | FHL-CB-142, FHL-CT-142, FHL-DS-146, FHL-ES-149, FHL-P-CB-142. RDF-P-CB-92. Pole replacement x1. Re-insulation x2. | 2026-11-09 07:30 | 2026-11-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160494
ISL_T6 | ISL-DS-503, ISL-DS-505 | 2026-11-09 07:30 | 2026-11-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160871
ISL_CB_658 | Affected Equipment of ISL_220BS_D Affected equipment ISL_T6, ISL-DS-505 Headgear Replacement | 2026-11-09 07:30 | 2026-11-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005098
AVI_BEN_2 | BEN-CT-CT532, BEN-CVT-VT9, BEN-DS-536, BEN-ES-539 | 2026-11-09 07:30 | 2026-11-10 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160200
MPE_287_267_VT207 | MPE-DS-224, MPE-DS-244, MPE-DS-254, MPE-DS-267, MPE-ES-260, MPE-VT-207, MPE-DS-234 | 2026-11-09 07:30 | 2026-11-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1150043
MPE_CB_288 | Affected equipment MPE_287_267_VT207 & KOE_MPE_2 & MPE_FDR_232 | 2026-11-09 07:30 | 2026-11-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1150045
MPE_FDR_242 | Affected equipment MPE_287_267_VT207 & KOE_MPE_2 & MPE_FDR_232 | 2026-11-09 07:30 | 2026-11-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1150047
MPE_FDR_262 | Affected equipment MPE_287_267_VT207 & KOE_MPE_2 & MPE_FDR_232 | 2026-11-09 07:30 | 2026-11-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1150048
ISL_C_26 | Affected equipment ISL_T6 | 2026-11-09 07:30 | 2026-11-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160819
MPE_CB_292 | System split | 2026-11-09 07:30 | 2026-11-09 23:00 | Daily | NNI | OPE - Open Ended | Approved | OW1150049
MPE_CB_252 | Affected equipment MPE_287_267_VT207 & KOE_MPE_2 & MPE_FDR_232 | 2026-11-09 07:30 | 2026-11-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1150044
ISL_CB_608 | Affected Equipment of ISL_220BS_D Affected equipment ISL_T6, ISL-DS-505 Headgear Replacement | 2026-11-09 07:30 | 2026-11-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005097
MPE_FDR_232 | Affected equipment MPE_287_267_VT207 & KOE_MPE_2 & MPE_FDR_232 | 2026-11-09 07:30 | 2026-11-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1163160
HAY_SC_9_T9 | HAY-CBL-T9-C9, HAY-CBL-T9-XT9, HAY-CBL-XT9-VT9A, HAY-SC9, HAY-SC9-EXC, HAY-SC9-NER, HAY-SC9-VT-9A | 2026-11-09 07:30 | 2026-11-20 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160624
ISL_220BS_D | Affected equipment ISL_T6, ISL-DS-505 Headgear Replacement | 2026-11-09 07:30 | 2026-11-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005096
MDN_MPE_2 | Affected equipment MPE_287_267_VT207 | 2026-11-09 07:30 | 2026-11-10 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163159
KOE_MPE_2 | Affected equipment MPE_287_267_VT207 | 2026-11-09 07:30 | 2026-11-10 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1163158
ISL_C_21 | Affected equipment ISL_T6, ISL-DS-505 Headgear Replacement | 2026-11-09 07:30 | 2026-11-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005095
INV_CB_722 | cancelled - INV-P-CB-722 Thomas Patrick | 2026-11-09 07:30 | 2026-11-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160777
HTU_T2 | Affected equipment | 2026-11-09 08:00 | 2026-11-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160736
OTA_HTU_WKM_2 | Tower Painting and Recoat CP_661_005_0_00 | 2026-11-09 08:00 | 2026-11-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142956
OTA_CB_488 | Affected Equipment of OTA_487_547 OTA-DS-523 Headgear refurb | 2026-11-09 08:00 | 2026-11-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161331
OTA_CB_538 | Affected Equipment of OTA_487_547 OTA-DS-523 Headgear refurb | 2026-11-09 08:00 | 2026-11-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161333
BOB_T4 | Affected Equipment Tower Painting | 2026-11-09 08:00 | 2026-11-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142873
DRY_BOB_HLY_1 | Tower Painting | 2026-11-09 08:00 | 2026-11-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142872
DRY_GLN_2 | Tower Painting | 2026-11-09 08:00 | 2026-11-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142838
MLG_T4 | Affected equipment of HAY_MLG_2, for Tower works x3 (B16, B19, B30) | 2026-11-09 08:00 | 2026-11-13 17:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162034
MLG_54_94 | Affected equipment of HAY_MLG_2, for Tower works x3 (B16, B19, B30) | 2026-11-09 08:00 | 2026-11-13 17:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162031
HAY_MLG_2 | Tower works x3 (B16, B19, B30) | 2026-11-09 08:00 | 2026-11-13 17:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162009
OTA_487_547 | OTA-DS-523 Headgear refurb | 2026-11-09 08:00 | 2026-11-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161315
MPE_CB_292 | System split | 2026-11-10 06:00 | 2026-11-10 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1162682
ISL_SVC_9 | ISL-CWU-SVC9, ISL-P-PSUP-SVC9-UPS-1. De-ionising resin change. UPS diagnostic Inspection and Service. | 2026-11-10 07:30 | 2026-11-10 18:00 | Daily | HVDC | RS - Removal from Service | Approved | OW2006034
TMU_T2 | Affected Equipment of TMU_54_48_94 TMU-CAPS-C1, TMU-ES-69, TMU-P-CAPS-C1, TMU-REA-R1 | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161672
TMU_C_2 | TMU-CAPS-C2, TMU-ES-119, TMU-P-CAPS-C2, TMU-REA-R2 | 2026-11-10 07:30 | 2026-11-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161665
STK_FDR_2352 | Affected Equipment of STK_33BS_C1 STK-CB-2392 does this need entire Bus? | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161561
STK_CB_2408 | Affected Equipment of STK_33BS_C1 STK-CB-2392 does this need entire Bus? | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161559
STK_CB_2248_2374 | Affected Equipment of STK_33BS_C1 STK-CB-2392 does this need entire Bus? | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161558
TMU_C_1 | TMU-CAPS-C1, TMU-ES-69, TMU-P-CAPS-C1, TMU-REA-R1 | 2026-11-10 07:30 | 2026-11-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161664
STK_C_34 | Affected Equipment of STK_33BS_C1 STK-CB-2392 does this need entire Bus? | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161557
STK_33BS_C1 | STK-CB-2392 does this need entire Bus? | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161553
TMU_54_48_94 | TMU-CAPS-C1, TMU-ES-69, TMU-P-CAPS-C1, TMU-REA-R1 | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161663
KPO_TMU_1 | Affected Equipment of TMU_54_48_94 TMU-CAPS-C1, TMU-ES-69, TMU-P-CAPS-C1, TMU-REA-R1 | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160982
HAY_CB_58 | HAY_110BZ Stage 2A; CB_58 protection upgrade. No other work on days 1, 6, 7. No other work on associated equipment on day 7 (commissioning). HAY-CT-58, HAY-P-CB-58 | 2026-11-11 07:00 | 2026-11-17 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162005
HWA_T3 | Affected equipment of HWA_FDR_2632 + HWA_CB_2648. Aligned with Beach Kupe shut. | 2026-11-11 07:00 | 2026-11-11 16:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005893
HWA_CB_2648 | HWA-CB-2648, HWA-P-CB-2648. Aligned with Beach Kupe shut. | 2026-11-11 07:00 | 2026-11-11 16:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160742
HWA_FDR_2632 | HWA-CB-2632, HWA-P-CB-2632. Aligned with Beach Kupe shut. | 2026-11-11 07:00 | 2026-11-11 16:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160744
MPE_FDR_302 | Affected equipment MPE_267_324_344 & MDN_MPE_1 | 2026-11-11 07:30 | 2026-11-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1150085
KOE_MPE_1 | CM lines maintenance Affected equipment MPE_267_324_344 & MDN_MPE_1. | 2026-11-11 07:30 | 2026-11-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1163168
MDN_MPE_1 | Affected equipment MPE_267_324_344 & MDN_MPE_1 | 2026-11-11 07:30 | 2026-11-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1163167
MPE_FDR_342 | Affected equipment MPE_267_324_344 & MDN_MPE_1 | 2026-11-11 07:30 | 2026-11-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1150086
MPE_267_324_344 | MPE-DS-304, MPE-DS-314, MPE-DS-324, MPE-VT-307, MPE-DS-344 | 2026-11-11 07:30 | 2026-11-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1150081
MPE_CB_252 | System split | 2026-11-11 07:30 | 2026-11-11 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1163165
MPE_CB_288 | Affected equipment MPE_267_324_344 & MDN_MPE_1 | 2026-11-11 07:30 | 2026-11-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1150082
RPO_626_634 | RPO-P-CB-632-CZP | 2026-11-11 07:30 | 2026-11-11 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161522
MPE_FDR_282 | Affected equipment MPE_267_324_344 & MDN_MPE_1 | 2026-11-11 07:30 | 2026-11-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1150084
MPE_CB_292 | Affected equipment MPE_267_324_344 & MDN_MPE_1 | 2026-11-11 07:30 | 2026-11-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1150083
HAY_110CBF | HAY_110BZ Stage 2A; CB_58 protection upgrade. | 2026-11-11 08:00 | 2026-11-11 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161952
HAY_110BZ | HAY_110BZ Stage 2A; CB_58 protection upgrade. No work in HAY 110kV yard. | 2026-11-11 08:00 | 2026-11-11 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161906
BEN_220CBF | BEN 220BZ - Filter 4 Migration | 2026-11-11 08:00 | 2026-11-12 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160255
BEN_220BZ | BEN 220BZ - Filter 4 Migration | 2026-11-11 08:00 | 2026-11-12 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160238
MPE_CB_252 | System split | 2026-11-12 06:00 | 2026-11-12 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1163166
HWA_T3 | HWA-CB-2622. HWA TOPS to be enabled. | 2026-11-12 07:00 | 2026-11-12 15:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005895
HWA_CB_2648 | CLO for the duration of HWA_T3, to maintain supply to Beach Kupe (via PCO tie). | 2026-11-12 07:00 | 2026-11-12 15:30 | Daily | SNI | CLO - Close | Approved | OW2005896
ATI_WKM_1 | ATI-CVT-132, ATI-DS-136, ATI-ES-139. Tower works x1 (A114). | 2026-11-12 07:30 | 2026-11-12 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160198
FHL_RDF_2 | FHL-DS-126, FHL-ES-129, FHL-P-CB-122. RDF-P-CB-62. Re-insulation x2. | 2026-11-12 07:30 | 2026-11-13 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160495
PEN_FDR_2302 | PEN-CB-2302, PEN-P-CB-2302 | 2026-11-12 07:30 | 2026-11-12 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161410
HAY_CB_2432 | HAY-CBL-CB2432-ST7 | 2026-11-13 07:30 | 2026-11-13 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160601
TKR_WIL_1 | WIL-CT-CT152. No lines work on day 3 (Mon 16th). Re-insulation x2. Strain attachment point replacements. | 2026-11-14 07:00 | 2026-11-20 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161634
THI_WKM_1 | Maintenance works, broken insulator, u-Bolts, birds nests, earthwire works, loose strands back span, bulging joint. | 2026-11-14 07:30 | 2026-11-21 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161606
ISL_T6 | ISL-CB-252 Pole Replacement, MP_RA5_032_0_00. CY4 Scheduled Maintenance Re-planned. | 2026-11-16 06:30 | 2026-11-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159775
ISL_C_26 | Affected Equipment ISL-CB-252 Pole Replacement, MP_RA5_031_0_00. CY4 Scheduled Maintenance Re-planned. | 2026-11-16 06:30 | 2026-11-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159776
ROS_FDR_162 | Offload to step into ROS 117-147 | 2026-11-16 07:00 | 2026-11-16 07:30 | Daily | NNI | PSO - Power System Operating | Approved | OW2005150
ROS_FDR_142 | Offload to step into ROS 117-147 | 2026-11-16 07:00 | 2026-11-16 07:30 | Daily | NNI | PSO - Power System Operating | Approved | OW2005152
DOB_T1 | DOB-CBL-1332 Low MV Cable Sheath Insulation. | 2026-11-16 07:00 | 2026-11-17 18:00 | Continuous | SI | RS - Removal from Service | Approved | OW1162542
KWA_CB_8 | Affected equipment of KWA_T2 & KWA_WIL_1 | 2026-11-16 07:00 | 2026-11-20 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161002
KWA_T2 | KWA-P-TF-T2 | 2026-11-16 07:00 | 2026-11-20 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161004
OTA_ROS_1 | Offload to step into ROS 117-147 | 2026-11-16 07:00 | 2026-11-16 07:30 | Daily | NNI | PSO - Power System Operating | Approved | OW2005149
HEP_ROS_2 | Offload to step into ROS 117-147 | 2026-11-16 07:00 | 2026-11-16 07:30 | Daily | NNI | PSO - Power System Operating | Approved | OW2005153
KWA_WIL_1 | KWA-DS-56, KWA-ES-59, WIL-P-CB-162. No lines work on day 1. | 2026-11-16 07:00 | 2026-11-20 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161007
CPK_WWD_WIL_2 | WIL-CT-CT142 (no lines on day 1). WWD-TEE-A0108-0109-00, WWD-TEE-A0109-0110-00, WWD-TEE-A0111-WWDG2-10 | 2026-11-16 07:00 | 2026-11-20 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160409
CPK_T4 | CPK-DS-84, CPK-ES-89 | 2026-11-16 07:00 | 2026-11-20 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160405
WIL_118_188 | WIL-CT-CT178, WIL-DCB-128, WIL-DCB-142, WIL-DCB-152, WIL-DCB-162, WIL-DCB-178, WIL-P-CB-178-188, WIL-VT-VT137 | 2026-11-16 07:00 | 2026-11-20 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161795
STK_T4 | Affected Equipment Stage 5 - Remove 272 BUS dropper from 110kV BUS | 2026-11-16 07:30 | 2026-11-16 17:30 | Daily | SI | RS - Removal from Service | Approved | OW1163679
TAK_T8 | T8 midlife refurbishment project T8 midlife refurbishment project | 2026-11-16 07:30 | 2026-11-27 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006426
BPE_T15 | Reinhausen work. BPE CB, CT, DS, ER, ES, NCT, TF, VT mtce. | 2026-11-16 07:30 | 2026-11-20 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160341
BLN_STK_1 | Affected Equipment Stage 5 - Remove 272 BUS dropper from 110kV BUS | 2026-11-16 07:30 | 2026-11-16 17:30 | Daily | SI | RS - Removal from Service | Approved | OW1163678
STK_267_272_282 | Stage 5 - Remove 272 BUS dropper from 110kV BUS | 2026-11-16 07:30 | 2026-11-16 17:30 | Daily | SI | RS - Removal from Service | Approved | OW1162757
INV_TWI_2 | Lines extra outage resource heavy | 2026-11-16 07:30 | 2026-11-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160795
HLY_TWH_1 | Headgear refurbishment project. HLY-CVT-582, HLY-DS-583, HLY-DS-586, HLY-DS-605, HLY-ES-589, HLY-TMN-A0032-20, HLY-TMN-A0039-20 | 2026-11-16 07:30 | 2026-11-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160715
HEN_T1 | Affected equipment | 2026-11-16 07:30 | 2026-11-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160665
HEN_HEP_2 | Affected equipment HEN_244_287_297 & HEN_T1 | 2026-11-16 07:30 | 2026-11-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160655
HEN_244_287_297 | HEN-DS-254, HEN-DS-274, HEN-DS-287, HEN-VT-1 | 2026-11-16 07:30 | 2026-11-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160644
HEN_HEP_1 | Affected equipment HEN_244_287_297 & HEN_T1 | 2026-11-16 07:30 | 2026-11-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160653
HEN_CB_288 | Affected equipment HEN_244_287_297 & HEN_T1 | 2026-11-16 07:30 | 2026-11-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160650
HAY_110CBF | HAY_110BZ Stage 2A; CB_58 protection upgrade. | 2026-11-16 08:00 | 2026-11-16 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161953
HAY_110BZ | HAY_110BZ Stage 2A; CB_58 protection upgrade. No work in HAY 110kV yard. | 2026-11-16 08:00 | 2026-11-16 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161907
PEN_T10 | Affected equipment | 2026-11-16 08:00 | 2026-11-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161427
PEN_T9 | Affected equipment PEN_220BS_B & PEN_CB_758 & PEN_CB_798 & PEN_T10 | 2026-11-16 08:00 | 2026-11-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161437
DRY_BOB_HLY_2 | Tower Painting, HLY DS 603 headgear refurb. CP_RA2_03C_0_00 | 2026-11-16 08:00 | 2026-11-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142876
BOB_T5 | Affected Equipment DRY_BOB_HLY_2 | 2026-11-16 08:00 | 2026-11-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142877
PEN_220BS_B | PEN-DS-774, PEN-ES-7749, PEN-DS-767, PEN-DS-777, PEN-DS-784, PEN-DS-797, PEN-ES-760, PEN-ES-790 | 2026-11-16 08:00 | 2026-11-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161371
PEN_CB_2332A | Place PEN T8 into service for the duration of T9 outage | 2026-11-16 08:00 | 2026-11-20 18:30 | Continuous | NNI | CLO - Close | Approved | OW1161383
PEN_CB_2332B | Place PEN T8 into service for the duration of T9 outage | 2026-11-16 08:00 | 2026-11-20 18:30 | Continuous | NNI | CLO - Close | Approved | OW1161385
PEN_CB_758 | PEN-P-CB-758 | 2026-11-16 08:00 | 2026-11-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161390
PEN_CB_772 | Affected equipment PEN_220BS_B & PEN_CB_758 & PEN_CB_798 & PEN_T10 | 2026-11-16 08:00 | 2026-11-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161392
PEN_CB_798 | PEN-CT-798, PEN-P-CB-798 | 2026-11-16 08:00 | 2026-11-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161394
STK_220BZ | Stage 5 - STK 220BZ - Disconnect T7 Trips for saftey | 2026-11-16 13:00 | 2026-11-16 17:00 | Daily | SI | RS - Removal from Service | Approved | OW1162759
STK_220CBF | Stage 5 - STK 220CBF - Disconnect T7 Trips for saftey | 2026-11-16 13:00 | 2026-11-16 17:00 | Daily | SI | RS - Removal from Service | Approved | OW1162760
MPE_CB_252 | System split for the duration of MDN_MPE_1 | 2026-11-17 07:30 | 2026-11-17 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW2005182
MPE_CB_292 | System split for MDN_MPE_1 | 2026-11-17 07:30 | 2026-11-17 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW2005186
MDN_MPE_1 | Attachment point, re-insulation and steel and bolts | 2026-11-17 07:30 | 2026-11-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005181
NPK_T1 | NPK_T1 protection replacement [CP_NPK_002_0_00]. Affected equipment of OKN_NPK_ONG_1. | 2026-11-17 07:30 | 2026-11-26 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161255
TWH_T2 | Affected equipment | 2026-11-17 07:30 | 2026-11-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161731
TWH_CB_428 | Affected equipment TWH_427_444_454 & HLY_TWH_1 & TWH_T2 | 2026-11-17 07:30 | 2026-11-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161720
TWH_427_444_454 | TWH-CB-428 | 2026-11-17 07:30 | 2026-11-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161717
OKN_NPK_ONG_1 | RSA3 conductor repairs [MP_RA3_03H_0_00]. BPE-ONG-A0366-0367-10, BPE-ONG-A0406-0407-10 | 2026-11-17 07:30 | 2026-11-26 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161297
TKU_T22 | CLO for the duration of TKU_T21, to maintain TKU 33kV supply. | 2026-11-17 07:30 | 2026-11-26 18:30 | Continuous | SNI | CLO - Close | Approved | OW1161642
TKU_T21 | TKU-M-VT21, TKU-P-TF-T21 | 2026-11-17 07:30 | 2026-11-26 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161641
TKU_DIS_137 | OPE for duration of TKU_T21, to ensure high-tension CB protection to TKU_T22 | 2026-11-17 07:30 | 2026-11-26 18:30 | Continuous | SNI | OPE - Open Ended | Approved | OW1161638
TKU_DIS_147 | OPE for duration of TKU_T21, to ensure high-tension CB protection to TKU_T22 | 2026-11-17 07:30 | 2026-11-26 18:30 | Continuous | SNI | OPE - Open Ended | Approved | OW1161639
TKU_FDR_1062 | TKU-M-CT1062 | 2026-11-17 07:30 | 2026-11-26 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161640
STK_110CBF | Stage 5 - STK 110BZ - Disconnect T7 Trips for saftey | 2026-11-17 08:30 | 2026-11-17 12:30 | Daily | SI | RS - Removal from Service | Approved | OW1162763
STK_110BZ | Stage 5 - STK 110BZ - Disconnect T7 Trips for saftey | 2026-11-17 08:30 | 2026-11-17 12:30 | Daily | SI | RS - Removal from Service | Approved | OW1162762
MPE_CB_292 | System split for MDN_MPE_1 | 2026-11-18 06:00 | 2026-11-19 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW2005188
MPE_CB_252 | System split for the duration of MDN_MPE_1 | 2026-11-18 06:00 | 2026-11-19 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW2005183
ISL_FDR_122 | ISL-CB-122, ISL-P-CB-122 | 2026-11-18 06:30 | 2026-11-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160849
MPE_FDR_302 | Revenue metering. MPE-M-CT302 | 2026-11-18 07:30 | 2026-11-18 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161167
DOB_T11_RFN_IGH_2 | Affected Equipment of IGH_387_377_344 IGH-VT-VT367 | 2026-11-18 07:30 | 2026-11-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005946
DOB_RFN_IGH_2 | Affected Equipment of IGH_387_377_344 IGH-VT-VT367 | 2026-11-18 07:30 | 2026-11-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160438
DOB_T11 | Affected Equipment of IGH_387_377_344 IGH-VT-VT367 | 2026-11-18 07:30 | 2026-11-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160439
IGH_387_377_344 | IGH-VT-VT367 | 2026-11-18 07:30 | 2026-11-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160763
WPT_T1 | Affected Equipment of IGH_387_377_344 IGH-VT-VT367 | 2026-11-18 07:30 | 2026-11-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005948
IGH_ROB_1 | Affected Equipment of IGH_387_377_344 IGH-VT-VT367 | 2026-11-18 07:30 | 2026-11-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005947
IGH_KIK_2 | Affected Equipment of IGH_387_377_344 IGH-VT-VT367 | 2026-11-18 07:30 | 2026-11-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160765
ISL_220BS_D | ISL-DS-505. CY4 Scheduled Maintenance Re-planned. | 2026-11-19 06:30 | 2026-11-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159777
ISL_CB_608 | Affected Equipment ISL-DS-505. CY4 Scheduled Maintenance Re-planned. | 2026-11-19 06:30 | 2026-11-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159778
ISL_CB_658 | Affected Equipment ISL-DS-505. CY4 Scheduled Maintenance Re-planned. | 2026-11-19 06:30 | 2026-11-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159779
ISL_C_21 | Affected Equipment ISL-DS-505. CY4 Scheduled Maintenance Re-planned. | 2026-11-19 06:30 | 2026-11-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159780
ROS_T2 | Affected equipment ROS_2012_2042_2058 | 2026-11-19 07:30 | 2026-11-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161487
ROS_FDR_2032 | Affected equipment ROS_2012_2042_2058 | 2026-11-19 07:30 | 2026-11-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161485
ROS_FDR_2022 | Affected equipment ROS_2012_2042_2058 | 2026-11-19 07:30 | 2026-11-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161484
ROS_FDR_2012 | Affected equipment ROS_2012_2042_2058 | 2026-11-19 07:30 | 2026-11-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161483
ROS_CB_2058 | Affected equipment ROS_2012_2042_2058 | 2026-11-19 07:30 | 2026-11-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161480
ROS_2012_2042_2058 | Revenue metering. ROS-M-VT23 | 2026-11-19 07:30 | 2026-11-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161478
PEN_CB_2318 | PEN-CB-2318, PEN-P-CB-2318 | 2026-11-19 07:30 | 2026-11-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161381
MPE_CB_292 | System split for the MDN_MPE_1 | 2026-11-20 06:00 | 2026-11-20 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW2005189
MPE_CB_252 | System split for the duration of MDN_MPE_1 | 2026-11-20 06:00 | 2026-11-20 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW2005185
BPE_T10 | Reinhausen work. | 2026-11-20 07:30 | 2026-11-22 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160340
PEN_FDR_2242 | PEN-CB-2242, PEN-P-CB-2242 | 2026-11-20 07:30 | 2026-11-20 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161407
ROS_FDR_162 | Offload to step out of ROS 117-147 | 2026-11-20 18:30 | 2026-11-20 19:00 | Daily | NNI | PSO - Power System Operating | Approved | OW2005156
OTA_ROS_1 | Offload to step out of ROS 117-147 | 2026-11-20 18:30 | 2026-11-20 19:00 | Daily | NNI | PSO - Power System Operating | Approved | OW2005154
HEP_ROS_2 | Offload to step out of ROS 117-147 | 2026-11-20 18:30 | 2026-11-20 19:00 | Daily | NNI | PSO - Power System Operating | Approved | OW2005161
ROS_FDR_142 | Offload to step out of ROS 117-147 | 2026-11-20 18:30 | 2026-11-20 19:00 | Daily | NNI | PSO - Power System Operating | Approved | OW2005159
THI_WRK_1 | WRK-CT-112, WRK-DS-116, WRK-ES-119 | 2026-11-22 07:30 | 2026-11-23 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161607
WVY_T1 | WVY site shut (alternate date 29/11/26). WVY-TF-T1. | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161889
WVY_RTU_1 | SMS & GPS replacements [CP_RA3_03C_0_00]. Aligned with WVY shut | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161888
WVY_CB_42 | Affected equipment of WVY site shut (alternate date 29/11/26) | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161883
WVY_CB_112 | Affected equipment of WVY site shut (alternate date 29/11/26) | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161882
WVY_57_94 | Affected equipment of WVY site shut (alternate date 29/11/26) | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161881
WVY_47_134 | Affected equipment of WVY site shut (alternate date 29/11/26) | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161880
HWA_WVY_1 | Affected equipment of WVY site shut (alternate date 29/11/26) | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW1160753
MLG_64_104 | MLG-DS-104, MLG-DS-64, MLG-ES-79, MLG-VT-67. Affected equipmentof HAY_MLG_1. | 2026-11-23 07:00 | 2026-11-27 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1161058
HAY_MLG_1 | HAY-CB-202. Tower works x6 (B5, B8, B11, B16, B28, B30). | 2026-11-23 07:00 | 2026-11-27 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162008
MLG_T3 | Affected equipment of HAY_MLG_1 | 2026-11-23 07:00 | 2026-11-27 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162033
BPE_TWC_LTN_1 | Strain attachment point replacements | 2026-11-23 07:00 | 2026-11-27 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2006224
MLG_T1 | MLG-CB-39, MLG-CBL-39, MLG-TF-T1, MLG-VT-39. | 2026-11-23 07:00 | 2026-11-27 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1161068
CST_SFD_2 | SFD-CBL-222-CST2. Tower painting x6 (A99A - A100A, A101-A104) [CP_752_002_0_00]. Tower recoating x13 (A56-A68) [CP_752_005_0_00]. | 2026-11-23 07:30 | 2026-12-04 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160414
TGA_237_244_264 | TGA-BS-110-247-244, TGA-DS-244, TGA-DS-247, TGA-DS-264, TGA-VT-2 | 2026-11-23 07:30 | 2026-11-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161596
TGA_33BS_A | TGA-BS-33-A | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161597
TGA_CB_2188 | Affected equipment TGA_33BS_A | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161598
TGA_CB_2208 | Affected equipment TGA_33BS_A | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161599
TGA_FDR_2132 | Affected equipment TGA_33BS_A | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161600
TGA_FDR_2142 | Affected equipment TGA_33BS_A | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161601
TGA_FDR_2162 | Affected equipment TGA_33BS_A | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161602
TGA_FDR_2172 | Affected equipment TGA_33BS_A | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161603
DVK_T2 | Affected equipment of WDV_DVK_WPW_1 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160465
TGA_T3 | Affected equipment TGA_33BS_A | 2026-11-23 07:30 | 2026-11-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161605
KMO_TGA_1 | HAI-TGA-ATGAS1-00, HAI-TGA-ATGAS2-00, HAI-TGA-ATGAS3-00, KMO-DS-116, KMO-ES-119 | 2026-11-23 07:30 | 2026-11-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160973
PEN_FDR_2262 | PEN-CB-2262, PEN-P-CB-2262 | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161409
HAY_T24 | Reinhausen work. HAY-TF-T24 | 2026-11-23 07:30 | 2026-11-25 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160628
WDV_DVK_WPW_1 | Pole replacements x4 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161765
WIL_T3 | WIL CBL mtce. | 2026-11-23 07:30 | 2026-12-03 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161801
NMA_CB_688 | Affected Equipment of NMA_615_737 INV-MAN-A0277-0278-00, INV-MAN-A0297-10, INV-MAN-A0298-10, INV-MAN-A0348-0349-20, INV-P-CB-632/642, MAN-CB-202, MAN-P-CB-202 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161216
NMA_615_737 | INV-MAN-A0277-0278-00, INV-MAN-A0297-10, INV-MAN-A0298-10, INV-MAN-A0348-0349-20, INV-P-CB-632/642, MAN-CB-202, MAN-P-CB-202 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161208
HTU_T1 | Affected equipment OTA_HTU_WKM_1 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160735
WPW_T2 | Affected equipment of WDV_DVK_WPW_1 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161841
INV_MAN_2 | INV-MAN-A0277-0278-00, INV-MAN-A0297-10, INV-MAN-A0298-10, INV-MAN-A0348-0349-20, INV-P-CB-632/642, MAN-CB-202, MAN-P-CB-202 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160783
WRK_FDR_2082 | WRK-CBL-2082-FDR | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161862
DOB_RFN_IGH_2 | ca lifting inspect | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161896
DOB_T11 | Affected Equipment of DOB_RFN_IGH_2 ca lifting inspect | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161897
BEN_220CBF | BEN 220BZ - Filter 5 Migration | 2026-11-23 08:00 | 2026-11-23 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160256
PEN_CB_8612 | Place PEN REA into service for the duration of OTA_PEN_6 | 2026-11-23 08:00 | 2026-11-27 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW2005223
OTA_HTU_WKM_1 | Tower Painting and recoat CP_661_005_0_00 | 2026-11-23 08:00 | 2026-11-27 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142954
OTA_PEN_6 | Attachment points, re-insulation & Steel and bolts | 2026-11-23 08:00 | 2026-11-27 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005222
BEN_220BZ | BEN 220BZ - Filter 5 Migration | 2026-11-23 08:00 | 2026-11-23 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160239
PEN_T10 | System split whilst PEN REA is in service | 2026-11-23 08:00 | 2026-11-27 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW2005224
DRY_GLN_1 | Tower Painting | 2026-11-23 08:00 | 2026-11-27 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142839
BEN_F_5 | BEN 220BZ - Filter 5 Migration | 2026-11-23 08:00 | 2026-11-27 18:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160273
HAY_CB_258 | HAY_110BZ Stage 2B; CB_258 protection upgrade. No other work ondays 1, 6, 7. No other work on associated equipment on day 7 (commissioning). | 2026-11-24 07:00 | 2026-11-30 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162002
OTA_404_437_507 | OTA DIS 425 headgear replacement | 2026-11-24 07:30 | 2026-11-25 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW2005662
BPE_TNG_1 | BPE-P-CB-752, TNG-DS-316, TNG-ES-319. BPE-TNG prot upgrade Stage 7: BPE-TNG protection upgrade and commissioning of TNG 220kV VT selection scheme [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. Tower painting x23 (A50-A72). | 2026-11-24 07:30 | 2026-12-01 17:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160345
OTA_CB_478 | Affected Equipment of OTA_404_437_507 OTA DIS 425 headgear replacement | 2026-11-24 07:30 | 2026-11-25 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW2005664
OTA_CB_402 | Affected Equipment of OTA_404_437_507 OTA DIS 425 headgear replacement | 2026-11-24 07:30 | 2026-11-25 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW2005663
BPE_220BZ | BPE-TNG prot upgrade Stage 7: Commissioning of TNG 220kV VT selection scheme [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-11-24 08:00 | 2026-11-24 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005579
TNG_220CBF | Affected equipment of TNG_220BZ, for BPE-TNG prot upgrade Stage7 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-11-24 08:00 | 2026-11-24 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005592
TNG_220BZ | BPE-TNG prot upgrade Stage 7: Commissioning of TNG 220kV VT selection scheme [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-11-24 08:00 | 2026-11-24 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005576
HAY_110BZ | HAY_110BZ Stage 2B; CB_258 protection upgrade. No work in HAY 110kV yard. | 2026-11-24 08:00 | 2026-11-24 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161908
BPE_220CBF | Affected equipment of BPE_220BZ, for BPE-TNG prot upgrade Stage7 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-11-24 08:00 | 2026-11-24 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005591
HAY_110CBF | HAY_110BZ Stage 2B; CB_258 protection upgrade. | 2026-11-24 08:00 | 2026-11-24 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161954
KTA_C_1 | REA-C1 PM | 2026-11-24 08:30 | 2026-11-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162974
TNG_220BS_B | TNG-DS-315 (BPE-1) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-230 | 2026-11-25 07:30 | 2026-11-25 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161687
ISL_220BZ | ISL-P-BZ-220 | 2026-11-26 07:30 | 2026-11-26 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160806
TNG_220BS_A | TNG-DS-313 (BPE-1) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-220 | 2026-11-26 07:30 | 2026-11-26 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161680
BEN_220BZ | BEN 220BZ - Filter 5 Migration | 2026-11-26 08:00 | 2026-11-27 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160240
BEN_220CBF | BEN 220BZ - Filter 5 Migration | 2026-11-26 08:00 | 2026-11-27 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160257
FHL_T2 | FHL-TF-T2. 12-hour heat soak on last day. | 2026-11-27 07:30 | 2026-12-12 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160497
PEN_CB_8612 | Place PEN REA into service for the duration of OTA_PEN_6 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1161402
PEN_CB_698 | PEN-P-CB-698 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161388
PEN_CB_758 | PEN-P-CB-758 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161391
PEN_C_1 | PEN-CAPS-C1, PEN-CB-732, PEN-CT-C1, PEN-ES-739, PEN-REA-C1 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161375
PEN_T5 | CB 712 Siemens relay replacement | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161432
PEN_T6 | Affected equipment PEN_220BS_A & OTA_PEN_6 & PEN_C_1 & PEN_CB_698 & PEN_CB_758 & PEN_CB_848 & PEN_T10 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161434
PEN_T7 | Affected equipment PEN_220BS_A & OTA_PEN_6 & PEN_C_1 & PEN_CB_698 & PEN_CB_758 & PEN_CB_848 & PEN_T10, PEN-CB-2482B, PEN-CB-2482A | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161435
OTA_PEN_6 | OTA-CB-522, OTA-CT-522, PEN-CB-752, PEN-CT-752, PEN-CVT-752, PEN-DS-756, PEN-ES-759, PEN-P-CB-752, PEN-CBL-698-848, PEN-ES-690,PEN-ES-850 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161340
PEN_T8 | PEN-CB-2332A, PEN_220BS_A & OTA_PEN_6 & PEN_C_1 & PEN_CB_698 & PEN_CB_758 & PEN_CB_848 & PEN_T10, PEN-CB-2332B | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161436
PEN_CB_848 | PEN-CB-848 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161399
PEN_220BS_A | PEN-DS-697, PEN-DS-704, PEN-DS-714, PEN-DS-734, PEN-DS-744, PEN-DS-754, PEN-DS-757, PEN-DS-764, PEN-ES-750 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161370
HAY_110BZ | HAY_110BZ Stage 2B; CB_258 protection upgrade. No work in HAY 110kV yard. | 2026-11-29 08:00 | 2026-11-29 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161909
HAY_110CBF | HAY_110BZ Stage 2B; CB_258 protection upgrade. | 2026-11-29 08:00 | 2026-11-29 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161955
ISL_T7 | ISL-CB-532 Corroding pipework M8 flange fastenings - P3 | 2026-11-30 06:30 | 2026-12-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005105
LTN_T2 | Affected equipment of BPE_LTN_2, for Strain attachment point replacements | 2026-11-30 07:00 | 2026-12-04 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2006227
ALB_HEN_3 | ALB-HPI-A0403-20, ALB-HPI-A0405-0406-20, ALB-HPI-A0416-00, ALB-HPI-A0435-0436-20, ALB-HPI-A0435-30, HEN-DS-456, HEN-MDN-A0013-20, HEN-MDN-A0018-0019-20, HEN-MDN-A0029-00 | 2026-11-30 07:00 | 2026-12-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160133
HEN_C_1 | Affected equipment HEN_414_447_487 & ALB_HEN_3 & HEN_OTA_1 & HEN_T1 | 2026-11-30 07:00 | 2026-12-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160648
BPE_LTN_2 | Strain attachment point replacements | 2026-11-30 07:00 | 2026-12-04 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2006225
HEN_414_447_487 | Headgear refurbishment project. HEN-DS-467 | 2026-11-30 07:00 | 2026-12-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160646
HEN_OTA_1 | HEN-CB-462, HEN-CT-462, HEN-CVT-462, HEN-DS-466, HEN-ES-469, HEN-OTA-A0003-00, HEN-OTA-A0004-00, HEN-OTA-A0005-00, HEN-OTA-A0006-00, HEN-OTA-A0007-00, HEN-OTA-A0009-00, HEN-OTA-A0010-00, HEN-OTA-A0010-10, HEN-OTA-A0011-00, HEN-OTA-A0012-00, HEN-OTA-A0013-00, HEN-OTA-A0013-10, HEN-OTA-A0014-00, HEN-OTA-A0020-00, HEN-OTA-A0022-00, HEN-OTA-A0024-00, HEN-OTA-A0028-00, HEN-OTA-A0029-00, HEN-OTA-A0031-00, HEN-OTA-A0034-10, HEN-OTA-A0037-10, HEN-OTA-A0052-00, HEN-OTA-A0056-10, HEN-, OTA-VT-VT1272 | 2026-11-30 07:00 | 2026-12-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160663
HEN_T2 | Affected equipment HEN_414_447_487 & ALB_HEN_3 & HEN_OTA_1 & HEN_T1 | 2026-11-30 07:00 | 2026-12-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160667
LTN_CB_212 | Affected equipment of BPE_LTN_2, for Strain attachment point replacements | 2026-11-30 07:00 | 2026-12-04 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2006226
HEN_T1 | HEN-CB-432 | 2026-11-30 07:00 | 2026-12-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160666
HEN_CB_488 | Affected equipment HEN_414_447_487 & ALB_HEN_3 & HEN_OTA_1 & HEN_T1 | 2026-11-30 07:00 | 2026-12-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160651
FHL_WPW_1 | FHL-CT-152, FHL-DS-156, FHL-ES-159, FHL-P-CB-152. WPW-ES-79. Pole replacements x12. Condition assessments. | 2026-11-30 07:00 | 2026-12-04 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160500
NMA_CB_738 | Affected equipment NMA_687_835 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161239
TMN_T8 | TMN-TF-T8 [CP_TMN_77_00_00]. Reinhausen work. Affected equipment of TMN_454_466_494 [CP_RA3_03F_0_00, CP_TMN_001_0_00]. | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161660
HTU_T2 | Affected equipment OTA_HTU_WKM_2 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160737
HAM_KPO_1 | HAM-KPO-A0051-00, HAM-KPO-A1-Z-CBL-SHEATH, HAM-P-CB-112 | 2026-11-30 07:30 | 2026-12-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160563
NMA_687_835 | NMA-DS-737 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161212
CPK_T12 | CPK-CBL-2212, CPK-CBL-LK2827-LS12, CPK-CBL-T12-LK2827, CPK-NCT-T12, CPK-TF-LS12, CPK-TF-T12 | 2026-11-30 07:30 | 2026-12-03 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160401
CPK_FDR_2832 | Affected equipment of CPK_T12 | 2026-11-30 07:30 | 2026-12-03 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160400
HAY_F_4 | S4.WA-Z1.Q1, S4.WA-Z1.Z1.Q1, S4.WA-Z1.Z1.R1A, S4.WA-Z1.Z1.R1B, S4.WA-Z1.Z1.R1C, S4.WA-Z1.Z2.Q1, S4.WA-Z1.Z2.R1A, S4.WA-Z1.Z2.R1B, S4.WA-Z1.Z2.R1C HVDC HAY-DC Pole 2 Era AC Disconnector/Earth Switch Refurbishments | 2026-11-30 07:30 | 2026-12-11 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160611
CBG_T4 | CBG-CBL-T4-2752, CBG-CBL-T4-LS4, CBG-TF-LS4, CBG-TF-T4, CBG-VT-242, CBG-VT-2822 | 2026-11-30 07:30 | 2026-12-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160380
NMA_T2 | NMA-CB-722, NMA-CBL-1132, NMA-CT-CT722, NMA-DS-723, NMA-TF-T2, NMA-VT-VT2 | 2026-11-30 07:30 | 2026-12-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161251
STK_T7 | STK T7 Transformer Protection Replacement, MP_STK_00S_0_00 | 2026-11-30 08:00 | 2026-12-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1152373
STK_C_7A | Affected Equipment of STK_767_747_707 Stage 5 - Change over DS724, 727, 747, 767, 787 secondary status | 2026-11-30 08:00 | 2026-12-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005950
BEN_220CBF | BEN 220BZ - Filter 6 Migration | 2026-11-30 08:00 | 2026-11-30 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160258
STK_R_7B | Affected Equipment of STK_767_747_707 Stage 5 - Change over DS724, 727, 747, 767, 787 secondary status | 2026-11-30 08:00 | 2026-12-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005956
STK_767_747_707 | Stage 5 - Change over DS724, 727, 747, 767, 787 secondary status | 2026-11-30 08:00 | 2026-12-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1162764
TNG_220BZ | BPE-TNG prot upgrade Stage 7: Commissioning of TNG 220kV VT selection scheme [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-11-30 08:00 | 2026-11-30 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005577
BPE_220BZ | BPE-TNG prot upgrade Stage 7: Commissioning of TNG 220kV VT selection scheme [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-11-30 08:00 | 2026-11-30 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005580
BPE_220CBF | Affected equipment of BPE_220BZ, for BPE-TNG prot upgrade Stage7 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-11-30 08:00 | 2026-11-30 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005594
STK_C_7B | Affected Equipment of STK_767_747_707 Stage 5 - Change over DS724, 727, 747, 767, 787 secondary status | 2026-11-30 08:00 | 2026-12-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005951
DRY_GLN_2 | Tower Painting | 2026-11-30 08:00 | 2026-12-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142840
STK_CB_1202 | Affected Equipment of STK_767_747_707 Stage 5 - Change over DS724, 727, 747, 767, 787 secondary status | 2026-11-30 08:00 | 2026-12-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005949
OTA_HTU_WKM_2 | Tower Painting and recoat CP_661_005_0_00 | 2026-11-30 08:00 | 2026-12-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142957
STK_R_7A | Affected Equipment of STK_767_747_707 Stage 5 - Change over DS724, 727, 747, 767, 787 secondary status | 2026-11-30 08:00 | 2026-12-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005955
STK_C_7C | Affected Equipment of STK_767_747_707 Stage 5 - Change over DS724, 727, 747, 767, 787 secondary status | 2026-11-30 08:00 | 2026-12-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005952
TNG_220CBF | Affected equipment of TNG_220BZ, for BPE-TNG prot upgrade Stage7 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-11-30 08:00 | 2026-11-30 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005593
BEN_220BZ | BEN 220BZ - Filter 6 Migration | 2026-11-30 08:00 | 2026-11-30 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160241
STK_C_7D | Affected Equipment of STK_767_747_707 Stage 5 - Change over DS724, 727, 747, 767, 787 secondary status | 2026-11-30 08:00 | 2026-12-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005953
STK_R_7 | Affected Equipment of STK_767_747_707 Stage 5 - Change over DS724, 727, 747, 767, 787 secondary status | 2026-11-30 08:00 | 2026-12-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005954
BEN_F_6 | BEN 220BZ - Filter 6 Migration | 2026-11-30 08:00 | 2026-12-04 18:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160275
PEN_T10 | Affected equipment | 2026-12-01 08:00 | 2026-12-03 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161429
PEN_FDR_122 | Affected equipment PEN_110BS_B & OTA_PEN_2 & PEN_C_14 & PEN_T10 | 2026-12-01 08:00 | 2026-12-03 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161404
PEN_CB_118 | Affected equipment PEN_110BS_B & OTA_PEN_2 & PEN_C_14 & PEN_T10 | 2026-12-01 08:00 | 2026-12-03 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161380
PEN_110BS_B | PEN-DS-117, PEN-DS-124, PEN-DS-134, PEN-DS-144, PEN-DS-164, PEN-DS-174, PEN-VT-177 | 2026-12-01 08:00 | 2026-12-03 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161368
PEN_C_12 | Affected equipment PEN_110BS_B & OTA_PEN_2 & PEN_C_14 & PEN_T10 | 2026-12-01 08:00 | 2026-12-03 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161377
OTA_PEN_2 | Affected equipment | 2026-12-01 08:00 | 2026-12-03 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161338
TMN_454_466_494 | TMN-DS-466 (TWH-1) headgear refurbishment [CP_RA3_03F_0_00]. TMN 220kV bus insulator replacements [CP_TMN_001_0_00]. | 2026-12-02 07:30 | 2026-12-04 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161656
TMN_CB_458 | Affected equipment of TMN_454_466_494 | 2026-12-02 07:30 | 2026-12-04 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161658
TMN_TWH_1 | HLY-TMN-A0070-20, HLY-TMN-A0078-20, HLY-TMN-A0168-20, HLY-TMN-A0170-20, HLY-TMN-A0173-20, HLY-TMN-A0174-20, HLY-TMN-A0176-20, HLY-TMN-A0178-20, HLY-TMN-A0179-20, HLY-TMN-A0181-20, HLY-TMN-A0183-20, HLY-TMN-A0186-20, HLY-TMN-A0191-20, HLY-TMN-A0193-20, HLY-TMN-A0194-20, HLY-TMN-A0196-20, HLY-TMN-A0200-20 | 2026-12-02 07:30 | 2026-12-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161661
HAY_T35 | S4.P2-AL.T2 | 2026-12-03 07:30 | 2026-12-03 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160630
KIK_STK_1 | Stage 5 - STK_KIK_1 Intertrip Modifications for the STK T7 Transformer Protection Replacement | 2026-12-03 07:30 | 2026-12-03 17:30 | Daily | SI | RS - Removal from Service | Approved | OW1162765
BEN_220CBF | BEN 220BZ - Filter 6 Migration | 2026-12-03 08:00 | 2026-12-04 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160259
BEN_220BZ | BEN 220BZ - Filter 6 Migration | 2026-12-03 08:00 | 2026-12-04 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160242
HAY_SC_2 | 1 yrs, HAY-SC2, HAY-SC2-CB-2A, HAY-SC2-EXC, HAY-SC2-NER, HAY-SC2-R1, HAY-SC2-ST-2, HAY-SC2-XT-2 | 2026-12-04 07:30 | 2026-12-06 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160621
ISL_FDR_272 | ISL-CB-272, ISL-DS-273, ISL-DS-275, ISL-DS-276 | 2026-12-07 06:30 | 2026-12-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160857
CST_SFD_3 | SFD-CBL-82-CST3. Tower painting x6 (A99-A100, A101-A104) [CP_752_002_0_00]. Tower recoating x13 (A56-A68) [CP_752_005_0_00]. | 2026-12-07 07:30 | 2026-12-18 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160415
TIM_T3 | TIM-CB-2752, TIM-CBL-T3-CB2752, TIM-CBL-T3-NER3, TIM-CT-CT92, TIM-P-TF-T3, TIM-RES-NER3, TIM-TF-T3, TIM-VT-VT2752 | 2026-12-07 07:30 | 2026-12-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161614
NMA_220BS_A3 | pdm maint. | 2026-12-07 07:30 | 2026-12-10 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161202
NMA_CB_708 | Affected Equipment of NMA_220BS_A3 pdm maint. | 2026-12-07 07:30 | 2026-12-10 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161222
WDV_DVK_WPW_2 | Pole replacements x4 [CP_RA4_01T_0_00]. | 2026-12-07 07:30 | 2026-12-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161767
PRM_T2 | PRM-M-CT2242, PRM-M-VT2242. Affected equipment of BPE_PRM_HAY_2. | 2026-12-07 07:30 | 2026-12-12 19:29 | Continuous | SNI | RS - Removal from Service | Approved | OW1161451
NMA_CB_718 | Affected Equipment of NMA_220BS_A3 pdm maint. | 2026-12-07 07:30 | 2026-12-10 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161230
CBG_T3 | Affected Equipment of HAM_KPO_2 HAM-KPO-A Structure Realignment | 2026-12-07 07:30 | 2026-12-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006107
HAM_KPO_2 | HAM-KPO-A Structure Realignment | 2026-12-07 07:30 | 2026-12-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006106
TNG_T3 | Corrosive Sulphur Work, requires 12 hour soak on 14/12/2026. | 2026-12-07 07:30 | 2026-12-15 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW2006349
WPW_T1 | WPW-P-TF-T1 [CP_WPW_00L_0_00]. Affected equipment of WDV_DVK_WPW_2. | 2026-12-07 07:30 | 2026-12-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161837
BPE_PRM_HAY_2 | HAY CT maintenance. Tower painting (B5-B7) [CP_768_002_0_00]. Tower recoating (B280-B288, B290) [CP_768_004_0_00]. | 2026-12-07 07:30 | 2026-12-12 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160338
SVL_FDR_2742 | SVL-CBL-2742 | 2026-12-07 07:30 | 2026-12-07 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161573
OTA_ROS_2 | OTA-CT-172, OTA-P-CB-172, OTA-PEN-B0002A-0003-20, OTA-PEN-B0003-0004-20, OTA-PEN-B0004-0005A-10, OTA-PEN-B0011A-0012-10, OTA-PEN-B0012-0013-20, OTA-PEN-B0013-0014-20, OTA-PEN-B0015-0016-20, OTA-PEN-B0016-0017-20, OTA-PEN-B0017-0018-20, OTA-PEN-B0018-0019-20, OTA-PEN-B0019-0020-20, OTA-PEN-B2-Z-CBL-SHEATH, PEN-ROS-A0025-20, PEN-ROS-A0037-20, ROS-P-CB-82 | 2026-12-07 07:30 | 2026-12-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161342
DVK_T1 | DVK-P-TF-T1, DVK-TF-T1 [CP_DVK_70_00_00]. Affected equipment ofWDV_DVK_WPW_2. | 2026-12-07 07:30 | 2026-12-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160461
KIK_STK_2 | reinsulating KIK-STK-A0064-20, KIK-STK-A0065-20, KIK-STK-A0066-20, KIK-STK-A0067-20, KIK-STK-A0068-20, KIK-STK-A0069-20, KIK-STK-A0079-20, KIK-STK-A0080-20, KIK-STK-A0082-20, KIK-STK-A0092-20, KIK-STK-A0096-20, KIK-STK-A0098-20 | 2026-12-07 07:30 | 2026-12-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1162029
BRB_HPI_1 | Tower Painting | 2026-12-07 08:00 | 2026-12-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1143183
ISL_CB_768 | Affected Equipment of ISL_66BS_A ISL-CB-272, ISL-DS-273, ISL-DS-275, ISL-DS-276 | 2026-12-07 08:00 | 2026-12-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160843
ISL_CB_708 | Affected Equipment of ISL_66BS_A ISL-CB-272, ISL-DS-273, ISL-DS-275, ISL-DS-276 | 2026-12-07 08:00 | 2026-12-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160837
BEN_220BZ | BEN 220BZ - Filter 7 Migration | 2026-12-07 08:00 | 2026-12-07 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160243
ISL_66BS_A | ISL-CB-272, ISL-DS-273, ISL-DS-275, ISL-DS-276 | 2026-12-07 08:00 | 2026-12-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160808
HEN_HPI_1 | Lines maintenance | 2026-12-07 08:00 | 2026-12-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160659
ISL_220BS_A | affected equipment ISL-DS-667, ISL-DS-677, ISL-P-CB-668 | 2026-12-07 08:00 | 2026-12-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160797
BEN_F_7 | BEN 220BZ - Filter 7 Migration | 2026-12-07 08:00 | 2026-12-11 18:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160277
MPE_CB_292 | System split for the duration of BRB_HPI_1 | 2026-12-07 08:00 | 2026-12-07 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161142
BEN_220CBF | BEN 220BZ - Filter 7 Migration | 2026-12-07 08:00 | 2026-12-07 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1160260
ISL_FDR_172 | ISL-CB-172 | 2026-12-07 08:00 | 2026-12-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160852
MPE_CB_252 | System split for the duration of BRB_HPI_1 | 2026-12-07 08:00 | 2026-12-07 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161107
ISL_CB_668 | ISL-DS-667, ISL-DS-677, ISL-P-CB-668 | 2026-12-07 08:00 | 2026-12-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160829
ISL_CB_648 | Affected Equipment of ISL_220BS_A affected equipment ISL-DS-667, ISL-DS-677, ISL-P-CB-668 | 2026-12-07 08:00 | 2026-12-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005957
STK_RTU_3 | Stage 5 - STK T7 Transformer Protection Replacement RTU Config Load | 2026-12-07 08:30 | 2026-12-07 15:30 | Daily | SI | RS - Removal from Service | Approved | OW1162768
STK_RTU_2 | Stage 5 - STK T7 Transformer Protection Replacement RTU Config Load | 2026-12-07 11:30 | 2026-12-07 15:30 | Daily | SI | RS - Removal from Service | Approved | OW1162769
STK_RTU_1 | Stage 5 - STK T7 Transformer Protection Replacement RTU Config Load | 2026-12-07 15:30 | 2026-12-07 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1162770
MPE_CB_292 | System split for the duration of BRB_HPI_1 | 2026-12-08 06:00 | 2026-12-10 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161143
MPE_CB_252 | System split for the duration of BRB_HPI_1 | 2026-12-08 06:00 | 2026-12-10 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161108
BPE_110BS_B | BPE_110BS_B | 2026-12-08 06:30 | 2026-12-08 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160315
BPE_CB_48 | Affected equipment of BPE_110BS_B | 2026-12-08 06:30 | 2026-12-08 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160324
HAY_T1 | HAY_110BZ Stage 3I; Bay 70 - Interconnector T1 (CP_HAY_IN_00_00). No other HAY work on days 1, 7, 8. No other work on associated equipment on day 8 (commissioning). HAY 11kV surge arrestor replacement (CP_RA4_03C_0_00). HAY-CT-442, HAY-CT-72, HAY-SA-1C,HAY-TF-T1, HAY-VT-VT14R. | 2026-12-08 07:00 | 2026-12-15 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162018
HAY_SC_1 | Affected equipment of HAY_T1, for HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. | 2026-12-08 07:00 | 2026-12-15 18:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1162012
HAY_R1 | Affected equipment of HAY_T1, for HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. | 2026-12-08 07:00 | 2026-12-15 18:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1162010
TNG_T11 | BPE-TNG prot upgrade Stage 8: Upgrade TNG T11 + T12 dead bus protection [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-12-08 07:30 | 2026-12-08 17:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005581
WHU_WKO_1 | WKO-CB-552 | 2026-12-08 07:30 | 2026-12-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161789
WHU_T3 | WHU-TF-T3 | 2026-12-08 07:30 | 2026-12-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161788
WRD_T7 | WRD-CBL-ET7-NER7, WRD-CBL-T7-ET7, WRD-CBL-T7-H27, WRD-CT-NCT7, WRD-NCTD-T7, WRD-RES-NER7, WRD-TF-ET7, WRD-TF-T7 | 2026-12-08 07:30 | 2026-12-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161844
IGH_KIK_2 | KIK-CB-122 GH-WPT-B0022-00, IGH-WPT-B0020-00, IGH-WPT-B0023-00,IGH-WPT-B0024-00, IGH-WPT-B0026-00, IGH-WPT-B0025-00, IGH-WPT-B0021-00 | 2026-12-08 07:30 | 2026-12-10 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160766
TNG_T12 | BPE-TNG prot upgrade Stage 8: Upgrade TNG T11 + T12 dead bus protection [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2026-12-08 07:30 | 2026-12-08 17:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005582
SVL_FDR_2762 | SVL-CBL-2762 | 2026-12-08 07:30 | 2026-12-08 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161575
STK_110BZ | Stage 5 - STK 110BZ modifications and tesing for T7 TransformerProtection Replacement | 2026-12-08 08:00 | 2026-12-08 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1162771
STK_110CBF | Stage 5 - STK 110BZ modifications and tesing for T7 TransformerProtection Replacement | 2026-12-08 08:00 | 2026-12-08 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1162772
HAY_110BZ | HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. No work in HAY 110kV yard. | 2026-12-08 08:00 | 2026-12-08 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161928
HAY_110CBF | HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. | 2026-12-08 08:00 | 2026-12-08 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161974
ISL_FDR_222 | ISL-CT-CT222, ISL-ES-229 | 2026-12-09 06:30 | 2026-12-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160855
STK_220CBF | Stage 5 - STK 220BZ modifications and tesing for T7 TransformerProtection Replacement | 2026-12-09 08:00 | 2026-12-09 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1162774
STK_220BZ | Stage 5 - STK 220BZ modifications and tesing for T7 TransformerProtection Replacement | 2026-12-09 13:00 | 2026-12-09 17:00 | Daily | SI | RS - Removal from Service | Approved | OW1162773
ISL_66BS_C | ISL-CB-272, ISL-DS-273, ISL-DS-275, ISL-DS-276 | 2026-12-10 06:30 | 2026-12-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160811
ISL_C_25 | ISL-CB-1492 | 2026-12-10 06:30 | 2026-12-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160818
ISL_220BS_F | affected equipment ISL-DS-667, ISL-DS-677, ISL-P-CB-668 | 2026-12-10 06:30 | 2026-12-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160803
ISL_CB_748 | Affected Equipment of ISL_66BS_C ISL-CB-272, ISL-DS-273, ISL-DS-275, ISL-DS-276 | 2026-12-10 06:30 | 2026-12-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160840
ISL_CB_728 | Affected Equipment of ISL_66BS_C ISL-CB-272, ISL-DS-273, ISL-DS-275, ISL-DS-276 | 2026-12-10 06:30 | 2026-12-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160839
STK_C_7B | Affected Equipment of STK_267_272_282 Stage 5 -Reinstate 272 BUS dropper back on 110kV BUS | 2026-12-10 08:00 | 2026-12-10 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005966
STK_R_7B | Affected Equipment of STK_267_272_282 Stage 5 -Reinstate 272 BUS dropper back on 110kV BUS | 2026-12-10 08:00 | 2026-12-10 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005971
BEN_220BZ | BEN 220BZ - CB408 Migration | 2026-12-10 08:00 | 2026-12-11 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160244
BEN_220CBF | BEN 220BZ - Filter 7 Migration | 2026-12-10 08:00 | 2026-12-11 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160261
STK_C_7D | Affected Equipment of STK_267_272_282 Stage 5 -Reinstate 272 BUS dropper back on 110kV BUS | 2026-12-10 08:00 | 2026-12-10 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005968
STK_C_7C | Affected Equipment of STK_267_272_282 Stage 5 -Reinstate 272 BUS dropper back on 110kV BUS | 2026-12-10 08:00 | 2026-12-10 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005967
STK_C_7A | Affected Equipment of STK_267_272_282 Stage 5 -Reinstate 272 BUS dropper back on 110kV BUS | 2026-12-10 08:00 | 2026-12-10 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005965
STK_CB_1202 | Affected Equipment of STK_267_272_282 Stage 5 -Reinstate 272 BUS dropper back on 110kV BUS | 2026-12-10 08:00 | 2026-12-10 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005964
STK_R_7A | Affected Equipment of STK_267_272_282 Stage 5 -Reinstate 272 BUS dropper back on 110kV BUS | 2026-12-10 08:00 | 2026-12-10 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005970
STK_267_272_282 | Stage 5 -Reinstate 272 BUS dropper back on 110kV BUS | 2026-12-10 08:00 | 2026-12-10 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1162776
BLN_STK_1 | Affected Equipment Stage 5 -Reinstate 272 BUS dropper back on 110kV BUS | 2026-12-10 08:00 | 2026-12-10 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1163680
STK_R_7 | Affected Equipment of STK_267_272_282 Stage 5 -Reinstate 272 BUS dropper back on 110kV BUS | 2026-12-10 08:00 | 2026-12-10 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005969
STK_T4 | Affected Equipment Stage 5 -Reinstate 272 BUS dropper back on 110kV BUS | 2026-12-10 08:00 | 2026-12-10 18:00 | Daily | SI | RS - Removal from Service | Approved | OW1163681
MPE_CB_292 | System split for the duration of BRB_HPI_1 | 2026-12-11 06:00 | 2026-12-11 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161144
MPE_CB_252 | System split for the duration of BRB_HPI_1 | 2026-12-11 06:00 | 2026-12-11 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161109
KIK_STK_2 | KIK-STK-A0100-20, KIK-STK-A0102-20, KIK-STK-A0104-20, KIK-STK-A0115-20, KIK-CVT-VT332, KIK-DS-336, KIK-ES-339, KIK-P-CB-332, KIK-STK-A0064-20, KIK-STK-A0065-20, KIK-STK-A0066-20, KIK-STK-A0067-20, KIK-STK-A0068-20, KIK-STK-A0069-20, KIK-STK-A0079-20, KIK-STK-A0080-20, KIK-STK-A0082-20, KIK-STK-A0092-20, KIK-STK-A0096-20, KIK-STK-A0098-20, KIK-STK-A0100-20, KIK-STK-A0102-20, KIK-STK-A0104-20, KIK-STK-A0115-20, STK-CVT-VT772, STK-DS-776, STK-ES-779, STK-P-CB-772 | 2026-12-14 06:30 | 2026-12-17 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160932
PEN_CB_828 | PEN-CB-828 | 2026-12-14 07:00 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161397
PEN_CB_848 | PEN-CB-848 | 2026-12-14 07:00 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161400
PAK_CB_472 | Affected Equipment of PAK_220BS_A PAK 472, 482 Siemens relay replacement | 2026-12-14 07:00 | 2026-12-14 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW2006302
PAK_CB_502 | Affected Equipment of PAK_220BS_A PAK 472, 482 Siemens relay replacement | 2026-12-14 07:00 | 2026-12-14 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW2006303
PEN_CB_8612 | Seimens Relay Replacement | 2026-12-14 07:00 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161403
PAK_PEN_3 | PEN-DS-856, PEN-ES-8549, PEN-ES-859, PEN-VT-CVT852 | 2026-12-14 07:00 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161362
PEN_CB_698 | PEN-P-CB-698 | 2026-12-14 07:00 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161389
PEN_T10 | Affected equipment | 2026-12-14 07:00 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161430
PAK_T3 | Affected Equipment of PAK_220BS_A PAK 472, 482 Siemens relay replacement | 2026-12-14 07:00 | 2026-12-14 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW2006305
PAK_R562 | Affected Equipment of PAK_220BS_A PAK 472, 482 Siemens relay replacement | 2026-12-14 07:00 | 2026-12-14 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW2006304
PAK_CB_412 | Affected Equipment of PAK_220BS_A PAK 472, 482 Siemens relay replacement | 2026-12-14 07:00 | 2026-12-14 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW2006300
PAK_CB_452 | Affected Equipment of PAK_220BS_A PAK 472, 482 Siemens relay replacement | 2026-12-14 07:00 | 2026-12-14 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW2006301
PEN_220BS_D | PEN-DS-724, PEN-DS-837, PEN-DS-847, PEN-DS-854, PEN-DS-864, PEN-ES-830, PEN-ES-840, PEN-ES-8470 | 2026-12-14 07:00 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161373
HOB_PEN_1 | HOB-VT-VT182, PEN-DS-866, PEN-ES-8649, PEN-ES-8669, PEN-ES-869,PEN-REA-862, PEN-VT-CVT862 | 2026-12-14 07:00 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160718
PAK_220BS_A | PAK 472, 482 Siemens relay replacement | 2026-12-14 07:00 | 2026-12-14 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW2006299
INV_NMA_1 | Change to INV_NMA_1 for 5 Days - INV-DS-775, 776 DS Headgear Project | 2026-12-14 07:30 | 2026-12-18 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160786
EDG_OWH_2 | Lines maintenance and pole replacement | 2026-12-14 07:30 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160478
BPE_PRM_HAY_2 | HAY CT maintenance. Tower painting (B5-B7) [CP_768_002_0_00]. Tower recoating (B280-B288, B290) [CP_768_004_0_00]. | 2026-12-14 07:30 | 2026-12-17 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160339
OWH_T1 | Affected equipment | 2026-12-14 07:30 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161359
OWH_82_92_107 | Affected equipment | 2026-12-14 07:30 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161357
ARI_HAM_2 | System split for the duration of HAM_WKM_1 | 2026-12-14 07:30 | 2026-12-18 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1160166
KPO_TMU_1 | System split for the duration of HAM_WKM_1 | 2026-12-14 07:30 | 2026-12-18 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1160984
FHL_WPW_2 | FHL-CT-132, FHL-DS-136, FHL-ES-139, FHL-P-CB-132. Pole replacements x5. Condition assessments. | 2026-12-14 07:30 | 2026-12-18 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160502
HAM_WKM_1 | HAM-CT-412, HAM-CVT-2, HAM-DEV-A0509-20, HAM-DEV-A0512-20, HAM-DS-416, HAM-ES-419, HAM-SA-412, OTA-WKM-C0188-00, OTA-WKM-C0194-00 | 2026-12-14 07:30 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160577
HAM_DIS_447 | Closed for the duration of HAM 417_437_497 bus outage | 2026-12-14 07:30 | 2026-12-18 18:30 | Continuous | NNI | CLO - Close | Approved | OW1160555
HAM_417_437_497 | HAM-DS-437 | 2026-12-14 07:30 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160546
ARI_HAM_1 | System split for the duration of HAM_WKM_1 | 2026-12-14 07:30 | 2026-12-18 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1160161
PRM_T2 | Affected equipment of BPE_PRM_HAY_2. | 2026-12-14 07:30 | 2026-12-17 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161452
MDN_CB_308 | Affected equipment MDN_257_267_297 & MDN_MPE_1 | 2026-12-14 08:00 | 2026-12-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161036
MPE_CB_292 | System split for HPI_MDN | 2026-12-14 08:00 | 2026-12-14 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161145
HPI_MDN_1 | Tower Painting | 2026-12-14 08:00 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1143187
HAY_110BZ | HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. No work in HAY 110kV yard. | 2026-12-14 08:00 | 2026-12-14 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161929
MDN_257_267_297 | MDN-DS-267, MDN-DS-274, MDN-DS-294, MDN-DS-297 | 2026-12-14 08:00 | 2026-12-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161032
HAY_110CBF | HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. | 2026-12-14 08:00 | 2026-12-14 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161975
MDN_MPE_1 | MDN-CT-292, MDN-DS-296, MDN-ES-299, MDN-MPE-A0012-0013-00, MDN-MPE-A0013-0014-00, MDN-MPE-A0054-0055-00, MDN-MPE-A0074-0075-10,MDN-MPE-A0075-0076-10, MDN-MPE-A0076-0077-10, MDN-MPE-A0079-0080-10, MDN-MPE-A0082-0083-10, MDN-MPE-A0084-MPEG5-10, MDN-P-CB-292, MDN-VT-VT292, MPE-DS-316, MPE-ES-319, MPE-P-CB-312 | 2026-12-14 08:00 | 2026-12-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161041
MDN_T5 | Affected equipment MDN_257_267_297 & MDN_MPE_1 | 2026-12-14 08:00 | 2026-12-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161045
MDN_LST_5B | Affected equipment MDN T5 | 2026-12-14 08:00 | 2026-12-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1163028
MDN_STC_5 | Affected equipment MDN T5 | 2026-12-14 08:00 | 2026-12-16 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1163027
MPE_CB_252 | System split for HPI_MDN | 2026-12-14 08:00 | 2026-12-14 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161110
MPE_CB_292 | System split for HPI_MDN | 2026-12-15 06:00 | 2026-12-17 22:00 | Continuous | NNI | OPE - Open Ended | Approved | OW1161146
MPE_CB_252 | System split for HPI_MDN | 2026-12-15 06:00 | 2026-12-17 22:00 | Continuous | NNI | OPE - Open Ended | Approved | OW1161111
KIK_STC_2A | KIK-CAPS-K11-C1, KIK-CAPS-K11-C2 | 2026-12-15 06:30 | 2026-12-15 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160929
HAY_110BZ | HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. No work in HAY 110kV yard. | 2026-12-15 08:00 | 2026-12-15 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161930
HAY_110CBF | HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. | 2026-12-15 08:00 | 2026-12-15 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161976
KMO_127_167_177 | KMO-CB-178, KMO-CT-178 | 2026-12-16 07:30 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160957
KMO_CB_138 | Affected equipment KMO_127_167_177 & KMO_MTM_TGA_2 | 2026-12-16 07:30 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160961
KMO_CB_178 | Affected equipment KMO_127_167_177 & KMO_MTM_TGA_2 | 2026-12-16 07:30 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160962
KMO_MTM_TGA_2 | HAI-MTM-B0020-0021-10 | 2026-12-16 07:30 | 2026-12-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160970
MPE_CB_292 | System split for HPI_MDN | 2026-12-18 06:00 | 2026-12-18 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161147
MPE_CB_252 | System split for HPI_MDN | 2026-12-18 06:00 | 2026-12-18 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161112
HAY_R5 | HAY-CB-R52, HAY-ES-R559, HAY-ES-R59, HAY-REA-R5 | 2027-01-05 07:30 | 2027-01-07 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160617
TKU_WKM_1 | TKU-WKM Duplexing project. (CP_VAR_1DF_0_00) | 2027-01-11 07:00 | 2027-05-14 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1140941
CST_HUI_1 | Tower recoating x10 (A1-A10) [CP_750_001_0_00]. | 2027-01-11 07:30 | 2027-01-22 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160411
HLY_CB_642 | Affected equipment HLY_357_524_644 | 2027-01-11 07:30 | 2027-01-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160709
HLY_357_524_644 | HLY-DS-644 | 2027-01-11 07:30 | 2027-01-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160701
HLY_CB_582 | Affected equipment HLY_357_524_644 | 2027-01-11 07:30 | 2027-01-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160708
HLY_CB_522 | Affected equipment HLY_357_524_644 | 2027-01-11 07:30 | 2027-01-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160707
GFD_T6 | GFD-CBL-2152-LS6, GFD-CBL-T6-2152, GFD-CBL-T6-NER6, GFD-CBL-TS-T6, GFD-DS-94, GFD-ES-99, GFD-RES-NER6, GFD-TF-LS-LS6, GFD-TF-T6, GFD-VT-92 | 2027-01-12 07:00 | 2027-02-01 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1160510
HAY_T2 | HAY_110BZ Stage 3J; Bay 110 - Interconnector T2 (CP_HAY_IN_00_00). No other HAY work on days 1, 7, 8. No other work on associated equipment on day 8 (commissioning).HAY 11kV surge arrestor replacement (CP_RA4_03C_0_00).HAY-CT-112, HAY-CT-462, HAY-SA-2C, HAY-TF-T2. | 2027-01-12 07:00 | 2027-01-19 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162021
HAY_SC_2 | Affected Equipment of HAY_T2, for HAY_110BZ Stage 3J; Bay 110 -Interconnector T2. | 2027-01-12 07:00 | 2027-01-19 18:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1162013
GFD_HAY_1 | TF-SSC works. Affected equipment of GFD_T6. | 2027-01-12 07:00 | 2027-02-01 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1161901
HRP_TAB_1 | Tower works x21 (A57, A63-A64, A68, A88, A99, A101, A104-A105, A111-A112, A119, A122, A129, A141, A156, A158-A160). RSA4 Re-insulation x3. | 2027-01-12 07:30 | 2027-01-15 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160727
HEN_SWN_1 | Affected equipment with SWN 220 bus | 2027-01-12 07:30 | 2027-01-12 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1162465
BPE_PRM_HAY_1 | HAY CT, DS maintenance. Tower painting (A4-A9) [CP_767_001_0_00]. | 2027-01-12 07:30 | 2027-01-16 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160337
OTA_SWN_1 | Affected equipment with SWN 220 bus | 2027-01-12 07:30 | 2027-01-12 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1162464
SWN_220BS | SWN-CBL-T2-NER2, SWN-DS-254, SWN-DS-3046, SWN-ES-3049, SWN-P-TF-T2, SWN-RES-NER2, SWN-TF-T2, SWN-VT-VT3042 | 2027-01-12 07:30 | 2027-01-12 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1162463
PRM_T1 | PRM-M-CT2162, PRM-M-VT2162. Affected equipment of BPE_PRM_HAY_1. | 2027-01-12 07:30 | 2027-01-16 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161450
HWB_TMH_1 | HWB-SDN-A0003-20, HWB-SDN-A0004-20 | 2027-01-12 07:30 | 2027-01-15 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160762
KOE_MPE_1 | KOE-CT-162, KOE-DS-166, KOE-ES-169, KOE-MPE-A0024-00, KOE-MPE-A0048-00, KOE-MPE-A0062-10, KOE-MPE-A0070-10, KOE-MPE-A0084-10, KOE-MPE-A0088-00, KOE-MPE-A0126-10, KOE-P-CB-162, MPE-CT-322, MPE-DS-326, MPE-ES-329, MPE-P-CB-322 | 2027-01-12 07:30 | 2027-01-15 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160977
SWN_T2 | SWN-CBL-T2-NER2, SWN-DS-254, SWN-DS-3046, SWN-ES-3049, SWN-P-TF-T2, SWN-RES-NER2, SWN-TF-T2, SWN-VT-VT3042 | 2027-01-12 07:30 | 2027-01-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161590
HAY_110CBF | HAY_110BZ Stage 3J; Bay 110 - Interconnector T2. No work in HAY110kV yard. | 2027-01-12 08:00 | 2027-01-12 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161977
HAY_110BZ | HAY_110BZ Stage 3J; Bay 110 - Interconnector T2. No work in HAY110kV yard. | 2027-01-12 08:00 | 2027-01-12 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161931
KWA_CB_8 | Affected Equipment of KWA_WIL_1 Project: KWA WIL Line Protection Upgrade Code: CP_WIL_013_0_00 and CP_KWA_003_0_00 TP Project Manager: Claire Steele | 2027-01-13 07:00 | 2027-01-27 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2005777
KWA_WIL_1 | Project: KWA WIL Line Protection Upgrade Code: CP_WIL_013_0_00 and CP_KWA_003_0_00 TP Project Manager: Claire Steele | 2027-01-13 07:00 | 2027-01-27 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2005775
KWA_AVR_T2 | Affected Equipment of KWA_WIL_1 Project: KWA WIL Line Protection Upgrade Code: CP_WIL_013_0_00 and CP_KWA_003_0_00 TP Project Manager: Claire Steele | 2027-01-13 07:00 | 2027-01-27 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2005776
KWA_T2 | Affected Equipment of KWA_WIL_1 Project: KWA WIL Line Protection Upgrade Code: CP_WIL_013_0_00 and CP_KWA_003_0_00 TP Project Manager: Claire Steele | 2027-01-13 07:00 | 2027-01-27 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2005778
ISL_FDR_962 | Affected Equipment of ISL_T1 ISL-NCTD-T1 | 2027-01-13 07:30 | 2027-01-15 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005101
ISL_33BS_A | Affected Equipment of ISL_T1 ISL-NCTD-T1 | 2027-01-13 07:30 | 2027-01-15 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160807
ISL_T1 | ISL-NCTD-T1 | 2027-01-13 07:30 | 2027-01-15 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160867
ISL_FDR_882 | Affected Equipment of ISL_T1 ISL-NCTD-T1 | 2027-01-13 07:30 | 2027-01-15 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005099
ISL_LST_7 | Affected Equipment of ISL_T1 ISL-NCTD-T1 | 2027-01-13 07:30 | 2027-01-15 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005104
MLG_FDR_8 | MLG-CB-8, MLG-P-CB-8 | 2027-01-13 07:30 | 2027-01-13 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161065
ISL_LST_3 | Affected Equipment of ISL_T1 ISL-NCTD-T1 | 2027-01-13 07:30 | 2027-01-15 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005103
ISL_FDR_1032 | Affected Equipment of ISL_T1 ISL-NCTD-T1 | 2027-01-13 07:30 | 2027-01-15 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160847
ISL_FDR_1022 | Affected Equipment of ISL_T1 ISL-NCTD-T1 | 2027-01-13 07:30 | 2027-01-15 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160846
ISL_FDR_932 | Affected Equipment of ISL_T1 ISL-NCTD-T1 | 2027-01-13 07:30 | 2027-01-15 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005100
WAI_T2 | 5 yrs, WAI-CB-112, WAI-CB-2742, WAI-CBL-2742, WAI-CT-112, WAI-TF-T2B, WAI-VT-2742 | 2027-01-13 07:30 | 2027-01-15 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161757
ISL_FDR_972 | Affected Equipment of ISL_T1 ISL-NCTD-T1 | 2027-01-13 07:30 | 2027-01-15 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005102
ISL_CB_2058 | Affected Equipment of ISL_T1 ISL-NCTD-T1 | 2027-01-13 07:30 | 2027-01-15 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160821
WAI_CB_1362 | Affected equipment WAI_T2 | 2027-01-13 07:30 | 2027-01-15 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161753
WIL_118_188 | Remove DCB 162 Bus Droppers. KWA WIL Line Protection Upgrade. | 2027-01-13 08:00 | 2027-01-13 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005783
MLG_FDR_9 | MLG-CB-9, MLG-P-CB-9 | 2027-01-14 07:30 | 2027-01-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161066
TKA_T1 | TKA-CT-CT1042, TKA-CT-T1 | 2027-01-15 07:30 | 2027-01-15 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161621
SVL_FDR_2842 | SVL-CBL-2842 | 2027-01-15 07:30 | 2027-01-15 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161581
MLG_FDR_11 | MLG-CB-11, MLG-P-CB-11 | 2027-01-15 07:30 | 2027-01-15 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161061
TMI_LST_1 | TMI-TF-LS1 | 2027-01-15 07:30 | 2027-01-15 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161649
TKB_TWZ_1 | CA Lifting | 2027-01-18 07:30 | 2027-01-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161624
WIR_706_714_697 | Affected equipment | 2027-01-18 07:30 | 2027-01-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2006465
PAO_CB_232 | Affected equipment HAM_PAO_WHU_2 | 2027-01-18 07:30 | 2027-01-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161365
MHO_T3 | Affected equipment of BPE_MHO_1, for shelterbelt tree works andconductor repairs [MP_RA4_03N_0_00]. | 2027-01-18 07:30 | 2027-01-23 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161055
MAN_NMA_1 | Tower Painting• 18th - 22nd Jan 2027 - MAN_NMA_1 - Tower Painting Outage Window, we would like to use this outage thanks for the replacement of attachment points. | 2027-01-18 07:30 | 2027-01-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143113
OTA_WIR_1 | BOB-OTA-A0117B-00 | 2027-01-18 07:30 | 2027-01-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161349
ALB_FDR_322 | Affected equipment with ALB T5 | 2027-01-18 07:30 | 2027-01-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162980
BAL_GOR_1 | GOR-HWB-A0014-00, GOR-HWB-A0044-00, GOR-HWB-A0060-00, GOR-HWB-A0077-00, GOR-HWB-A0101-0102-10, GOR-HWB-A0116-00, GOR-HWB-A0117-00, GOR-HWB-A0120-00, GOR-HWB-A0128-00, GOR-HWB-A0139-00, GOR-HWB-A0189-00, GOR-HWB-A0196-00, GOR-HWB-A0213-00, GOR-HWB-A0218-00, GOR-HWB-A0249-00, GOR-HWB-A0250-00 | 2027-01-18 07:30 | 2027-01-22 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160202
BPE_MHO_1 | Shelterbelt tree works. Conductor repairs [MP_RA4_03N_0_00]. | 2027-01-18 07:30 | 2027-01-23 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160331
BPE_BRK_2 | BPE-DS-786 (BRK_2), BRK-CT-622, BRK-CVT-622, BRK-DS-613 (BPE_2), BRK-DS-625 (BPE_2), BRK-DS-626 (BPE_2), BRK-ES-629, BRK-P-CB-612/622. 1 day lines-free. Tower recoating (A68-A73, A75-A76). | 2027-01-18 07:30 | 2027-01-29 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160323
ALB_204_324_334 | Affected equipment with ALB T5 | 2027-01-18 07:30 | 2027-01-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162596
ALB_FDR_262 | ALB-M-CT262 | 2027-01-18 07:30 | 2027-01-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160130
ALB_T5 | Tap changer maintenance (Reinhausen). | 2027-01-18 07:30 | 2027-01-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162595
WIR_T2 | Affected equipment | 2027-01-18 07:30 | 2027-01-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161804
TWZ_CB_2572 | Bus Post Remediation Works | 2027-01-18 07:30 | 2027-01-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1162123
KAW_T5 | KAW T5 protection replacement. KAW-P-TF-T5, KAW-TF-T5 | 2027-01-18 07:30 | 2027-01-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160910
HAM_PAO_WHU_2 | HAM-WHU-A0014-20, HAM-WHU-A0019-20, HAM-WHU-A0020-20, HAM-WHU-A0021-20, HAM-WHU-A0025-20, HAM-WHU-A0027-20, HAM-WHU-A0028-20, HAM-WHU-A0029-20, HAM-WHU-A0030-20, HAM-WHU-A0031-20, HAM-WHU-A0033-20, HAM-WHU-A0036-20, HAM-WHU-A0037-20, HAM-WHU-A0039-20, HAM-WHU-A0070-20, HAM-WHU-A0077-20, HAM-WHU-A0080-20, HAM-WHU-A0085-20, PAO-DCB-232 | 2027-01-18 07:30 | 2027-01-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160566
ALB_FDR_302 | ALB-CB-302, ALB-CT-302, ALB-DS-306, ALB-ES-309, ALB-DS-304 | 2027-01-18 07:30 | 2027-01-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160131
BEN_T36 | S1.20T36-T36 | 2027-01-18 07:30 | 2027-01-20 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160285
MLG_FDR_12 | MLG-CB-12, MLG-P-CB-12 | 2027-01-18 07:30 | 2027-01-18 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161062
ALB_204_297_317 | ALB-DS-264, ALB-VT-2, ALB-DS-204, ALB-DS-277, ALB-DS-297 | 2027-01-18 07:30 | 2027-01-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160122
HAY_SC_8_T8 | HAY-SC8, HAY-SC8-EXC, HAY-SC8-NER, HAY_110BZ Stage 3O; Bay 120 - Transformer T8. No other work on days 1, 4, 5. No other work on associated equipment/lines on day 5 (commissioning). | 2027-01-18 07:30 | 2027-01-29 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160623
BRB_HPI_1 | Tower painting | 2027-01-18 08:00 | 2027-01-22 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1143186
HAY_110BZ | HAY_110BZ Stage 3J; Bay 110 - Interconnector T2. No work in HAY110kV yard. | 2027-01-18 08:00 | 2027-01-18 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161932
HAY_110CBF | HAY_110BZ Stage 3J; Bay 110 - Interconnector T2. | 2027-01-18 08:00 | 2027-01-18 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161978
MPE_CB_292 | System split for the duration of BRB_HPI | 2027-01-18 08:00 | 2027-01-18 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161148
MPE_CB_252 | System split for the duration of BRB_HPI | 2027-01-18 08:00 | 2027-01-18 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161113
HAM_T7 | replace bushings and carry out mid life refurbishment, includesrepainting, replacement of control and indication cubicle, replacement of some ancillary equipment, testing post bushing replacement work. Nissin Type FGCH Painted Steel CTs Inspection | 2027-01-18 08:30 | 2027-02-19 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1145699
MPE_CB_292 | System split for the duration of BRB_HPI | 2027-01-19 06:00 | 2027-01-21 22:00 | Continuous | NNI | OPE - Open Ended | Approved | OW1161149
MPE_CB_252 | System split for the duration of BRB_HPI | 2027-01-19 06:00 | 2027-01-21 22:00 | Continuous | NNI | OPE - Open Ended | Approved | OW1161114
BEN_F_5 | S1.20DB72-FB5, S1.20DB72-Q02 | 2027-01-19 07:30 | 2027-01-21 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160274
TKU_T22 | TKU-M-VT22, TKU-P-TF-T22 | 2027-01-19 07:30 | 2027-01-28 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161643
HAY_110BZ | HAY_110BZ Stage 3J; Bay 110 - Interconnector T2. No work in HAY110kV yard. | 2027-01-19 08:00 | 2027-01-19 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161933
HAY_110CBF | HAY_110BZ Stage 3J; Bay 110 - Interconnector T2. | 2027-01-19 08:00 | 2027-01-19 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161979
ALB_CB_818 | ALB-P-CB-818 | 2027-01-20 07:30 | 2027-01-20 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160129
MLG_FDR_10 | MLG-CB-10, MLG-P-CB-10 | 2027-01-20 07:30 | 2027-01-21 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161060
BEN_HAY_2 | BEN-HAY-A0827-20, BEN-HAY-A0828-20, BEN-HAY-A0834-20, BEN-HAY-A1482-20, BEN-HAY-A1513-20, BEN-HAY-A1526-20, FTB-P-P2-CSI, FTB-P2-BU-1, OTB-HAY-A0002-20, OTB-HAY-A0004-20, OTB-HAY-A0064A-30, OTB-P2-SA-3 | 2027-01-20 07:30 | 2027-01-21 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160279
STK_RTU_1 | STK T7 Transformer Protection Replacement RTU Tidy Up Config Load | 2027-01-21 11:30 | 2027-01-21 15:30 | Daily | SI | RS - Removal from Service | Approved | OW1162777
STK_RTU_3 | STK T7 Transformer Protection Replacement RTU Tidy Up Config Load | 2027-01-21 11:30 | 2027-01-21 15:30 | Daily | SI | RS - Removal from Service | Approved | OW1162779
STK_RTU_2 | STK T7 Transformer Protection Replacement RTU Tidy Up Config Load | 2027-01-21 11:30 | 2027-01-21 15:30 | Daily | SI | RS - Removal from Service | Approved | OW1162778
MPE_CB_252 | System split for the duration of BRB_HPI | 2027-01-22 06:00 | 2027-01-22 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161115
MPE_CB_292 | System split for the duration of BRB_HPI | 2027-01-22 06:00 | 2027-01-22 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161150
STK_C_32 | STK-CAPS-C32, STK-CBL-2192-C32, STK-REA-C32 | 2027-01-22 06:30 | 2027-01-22 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161556
TIM_11TIE_A_C | TIM-CBL-CB2728-2968, TIM-VT-VT2968 | 2027-01-22 07:30 | 2027-01-22 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161608
APS_CLH_1 | COL-OTI-A0240-00, COL-OTI-A0241-00, COL-OTI-A0242-00, COL-OTI-A0361-0362-10, COL-OTI-A0382-00, COL-OTI-A0396-00 | 2027-01-25 06:30 | 2027-01-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160138
BRY_857_897_867 | BRY-DS-884. CY4 Maintenance Re-planned. | 2027-01-25 06:30 | 2027-01-29 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159786
ASB_BRY_1 | Affected Equipment BRY-DS-884. CY4 Maintenance Re-planned. includes lines 7 days ASB-DS-386, BRY-P-CB-892, CHH-TWZ-A0306-00, CHH-TWZ-A0307-00, CHH-TWZ-A0308-00, CHH-TWZ-A0308-10 | 2027-01-25 06:30 | 2027-01-31 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159787
BRY_CB_878 | Affected Equipment BRY-DS-884. CY4 Maintenance Re-planned. | 2027-01-25 06:30 | 2027-01-29 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159788
BRY_C_7A | Affected Equipment BRY-DS-884. CY4 Maintenance Re-planned. | 2027-01-25 06:30 | 2027-01-29 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159789
BRY_T7 | Affected Equipment BRY-DS-884. CY4 Maintenance Re-planned. | 2027-01-25 06:30 | 2027-01-29 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159790
COL_OTI_2 | Affected equipment APS_CLH_1 | 2027-01-25 06:30 | 2027-01-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160395
BAL_GOR_1 | GOR-HWB-A0101-0102-10 GOR-HWB-A0196-00 GOR-HWB-A0213-00 GOR-HWB-A0218-00 GOR-HWB-A0249-00 GOR-HWB-A0250-00 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160203
BDE_11CBF | BDE-P-BZ-11 | 2027-01-25 07:30 | 2027-01-26 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160209
ROT_DIS_357 | Closed for the duration of ROT_TRK_1 | 2027-01-25 07:30 | 2027-02-05 18:30 | Continuous | NNI | CLO - Close | Approved | OW1161495
ROT_DIS_367 | Closed for the duration of ROT_TRK_1 | 2027-01-25 07:30 | 2027-02-05 18:30 | Continuous | NNI | CLO - Close | Approved | OW1161496
SVL_33BS_A | Feeder Protection upgrade | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161569
SVL_FDR_2782 | Affected Equipment of SVL_33BS_A | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161578
SVL_FDR_2762 | Affected Equipment of SVL_33BS_A | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161576
SVL_FDR_2742 | Affected Equipment of SVL_33BS_A | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161574
BDE_11BZ | BDE-P-BZ-11 | 2027-01-25 07:30 | 2027-01-26 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160208
SVL_CB_2808 | Affected Equipment of SVL_33BS_A | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161571
CST_HUI_2 | Tower recoating x10 (A1-A10) [CP_750_001_0_00]. | 2027-01-25 07:30 | 2027-02-05 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160412
BEN_F_3 | BEN 220BZ - Filter 3 Migration | 2027-01-25 07:30 | 2027-02-02 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW2005432
SVL_T1 | Affected equipment ALB_587_597_637 & ALB_SVL_1 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161589
NMA_TWI_2 | MAN-TWI-A0324-0325-20, MAN-TWI-A0354-20, MAN-TWI-A0359-20, MAN-TWI-A0360-20, MAN-TWI-A0373-20, MAN-TWI-A0379-20, MAN-TWI-A0388-20, MAN-TWI-A0389-0390-20, MAN-TWI-A0394-20, MAN-TWI-A0396-0397-20, MAN-TWI-A0397-0398-20, NMA-CT-CT752, TWI-SA-3, FM3 roller door servicing | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161253
NMA_CB_738 | Affected Equipment of NMA_220BS_A4 MAN-TWI-A0324-0325-20, MAN-TWI-A0354-20, MAN-TWI-A0359-20, MAN-TWI-A0360-20, MAN-TWI-A0373-20, MAN-TWI-A0379-20, MAN-TWI-A0388-20, MAN-TWI-A0389-0390-20, MAN-TWI-A0394-20, MAN-TWI-A0396-0397-20, MAN-TWI-A0397-0398-20, NMA-CT-CT752, TWI-SA-3, FM3 roller door servicing | 2027-01-25 07:30 | 2027-01-26 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161240
ALB_SVL_1 | ALB-CVT-592, ALB-DS-596, ALB-ES-599, ALB-SVL-A0002-20, ALB-SVL-A0004-10, ALB-SVL-A0005-00, ALB-SVL-A0005-10, ALB-SVL-A0010-10, ALB-SVL-A0013-00, ALB-SVL-A0016-00, ALB-SVL-A0018-10, ALB-SVL-A0020-00, ALB-SVL-A0021-00, ALB-SVL-A0022-00, ALB-SVL-A0025-00, ALB-SVL-A0028-10, ALB-SVL-A0029-00, Tower painting | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160135
NMA_CB_718 | Affected Equipment of NMA_220BS_A4 MAN-TWI-A0324-0325-20, MAN-TWI-A0354-20, MAN-TWI-A0359-20, MAN-TWI-A0360-20, MAN-TWI-A0373-20, MAN-TWI-A0379-20, MAN-TWI-A0388-20, MAN-TWI-A0389-0390-20, MAN-TWI-A0394-20, MAN-TWI-A0396-0397-20, MAN-TWI-A0397-0398-20, NMA-CT-CT752, TWI-SA-3, FM3 roller door servicing | 2027-01-25 07:30 | 2027-01-26 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161231
KAW_T6 | KAW T6 Protection replacement. KAW-DS-1097, KAW-NCT-ET6, KAW-P-TF-T6 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160912
ROT_TRK_1 | Line Protection replacement and bus zone installation TRK-P-CB-162 | 2027-01-25 07:30 | 2027-02-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161507
MAN_NMA_2 | Tower Painting • 25th to 30th Jan 2027 - MAN-NMA_2 - I neededto check our resources for this outage window, yes, we are all good so we will use this outage, again we are replacing attachment points. | 2027-01-25 07:30 | 2027-01-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143116
TMU_T2 | TMU-TF-T2 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161673
TMU_CB_2812 | TMU-CB-2812 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161666
NMA_220BS_A4 | MAN-TWI-A0324-0325-20, MAN-TWI-A0354-20, MAN-TWI-A0359-20, MAN-TWI-A0360-20, MAN-TWI-A0373-20, MAN-TWI-A0379-20, MAN-TWI-A0388-20, MAN-TWI-A0389-0390-20, MAN-TWI-A0394-20, MAN-TWI-A0396-0397-20, MAN-TWI-A0397-0398-20, NMA-CT-CT752, TWI-SA-3, FM3 roller door servicing | 2027-01-25 07:30 | 2027-01-26 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161207
MPE_CB_252 | System split with HPI_MDN | 2027-01-25 08:00 | 2027-01-25 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161116
BEN_220BZ | BEN 220BZ - Filter 3 Migration | 2027-01-25 08:00 | 2027-01-25 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005433
BEN_220CBF | BEN 220BZ - Filter 3 Migration | 2027-01-25 08:00 | 2027-01-25 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005434
HPI_MDN_1 | Tower Painting | 2027-01-25 08:00 | 2027-01-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1143188
MNG_T2 | Tap changer maintenance (Reinhausen). | 2027-01-25 08:00 | 2027-01-27 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162594
MPE_CB_292 | System split with HPI_MDN | 2027-01-25 08:00 | 2027-01-25 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161151
MPE_CB_252 | System split with HPI_MDN | 2027-01-26 06:00 | 2027-01-28 22:00 | Continuous | NNI | OPE - Open Ended | Approved | OW1161117
MPE_CB_292 | System split with HPI_MDN | 2027-01-26 06:00 | 2027-01-28 22:00 | Continuous | NNI | OPE - Open Ended | Approved | OW1161152
MLG_FDR_6 | MLG-CB-6, MLG-P-CB-6. | 2027-01-26 07:00 | 2027-01-27 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161063
WDV_DVK_WPW_1 | Pole replacements x4 | 2027-01-26 07:30 | 2027-01-29 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161766
MTN_T1 | MTN-TF-T1. 12-hour heat soak on last day. | 2027-01-26 07:30 | 2027-02-05 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161179
KIK_STC_2 | KIK-STC-2A, KIK-STC-2B, KIK-TF-LS6-K13-T6 | 2027-01-26 07:30 | 2027-01-27 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160928
KIK_T2 | KIK-P-TF-T2, KIK-TF-T2 | 2027-01-26 07:30 | 2027-01-27 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160936
WPW_T2 | Affected equipment of WDV_DVK_WPW_1 | 2027-01-26 07:30 | 2027-01-29 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161842
KIK_220BS_A | KIK-DS-373 Disconnector & Earth Switch type Hapam SSB-III = Contact Alignment and Re-greasing (2019089) 500648677 | 2027-01-26 07:30 | 2027-01-26 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1163095
DVK_T2 | Affected equipment of WDV_DVK_WPW_1 | 2027-01-26 07:30 | 2027-01-29 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160466
WIL_118_188 | Reconnect DCB 162 Bus Droppers. KWA WIL Line Protection Upgrade. | 2027-01-26 08:00 | 2027-01-26 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005784
HAY_T5 | HAY_110BZ Stage 3K; Bay 290 - Interconnector T5 (CP_HAY_IN_00_00). No other HAY work on days 1, 7, 8. No other work on associated equipment on day 8 (commissioning). HAY 11kV surge arrestor replacement (CP_RA4_03C_0_00). HAY-CT-292, HAY-CT-622, HAY-SA-5C, HAY-TF-T5 | 2027-01-27 07:00 | 2027-02-03 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162022
HAY_SC_4 | Affected equipment of HAY_T5, for HAY_110BZ Stage 3K; Bay 290 -Interconnector T5. | 2027-01-27 07:00 | 2027-02-03 18:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1162015
HAY_SC_3 | Affected equipment of HAY_T5, for HAY_110BZ Stage 3K; Bay 290 -Interconnector T5. | 2027-01-27 07:00 | 2027-02-03 18:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1162014
HAY_R5 | HAY-CB-R52, HAY-ES-R559, HAY-ES-R59, HAY-REA-R5. Affected equipment of HAY_T5, for HAY_110BZ Stage 3K; Bay 290 - InterconnectorT5. | 2027-01-27 07:00 | 2027-02-03 18:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1162011
ROT_11BS_A | ROT-M-CT2742, ROT-M-VT2742 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161489
KIK_220BS_B | KIK-DS-375 Disconnector & Earth Switch type Hapam SSB-III = Contact Alignment and Re-greasing (2019178) 500648583 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1163096
NMA_687_835 | MAN-TWI-A0324-0325-20, MAN-TWI-A0354-20, MAN-TWI-A0359-20, MAN-TWI-A0360-20, MAN-TWI-A0373-20, MAN-TWI-A0379-20, MAN-TWI-A0388-20, MAN-TWI-A0389-0390-20, MAN-TWI-A0394-20, MAN-TWI-A0396-0397-20, MAN-TWI-A0397-0398-20, NMA-CT-CT752, TWI-SA-3, FM3 roller door servicing | 2027-01-27 07:30 | 2027-01-29 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161213
KIK_CB_328 | Affected Equipment of KIK_220BS_B KIK-DS-375 Disconnector & Earth Switch type Hapam SSB-III = Contact Alignment and Re-greasing(2019178) 500648583 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005208
ROT_T4 | ROT-M-CT2742, ROT-M-VT2742 | 2027-01-27 07:30 | 2027-01-28 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161506
ROT_CB_2778 | Affected Equipment of ROT_11BS_A ROT-M-CT2742, ROT-M-VT2742 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161494
KIK_CB_398 | Affected Equipment of KIK_220BS_B KIK-DS-375 Disconnector & Earth Switch type Hapam SSB-III = Contact Alignment and Re-greasing(2019178) 500648583 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005209
ROT_FDR_2762 | Affected Equipment of ROT_11BS_A ROT-M-CT2742, ROT-M-VT2742 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161502
ROT_FDR_2702 | Affected Equipment of ROT_11BS_A ROT-M-CT2742, ROT-M-VT2742 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161497
ROT_FDR_2712 | Affected Equipment of ROT_11BS_A ROT-M-CT2742, ROT-M-VT2742 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161498
ROT_FDR_2722 | Affected Equipment of ROT_11BS_A ROT-M-CT2742, ROT-M-VT2742 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161499
NMA_CB_738 | Affected Equipment of NMA_687_835 MAN-TWI-A0324-0325-20, MAN-TWI-A0354-20, MAN-TWI-A0359-20, MAN-TWI-A0360-20, MAN-TWI-A0373-20, MAN-TWI-A0379-20, MAN-TWI-A0388-20, MAN-TWI-A0389-0390-20, MAN-TWI-A0394-20, MAN-TWI-A0396-0397-20, MAN-TWI-A0397-0398-20, NMA-CT-CT752, TWI-SA-3, FM3 roller door servicing | 2027-01-27 07:30 | 2027-01-29 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161241
ROT_FDR_2732 | Affected Equipment of ROT_11BS_A ROT-M-CT2742, ROT-M-VT2742 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161500
ROT_FDR_2752 | Affected Equipment of ROT_11BS_A ROT-M-CT2742, ROT-M-VT2742 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161501
HAY_110BZ | HAY_110BZ Stage 3K; Bay 290 - Interconnector T5. No work in HAY110kV yard. | 2027-01-27 08:00 | 2027-01-27 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161934
HAY_110CBF | HAY_110BZ Stage 3K; Bay 290 - Interconnector T5. | 2027-01-27 08:00 | 2027-01-27 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161980
MLG_FDR_7 | MLG-CB-7, MLG-P-CB-7. | 2027-01-28 07:00 | 2027-01-29 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161064
PAK_CB_462 | Affected Equipment of PAK_220BS_B PAK 492 Siemens relay replacement | 2027-01-28 07:30 | 2027-01-28 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW2006316
PAK_WKM_1 | BHL-PAK-A-CBL-SHEATH, WKM-CVT-502 | 2027-01-28 07:30 | 2027-01-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161363
PAK_CB_522 | Affected Equipment of PAK_220BS_B PAK 492 Siemens relay replacement | 2027-01-28 07:30 | 2027-01-28 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW2006318
PEN_FDR_2362 | PEN-CB-2362, PEN-P-CB-2362 | 2027-01-28 07:30 | 2027-01-28 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161414
PAK_CB_432 | Affected Equipment of PAK_220BS_B PAK 492 Siemens relay replacement | 2027-01-28 07:30 | 2027-01-28 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW2006315
PAK_R582 | Affected Equipment of PAK_220BS_B PAK 492 Siemens relay replacement | 2027-01-28 07:30 | 2027-01-28 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW2006319
PAK_CB_492 | Affected Equipment of PAK_220BS_B PAK 492 Siemens relay replacement | 2027-01-28 07:30 | 2027-01-28 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW2006317
PAK_220BS_B | PAK 492 Siemens relay replacement | 2027-01-28 07:30 | 2027-01-28 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW2006314
MPE_CB_292 | System split with HPI_MDN | 2027-01-29 06:00 | 2027-01-29 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161153
MPE_CB_252 | System split with HPI_MDN | 2027-01-29 06:00 | 2027-01-29 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161118
PEN_FDR_2542 | PEN-CB-2542, PEN-P-CB-2542 | 2027-01-29 07:30 | 2027-01-29 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161421
ISL_220BS_D | BRY-ISL-A0044-0045-20, BRY-ISL-A0057-0057A-20, ISL-DS-435, dampers and spacers | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005107
OHW_WKM_1 | Spacer replacement project. OTA-WKM-C0298-0299-20, OTA-WKM-C0300-0301-20 and Tower painting | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161285
ISL_CB_658 | Affected Equipment of ISL_220BS_D BRY-ISL-A0044-0045-20, BRY-ISL-A0057-0057A-20, ISL-DS-435, dampers and spacers | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005109
BRB_T3 | BRB-CBL-182, BRB-TF-T3 | 2027-02-01 07:30 | 2027-02-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160357
ISL_CB_608 | Affected Equipment of ISL_220BS_D BRY-ISL-A0044-0045-20, BRY-ISL-A0057-0057A-20, ISL-DS-435, dampers and spacers | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005108
NMA_TWI_1 | MAN-TWI-A0324-0325-10, MAN-TWI-A0354-10, MAN-TWI-A0379-10, MAN-TWI-A0386-00, MAN-TWI-A0388-0389-10, MAN-TWI-A0388-10, MAN-TWI-A0393-00, MAN-TWI-A0394-10, MAN-TWI-A0396-0397-00, MAN-TWI-A0396-0397-10, MAN-TWI-A0397-0398-00, MAN-TWI-A0399-00, NMA-CT-CT792, TWI-SA-4, FM3 roller door servicing | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161252
FHL_WPW_1 | Pole replacements x12. Condition assessments. | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160501
BWK_HWB_1 | GOR-HWB-A0612-10, GOR-HWB-A0665-00, GOR-HWB-A0713-00 | 2027-02-01 07:30 | 2027-02-03 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160377
BRY_ISL_1 | BRY-ISL-A0044-0045-20, BRY-ISL-A0057-0057A-20, ISL-DS-435, dampers and spacers | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160374
BRK_CB_642 | BRK-CB-642, BRK-CT-642, BRK-P-CB-642. Affected equipment of BPE_BRK_1. | 2027-02-01 07:30 | 2027-02-12 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160361
ISL_C_21 | Affected Equipment of ISL_220BS_D BRY-ISL-A0044-0045-20, BRY-ISL-A0057-0057A-20, ISL-DS-435, dampers and spacers | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005110
BPE_BRK_1 | BPE-DS-526, BRK-CT-652, BRK-CVT-652, BRK-DS-643, BRK-DS-655, BRK-DS-656, BRK-ES-659, BRK-P-CB-652. Tower recoating (A68-A73, A75-A76). | 2027-02-01 07:30 | 2027-02-12 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160322
OTA_220BZ_B_PROT2 | OTA-P-BZ-1-220-B | 2027-02-02 07:30 | 2027-02-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161311
OTA_220CBF_PROT1 | Affected equipment | 2027-02-02 07:30 | 2027-02-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161313
OTA_C_11 | OTA-CB-262 | 2027-02-02 07:30 | 2027-02-02 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161318
HAY_SC_10_T10 | HAY-CBL-T10-C10, HAY-CBL-T10-XT10, HAY-CBL-XT10-VT10A, HAY-SC10, HAY-SC10-EXC, HAY-SC10-NER, HAY-SC10-VT-10A | 2027-02-02 07:30 | 2027-02-12 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160619
OHG_SFD_1 | SFD-CVT-21, SFD-DS-743, SFD-DS-755, SFD-DS-756, SFD-ES-759. (CVT requires no other work for 1/2 day). | 2027-02-02 07:30 | 2027-02-04 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW2005712
KAW_97_VT107 | KAW-DS-107, KAW-VT-107 | 2027-02-02 07:30 | 2027-02-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160893
IGH_MCH_1 | Tower Painting | 2027-02-02 07:30 | 2027-02-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143093
EDG_KAW_2 | EDG-KAW-B0076-10, EDG-KAW-B0078-10, EDG-KAW-B0080-10, EDG-KAW-B0084-10, KAW-CT-112, KAW-P-CB-112 | 2027-02-02 07:30 | 2027-02-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160475
LTN_T3 | Affected equipment of BPE_TWC_LTN_1. | 2027-02-02 07:30 | 2027-02-03 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161017
LTN_AVR_T3 | Affected equipment of LTN_T3. | 2027-02-02 07:30 | 2027-02-03 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161015
KAW_T7 | Protection upgrade. KAW-CT-102, KAW-DS-1103, KAW-DS-1107, KAW-ES-109, KAW-NCT-7, KAW-NCT-ET7, KAW-P-TF-T7, KAW-TF-ET7, KAW-TF-T7 | 2027-02-02 07:30 | 2027-02-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160913
BPE_TWC_LTN_1 | LTN-CVT-CVT262. BPE-WIL-A0050-10. No lines work day 1. | 2027-02-02 07:30 | 2027-02-03 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160346
HAY_110CBF | HAY_110BZ Stage 3K; Bay 290 - Interconnector T5. | 2027-02-02 08:00 | 2027-02-02 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161981
HAY_110BZ | HAY_110BZ Stage 3K; Bay 290 - Interconnector T5. No work in HAY110kV yard. | 2027-02-02 08:00 | 2027-02-02 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161935
OTA_ROS_2 | Attachment points, re-insulation & Steel and bolts | 2027-02-02 08:00 | 2027-02-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005227
HLY_CB_242 | HLY-P-CB-242 | 2027-02-03 07:30 | 2027-02-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160703
OHC_CB_1358 | Affected equipment OHC_1307_1506 | 2027-02-03 07:30 | 2027-02-03 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161273
OHC_1506_1507 | OHC-DS-1514 | 2027-02-03 07:30 | 2027-02-03 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161272
OHC_1307_1506 | OHC-DS-1414 | 2027-02-03 07:30 | 2027-02-03 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161271
OHC_TWZ_4 | Affected equipment OHC_1506_1507 | 2027-02-03 07:30 | 2027-02-03 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161275
OTA_C_12 | OTA-CB-272 | 2027-02-03 07:30 | 2027-02-03 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161319
BEN_220CBF | BEN 220BZ - Filter 3 Migration | 2027-02-03 08:00 | 2027-02-04 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005436
BEN_220BZ | BEN 220BZ - Filter 3 Migration | 2027-02-03 08:00 | 2027-02-04 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005435
HAY_110CBF | HAY_110BZ Stage 3K; Bay 290 - Interconnector T5. | 2027-02-03 08:00 | 2027-02-03 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161982
HAY_110BZ | HAY_110BZ Stage 3K; Bay 290 - Interconnector T5. No work in HAY110kV yard. | 2027-02-03 08:00 | 2027-02-03 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161936
OHB_806_1007 | OHB-DS-914 | 2027-02-04 07:30 | 2027-02-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161267
BAL_BWK_1 | BAL-DEV-A0010-00, BAL-DEV-A0013-00, BAL-DEV-A0030-00, BWK-CB-192, GOR-HWB-A0440-00 | 2027-02-04 07:30 | 2027-02-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160201
KIN_FDR_2242 | KIN-CB-2242, KIN-P-CB-2242 | 2027-02-04 07:30 | 2027-02-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160946
BEN_OHB_1 | Affected equipment OHB_806_1007 | 2027-02-04 07:30 | 2027-02-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160280
OHB_807_806 | OHB-DS-814 | 2027-02-05 07:30 | 2027-02-05 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161268
ISL_C_14 | ISL-REA-C14 | 2027-02-09 06:30 | 2027-02-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160813
HAY_FDR_1012 | Affected equipment of HAY_T11, for HAY_110BZ Stage 3L; Bay 130 - Transformer T11. | 2027-02-09 07:00 | 2027-02-14 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162006
HAY_CB_2892 | Affected equipment of HAY_T11, for HAY_110BZ Stage 3L; Bay 130 - Transformer T11. | 2027-02-09 07:00 | 2027-02-14 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162004
HAY_T11 | HAY_110BZ Stage 3L; Bay 130 - Transformer T11. No other HAY work on days 1, 5, 6. No other work on associated equipment/lines on day 6 (commissioning). | 2027-02-09 07:00 | 2027-02-14 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162019
FHL_WPW_1 | Pole replacements. | 2027-02-09 07:00 | 2027-02-12 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW2006231
GOR_ROX_1 | GOR-ROX-A0244-00 GOR-ROX-A0252-00 GOR-ROX-A0286-00 | 2027-02-09 07:30 | 2027-02-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160526
ARI_HAM_2 | Open for the duration of HAM_OHW_1 | 2027-02-09 07:30 | 2027-02-14 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW2006234
ARI_HAM_1 | Open for the duration of HAM_OHW_1 | 2027-02-09 07:30 | 2027-02-14 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW2006233
ARI_CB_48 | Closed for the duration of HAM_OHW_1 | 2027-02-09 07:30 | 2027-02-14 18:30 | Continuous | NNI | CLO - Close | Approved | OW2006232
MGM_WDV_1 | MGM-CB-152, MGM-CT-152, MGM-VT-152. GYT/MGM/MST/UHT/WDV duplicated protection upgrade project Stage 1 [CP_VAR_21A_0_00]. AGS clamp replacements x10 (A71, A75, A77, A82-83, A89-90, A96, A105, A114). | 2027-02-09 07:30 | 2027-02-12 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161054
ISL_T7 | ISL-CB-312, ISL-P-TF-T7, ISL-TF-T7B, ISL-TF-T7R, ISL-TF-T7Y | 2027-02-09 07:30 | 2027-02-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160872
HAM_OHW_1 | Tower Painting. Ref chacks for HAM CT 458 replacement PJ CP_HAM_001_0_00 | 2027-02-09 07:30 | 2027-02-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1143046
HAY_WIL_LTN_1 | HAY-DS-576. Tower works x1 (A307). Remove droppers on JFD_LTN_1for tower painting [CP_770_007_0_00]. | 2027-02-09 07:30 | 2027-02-09 18:29 | Daily | SNI | RS - Removal from Service | Approved | OW1160635
OTB_SMK_1 | OTB-TF-LS21 | 2027-02-09 07:30 | 2027-02-11 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1161350
INV_TWI_1 | INV-TWI-A0002-10 INV-TWI-A0005-10 INV-TWI-A0006-10 INV-TWI-A0017-10 INV-TWI-A0017-10 INV-TWI-A0019-10 INV-TWI-A0020-10 INV-TWI-A0020-10 INV-TWI-A0023-10 INV-TWI-A0023-10 INV-TWI-A0031-10 INV-TWI-A0031-10 | 2027-02-09 07:30 | 2027-02-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160793
BRK_OHG_1 | BRK-CB-632, BRK-CT-632, BRK-P-CB-632, BRK-P-CB-632/642. (CVT requires no other work for 1/2 day). Tower recoating x10 (A165-A174) [CP_758_003_0_00]. | 2027-02-09 07:30 | 2027-02-19 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW2005711
HAM_CB_458 | HAM CT 458 replacement project | 2027-02-09 07:30 | 2027-02-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1156746
HAM_DIS_447 | Closed for the duration of HAM_CB_458. HAM CT 458 replacement project | 2027-02-09 07:30 | 2027-02-14 18:30 | Continuous | NNI | CLO - Close | Approved | OW1156747
KAW_MAT_1 | KAW-MAT-A0002-0003-00, KAW-MAT-A0003-00, KAW-MAT-A0003-0004-10,KAW-MAT-A0009-00, KAW-MAT-A0014-00 | 2027-02-09 07:30 | 2027-02-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160901
KPO_TMU_1 | Open for the duration of HAM_OHW_1 | 2027-02-09 07:30 | 2027-02-14 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW2006235
HAY_110BZ | HAY_110BZ Stage 3L; Bay 130 - Transformer T11. No work in HAY 110kV yard. | 2027-02-09 08:00 | 2027-02-09 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161937
HAY_110CBF | HAY_110BZ Stage 3L; Bay 130 - Transformer T11. | 2027-02-09 08:00 | 2027-02-09 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161983
NMA_220BS_A1 | NMA-CBL-1092, NMA-TF-T1 | 2027-02-09 08:00 | 2027-02-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161199
NMA_T1 | NMA-CBL-1092, NMA-TF-T1 | 2027-02-09 08:00 | 2027-02-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161250
NMA_CB_708 | Affected Equipment of NMA_220BS_A1 NMA-CBL-1092, NMA-TF-T1 | 2027-02-09 08:00 | 2027-02-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161223
MNG_ROS_1 | Attachment points, re-insulation & Steel and bolts | 2027-02-09 08:00 | 2027-02-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005723
NMA_CB_688 | Affected Equipment of NMA_220BS_A1 NMA-CBL-1092, NMA-TF-T1 | 2027-02-09 08:00 | 2027-02-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161217
JFD_LTN_1 | Tower works x8 (A83, A85, A96-A97, A135-A137, A274). Tower painting x19 (A57-A75) [CP_770_007_0_00]. JFD_LTN_1 droppers removedto leave HAY_WIL_1 in-service. | 2027-02-09 18:30 | 2027-02-26 07:29 | Continuous | SNI | RS - Removal from Service | Approved | OW1160878
KWA_T3 | Affected Equipment of KWA_WIL_2 KWA WIL Line Protection Upgrade. | 2027-02-10 07:00 | 2027-02-24 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2005795
KWA_WIL_2 | KWA WIL Line Protection Upgrade. | 2027-02-10 07:00 | 2027-02-24 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2005792
KWA_AVR_T1 | Affected Equipment of KWA_WIL_2 KWA WIL Line Protection Upgrade. | 2027-02-10 07:00 | 2027-02-24 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2005793
KWA_CB_14 | Affected Equipment of KWA_WIL_2 KWA WIL Line Protection Upgrade. | 2027-02-10 07:00 | 2027-02-24 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2005794
OWH_11CBF | OWH-P-BZ-11 | 2027-02-10 07:30 | 2027-02-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161356
OWH_11BZ_K | OWH-P-BZ-11 | 2027-02-10 07:30 | 2027-02-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161355
PNI_214_224_277 | PNI-BS-33-214-237 | 2027-02-10 07:30 | 2027-02-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161438
PNI_FDR_212 | Affected equipment PNI_214_257 & PNI_T1 | 2027-02-10 07:30 | 2027-02-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161440
PNI_LST_1 | Affected equipment of PNI_214_224_277, for PNI-BS-33-214-237 | 2027-02-10 07:30 | 2027-02-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161442
PNI_T1 | TF-SSC works. PNI-M-VT222, PNI-TF-T1R. 33kV droppers to be removed to allow 12-hour heat soak and metering concurrently on lastday. | 2027-02-10 07:30 | 2027-02-22 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161444
PNI_TKR_1 | Affected equipment PNI_214_257 & PNI_T1 | 2027-02-10 07:30 | 2027-02-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161447
WIL_178_VT217 | Remove DCB 222 Bus Droppers. KWA WIL Line Protection Upgrade. | 2027-02-10 08:00 | 2027-02-10 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005790
ARA_44_76 | ARA-DS-64 (G3) refurbishment [CP_RA3_03F_0_00] | 2027-02-12 07:30 | 2027-02-17 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160145
ARA_WRK_1 | ARA-DS-76. Affected equipment of ARA_44_76. LOC to ARA - Mercury have aligned. | 2027-02-12 07:30 | 2027-02-17 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160146
WRK_57_103_87 | WRK-DS-64 (T3), WRK-DS-67, WRK-DS-74 (T4), WRK-DS-77, WRK-DS-103 (CB_108), WRK-DS-134 (ARA_1) | 2027-02-12 07:30 | 2027-02-17 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161848
HAY_110BZ | HAY_110BZ Stage 3L; Bay 130 - Transformer T11. No work in HAY 110kV yard. | 2027-02-13 08:00 | 2027-02-13 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161938
HAY_110CBF | HAY_110BZ Stage 3L; Bay 130 - Transformer T11. | 2027-02-13 08:00 | 2027-02-13 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161984
HAY_110BZ | HAY_110BZ Stage 3L; Bay 130 - Transformer T11. No work in HAY 110kV yard. | 2027-02-14 08:00 | 2027-02-14 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161939
HAY_110CBF | HAY_110BZ Stage 3L; Bay 130 - Transformer T11. | 2027-02-14 08:00 | 2027-02-14 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161985
HWA_SFD_1 | OPE for the duration of SFD_T9, for post-contingent overloadingprevention | 2027-02-15 07:00 | 2027-02-17 18:30 | Continuous | SNI | OPE - Open Ended | Approved | OW1160745
KMO_TMI_1 | KMO-CT-202, KMO-ES-209, KMO-P-CB-202, TMI-CB-132 | 2027-02-15 07:00 | 2027-02-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160974
KMO_T4 | Affected equipment KMO_167_177_204 & KMO_MTM_1 & KMO_TMI_1 | 2027-02-15 07:00 | 2027-02-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160972
SFD_CB_752 | SFD-DS-754, SFD-DS-755 headgear refurbishments [CP_RA3_03F_0_00]. Affected equipment of SFD_727_754 & BRK_SFD_1. | 2027-02-15 07:00 | 2027-02-17 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161546
KMO_MTM_1 | HAI-MTM-B0038-0039-10, KMO-DS-196, KMO-ES-199 | 2027-02-15 07:00 | 2027-02-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160969
KMO_CB_178 | Affected equipment KMO_167_177_204 & KMO_MTM_1 & KMO_TMI_1 | 2027-02-15 07:00 | 2027-02-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160963
SFD_T9 | Affected equipment of SFD_727_754 | 2027-02-15 07:00 | 2027-02-17 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161550
HWA_T2 | OPE for the duration of HWA_SFD_1, to prevent recirculating currents through the HWA 33kV | 2027-02-15 07:00 | 2027-02-17 18:30 | Continuous | SNI | OPE - Open Ended | Approved | OW1160749
KMO_167_177_204 | KMO-DS-177, KMO-DS-184, KMO-DS-194, KMO-DS-204, KMO-VT-177 | 2027-02-15 07:00 | 2027-02-17 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160958
SFD_727_754 | SFD-DS-754 headgear refurbishment [CP_RA3_03F_0_00]. | 2027-02-15 07:00 | 2027-02-17 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161537
HTI_T2 | SF6 CB pole replacement project HTI-CB-132, HTI-CBL-T2-2152, HTI-CBL-T2-LS2, HTI-CT-132, HTI-NCT-2, HTI-TF-LS2, HTI-TF-T2B, HTI-TF-T2R, HTI-TF-T2SP, HTI-TF-T2Y | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160732
HEN_MPE_2 | HEN-CB-322, HEN-CT-322, HEN-DS-326, HEN-ES-329, HEN-MPE-A0027-20, HEN-MPE-A0043-20, HEN-MPE-A0079-20, HEN-MPE-A0082-0083-20, HEN-MPE-A0085-0086-20, HEN-MPE-A0086-20, HEN-MPE-A0108-0109-20, HEN-MPE-A0126-0127-20, HEN-MPE-A0132-0133-20, HEN-MPE-A0134-20, HEN-MPE-A0137-0138-20, HEN-MPE-A0156-20, HEN-MPE-A0162-20, HEN-MPE-A0163-20, HEN-MPE-A0183B-00, HEN-MPE-A0275-20, HEN-MPE-A0278-20, HEN-MPE-A0280-20, HEN-MPE-A0289-20, HEN-P-CB-322, MPE-P-CB-252 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160662
STK_T10 | STK-CB-822, STK-CBL-ET10, STK-CBL-NER10, STK-CBL-T10-2442, STK-CT-CT822, STK-CT-T10HV, STK-TF-ET10, STK-TF-T10 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161562
SVL_33BS_B | Feeder protection upgrade | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161570
WEL_T1 | WEL-TF-T1B, WEL-TF-T1R | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161772
SVL_CB_2808 | Affected Equipment of SVL_33BS_B | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161572
SVL_FDR_2822 | Affected Equipment of SVL_33BS_B | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161580
ISL_SVC_9 | ISL-CAPS-K0-C1, ISL-CT-CT812-D0-T1, ISL-CT-TCR9-K1-T2, ISL-CWU-SVC9, ISL-DS-813, ISL-DS-815, ISL-NCTD-T9, ISL-SVC-9, ISL-VT-VT812-D0-T5 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160866
WRK_CB_108 | Affected equipment of WRK_57_103_87. | 2027-02-15 07:30 | 2027-02-17 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161852
IGH_KIK_2 | Tower Painting | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1157291
KAW_T2 | KAW T2 protection replacement KAW-P-TF-T2, KAW-TF-T2 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160908
GOR_T12 | Affected Equipment of NMA_GOR_TMH_2 includes Lines | 2027-02-15 07:30 | 2027-02-24 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160534
WRK_DIS_117 | CLO for the duration of WRK_57_103_87, to maintain a solid 220kV bus. | 2027-02-15 07:30 | 2027-02-17 18:30 | Continuous | SNI | CLO - Close | Approved | OW1161859
SVL_FDR_2842 | Affected Equipment of SVL_33BS_B | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161582
GLN_T5 | Surge arrestor, bushing replacements, GLN-BS-220-T5-CLEAN, GLN-BS-33-T5-CLEAN, GLN-CT-622, GLN-SA-5A, GLN-SA-5B, GLN-TF-T5 | 2027-02-15 07:30 | 2027-02-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160520
SVL_FDR_2862 | Affected Equipment of SVL_33BS_B | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161583
FHL_WPW_2 | Pole replacements x5. Condition assessments. | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160503
SVL_FDR_2882 | Affected Equipment of SVL_33BS_B | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161586
SVL_FDR_2902 | Affected Equipment of SVL_33BS_B | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161588
MTO_T2 | Affected equipment HEN_MPE_2 & WEL_T1 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161184
SVL_T2 | Affected Equipment Tower Painting | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142694
ALB_SVL_2 | Tower Painting | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142693
NMA_CB_688 | Affected Equipment of NMA_615_737 NMA-CBL-1092, NMA-TF-T1 | 2027-02-15 08:00 | 2027-02-18 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161218
ISL_CB_668 | Affected Equipment of ISL_220BS_F ISL-DS-803 ISL-DS-813 | 2027-02-15 08:00 | 2027-02-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160830
NMA_GOR_TMH_2 | CP_EDN_00E_0_00 Powernet EDN New 220kV GXP Build | 2027-02-15 08:00 | 2027-02-24 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161249
ISL_C_27 | ISL-DS-803, ISL-DS-805, ISL-P-CAPS-C27 | 2027-02-15 08:00 | 2027-02-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160820
ISL_220BS_F | ISL-DS-803 ISL-DS-813 | 2027-02-15 08:00 | 2027-02-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160804
MAN_NMA_1 | Tower Painting | 2027-02-15 08:00 | 2027-02-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143114
ISL_CB_688 | Affected Equipment of ISL_220BS_F ISL-DS-803 ISL-DS-813 | 2027-02-15 08:00 | 2027-02-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160833
NMA_615_737 | NMA-CBL-1092, NMA-TF-T1 | 2027-02-15 08:00 | 2027-02-18 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161209
BPE_MTR_1 | MTR-REA-R92. Tower painting (A122-A130). | 2027-02-15 09:00 | 2027-02-27 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160335
ISL_66BZ | ISL-P-BZ-66 | 2027-02-16 07:30 | 2027-02-16 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160812
ISL_CB_658 | Affected Equipment of ISL_220BS_E ISL-DS-805 | 2027-02-17 07:30 | 2027-02-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160827
HEN_220CBF | HEN-P-BZ-220 | 2027-02-17 07:30 | 2027-02-18 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160643
HEN_220BZ_A2 | Affected equipment with HEN_220CBF | 2027-02-17 07:30 | 2027-02-18 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160642
HEN_220BZ_A1 | Affected equipment with HEN_220CBF | 2027-02-17 07:30 | 2027-02-18 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160641
ISL_CB_688 | Affected Equipment of ISL_220BS_E ISL-DS-805 | 2027-02-17 07:30 | 2027-02-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160834
ISL_220BS_E | ISL-DS-805 | 2027-02-17 07:30 | 2027-02-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160801
HAY_POLE_3 | Affected Equipment Scheduled Maintenance | 2027-02-18 05:00 | 2027-02-21 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1150928
BEN_POLE_3 | Affected Equipment Scheduled Maintenance | 2027-02-18 05:00 | 2027-02-21 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1150927
BEN_HAY_1 | Scheduled Maintenance | 2027-02-18 05:00 | 2027-02-23 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1150926
OPK_SFD_1 | SFD-P-CB-162. Benchmarking [CP_VAR_1B7_0_00]. | 2027-02-18 07:30 | 2027-02-18 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161301
SFD_137_187 | SFD-DS-164, SFD-DS-167, SFD-DS-177 | 2027-02-18 07:30 | 2027-02-18 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161531
SFD_CB_148 | Affected equipment SFD_137_187 | 2027-02-18 07:30 | 2027-02-18 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161539
HAY_R1 | Affected equipment HAY_T1 & HAY_SC_1 | 2027-02-18 07:30 | 2027-02-18 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160616
HAM_T1 | HAM-M-VT2752 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160569
SFD_CB_148 | SFD-DS-137. Affected equipment of SFD_117_167. | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161540
HAM_FDR_2802 | Affected Equipment of HAM_11KV_BS_A HAM-M-VT2752 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160562
SFD_T8 | SFD-DS-134. Affected equipment of SFD_117_167. | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161549
HAM_FDR_2782 | Affected Equipment of HAM_11KV_BS_A HAM-M-VT2752 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160561
HAM_FDR_2762 | Affected Equipment of HAM_11KV_BS_A HAM-M-VT2752 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160560
HAM_FDR_2742 | Affected Equipment of HAM_11KV_BS_A HAM-M-VT2752 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160559
HAM_FDR_2722 | Affected Equipment of HAM_11KV_BS_A HAM-M-VT2752 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160558
HAM_CB_2818 | Affected Equipment of HAM_11KV_BS_A HAM-M-VT2752 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160552
SFD_117_167 | SFD-DS-134, SFD-DS-137 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161530
SFD_CB_122 | OPE for the duration of SFD_117_167, to leave CST_JRD_1 leg in-service. | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | SNI | OPE - Open Ended | Approved | OW1161538
HAM_11KV_BS_A | HAM-M-VT2752 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160542
BEN_BGR_1 | Scheduled Maintenance | 2027-02-20 05:00 | 2027-02-21 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1158682
BEN_HAY_2 | Scheduled Maintenance | 2027-02-20 05:00 | 2027-03-01 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1150929
BEN_POLE_2 | Affected Equipment Scheduled Maintenance | 2027-02-20 05:00 | 2027-03-01 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1150930
HAY_POLE_2 | Affected Equipment Scheduled Maintenance | 2027-02-20 05:00 | 2027-03-01 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1150931
BEN_BIPOLE | Scheduled Maintenance | 2027-02-20 05:00 | 2027-02-23 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1150932
HAY_BIPOLE | Scheduled Maintenance | 2027-02-20 05:00 | 2027-02-23 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1150933
HAY_THW_1B | OTB-HAY-A0045-40, OTB-HAY-A0065A-40, OTB-HAY-A0073-40, OTB-HAY-A0076-40 | 2027-02-20 07:30 | 2027-02-21 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160633
HAY_THW_1A | OTB-HAY-A0045-20, OTB-HAY-A0050A-20, OTB-HAY-A0065A-20, OTB-HAY-A0073-20 | 2027-02-20 07:30 | 2027-02-21 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160632
FTB_OTB_CBL_4 | FTB-P2-CBLT-4, FTB-P2-SA-3, OTB-P2-CBLT-4 | 2027-02-20 07:30 | 2027-02-21 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160506
FTB_OTB_CBL_5 | FTB-P2/3-CBLT-5, FTB-P2/3-SA-2, OTB-P2/3-CBLT-5, OTB-P2/3-SA-2 | 2027-02-20 07:30 | 2027-02-21 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160507
FTB_OTB_CBL_6 | FTB-P3-CBLT-6, FTB-P3-SA-1, OTB-P3-CBLT-6, OTB-P3-SA-1 | 2027-02-20 07:30 | 2027-02-21 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160508
BEN_220CBF | Meridian Bay - T46/G5/G6 Migration Meridian Bay - T46/G5/G6 Migration CP_BEN_AZ_00_00 | 2027-02-20 08:00 | 2027-02-20 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005469
BEN_220BZ | Meridian Bay - T46/G5/G6 Migration Meridian Bay - T46/G5/G6 Migration CP_BEN_AZ_00_00 | 2027-02-20 08:00 | 2027-02-20 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005467
MTO_T1 | MTO-CB-1292, MTO-NCT-1, MTO-P-TF-T1, MTO-TF-LS1, MTO-TF-T1, MTO-VT-11 | 2027-02-22 07:00 | 2027-02-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161183
EDG_KAW_2 | EDG-KAW-B0076-10, EDG-KAW-B0078-10, EDG-KAW-B0080-10, EDG-KAW-B0084-10, KAW-CT-112, KAW-P-CB-112 | 2027-02-22 07:00 | 2027-02-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160476
HEN_MPE_1 | HEN-MPE-A0001-0002-10, HEN-MPE-A0001-10, HEN-MPE-A0003-0004-10,HEN-MPE-A0005-0006-10, HEN-MPE-A0008-0009-10, HEN-MPE-A0022-00,HEN-MPE-A0043-10, HEN-MPE-A0080-00, HEN-MPE-A0088-00, HEN-MPE-A0092-10, HEN-MPE-A0105-00, HEN-MPE-A0111-00, HEN-MPE-A0111-10, HEN-MPE-A0112-0113-10, HEN-MPE-A0113-00, HEN-MPE-A0114-00, HEN-MPE-A0115-00, HEN-MPE-A0116-00, HEN-MPE-A0119-00, HEN-MPE-A0120-00, HEN-MPE-A0121-00, HEN-MPE-A0122-00, HEN-MPE-A0123-00, HEN-MPE-A0125-00, HEN-MPE-A0129-00, HEN-, HEN-P-CB-302, MPE-P-CB-292 | 2027-02-22 07:00 | 2027-02-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160661
EDG_217_207_324 | EDG-DS-207, EDG-VT-VT207 | 2027-02-22 07:00 | 2027-02-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160470
HAM_T7 | Reinhausen tap changer maintenance | 2027-02-22 07:00 | 2027-02-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160573
ARI_HTI_1 | CA Lift | 2027-02-22 07:00 | 2027-02-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160169
WEL_T2 | Affected equipment HEN_MPE_1 & MTO_T1 | 2027-02-22 07:00 | 2027-02-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161773
ISL_T6 | ISL-DS-503 Headgear Replacement | 2027-02-22 07:30 | 2027-02-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005139
IGH_ROB_1 | Tower Painting | 2027-02-22 07:30 | 2027-02-26 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1157293
BRK_CB_612 | BRK-CB-612, BRK-CT-612, BRK-P-CB-612. Affected equipment of BRK_SFD_2. | 2027-02-22 07:30 | 2027-03-05 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160360
BRK_SFD_2 | BRK-CB-602, BRK-CT-602, BRK-CVT-602, BRK-DS-603, BRK-DS-606, BRK-DS-615, BRK-ES-609, BRK-P-CB-602, BRK-P-CB-602/612, BRK-P-CB-642/652, SFD-CB-692, SFD-DS-683, SFD-DS-695, SFD-DS-696. (CVT requires no other work for 1/2 day). Tower recoating x10 (A165-A174) [CP_758_003_0_00]. | 2027-02-22 07:30 | 2027-03-05 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160368
BRY_C_5A | Affected equipment BRY_T5 | 2027-02-22 07:30 | 2027-02-26 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160372
HKK_C7C8C9 | HKK-CB-1402 | 2027-02-22 07:30 | 2027-02-22 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160690
GOR_ROX_1 | GOR-ROX-A0095-00, GOR-ROX-A0098-00, GOR-ROX-A0108-00, GOR-ROX-A0120-00, GOR-ROX-A0121-00, GOR-ROX-A0127-00, GOR-ROX-A0143-00, GOR-ROX-A0153-00, GOR-ROX-A0159-00, GOR-ROX-A0216-00, GOR-ROX-A0232-10, GOR-ROX-A0244-00, GOR-ROX-A0252-00, GOR-ROX-A0286-00, GOR-ROX-A0397-10, GOR-ROX-A0400-10 | 2027-02-22 07:30 | 2027-02-26 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160524
BRY_T5 | BRY-REA-C5A, BRY-VT-VT492 | 2027-02-22 07:30 | 2027-02-26 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160375
ISL_CB_628 | Affected Equipment of ISL_220BS_B Affected equipment ISL-DS-503Headgear Replacement | 2027-02-22 07:30 | 2027-02-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005137
MAN_NMA_2 | Tower Painting | 2027-02-22 07:30 | 2027-02-27 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143117
ISL_C_26 | Affected Equipment of ISL_T6 ISL-DS-503 Headgear Replacement | 2027-02-22 07:30 | 2027-02-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005140
OHW_CB_312 | OHW-CB-312, OHW-ES-3069, OHW-ES-3169 | 2027-02-22 07:30 | 2027-02-27 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161281
ISL_220BS_B | Affected equipment ISL-DS-503 Headgear Replacement | 2027-02-22 07:30 | 2027-02-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005136
OHW_OTA_2 | OHW-DS-296, OHW-DS-306, OHW-ES-299, OHW-VT-CVT292, OTA-WKM-C0306-0307-20, , OTA-WKM-C0363-0364-20, OTA-WKM-C0364-0365-20, OTA-WKM-C0365-0366-20, OTA-WKM-C0391-0392-20, OTA-WKM-C0449-0450-20, OTA-WKM-C0453-0454-20, OTA-WKM-C0455-0456-20, OTA-WKM-C0456-0457-20, OTA-WKM-C0488-0489-20 OHW-ES-2949, OHW-ES-2969, OHW-P-CB-292 | 2027-02-22 07:30 | 2027-02-27 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161284
ISL_CB_648 | Affected Equipment of ISL_220BS_B Affected equipment ISL-DS-503Headgear Replacement | 2027-02-22 07:30 | 2027-02-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005138
HEN_HEP_2 | Affected equipment HEP_247_257_314 & HEP_ROS_1 | 2027-02-22 08:00 | 2027-02-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160656
HEP_C_12 | Affected equipment HEP_247_257_314 & HEP_ROS_1 | 2027-02-22 08:00 | 2027-02-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160675
HEP_247_257_314 | VT replacement project. HEP-VT-VT257 | 2027-02-22 08:00 | 2027-02-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160673
HEP_C_13 | Affected equipment HEP_247_257_314 & HEP_ROS_1 | 2027-02-22 08:00 | 2027-02-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160676
HEP_CB_248 | Affected equipment HEP_247_257_314 & HEP_ROS_1 | 2027-02-22 08:00 | 2027-02-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160677
HEN_HEP_1 | Affected equipment HEP_247_257_314 & HEP_ROS_1 | 2027-02-22 08:00 | 2027-02-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005996
HEP_ROS_1 | HEP-P-CB-252, ROS-P-CB-52 | 2027-02-22 08:00 | 2027-02-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160683
DOB_T2 | DOB T2 OLTC Main Current collector replacement. NCT2 leaking Low CA. | 2027-02-22 08:00 | 2027-02-26 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1162507
HEP_T3 | Affected equipment HEP_247_257_314 & HEP_ROS_1 | 2027-02-22 08:00 | 2027-02-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160685
GLN_T4 | Surge arrestor & bushings replacement PJ, GLN-SA-4A, GLN-SA-4B,GLN-TF-T4 | 2027-02-22 08:00 | 2027-02-28 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160519
SFD_CB_612 | ([OPTION 1] SFD-CT-612, SFD-CVT-22, SFD-DS-616, SFD-ES-619, SFD-P-CB-612). Affected equipment of SFD_617_647. | 2027-02-23 07:30 | 2027-02-25 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161543
SFD_617_647 | SFD-DS-614. LOC to SPL. | 2027-02-23 07:30 | 2027-02-25 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161534
WIL_178_VT217 | Reconnect DCB 222 Bus Droppers. KWA WIL Line Protection Upgrade. | 2027-02-23 08:00 | 2027-02-23 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005796
SFD_CB_552 | SFD-DS-554. LOC to G22. Affected equipment of SFD_524_617. | 2027-02-24 07:30 | 2027-02-24 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161541
SFD_CB_582 | Affected equipment of SFD_524_617, for SFD-DS-554 | 2027-02-24 07:30 | 2027-02-24 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161542
KMO_T2 | KMO-CBL-T2-ET2, KMO-TF-ET2, KMO-TF-T2 | 2027-02-24 07:30 | 2027-02-26 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160971
SFD_524_617 | SFD-DS-554. LOC to G22. | 2027-02-24 07:30 | 2027-02-24 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161533
HAY_WIL_LTN_1 | Reinstate droppers on JFD_LTN_1 [CP_770_007_0_00]. | 2027-02-26 07:30 | 2027-02-26 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160636
BEN_220CBF | Meridian Bay - T46/G5/G6 Migration Meridian Bay - T46/G5/G6 Migration CP_BEN_AZ_00_00 | 2027-02-26 08:00 | 2027-02-26 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005470
BEN_220BZ | Meridian Bay - T46/G5/G6 Migration Meridian Bay - T46/G5/G6 Migration CP_BEN_AZ_00_00 | 2027-02-26 08:00 | 2027-02-26 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005471
OKN_CB_39 | Affected equipment of OKN site shut (alternate date 7/03/27) | 2027-02-28 07:30 | 2027-02-28 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161295
OKN_CB_72 | OPE for OKN site shut (alternate date 7/03/27), to leave NPK_ONG_1 leg in-service | 2027-02-28 07:30 | 2027-02-28 18:30 | Daily | SNI | OPE - Open Ended | Approved | OW1161296
MTR_OKN_1 | Affected equipment of OKN site shut (alternate date 7/03/27) | 2027-02-28 07:30 | 2027-02-28 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161191
OKN_T2 | OKN site shut (alternate date 7/03/27). OKN-TF-T2. | 2027-02-28 07:30 | 2027-02-28 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161298
OKN_CB_38 | Affected equipment of OKN site shut (alternate date 7/03/27) | 2027-02-28 07:30 | 2027-02-28 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161294
OKN_72_82_92 | Affected equipment of OKN site shut (alternate date 7/03/27) | 2027-02-28 07:30 | 2027-02-28 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161293
BRB_MDN_1 | BRB-DEV-A0406-0407-20, BRB-DEV-A0411-BRBB2-10, BRB-SA-172, HEN-MDN-A0331-00, MDN-CVT-CVT472, MDN-DS-476, MDN-ES-479, MDN-P-CB-472 | 2027-03-01 07:00 | 2027-03-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160355
MPE_CB_292 | System split for the duration of MDN_MPE_2 | 2027-03-01 07:00 | 2027-03-01 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161154
MDN_297_237_257 | MDN-DS-237 | 2027-03-01 07:00 | 2027-03-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161033
MDN_457_494_497 | MDN-DS-467, MDN-DS-474, MDN-DS-494, MDN-DS-497 | 2027-03-01 07:00 | 2027-03-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161035
MDN_CB_308 | Affected equipment MDN_297_237_257 & MDN_MPE_2 & MDN_T6 & MDN_STC_6 | 2027-03-01 07:00 | 2027-03-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161037
MDN_CB_508 | Affected equipment MDN_457_494_497 & BRB_MDN_1 & MDN_T6 & MDN_STC_6 | 2027-03-01 07:00 | 2027-03-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161038
MDN_LST_6B | Affected equipment MDN_457_494_497 & BRB_MDN_1 & MDN_T6 & MDN_STC_6 | 2027-03-01 07:00 | 2027-03-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161040
MPE_CB_252 | System split for the duration of MDN_MPE_2 | 2027-03-01 07:00 | 2027-03-01 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161119
MDN_MPE_2 | MDN-CT-252, MDN-DS-256, MDN-ES-259, MDN-MPE-A0012-0013-20, MDN-MPE-A0013-0014-20, MDN-MPE-A0084-MPEG3-10, MDN-P-CB-252, MDN-VT-VT252, MPE-P-CB-272 | 2027-03-01 07:00 | 2027-03-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161042
MDN_T6 | MDN-P-CB-232 | 2027-03-01 07:00 | 2027-03-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161047
KAW_FDR_72 | FDR 72 protection replacement project. To align with KAG shutdown. KAW-P-CB-72 | 2027-03-01 07:30 | 2027-03-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160900
GLN_T6 | Surge arrestor & bushings replacement PJ, GLN-BS-220-T6-CLEAN, GLN-BS-33-T6-CLEAN, GLN-SA-6A, GLN-SA-6B, GLN-TF-T6 | 2027-03-01 07:30 | 2027-03-07 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160521
HAY_WIL_LTN_2 | HAY-CT-532, WIL-CB-882. Tower painting x19 (A57-A75). Remove JFD_LTN_2 droppers for tower painting [CP_770_007_0_00]. | 2027-03-01 07:30 | 2027-03-02 18:29 | Continuous | SNI | RS - Removal from Service | Approved | OW1160637
TRK_220CBF | Affected equipment | 2027-03-01 07:30 | 2027-03-03 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161705
TRK_220BZ_A | TRK-P-BZ-220-A | 2027-03-01 07:30 | 2027-03-03 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161704
GLN_CB_2348 | Closed for the duration of GLN T6 outage | 2027-03-01 07:30 | 2027-03-07 18:30 | Continuous | NNI | CLO - Close | Approved | OW1160515
GLN_DIS_2347 | Closed for the duration of GLN T6 outage | 2027-03-01 07:30 | 2027-03-07 18:30 | Continuous | NNI | CLO - Close | Approved | OW1160518
HWB_SDN_1 | HWB-SDN-A0003-00, HWB-SDN-A0003-10, HWB-SDN-A0004-00, HWB-SDN-A0004-10, HWB-SDN-A0019-00, HWB-SDN-A0021-00, HWB-SDN-A0023-00, HWB-SDN-A0025-00, HWB-SDN-A0031-00, HWB-SDN-A0032-00 | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160761
ISL_CB_628 | Affected equipment ISL_220BS_C | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160824
IGH_MCH_1 | Tower Painting | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143094
INV_MAN_2 | Tower Painting | 2027-03-01 07:30 | 2027-03-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143095
ISL_CB_608 | Affected equipment ISL_220BS_C | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160823
WPR_T13 | WPR-P-TF-T13, WPR-TF-T13 | 2027-03-01 07:30 | 2027-03-03 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161831
ISL_220BS_C | ISL-DS-423 | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160798
PNI_237_294 | PNI-BS-33-237-294 | 2027-03-01 07:30 | 2027-03-02 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161439
PNI_FDR_292 | Affected equipment PNI_237_294 & PNI_T2 | 2027-03-01 07:30 | 2027-03-02 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161441
PNI_LST_1 | Affected equipment PNI_237_294 & PNI_T2 | 2027-03-01 07:30 | 2027-03-02 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161443
PNI_T2 | PNI-CB-282, PNI-CB-92, PNI-CT-92, PNI-DS-94, PNI-ES-99, PNI-NCT-T2, PNI-P-TF-T2, PNI-TF-T2, PNI-VT-282, PNI-VT-94. Corrosive sulphur work. No metering. | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161445
PNI_TKR_2 | Affected equipment PNI_237_294 & PNI_T2 | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161448
ISL_C_22 | Affected equipment ISL_220BS_C | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160817
IGH_ROB_1 | CA Lifting INSPECTIONS | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1162027
MDN_STC_6 | MDN-P-PSUP-STC6-UPS-1, MDN-STC-6, MDN-STC6-VCS | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1161044
NMA_CB_718 | Affected Equipment of NMA_220BS_A3 pdm maint. | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161232
MTI_RTU_1 | SMS & GPS replacements [CP_RA3_03C_0_00] | 2027-03-01 07:30 | 2027-03-01 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161172
NMA_CB_708 | Affected Equipment of NMA_220BS_A3 pdm maint. | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161224
NMA_220BS_A3 | pdm maint. | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161203
ISL_T2 | Affected equipment ISL_220BS_C ISL-NCTD-T2, Affected equipment ISL-DS-423 Headgear Replacement | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160869
BPE_TKU_1 | BPE-TKU-A/B TTU project. Tower works x8 (A11-12, A14-A17, A32, A36). Tower painting x20 (A52-A72) [CP_716_004_0_00]. | 2027-03-01 07:30 | 2027-05-14 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160343
MPE_CB_252 | System split for the duration of MDN_MPE_2 | 2027-03-02 06:00 | 2027-03-04 22:00 | Continuous | NNI | OPE - Open Ended | Approved | OW1161120
MPE_CB_292 | System split for the duration of MDN_MPE_2 | 2027-03-02 06:00 | 2027-03-04 22:00 | Continuous | NNI | OPE - Open Ended | Approved | OW1161155
HAY_T12 | HAY_110BZ Stage 3M; Bay 270 - Transformer T12. No other HAY work on days 1, 5, 6. No other work on associated equipment/lines on day 6 (commissioning). | 2027-03-02 07:00 | 2027-03-07 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162020
HAY_FDR_1052 | Affected equipment of HAY_T12, for HAY_110BZ Stage 3M; Bay 270 - Transformer T12. | 2027-03-02 07:00 | 2027-03-07 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162007
HAY_CB_2772 | Affected equipment of HAY_T12, for HAY_110BZ Stage 3M; Bay 270 - Transformer T12. | 2027-03-02 07:00 | 2027-03-07 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162003
SFD_CB_612 | ([OPTION 2] SFD-CT-612, SFD-CVT-22, SFD-DS-616, SFD-ES-619, SFD-P-CB-612). Affected equipment of SFD_637_667. | 2027-03-02 07:30 | 2027-03-04 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161544
SFD_CB_662 | Affected equipment of SFD_667_727, for SFD-DS-664, SFD-DS-697. | 2027-03-02 07:30 | 2027-03-04 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161545
SFD_637_667 | SFD-DS-634. LOC to SPL. | 2027-03-02 07:30 | 2027-03-04 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161535
SFD_667_697 | SFD-DS-664, SFD-DS-697 headgear refurbishments [CP_RA3_03F_0_00]. | 2027-03-02 07:30 | 2027-03-04 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161536
HAY_110BZ | HAY_110BZ Stage 3M; Bay 270 - Transformer T12. No work in HAY 110kV yard. | 2027-03-02 08:00 | 2027-03-02 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161940
HAY_110CBF | HAY_110BZ Stage 3M; Bay 270 - Transformer T12. | 2027-03-02 08:00 | 2027-03-02 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161986
JFD_LTN_2 | Tower painting x19 (A57-A75) [CP_770_007_0_00]. JFD_LTN_2 droppers removed to leave HAY_WIL_2 in-service. | 2027-03-02 18:30 | 2027-03-19 07:29 | Continuous | SNI | RS - Removal from Service | Approved | OW1160879
BEN_T29 | BEN-CB-852, BEN-NCTD-T29, BEN-TF-T29 | 2027-03-03 07:30 | 2027-03-05 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160283
APS_FDR_622 | Affected equipment APS_T1 | 2027-03-03 07:30 | 2027-03-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160140
EDG_TRK_2 | EDG-TRK-A0048-20, EDG-TRK-A0067-20, EDG-TRK-A0079-20, EDG-TRK-A0092-20, EDG-TRK-A0100-0101-20, EDG-TRK-A0100-20, EDG-TRK-A0105-20, EDG-TRK-A0106-20, EDG-TRK-A0108-20, EDG-TRK-A0109-20, EDG-TRK-A0110-20, EDG-TRK-A0112-20, EDG-TRK-A0114-20, EDG-TRK-A0124-20, EDG-TRK-A0131-20, EDG-TRK-A0133-20, EDG-TRK-A0138-20, TRK-DS-366 | 2027-03-03 07:30 | 2027-03-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160483
APS_T1 | APS-TF-T1B, APS-TF-T1R, APS-TF-T1Y | 2027-03-03 07:30 | 2027-03-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160144
EDG_T5 | Affected equipment EDG_427_437_447 & EDG_TRK_2 | 2027-03-03 07:30 | 2027-03-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160480
EDG_427_437_447 | Headgear refurbishment EDG-DS-437 | 2027-03-03 07:30 | 2027-03-05 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160473
MPE_CB_252 | System split for the duration of MDN_MPE_2 | 2027-03-05 06:00 | 2027-03-05 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161121
MPE_CB_292 | System split for the duration of MDN_MPE_2 | 2027-03-05 06:00 | 2027-03-05 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161156
HAY_110BZ | HAY_110BZ Stage 3M; Bay 270 - Transformer T12. No work in HAY 110kV yard. | 2027-03-06 08:00 | 2027-03-06 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161941
BEN_220BZ | Meridian Bay - T42/G1/G2 Migration CP_BEN_AZ_00_00 | 2027-03-06 08:00 | 2027-03-06 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005479
HAY_110CBF | HAY_110BZ Stage 3M; Bay 270 - Transformer T12. | 2027-03-06 08:00 | 2027-03-06 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161987
BEN_220CBF | Meridian Bay - T42/G1/G2 Migration CP_BEN_AZ_00_00 | 2027-03-06 08:00 | 2027-03-06 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005480
MGM_MST_1 | MGM-CB-172, MGM-CT-172, MGM-DS-176, MGM-ES-179, MGM-P-CB-172, MGM-VT-172. Last day for VT testing - no lines. Pole replacementsx6. GYT/MGM/MST/UHT/WDV duplicated protection upgrade project Stage 2 [CP_VAR_21A_0_00]. | 2027-03-07 07:30 | 2027-03-12 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161050
HAY_110BZ | HAY_110BZ Stage 3M; Bay 270 - Transformer T12. No work in HAY 110kV yard. | 2027-03-07 08:00 | 2027-03-07 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161942
HAY_110CBF | HAY_110BZ Stage 3M; Bay 270 - Transformer T12. | 2027-03-07 08:00 | 2027-03-07 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161988
ISL_FDR_192 | ISL-CB-192, ISL-CT-CT192, ISL-DS-196, ISL-DS-193, ISL-DS-195. CY4 Re-planned. | 2027-03-08 06:30 | 2027-03-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159809
ISL_CB_768 | Affected Equipment ISL-DS-193 and Hot-end hardware corroded. CY4 Re-planned. | 2027-03-08 06:30 | 2027-03-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159804
ISL_CB_708 | Affected Equipment ISL-DS-193 and Hot-end hardware corroded. CY4 Re-planned. | 2027-03-08 06:30 | 2027-03-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159803
ISL_66BS_A | ISL-DS-193 and Hot-end hardware corroded. CY4 Re-planned. | 2027-03-08 06:30 | 2027-03-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159802
APS_OTI_1 | structure replacement COL-OTI-A0467-00, COL-OTI-A0468-00, COL-OTI-A0469-00, COL-OTI-A0470-00, COL-OTI-A0472-00, COL-OTI-A0473-00, COL-OTI-A0474-00, COL-OTI-A0475-00, COL-OTI-A0476-00, COL-OTI-A0477-00, COL-OTI-A0478-00, COL-OTI-A0524-00, COL-OTI-A0505A, COL-OTI-A0505A-0507A-10, COL-OTI-A0486-0487-10 | 2027-03-08 06:30 | 2027-03-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160142
COL_OTI_2 | structure replacement COL-OTI-A0467-00, COL-OTI-A0468-00, COL-OTI-A0469-00, COL-OTI-A0470-00, COL-OTI-A0472-00, COL-OTI-A0473-00, COL-OTI-A0474-00, COL-OTI-A0475-00, COL-OTI-A0476-00, COL-OTI-A0477-00, COL-OTI-A0478-00, COL-OTI-A0524-00, COL-OTI-A0505A, COL-OTI-A0505A-0507A-10, COL-OTI-A0486-0487-10 | 2027-03-08 06:30 | 2027-03-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160396
EDG_TRK_2 | Reinsulation and Attachment Points | 2027-03-08 07:00 | 2027-03-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162884
CPK_T5 | Reinhausen tap changer maintenance | 2027-03-08 07:30 | 2027-03-12 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW2006147
DRY_CB_432 | Affected Equipment of DRY_220BS_B DRY CB462 Siemens relay replacement | 2027-03-08 07:30 | 2027-03-08 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW2006328
DRY_220BS_B | DRY CB462 Siemens relay replacement | 2027-03-08 07:30 | 2027-03-08 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW2006327
DRY_BOB_HLY_1 | Attachment point replacements PJ. HLY-OTA-A0063-10, HLY-OTA-A0092-10, HLY-OTA-A0095-10, HLY-OTA-A0099-10, HLY-OTA-A0100-10, HLY-OTA-A0104-10, HLY-OTA-A0106-10, HLY-OTA-A0107-10, HLY-OTA-A0111-10, HLY-OTA-A0118-10 | 2027-03-08 07:30 | 2027-03-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160445
MAN_NMA_3 | Tower Painting | 2027-03-08 07:30 | 2027-03-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143097
ABY_TIM_1 | TKA-TIM-A0314-00 TKA-TIM-A0320-00 TKA-TIM-A0386-00 TKA-TIM-A0399-00 TKA-TIM-A0410-00 | 2027-03-08 07:30 | 2027-03-12 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160118
CPK_WIL_1 | Affected equipment of CPK_T5, for Reinhausen tap changer maintenance | 2027-03-08 07:30 | 2027-03-12 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW2006148
BOB_T4 | BOB-TF-T4 | 2027-03-08 07:30 | 2027-03-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160312
ROS_FDR_62 | Protection replacement ROS-P-CB-62 | 2027-03-08 07:30 | 2027-03-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161486
BRK_SFD_3 | Tower painting x49 Towers 314, 318-332, 348-380, [CP_760_005_0_00]. Optimised. | 2027-03-08 07:30 | 2027-03-25 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW2006237
WEL_T2 | Affected Equipment Tower Painting | 2027-03-08 08:00 | 2027-03-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142853
MTO_T1 | Affected Equipment Tower Painting | 2027-03-08 08:00 | 2027-03-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142852
HEN_MPE_1 | Tower Painting | 2027-03-08 08:00 | 2027-03-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142851
CUL_FDR_1222 | Remove 33kV tie Bus & Support post | 2027-03-09 07:30 | 2027-03-10 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005508
EDG_220BZ | EDG-P-BZ-220 | 2027-03-09 07:30 | 2027-03-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160471
EDG_220CBF | Affected equipment | 2027-03-09 07:30 | 2027-03-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160472
CUL_FDR_1242 | Remove 33kV tie Bus & Support post | 2027-03-09 07:30 | 2027-03-10 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005509
SVL_FDR_2862 | SVL-CBL-2862 | 2027-03-10 07:30 | 2027-03-10 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161584
TRK_DIS_407 | Closed for the duration of TRK_CB_618 | 2027-03-10 07:30 | 2027-03-12 18:30 | Continuous | NNI | CLO - Close | Approved | OW1161711
PEN_1678_2213_2215 | PEN-CBL-1678-2213/2215 | 2027-03-10 07:30 | 2027-03-10 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161369
TRK_CB_618 | TRK-CB-618, TRK-CT-618 | 2027-03-10 07:30 | 2027-03-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161709
TRK_567_607_627 | TRK-DS-607 | 2027-03-10 07:30 | 2027-03-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161708
KMO_TRK_1 | Affected equipment TRK_567_607_627 & TRK_CB_618 | 2027-03-10 07:30 | 2027-03-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160975
HOB_WRD_1 | HOB-VT-VT152, WRD-CT-NCT182A, WRD-CT-NCT182B, WRD-REA-R182, WRD-VT-VT182. HOB-WRD-A-CBL-13 Yph Sheath Repair MP_649_002_0_00 | 2027-03-10 07:30 | 2027-03-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160720
BEN_F_7 | S1.20DB80-FB7, S1.20DB80-Q02 | 2027-03-10 08:00 | 2027-03-12 18:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160278
ISL_CB_748 | Affected Equipment ISL-DS-195. CY4 Re-planned. | 2027-03-12 06:30 | 2027-03-12 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1159808
ISL_CB_728 | Affected Equipment ISL-DS-195. CY4 Re-planned. | 2027-03-12 06:30 | 2027-03-12 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1159807
ISL_66BS_C | ISL-DS-195. CY4 Re-planned. | 2027-03-12 06:30 | 2027-03-12 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1159806
BEN_220CBF | Meridian Bay - T42/G1/G2 Migration CP_BEN_AZ_00_00 | 2027-03-12 08:00 | 2027-03-12 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005481
BEN_220BZ | Meridian Bay - T42/G1/G2 Migration CP_BEN_AZ_00_00 | 2027-03-12 08:00 | 2027-03-12 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005482
BEN_HAY_1 | Maintenance | 2027-03-13 05:00 | 2027-03-14 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1163494
BEN_POLE_3 | Affected Equipment Maintenance | 2027-03-13 05:00 | 2027-03-14 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1163495
HAY_POLE_3 | Affected Equipment Maintenance | 2027-03-13 05:00 | 2027-03-14 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1163496
BEN_HAY_2 | Maintenance | 2027-03-13 05:00 | 2027-03-14 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1163497
BEN_POLE_2 | Affected Equipment Maintenance | 2027-03-13 05:00 | 2027-03-14 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1163498
HAY_POLE_2 | Affected Equipment Maintenance | 2027-03-13 05:00 | 2027-03-14 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1163499
BEN_BIPOLE | Maintenance | 2027-03-13 05:00 | 2027-03-14 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1163500
HAY_BIPOLE | Maintenance | 2027-03-13 05:00 | 2027-03-14 22:00 | Continuous | HVDC | RS - Removal from Service | Approved | OW1163501
MTR_1064_1074_1114 | Affected equipment of MTR site shut (alternate date 21/03/27) | 2027-03-14 07:30 | 2027-03-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161185
MTR_54_94 | Affected equipment of MTR site shut (alternate date 21/03/27) | 2027-03-14 07:30 | 2027-03-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161186
MTR_FDR_1072 | Affected equipment of MTR site shut (alternate date 21/03/27) | 2027-03-14 07:30 | 2027-03-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161187
MTR_FDR_1092 | Affected equipment of MTR site shut (alternate date 21/03/27) | 2027-03-14 07:30 | 2027-03-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161188
MTR_FDR_1112 | Affected equipment of MTR site shut (alternate date 21/03/27) | 2027-03-14 07:30 | 2027-03-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161189
MTR_T2 | MTR site shut (alternate date 21/03/27). MTR-TF-T2B, MTR-TF-T2R, MTR-TF-T2Y. | 2027-03-14 07:30 | 2027-03-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161193
MTR_OKN_1 | Affected equipment of MTR site shut (alternate date 21/03/27) | 2027-03-14 07:30 | 2027-03-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161192
MTR_LST_1 | Affected equipment of MTR site shut (alternate date 21/03/27) | 2027-03-14 07:30 | 2027-03-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161190
BPE_MTR_1 | Affected equipment of MTR site shut (alternate date 21/03/27) | 2027-03-14 07:30 | 2027-03-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160336
APS_CLH_1 | STRUCTURE REPLACEMENTS | 2027-03-15 06:30 | 2027-03-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160139
COL_OTI_2 | STRUCTURE REPLACEMENTS COL-OTI-A0241-00, COL-OTI-A0242-00, COL-OTI-A0382-00, COL-OTI-A0361-0362-10 | 2027-03-15 06:30 | 2027-03-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160397
GLN_CB_658 | Affected equipment | 2027-03-15 07:00 | 2027-03-15 11:59 | Daily | NNI | RS - Removal from Service | Approved | OW1162523
GLN_220BS_A | GLN bus clean with T4 | 2027-03-15 07:00 | 2027-03-15 11:59 | Daily | NNI | RS - Removal from Service | Approved | OW1162522
GLN_T4 | GLN bus clean | 2027-03-15 07:00 | 2027-03-15 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162521
ABY_TIM_1 | TKA-TIM-A0450-00 TKA-TIM-A0454-00 | 2027-03-15 07:30 | 2027-03-17 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160119
IGH_ROB_1 | Tower Painting | 2027-03-15 07:30 | 2027-03-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1157292
RDF_T4 | RDF-TF-T4 | 2027-03-15 07:30 | 2027-03-25 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161471
HAM_T4 | HAM CT replacement project, HAM-CBL-ET4-NER4, HAM-CBL-T4-2242, HAM-CBL-T4-ET4, HAM-CT-402, HAM-NCT-4, HAM-P-TF-T4, HAM-RES-NER4, HAM-TF-ET4, HAM-TF-T4 | 2027-03-15 07:30 | 2027-03-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1156748
ALB_T8 | ALB T8 Transformer Protection Replacement | 2027-03-15 07:30 | 2027-03-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160136
EDG_TRK_2 | Attachment Points | 2027-03-15 07:30 | 2027-03-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160484
OTA_ROS_1 | 2 yrs, OTA-PEN-B0002A-0003-10, OTA-PEN-B1-Z-CBL-SHEATH, Attachment point, re-insulation and steel and bolts. CP_622_12_00_00 | 2027-03-15 07:30 | 2027-03-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161341
HAM_387_404_447 | HAM-DS-404, HAM-DS-407, HAM-DS-427 | 2027-03-15 07:30 | 2027-03-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160545
ARI_HAM_2 | ARI-HAM-B0061-20, ARI-HAM-B0062-20, ARI-HAM-B0072-20, ARI-HAM-B0073-20, ARI-HAM-B0074-20, ARI-HAM-B0080-20, ARI-HAM-B0081-20, ARI-HAM-B0082-20, ARI-HAM-B0093-20, ARI-HAM-B0108-20, ARI-HAM-B0119-20, ARI-HAM-B0120-20, ARI-HAM-B0129-20, ARI-HAM-B0132-20, ARI-HAM-B0135-20, ARI-HAM-B0136-20, ARI-HAM-B0140-20 | 2027-03-15 07:30 | 2027-03-20 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160167
ISL_T2 | ISL-DS-425 Headgear Replacement | 2027-03-15 08:00 | 2027-03-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005168
ISL_LST_8 | Affected Equipment of ISL_T2 ISL-DS-425 Headgear Replacement | 2027-03-15 08:00 | 2027-03-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005171
ISL_C_22 | Affected Equipment of ISL_T2 ISL-DS-425 Headgear Replacement | 2027-03-15 08:00 | 2027-03-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005169
ISL_CB_658 | Affected Equipment of ISL_220BS_D Affected equipment ISL-DS-425Headgear Replacement | 2027-03-15 08:00 | 2027-03-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005165
ISL_CB_608 | Affected Equipment of ISL_220BS_D Affected equipment ISL-DS-425Headgear Replacement | 2027-03-15 08:00 | 2027-03-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005164
ISL_LST_4 | Affected Equipment of ISL_T2 ISL-DS-425 Headgear Replacement | 2027-03-15 08:00 | 2027-03-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005170
ISL_220BS_D | Affected equipment ISL-DS-425 Headgear Replacement | 2027-03-15 08:00 | 2027-03-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005163
ISL_C_21 | Affected Equipment of ISL_220BS_D Affected equipment ISL-DS-425Headgear Replacement | 2027-03-15 08:00 | 2027-03-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005166
MTO_T2 | Affected Equipment Tower Painting | 2027-03-15 08:00 | 2027-03-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142860
HEN_MPE_2 | Tower Painting | 2027-03-15 08:00 | 2027-03-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142859
INV_ROX_2 | INV-ROX-B0027-00, INV-ROX-B0028-00, INV-ROX-B0029-00, INV-ROX-B0030-00, INV-ROX-B0031-00, INV-ROX-B0032-00, INV-ROX-B0036-00, INV-ROX-B0042-00, INV-ROX-B0043-00, INV-ROX-B0046-00, INV-ROX-B0048-00, INV-ROX-B0050-00, INV-ROX-B0051-00 | 2027-03-15 08:00 | 2027-03-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160788
WEL_T1 | Affected Equipment Tower Painting | 2027-03-15 08:00 | 2027-03-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142861
GLN_CB_658 | Affected equipment | 2027-03-15 12:00 | 2027-03-15 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162525
GLN_220BS_B | GLN bus clean with T4 | 2027-03-15 12:00 | 2027-03-15 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162524
GLN_CB_658 | Affected equipment | 2027-03-16 07:00 | 2027-03-16 11:59 | Daily | NNI | RS - Removal from Service | Approved | OW1162529
DRY_GLN_2 | GLN-BS-220-DRY-GLN-2 | 2027-03-16 07:00 | 2027-03-16 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160449
GLN_220BS_A | GLN bus clean with DRY_GLN_2 | 2027-03-16 07:00 | 2027-03-16 11:59 | Daily | NNI | RS - Removal from Service | Approved | OW1162527
HAY_TKR_2 | HAY_110BZ Stage 3A; Bay 60 - Takapu Rd cct 2. No other HAY workon days 1, 4, 5. No other work on associated equipment/lines onday 5 (commissioning). | 2027-03-16 07:00 | 2027-03-20 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162024
TKR_WIL_2 | Re-insulation x2. Attachment points. Affected equipment of TKR_127_174_184. | 2027-03-16 07:30 | 2027-03-19 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161636
TKR_T1 | Affected equipment of TKR_127_174_184 | 2027-03-16 07:30 | 2027-03-19 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161633
TKR_FDR_2272 | Reinsulation x2 structures | 2027-03-16 07:30 | 2027-03-17 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161632
BEN_F_3 | S1.WA-Z2.Q1, S1.WA-Z2.Q2, S1.WA-Z2.Z1.L1A, S1.WA-Z2.Z1.L1B, S1.WA-Z2.Z1.L1C, S1.WA-Z2.Z1.L2A, S1.WA-Z2.Z1.L2B, S1.WA-Z2.Z1.L2C,S1.WA-Z2.Z2.L1A, S1.WA-Z2.Z2.L1B, S1.WA-Z2.Z2.L1C, S1.WA-Z2.Z2.R1A, S1.WA-Z2.Z2.R1B | 2027-03-16 07:30 | 2027-03-18 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160270
TKR_CB_172_ITRIP | TKR-P-ITRP-CB-92-172 | 2027-03-16 07:30 | 2027-03-19 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161629
TKR_127_174_184 | TKR-DS-147, TKR-DS-164, TKR-DS-174, TKR-VT-1 | 2027-03-16 07:30 | 2027-03-19 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161625
OHB_1007_1107 | OHB-DS-1014 | 2027-03-16 07:30 | 2027-03-16 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161265
OHB_1106_1107 | OHB-DS-1114 | 2027-03-16 07:30 | 2027-03-16 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161266
PNI_TKR_2 | Affected equipment of TKR_127_174_184 | 2027-03-16 07:30 | 2027-03-19 18:29 | Continuous | SNI | RS - Removal from Service | Approved | OW1161449
CUL_FDR_142 | CUL-CB-142, CUL-P-CB-142 | 2027-03-16 07:30 | 2027-03-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160425
PNI_T2 | Affected equipment of PNI_TKR_2 | 2027-03-16 07:30 | 2027-03-19 18:29 | Continuous | SNI | RS - Removal from Service | Approved | OW1161446
HAY_110CBF | HAY_110BZ Stage 3A; Bay 60 - Takapu Rd cct 2. | 2027-03-16 08:00 | 2027-03-16 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161989
HAY_110BZ | HAY_110BZ Stage 3A; Bay 60 - Takapu Rd cct 2. No work in HAY 110kV yard. | 2027-03-16 08:00 | 2027-03-16 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161943
GLN_CB_658 | Affected equipment | 2027-03-16 12:00 | 2027-03-16 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162531
GLN_220BS_B | GLN bus clean with DRY_GLN_2 | 2027-03-16 12:00 | 2027-03-16 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162530
GLN_CB_658 | Affected equipment | 2027-03-17 07:00 | 2027-03-17 11:59 | Daily | NNI | RS - Removal from Service | Approved | OW1162564
GLN_220BS_A | GLN bus clean with T5 | 2027-03-17 07:00 | 2027-03-17 11:59 | Daily | NNI | RS - Removal from Service | Approved | OW1162563
GLN_T5 | GLN bus clean | 2027-03-17 07:00 | 2027-03-17 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162562
SBK_66BZ | SBK-P-BZ-66 | 2027-03-17 07:30 | 2027-03-17 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161525
GLN_CB_658 | Affected equipment | 2027-03-17 12:00 | 2027-03-17 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162566
GLN_220BS_B | GLN bus clean with T5 | 2027-03-17 12:00 | 2027-03-17 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162565
DRY_220BS_B | DRY CB 432 Siemens relay replacement | 2027-03-18 07:00 | 2027-03-19 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1162922
DRY_CB_462 | Affected equipment with bus B | 2027-03-18 07:00 | 2027-03-19 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1162923
DRY_GLN_1 | GLN-BS-220-DRY-GLN-1 | 2027-03-18 07:00 | 2027-03-19 18:00 | Continuous | NNI | RS - Removal from Service | Approved | OW1162497
GLN_220BS_A | GLN-BS-220-DRY-GLN-1 | 2027-03-18 07:00 | 2027-03-18 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162500
GLN_CB_658 | Affected equipment | 2027-03-18 07:00 | 2027-03-18 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162501
TKA_T6 | Affected Equipment of ABY_TKA_1 TKA-TIM-A0191-00 | 2027-03-18 07:30 | 2027-03-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161623
HAM_CB_1522 | Place HAM T7 into service for the duration of T8 outage. CT stability checks HAM CT replacement project | 2027-03-18 07:30 | 2027-03-19 18:30 | Continuous | NNI | CLO - Close | Approved | OW1156750
HAM_T8 | CT stability checks HAM CT replacement project | 2027-03-18 07:30 | 2027-03-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1156749
TKR_FDR_2142 | KHD-TKR-A0037-00, TKR gantry reinsulation/attachment points. | 2027-03-18 07:30 | 2027-03-19 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161631
ROS_AUVLS | ROS-P-UVLS | 2027-03-18 07:30 | 2027-03-18 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161479
ABY_TKA_1 | TKA-TIM-A0191-00 | 2027-03-18 07:30 | 2027-03-19 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160121
GLN_CB_658 | Affected equipment | 2027-03-19 07:00 | 2027-03-19 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162504
GLN_220BS_B | GLN-BS-220-DRY-GLN-1 | 2027-03-19 07:00 | 2027-03-19 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162503
PEN_FDR_2442 | PEN-CB-2442, PEN-P-CB-2442 | 2027-03-19 07:30 | 2027-03-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161417
PTS_1608_HEN_MPE | HEN-C-PTSG-1608B | 2027-03-19 07:30 | 2027-03-19 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161457
HAY_WIL_LTN_2 | Reinstate JFD_LTN_2 droppers [CP_770_007_0_00]. | 2027-03-19 07:30 | 2027-03-19 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160638
HAY_110CBF | HAY_110BZ Stage 3A; Bay 60 - Takapu Rd cct 2. | 2027-03-19 08:00 | 2027-03-19 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161990
HAY_110BZ | HAY_110BZ Stage 3A; Bay 60 - Takapu Rd cct 2. No work in HAY 110kV yard. | 2027-03-19 08:00 | 2027-03-19 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161944
HAY_110CBF | HAY_110BZ Stage 3A; Bay 60 - Takapu Rd cct 2. | 2027-03-20 08:00 | 2027-03-20 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161991
BEN_220CBF | Meridian Bay - T44/G3/G4 Migration CP_BEN_AZ_00_00 | 2027-03-20 08:00 | 2027-03-20 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005474
BEN_220BZ | Meridian Bay - T44/G3/G4 Migration CP_BEN_AZ_00_00 | 2027-03-20 08:00 | 2027-03-20 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005473
HAY_110BZ | HAY_110BZ Stage 3A; Bay 60 - Takapu Rd cct 2. No work in HAY 110kV yard. | 2027-03-20 08:00 | 2027-03-20 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161945
COL_OTI_2 | COL-OTI-A0031-00, COL-OTI-A0045-00, COL-OTI-A0119-00 | 2027-03-22 06:30 | 2027-03-24 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160398
CLH_COL_1 | COL-OTI-A0031-00, COL-OTI-A0045-00, COL-OTI-A0119-00 | 2027-03-22 06:30 | 2027-03-24 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160382
GLN_T6 | GLN-BS-220-T6-CLEAN, GLN-BS-33-T6-CLEAN | 2027-03-22 07:00 | 2027-03-22 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162567
GLN_220BS_A | GLN-BS-220-T6-CLEAN, GLN-BS-33-T6-CLEAN | 2027-03-22 07:00 | 2027-03-22 11:59 | Daily | NNI | RS - Removal from Service | Approved | OW1162568
GLN_CB_658 | Affected equipment | 2027-03-22 07:00 | 2027-03-22 11:59 | Daily | NNI | RS - Removal from Service | Approved | OW1162569
GLN_CB_2318 | Open for the duration of T6 | 2027-03-22 07:00 | 2027-03-22 18:00 | Daily | NNI | OPE - Open Ended | Approved | OW1162570
GLN_CB_2348 | Closed for the duration of T6 | 2027-03-22 07:00 | 2027-03-22 18:00 | Daily | NNI | CLO - Close | Approved | OW1162571
GLN_DIS_2347 | Closed for the duration of T6 | 2027-03-22 07:00 | 2027-03-22 18:00 | Daily | NNI | CLO - Close | Approved | OW1162572
KAI_SBK_1 | Affected Equipment of KAI_74_87 KAI VTJB Replacement | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005516
TMK_TIM_1_TMK_T1 | Lines ONLY -ASH-TIM-A0422-00, ASH-TIM-A0423-00, ASH-TIM-A0456-10, ASH-TIM-A0459-00, TMK-CVT-CVT132 | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161653
MDN_LST_5B | Affected equipment MDN T5 | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1163030
MDN_437_457_467 | MDN-DS-434, MDN-DS-437, MDN-DS-454, MDN-DS-457 | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161034
KAI_T1 | Affected Equipment of KAI_74_87 KAI VTJB Replacement | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005517
HPI_MDN_1 | CB Pole replacement, conductor repairs projects. HPI-CB-372, MDN-CVT-452, MDN-DS-456, MDN-ES-459, MDN-P-CB-452 | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160726
MPE_CB_292 | System split for the duration of HPI_MDN_1 | 2027-03-22 07:30 | 2027-03-22 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161157
MPE_CB_252 | System split for the duration of HPI_MDN_1 | 2027-03-22 07:30 | 2027-03-22 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161122
KAI_74_87 | KAI VTJB Replacement | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005515
INV_MAN_2 | Tower Painting | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143096
MDN_T5 | Affected equipment MDN_437_457_467 & HPI_MDN_1 | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161046
MDN_CB_508 | Affected equipment MDN_437_457_467 & HPI_MDN_1 | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161039
HLY_CB_682 | HLY-P-CB-682 | 2027-03-22 08:00 | 2027-03-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160711
HLY_OHW_2 | HLY-DS-223, HLY-DS-226, HLY-DS-245, HLY-ES-229 | 2027-03-22 08:00 | 2027-03-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160712
GLN_CB_658 | Affected equipment | 2027-03-22 12:00 | 2027-03-22 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162574
GLN_220BS_B | GLN-BS-220-T6-CLEAN, GLN-BS-33-T6-CLEAN | 2027-03-22 12:00 | 2027-03-22 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162573
MPE_CB_252 | System split for the duration of HPI_MDN_1 | 2027-03-23 06:00 | 2027-03-24 22:00 | Continuous | NNI | OPE - Open Ended | Approved | OW1161123
MPE_CB_292 | System split for the duration of HPI_MDN_1 | 2027-03-23 06:00 | 2027-03-24 22:00 | Continuous | NNI | OPE - Open Ended | Approved | OW1161158
GLN_CB_658 | Affected equipment | 2027-03-23 07:00 | 2027-03-23 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162576
GLN_220BS_A | GLN 220kV bus Clean | 2027-03-23 07:00 | 2027-03-23 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162575
BEN_TWZ_1 | BEN-CT-CT472, BEN-CVT-VT3, BEN-DS-473, BEN-DS-476, BEN-ES-479, TWZ-CT-CT2562, TWZ-CVT-CVT2562, TWZ-DS-2565, TWZ-DS-2566, TWZ-DS-2573, TWZ-ES-2569, TWZ-P-CB-2562 | 2027-03-23 07:30 | 2027-03-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160287
BEN_220CBF | Required to test BZ scheme after 473 mech box replaced. | 2027-03-23 07:30 | 2027-03-25 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1162134
BEN_220BZ | Required to test BZ scheme after 473 mech box replaced. | 2027-03-23 07:30 | 2027-03-25 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1162133
BEN_220BS_B | Required to replace BEN-DS-473 mech box while BEN_TWZ_1 OOS. | 2027-03-23 07:30 | 2027-03-25 18:00 | Continuous | SI | RS - Removal from Service | Approved | OW1162132
GLN_CB_658 | Affected equipment | 2027-03-24 07:00 | 2027-03-24 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162578
GLN_220BS_B | GLN 220kV bus clean | 2027-03-24 07:00 | 2027-03-24 18:00 | Daily | NNI | RS - Removal from Service | Approved | OW1162577
MPE_CB_292 | System split for the duration of HPI_MDN_1 | 2027-03-25 06:00 | 2027-03-25 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161159
MPE_CB_252 | System split for the duration of HPI_MDN_1 | 2027-03-25 06:00 | 2027-03-25 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161124
BEN_220BZ | Meridian Bay - T44/G3/G4 Migration CP_BEN_AZ_00_00 | 2027-03-26 08:00 | 2027-03-26 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005477
BEN_220CBF | Meridian Bay - T44/G3/G4 Migration CP_BEN_AZ_00_00 | 2027-03-26 08:00 | 2027-03-26 18:00 | Daily | SI | RS - Removal from Service | Approved | OW2005475
MHO_T4 | MHO-TF-T4 | 2027-03-30 07:30 | 2027-04-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161056
STK_T6 | STK-CBL-ET6, STK-CBL-NER6, STK-CBL-T6-2132, STK-CT-2132, STK-CT-CT702, STK-CT-T6HV, STK-TF-ET6, STK-TF-T6 | 2027-03-30 07:30 | 2027-04-03 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161563
STK_DIS_807 | Affected equipment STK_727_777 & STK_T6 | 2027-03-30 07:30 | 2027-04-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161560
STK_AVR_T6 | Affected equipment STK_727_777 & STK_T6 | 2027-03-30 07:30 | 2027-04-03 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161555
STK_727_777 | STK-DS-704, STK-DS-707 | 2027-03-30 07:30 | 2027-04-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161554
BPE_MHO_2 | Shelterbelt tree works. Conductor repairs x2 spans [MP_RA4_03N_0_00]. Affected equipment of MHO_T4 | 2027-03-30 07:30 | 2027-04-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160332
KIN_TRK_2 | ARI-EDG-B Structure Replacement Project | 2027-03-30 07:30 | 2027-04-02 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005925
KOE_MPE_2 | KOE-CB-102, KOE-CT-102, KOE-DS-106, KOE-ES-109, KOE-MPE-A0086-20, KOE-MPE-A0089-20, KOE-P-CB-102 | 2027-03-30 07:30 | 2027-04-02 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160978
MTI_WPA_1 | MTI-P-CB-92 [CP_MTI_002_0_00]. Tower painting x13 (A1-A13) [CP_702_001_0_00]. | 2027-03-30 07:30 | 2027-04-10 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161175
OTA_SWN_1 | OTA-DS-575, OTA-DS-573, HEN-OTA-A0013-20, OTA-CT-572, OTA-CVT-572, OTA-DS-576, OTA-ES-579, OTA-P-CB-572 | 2027-03-30 07:30 | 2027-04-02 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161344
LFD_DIS_76 | Affected Equipment of KIN_TRK_2 ARI-EDG-B Structure ReplacementProject | 2027-03-30 07:30 | 2027-04-02 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005926
HAY_TKR_1 | HAY_110BZ Stage 3B; Bay 80 - Takapu Rd cct 1. No other HAY workon days 1, 4, 5. No other work on associated equipment/lines onday 5 (commissioning). HAY-CT-82. | 2027-03-31 07:00 | 2027-04-04 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162023
KAW_T12_T13_OPS | KAW-P-SPS-TF | 2027-03-31 07:30 | 2027-04-02 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160905
OTA_537_597_587 | OTA-DS-573, HEN-OTA-A0013-20, OTA-CT-572, OTA-CVT-572, OTA-DS-576, OTA-ES-579, OTA-P-CB-572 | 2027-03-31 07:30 | 2027-03-31 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161317
TWZ_T18 | TWZ-CBL-2188-2217, TWZ-CBL-LS18-2232, TWZ-CBL-T18-2232, TWZ-CBL-T18-NER18, TWZ-RES-NER-18, TWZ-TF-LS18 | 2027-03-31 07:30 | 2027-04-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161746
BPE_T2 | BPE-TNG prot upgrade Stage 9: BPE-T2 protection upgrade [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-03-31 07:30 | 2027-04-11 17:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161891
TWZ_CB_2532 | Affected equipment TWZ_2676_2437 & OHB_TWZ_3 & TWZ_T18 | 2027-03-31 07:30 | 2027-04-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161744
TWZ_CB_2462 | Affected equipment TWZ_2676_2437 & OHB_TWZ_3 & TWZ_T18 | 2027-03-31 07:30 | 2027-04-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161743
OTA_CB_598 | Affected Equipment of OTA_537_597_587 OTA-DS-573, HEN-OTA-A0013-20, OTA-CT-572, OTA-CVT-572, OTA-DS-576, OTA-ES-579, OTA-P-CB-572 | 2027-03-31 07:30 | 2027-03-31 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161335
OTA_CB_538 | Affected Equipment of OTA_537_597_587 OTA-DS-573, HEN-OTA-A0013-20, OTA-CT-572, OTA-CVT-572, OTA-DS-576, OTA-ES-579, OTA-P-CB-572 | 2027-03-31 07:30 | 2027-03-31 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161334
OHB_TWZ_3 | Affected Equipment of TWZ_2676_2437 TWZ-DS-2534 | 2027-03-31 07:30 | 2027-04-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005904
TWZ_2676_2437 | TWZ-DS-2534 | 2027-03-31 07:30 | 2027-04-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161741
BPE_110CBF | Affected equipment of BPE_110BZ, for BPE-TNG prot upgrade Stage9 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-03-31 08:00 | 2027-03-31 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005595
BPE_220CBF | Affected equipment of BPE_220BZ, for BPE-TNG prot upgrade Stage9 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-03-31 08:00 | 2027-03-31 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005596
BPE_220BZ | BPE-TNG prot upgrade Stage 9: BPE-T2 protection upgrade [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-03-31 08:00 | 2027-03-31 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005583
HAY_110CBF | HAY_110BZ Stage 3B; Bay 80 - Takapu Rd cct 1. | 2027-03-31 08:00 | 2027-03-31 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161992
BPE_110BZ | BPE-TNG prot upgrade Stage 9: BPE-T2 protection upgrade [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-03-31 08:00 | 2027-03-31 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005584
HAY_110BZ | HAY_110BZ Stage 3B; Bay 80 - Takapu Rd cct 1. No work in HAY 110kV yard. | 2027-03-31 08:00 | 2027-03-31 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161946
MAN_NMA_3 | Tower Painting | 2027-03-31 09:00 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143098
OTA_527_587_597 | OTA-DS-575, HEN-OTA-A0013-20, OTA-CT-572, OTA-CVT-572, OTA-DS-576, OTA-ES-579, OTA-P-CB-572 | 2027-04-01 07:30 | 2027-04-01 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161316
KIN_T8 | KIN-M-CT2542, KIN-M-VT2542, KIN-TF-T8 | 2027-04-01 07:30 | 2027-04-02 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160950
OTA_CB_528 | Affected Equipment of OTA_527_587_597 OTA-DS-575, HEN-OTA-A0013-20, OTA-CT-572, OTA-CVT-572, OTA-DS-576, OTA-ES-579, OTA-P-CB-572 | 2027-04-01 07:30 | 2027-04-01 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161332
SBK_WPR_1 | SBK-WPR-A0006-0007-20, SBK-WPR-A0025-0026-20, SBK-WPR-A0077-0078-20 | 2027-04-01 07:30 | 2027-04-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161529
OTA_CB_598 | Affected Equipment of OTA_527_587_597 OTA-DS-575, HEN-OTA-A0013-20, OTA-CT-572, OTA-CVT-572, OTA-DS-576, OTA-ES-579, OTA-P-CB-572 | 2027-04-01 07:30 | 2027-04-01 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161336
HEP_FDR_2252 | HEP-CB-2252, HEP-P-CB-2252 | 2027-04-01 07:30 | 2027-04-01 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160681
KAI_11BS_R | KAI-BS-11-REAR | 2027-04-02 07:30 | 2027-04-02 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160882
HAY_110BZ | HAY_110BZ Stage 3B; Bay 80 - Takapu Rd cct 1. No work in HAY 110kV yard. | 2027-04-03 08:00 | 2027-04-03 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161947
HAY_110CBF | HAY_110BZ Stage 3B; Bay 80 - Takapu Rd cct 1. | 2027-04-03 08:00 | 2027-04-03 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161993
HAY_110CBF | HAY_110BZ Stage 3B; Bay 80 - Takapu Rd cct 1. | 2027-04-04 08:00 | 2027-04-04 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161994
HAY_110BZ | HAY_110BZ Stage 3B; Bay 80 - Takapu Rd cct 1. No work in HAY 110kV yard. | 2027-04-04 08:00 | 2027-04-04 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161948
IGH_ROB_2 | Tower Steel Replacement on IGH-WMG-A line.-IGH-WMG-A0061, IGH-WMG-A0062, IGH-WMG-A0064, IGH-WMG-A0065 | 2027-04-05 06:30 | 2027-04-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1163103
ARI_HTI_ONG_1 | Tower painting x10 (B231-B240) [CP_708_002_0_00] | 2027-04-05 07:00 | 2027-04-16 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160170
KIN_TRK_2 | ARI-EDG-B0067A-00, ARI-EDG-B0080-00, ARI-EDG-B0118-00, ARI-EDG-B0145-00, ARI-EDG-B0148-00, ARI-EDG-B0153-00, KIN-CT-352, LCH-KIN-B0604-00, LCH-KIN-B0615-00, LCH-KIN-B0643-00, LCH-KIN-B0657-00, LFD-DS-76, TRK-DEV-B0015-00, TRK-DEV-B0016-00 | 2027-04-05 07:30 | 2027-04-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160953
HOB_T12 | HOB-CBL-T12-110, HOB-NCT-12, HOB-TF-T12 | 2027-04-05 07:30 | 2027-04-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160719
MST_GYT_UHT_2 | MST-DCB-82, UHT-CB-62, UHT-CT-62, UHT-DS-66, UHT-ES-69, UHT-P-CB-62. GYT/MGM/MST/UHT/WDV duplicated protection upgrade project Stage 3 [CP_VAR_21A_0_00]. | 2027-04-05 07:30 | 2027-04-07 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161170
GYT_T3 | GYT-TF-T3 | 2027-04-05 07:30 | 2027-04-07 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160541
KIK_CB_328 | KIK-P-CB-328 | 2027-04-05 07:30 | 2027-04-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160919
KAI_T2 | Affected Equipment of KAI_87_94 Safety for new CB82 Pole Replacement | 2027-04-05 07:30 | 2027-04-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005521
KIK_CB_398 | Affected equipment KIK_220BS_B & KIK_CB_328 | 2027-04-05 07:30 | 2027-04-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160925
MST_T3 | Affected equipment of MST_67_44, for MST-DCB-82 (GYT-UHT-2) | 2027-04-05 07:30 | 2027-04-05 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161171
KIK_220BS_B | affected equipment KIK_CB_398, KIK_CB_328 | 2027-04-05 07:30 | 2027-04-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160917
ISL_KIK_1 | ISL-CVT-VT572, ISL-DS-573, ISL-DS-575, ISL-DS-576, ISL-ES-579, ISL-KIK-A0276-10, KIK-CVT-VT362, KIK-DS-366 | 2027-04-05 07:30 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160860
TRK_124_157 | TRK-BS-110-124-147, TRK-VT-VT137 | 2027-04-05 07:30 | 2027-04-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161702
MST_67_44 | MST-DCB-82 (GYT-UHT-2) | 2027-04-05 07:30 | 2027-04-05 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161168
INV_TWI_2 | INV-DS-615, INV-P-CB-612/642, INV-TWI-A0002-20, INV-TWI-A0005-20, INV-TWI-A0006-20, INV-TWI-A0010-20, INV-TWI-A0017-20, INV-TWI-A0019-20, INV-TWI-A0020-20, INV-TWI-A0023-20, INV-TWI-A0031-0032-20, INV-TWI-A0031-20, INV-TWI-A0032-20, INV-TWI-A0033-20, INV-TWI-A0047-0048-20, INV-TWI-A0048-0049-20, INV-TWI-A0049-0050-20,INV-TWI-A0050-0051-20, INV-TWI-AINVG16-10, INV-TWI-ATWIB4-10, TWI-P-CB-402, TWI-SA-1, FM3 roller door servicing | 2027-04-05 07:30 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160796
INV_CB_642 | INV-DS-615, INV-P-CB-612/642, INV-TWI-A0002-20, INV-TWI-A0005-20, INV-TWI-A0006-20, INV-TWI-A0010-20, INV-TWI-A0017-20, INV-TWI-A0019-20, INV-TWI-A0020-20, INV-TWI-A0023-20, INV-TWI-A0031-0032-20, INV-TWI-A0031-20, INV-TWI-A0032-20, INV-TWI-A0033-20, INV-TWI-A0047-0048-20, INV-TWI-A0048-0049-20, INV-TWI-A0049-0050-20,INV-TWI-A0050-0051-20, INV-TWI-AINVG16-10, INV-TWI-ATWIB4-10, TWI-P-CB-402, TWI-SA-1, FM3 roller door servicing | 2027-04-05 07:30 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160774
LFD_DIS_76 | Affected equipment TRK_124_157 & KIN_TRK_2 | 2027-04-05 07:30 | 2027-04-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161011
WEL_T2 | Affected Equipment OVR031104 | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142858
MTO_T1 | Affected Equipment OVR031104 | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142857
HEN_MPE_1 | Tower Painting | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142856
BDE_11BZ | BDE-M-CT-BUS-B, BDE-M-VT20 | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005891
ISL_CB_658 | Affected Equipment of ISL_220BS_E ISL-DS-575 ISL-DS-575 | 2027-04-05 08:00 | 2027-04-07 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160828
HLY_164_397 | HLY-DS-384, HLY-ES-379 | 2027-04-05 08:00 | 2027-04-07 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160697
BDE_11BS_B | BDE-M-CT-BUS-B, BDE-M-VT20 | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160207
SVL_T1 | Affected equipment Tower Painting | 2027-04-05 08:00 | 2027-04-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142688
ALB_SVL_1 | Tower Painting | 2027-04-05 08:00 | 2027-04-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142687
HLY_CB_262 | HLY-P-CB-262 | 2027-04-05 08:00 | 2027-04-07 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160704
ISL_220BS_E | ISL-DS-575 ISL-DS-575 | 2027-04-05 08:00 | 2027-04-07 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160802
BDE_C_4 | BDE-CAPS-C4, BDE-CBL-20, BDE-REA-C4 | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160212
BDE_C_5 | BDE-CAPS-C5, BDE-CBL-21, BDE-REA-C5 | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160213
BDE_CB_38 | Affected equipment BDE_11BS_B & BDE_C_4 & BDE_C_5 | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160214
BDE_FDR_23 | Affected equipment BDE_11BS_B & BDE_C_4 & BDE_C_5 | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160216
BDE_FDR_24 | Affected equipment BDE_11BS_B & BDE_C_4 & BDE_C_5 | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160217
BDE_FDR_25 | Affected equipment BDE_11BS_B & BDE_C_4 & BDE_C_5 | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160218
BDE_T2 | Affected equipment BDE_11BS_B & BDE_C_4 & BDE_C_5 | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160222
HLY_T21 | HLY-P-TF-T21, HLY-TF-T21 | 2027-04-05 08:00 | 2027-04-07 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160713
HAM_STC_3 | CP_HAM_OS_00_00 ES & SA replacement works | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160568
ISL_CB_688 | Affected Equipment of ISL_220BS_E ISL-DS-575 ISL-DS-575 | 2027-04-05 08:00 | 2027-04-07 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160835
BDE_11CBF | BDE-M-CT-BUS-B, BDE-M-VT20 | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005890
HAM_C_1 | Affected Equipment of HAM_147_VT157 CP_HAM_OS_00_00 ES & SA replacement works | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160547
HLY_CB_382 | Affected equipment | 2027-04-05 08:00 | 2027-04-07 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162245
BDE_11BS_B_AFD | BDE-M-CT-BUS-B, BDE-M-VT20 | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005889
HAM_147_VT157 | CP_HAM_OS_00_00 ES & SA replacement works | 2027-04-05 08:00 | 2027-04-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160543
LIV_WTK_1 | AVI-LIV-A0026-00 | 2027-04-06 07:30 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161014
WTK_T21 | Affected equipment WTK_56_447 & LIV_WTK_1 & WTK_CB_438 & WTK_T23 & OAM_STU_BPD_WTK_2 & OAM_T2 | 2027-04-06 07:30 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161872
HWA_T2 | OPE for the duration of HWA_SFD_1, to prevent recirculating currents through the HWA 33kV | 2027-04-06 07:30 | 2027-04-08 18:30 | Continuous | SNI | OPE - Open Ended | Approved | OW2005190
WTK_T28 | WTK-CB-1002, WTK-P-CB-18 | 2027-04-06 07:30 | 2027-04-09 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161877
WTK_LST_31 | Affected Equipment of WTK_T21 Affected equipment WTK_56_447 & LIV_WTK_1 & WTK_CB_438 & WTK_T23 & OAM_STU_BPD_WTK_2 & OAM_T2 | 2027-04-06 07:30 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161870
WTK_11BS_A | Affected Equipment of WTK_T21 Affected equipment WTK_56_447 & LIV_WTK_1 & WTK_CB_438 & WTK_T23 & OAM_STU_BPD_WTK_2 & OAM_T2 | 2027-04-06 07:30 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161865
WTK_56_447 | WTK-DS-394, WTK-DS-414, WTK-DS-424, WTK-DS-437, WTK-ES-430 | 2027-04-06 07:30 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161867
WTK_CB_438 | WTK-P-CB-438 | 2027-04-06 07:30 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161868
HWA_SFD_1 | Pole replacement x1 (A499). | 2027-04-06 07:30 | 2027-04-08 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160746
BEN_F_6 | S1.20DB74-C3A, S1.20DB74-C3B, S1.20DB74-C3C, S1.20DB74-FB6, S1.20DB74-L3A, S1.20DB74-L3B, S1.20DB74-L3C, S1.20DB74-Q01, S1.20DB74-Q02, S1.20DB74-R1A, S1.20DB74-R1B, S1.20DB74-R1C, S1.20DB74-R2A, S1.20DB74-R2B, S1.20DB74-R2C, S1.20DB74-R3A, S1.20DB74-R3B, S1.20DB74-R3C | 2027-04-06 07:30 | 2027-04-08 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160276
ASB_TIM_TWZ_2 | ASB-CT-CT492, ASB-CVT-VT492, ASB-DS-496, ASB-P-CB-492, TIM-CVT-CVT282, TIM-DS-286, TIM-ES-289, TWZ-CT-CT2412, TWZ-CVT-CVT2412, TWZ-DS-2415, TWZ-DS-2416, TWZ-DS-2423, TWZ-ES-2419, TWZ-P-CB-2412 | 2027-04-07 06:30 | 2027-04-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160192
ASB_T10 | ASB-M-CT82, ASB-M-VT82 | 2027-04-07 07:30 | 2027-04-08 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160188
ASB_ISL_1 | ASB-DS-426, CHH-TWZ-A0308-20, ISL-DS-443, ISL-DS-445 | 2027-04-07 07:30 | 2027-04-08 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160187
ASB_FDR_82 | Affected equipment ASB_417_424_494 & ASB_ISL_1 & ASB_T10 | 2027-04-07 07:30 | 2027-04-08 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160185
HEP_ROS_2 | HEP-ROS-A0083-0084-00 | 2027-04-07 07:30 | 2027-04-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160684
ASB_417_424_494 | ASB-DS-424 | 2027-04-07 07:30 | 2027-04-08 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160179
OTA_STC_15 | OTA-COOL-STC15, OTA-STC-15 | 2027-04-07 07:30 | 2027-04-07 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1161343
CUL_T23 | CUL-P-TF-T23, CUL-TF-T23 | 2027-04-07 07:30 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160429
TIM_T8 | Affected equipment ASB_TIM_TWZ_2 | 2027-04-07 07:30 | 2027-04-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161620
KAW_CB_2818 | KAW-CB-2818 | 2027-04-08 07:30 | 2027-04-08 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160894
ISL_CB_668 | Affected Equipment of ISL_220BS_F ISL-DS-573 ISL-DS-573 | 2027-04-08 07:30 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160831
ISL_CB_688 | Affected Equipment of ISL_220BS_F ISL-DS-573 ISL-DS-573 | 2027-04-08 07:30 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160836
ASB_CB_492 | ASB-P-CB-492 Transmission circuit protection Diagnostic inspection and service | 2027-04-08 07:30 | 2027-04-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160182
ISL_220BS_F | ISL-DS-573 ISL-DS-573 | 2027-04-08 07:30 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160805
ROS_T4 | ROS-M-CT2312, ROS-M-VT2312 | 2027-04-08 07:30 | 2027-04-09 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161488
ISL_SBK_1 | ISL-CB-342 | 2027-04-08 07:30 | 2027-04-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160863
BRK_T1 | BRK 33kV site shut (alternate date 18/04/27). BRK-DS-583, BRK-TF-T1B, BRK-TF-T1R, BRK-TF-T1Y. | 2027-04-10 07:30 | 2027-04-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160371
BRK_LST_1 | Affected equipment of BRK 33kV site shut (alternate date 18/04/27) | 2027-04-10 07:30 | 2027-04-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160366
BRK_FDR_1112 | BRK 33kV site shut (alternate date 18/04/27). BRK-CB-1112, BRK-CT-1112, BRK-DS-1116, BRK-ES-1119. | 2027-04-10 07:30 | 2027-04-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160364
BRK_FDR_1092 | Affected equipment of BRK 33kV site shut (alternate date 18/04/27) | 2027-04-10 07:30 | 2027-04-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160363
BRK_DIS_1101 | Affected equipment of BRK 33kV site shut (alternate date 18/04/27) | 2027-04-10 07:30 | 2027-04-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160362
BRK_1094_1104_1114 | Affected equipment of BRK 33kV site shut (alternate date 18/04/27) | 2027-04-10 07:30 | 2027-04-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160358
BPE_110CBF | Affected equipment of BPE_110BZ, for BPE-TNG prot upgrade Stage9 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-04-10 08:00 | 2027-04-10 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005598
BPE_110BZ | BPE-TNG prot upgrade Stage 9: BPE-T2 protection upgrade [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-04-10 08:00 | 2027-04-10 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005586
BPE_220BZ | BPE-TNG prot upgrade Stage 9: BPE-T2 protection upgrade [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-04-10 08:00 | 2027-04-10 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005585
BPE_220CBF | Affected equipment of BPE_220BZ, for BPE-TNG prot upgrade Stage9 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-04-10 08:00 | 2027-04-10 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005597
DRY_BOB_HLY_2 | HLY-OTA-A0030-20, HLY-OTA-A0070-00, HLY-OTA-A0092-20, HLY-OTA-A0096-00, HLY-OTA-A0099-20, HLY-OTA-A0100-20 | 2027-04-12 07:30 | 2027-04-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160447
BOB_T5 | BOB-TF-T5 | 2027-04-12 07:30 | 2027-04-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160314
BDE_C_1 | BDE-CAPS-C1, BDE-CBL-17 | 2027-04-12 07:30 | 2027-04-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160210
BOB_FDR_242 | Affected equipment BOB_214_227_267 & ARI_BOB_1 & BOB_T5 | 2027-04-12 07:30 | 2027-04-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160310
BOB_FDR_212 | Affected equipment BOB_214_227_267 & ARI_BOB_1 & BOB_T5 | 2027-04-12 07:30 | 2027-04-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160309
BOB_214_227_267 | BOB-DS-227, BOB-DS-247 | 2027-04-12 07:30 | 2027-04-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160308
ROS_FDR_142 | Protection replacement ROS-P-CB-142 | 2027-04-12 07:30 | 2027-04-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161481
MTI_WKM_1 | Tower painting x7 (A1-A3, A16, A23-A25) [CP_703_001_0_00]. | 2027-04-12 07:30 | 2027-04-16 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161173
MAN_NMA_1 | Tower Painting | 2027-04-12 07:30 | 2027-04-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143115
INV_CB_722 | INV-DS-716, INV-P-CB-712/722, INV-TWI-A0002-00, INV-TWI-A0002-10, INV-TWI-A0003-00, INV-TWI-A0005-10, INV-TWI-A0006-00, INV-TWI-A0006-10, INV-TWI-A0007-00, INV-TWI-A0010-00, INV-TWI-A0010-10,INV-TWI-A0011-00, INV-TWI-A0017-00, INV-TWI-A0017-10, INV-TWI-A0019-10, INV-TWI-A0020-10, INV-TWI-A0023-00, INV-TWI-A0023-10, INV-TWI-AINVP1-10, INV-TWI-ATWIB3-10, TWI-P-CB-442, TWI-SA-2, FM3roller door servicing | 2027-04-12 07:30 | 2027-04-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160778
HOB_220BZ_A_PROT1 | HOB-P-BZ-220 | 2027-04-12 07:30 | 2027-04-13 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160716
HOB_220CBF_PROT1 | Affected equipment | 2027-04-12 07:30 | 2027-04-13 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160717
INV_TWI_1 | INV-DS-716, INV-P-CB-712/722, INV-TWI-A0023-10, INV-TWI-A0028-00, INV-TWI-A0031-10, INV-TWI-A0032-00, INV-TWI-A0032-10, INV-TWI-A0033-10, INV-TWI-A0047-0048-10, INV-TWI-A0048-0049-00, INV-TWI-A0048-0049-10, INV-TWI-A0049-0050-00, INV-TWI-A0050-0051-00, INV-TWI-A0050-0051-10, INV-TWI-A0051-0052-00, INV-TWI-AINVP1-10, INV-TWI-ATWIB3-10, TWI-P-CB-442, TWI-SA-2, FM3 roller door servicing | 2027-04-12 07:30 | 2027-04-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160794
KAI_87_94 | Safety for new CB82 Pole Replacement | 2027-04-12 07:30 | 2027-04-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005520
KAI_SBK_2 | Safety for new CB82 Pole Replacement | 2027-04-12 07:30 | 2027-04-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005519
BRB_T2 | BRB-CBL-112, BRB-TF-T2 | 2027-04-12 07:30 | 2027-04-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160356
WKM_220BS_C | WKM-DS-45 (MTI_1), WKM-DS-75 (OTA_2), WKM-DS-325 (TIE_2). | 2027-04-12 07:30 | 2027-04-12 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161806
WKM_CB_228 | Affected equipment of WKM_220BS_C, for WKM 3DS mtce. | 2027-04-12 07:30 | 2027-04-12 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161808
BRK_FDR_1112 | Required for 1x day on its own, following BRK 33kV shut. | 2027-04-12 07:30 | 2027-04-12 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160365
WKM_CB_288 | Affected equipment of WKM_220BS_C, for WKM 3DS mtce. | 2027-04-12 07:30 | 2027-04-12 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161810
OTA_ROS_1 | Attachment point, re-insulation and steel and bolts | 2027-04-12 08:00 | 2027-04-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005192
MPE_CB_252 | System split for the duration of ALB_HPI_1 | 2027-04-12 08:00 | 2027-04-12 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161125
ALB_HPI_1 | Tower Painting | 2027-04-12 08:00 | 2027-04-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142695
HPI_MDN_1 | Affected Equipment Tower Painting | 2027-04-12 08:00 | 2027-04-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142696
MPE_CB_292 | System split for the duration of ALB_HPI_1 | 2027-04-12 08:00 | 2027-04-12 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161160
MPE_CB_252 | System split for the duration of ALB_HPI_1 | 2027-04-13 06:00 | 2027-04-15 22:00 | Continuous | NNI | OPE - Open Ended | Approved | OW1161126
MPE_CB_292 | System split for the duration of ALB_HPI_1 | 2027-04-13 06:00 | 2027-04-15 22:00 | Continuous | NNI | OPE - Open Ended | Approved | OW1161161
ASB_BRY_1 | Affected Equipment of ASB_337_364_386_407 ASB-DS-384 | 2027-04-13 07:30 | 2027-04-13 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005172
NPK_RTU_1 | SMS & GPS replacements [CP_RA3_03C_0_00] | 2027-04-13 07:30 | 2027-04-13 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161254
BEN_T27 | BEN-NCTD-T27 | 2027-04-13 07:30 | 2027-04-15 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160282
ASB_T3 | Affected Equipment of ASB_337_364_386_407 ASB-DS-384 | 2027-04-13 07:30 | 2027-04-13 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005173
CUL_104_117_127 | Affected equipment CUL_T1 | 2027-04-13 07:30 | 2027-04-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160418
CUL_1236_1276_1271 | Affected equipment CUL_T1 | 2027-04-13 07:30 | 2027-04-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160419
ASB_CB_398 | Affected equipment ASB_337_364_386_407 & ASB_BRY_1 & ASB_T3 | 2027-04-13 07:30 | 2027-04-13 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160181
CUL_66BS | Affected equipment CUL_T1 | 2027-04-13 07:30 | 2027-04-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160420
CUL_CB_102 | Affected equipment CUL_T1 | 2027-04-13 07:30 | 2027-04-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160421
CUL_CB_142 | Affected Equipment of CUL_104_117_127 Affected equipment CUL_T1 | 2027-04-13 07:30 | 2027-04-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160422
ASB_337_364_386_407 | ASB-DS-384 | 2027-04-13 07:30 | 2027-04-13 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160176
CUL_T1 | CUL-CB-102, CUL-CB-1232 | 2027-04-13 07:30 | 2027-04-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160426
OHK_220CBF | OHK-P-CB-132 | 2027-04-14 07:30 | 2027-04-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161276
ASB_FDR_42 | Affected equipment ASB_347_296 & ASB_T1 | 2027-04-14 07:30 | 2027-04-16 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160183
EDG_110KV_BZ | EDG-P-BZ-110-A | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160469
HLY_CB_342 | Affected equipment HLY_224_344_357 & HLY_T22 | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160705
EDG_110CBF | Affected equipment | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160468
ASB_347_296 | ASB-DS-294 | 2027-04-14 07:30 | 2027-04-16 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160177
CUL_FDR_1242 | CUL-CB-1242, CUL-P-CB-1242 | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160424
ASB_T1 | Affected Equipment of ASB_347_296 ASB-DS-294 | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005176
HLY_CB_222 | Affected equipment HLY_224_344_357 & HLY_T22 | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160702
HLY_224_344_357 | HLY-DS-224, HLY-DS-324, HLY-DS-344, HLY-ES-339 | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160700
PTS_1872_MAN_NMA | MAN-C-PTSG-1872, NMA-C-PTSG-1872 | 2027-04-14 07:30 | 2027-04-14 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161459
WTK_T23 | WTK-NCTD-T23 | 2027-04-14 07:30 | 2027-04-15 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161874
ASB_T8 | ASB-NCDT-T8 Affected equipment ASB_347_296 & ASB_T1 | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160189
HAY_110BZ | HAY-P-BZ-110, HAY-P-BZ-110-A1, HAY-P-BZ-110-A2, HAY-P-BZ-110-B,HAY-P-BZ-110-CK | 2027-04-14 07:30 | 2027-04-14 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160578
HLY_T22 | HLY-P-TF-T22, HLY-TF-T22 | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160714
MPE_CB_252 | System split for the duration of ALB_HPI_1 | 2027-04-16 06:00 | 2027-04-16 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161127
MPE_CB_292 | System split for the duration of ALB_HPI_1 | 2027-04-16 06:00 | 2027-04-16 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161162
ASB_TIM_TWZ_1 | ASB-DS-296, CHH-TWZ-A0236-10, CHH-TWZ-A0239-10, CHH-TWZ-A0248-10, CHH-TWZ-A0249-10, CHH-TWZ-A0250-10, CHH-TWZ-A0253-10, CHH-TWZ-A0254-10, CHH-TWZ-A0255-10, CHH-TWZ-A0256-10, CHH-TWZ-A0271-10,CHH-TWZ-A0272-10, CHH-TWZ-A0273-10, CHH-TWZ-A0274-10, CHH-TWZ-A0275-10, CHH-TWZ-A0276-10, CHH-TWZ-A0277-10, CHH-TWZ-A0278-10, CHH-TWZ-A0279-10, CHH-TWZ-A0280-10, CHH-TWZ-A0281-10, TWZ-P-CB-2442 CHH-TWZ-A0236-10, CHH-TWZ-A0239-10, CHH-TWZ-A0248-10, CHH-TWZ-A0249-10 | 2027-04-19 06:30 | 2027-04-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160191
NMA_CB_738 | Affected Equipment of NMA_687_835 pdm maint. | 2027-04-19 07:00 | 2027-04-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161242
TIM_T5 | TIM-CBL-T5-ET5, TIM-CBL-T5-NER5, TIM-P-CB-212 | 2027-04-19 07:00 | 2027-04-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161616
TIM_T4 | Affected Equipment of TIM_44_54_87 TIM-CSA-78 | 2027-04-19 07:00 | 2027-04-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161615
TIM_CB_2752 | Affected Equipment of TIM_44_54_87 TIM-CSA-78 | 2027-04-19 07:00 | 2027-04-20 18:30 | Continuous | SI | CLO - Close | Approved | OW1161613
TMK_TIM_1_TMK_T1 | Affected Equipment of TIM_44_54_87 TIM-CSA-78 | 2027-04-19 07:00 | 2027-04-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161654
TIM_44_54_87 | TIM-CSA-78 | 2027-04-19 07:00 | 2027-04-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161609
MAN_NMA_2 | Tower Painting | 2027-04-19 07:00 | 2027-04-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1143118
NMA_687_835 | pdm maint. | 2027-04-19 07:00 | 2027-04-20 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161214
ARI_KIN_1 | Pole replacement, Under-clearance work | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160171
OHK_CB_132 | OHK-CT-132. Affected equipment of OHK_WRK_1. | 2027-04-19 07:30 | 2027-04-21 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161278
MST_GYT_UHT_1 | Tower crossarm works x1 (A149). GYT/MGM/MST/UHT/WDV duplicated protection upgrade project Stage 4 [CP_VAR_21A_0_00]. | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161169
KIW_TMH_1 | pdm maint | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2006040
OHK_CB_102 | OHK-CT-102. Affected equipment of OHK_WRK_1. | 2027-04-19 07:30 | 2027-04-21 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161277
WPR_T13 | Affected Equipment of ISL_WPR_CUL_KIK_3 CUL-DS-416, CUL-P-CB-412, ISL-KIK-B0021-0022-20, ISL-KIK-B0216-20, ISL-KIK-B0223-20, ISL-KIK-B0231-20, ISL-KIK-B0234-20, ISL-KIK-B0236-20, ISL-KIK-B0240-20, ISL-KIK-B0242-20, ISL-KIK-B0247-20, ISL-KIK-B0270-20, ISL-KIK-B0271-20, ISL-KIK-B0272-20, ISL-KIK-B0328-20, ISL-KIK-BISLG83-10, ISL-P-CB-542, KIK-DS-324, KIK-DS-326, KIK-DS-334, KIK-P-CB-322, WPR-DS-476, WPR-P-CB-472 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161832
MTI_WKM_2 | WKM CT maintenance. Tower painting x6 (B1-B3, B15, B23-B24) [CP_704_001_0_00]. | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161174
TRK_110BZ_A | TRK-P-BZ-110-A | 2027-04-19 07:30 | 2027-04-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161700
ARI_KIN_2 | Pole replacement, Under-clearance work | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160173
TRK_110CBF | Affected equipment | 2027-04-19 07:30 | 2027-04-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161701
KIK_STK_2 | KIK-DS-324 Disconnector & Earth Switch type Hapam SSB-III = Contact Alignment and Re-greasing (2019086) 500648585 ISL_WPR_CUL_KIK_3, KIK_STK_2 KIK-DS-334 Disconnector & Earth Switch type Hapam SSB-III = Contact Alignment and Re-greasing (2019087) 500648589 ISL_WPR_CUL_KIK_3, KIK_STK_2 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160933
OHK_WRK_1 | OHK-CVT-102, OHK-DS-106, OHK-DS-1326, OHK-ES-109, WRK-WKM-A0062-00 | 2027-04-19 07:30 | 2027-04-21 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161279
KIK_MCH_1 | CA Lifting Inspections | 2027-04-19 07:30 | 2027-04-22 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160927
MNG_FDR_262 | CT replacement PJ. MNG-CT-262 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161076
ASY_SBK_1 | ASY-CB-152 Pole Replacement | 2027-04-19 07:30 | 2027-04-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005174
ISL_WPR_CUL_KIK_3 | CUL-DS-416, CUL-P-CB-412, ISL-KIK-B0021-0022-20, ISL-KIK-B0216-20, ISL-KIK-B0223-20, ISL-KIK-B0231-20, ISL-KIK-B0234-20, ISL-KIK-B0236-20, ISL-KIK-B0240-20, ISL-KIK-B0242-20, ISL-KIK-B0247-20, ISL-KIK-B0270-20, ISL-KIK-B0271-20, ISL-KIK-B0272-20, ISL-KIK-B0328-20, ISL-KIK-BISLG83-10, ISL-P-CB-542, KIK-DS-324, KIK-DS-326, KIK-DS-334, KIK-P-CB-322, WPR-DS-476, WPR-P-CB-472 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160876
MTN_T2 | Affected equipment of BPE_MTN_WGN_2 | 2027-04-19 07:30 | 2027-04-20 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161181
BPE_MTN_WGN_2 | Tower works x3 (B85A, B148-B149). | 2027-04-19 07:30 | 2027-04-20 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160334
GOR_T11 | Affected Equipment of NMA_GOR_TMH_1 pdm maint | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160527
CUL_T23 | Affected Equipment of ISL_WPR_CUL_KIK_3 CUL-DS-416, CUL-P-CB-412, ISL-KIK-B0021-0022-20, ISL-KIK-B0216-20, ISL-KIK-B0223-20, ISL-KIK-B0231-20, ISL-KIK-B0234-20, ISL-KIK-B0236-20, ISL-KIK-B0240-20, ISL-KIK-B0242-20, ISL-KIK-B0247-20, ISL-KIK-B0270-20, ISL-KIK-B0271-20, ISL-KIK-B0272-20, ISL-KIK-B0328-20, ISL-KIK-BISLG83-10, ISL-P-CB-542, KIK-DS-324, KIK-DS-326, KIK-DS-334, KIK-P-CB-322, WPR-DS-476, WPR-P-CB-472 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160430
GYT_T2 | Affected equipment of MST_GYT_UHT_1. | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160540
WEL_T1 | Affected Equipment Tower Painting | 2027-04-19 08:00 | 2027-04-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142864
PEN_FDR_3122 | Affected Equipment of PEN_T22 PEN-CB-2222, PEN-P-CB- 2222 | 2027-04-19 08:00 | 2027-04-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005900
MTO_T2 | Affected Equipment Tower Painting | 2027-04-19 08:00 | 2027-04-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142863
PEN_T22 | PEN-CB-2222, PEN-P-CB- 2222 | 2027-04-19 08:00 | 2027-04-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005899
HEN_MPE_2 | Tower Painting | 2027-04-19 08:00 | 2027-04-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142862
PEN_FDR_3132 | Affected Equipment of PEN_T22 PEN-CB-2222, PEN-P-CB- 2222 | 2027-04-19 08:00 | 2027-04-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005901
BRB_CB_158 | BRB-CB-158 | 2027-04-20 07:30 | 2027-04-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160353
ROT_T2 | ROT-P-AVR-T2 | 2027-04-21 07:30 | 2027-04-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161503
MTN_T1 | Affected equipment of BPE_MTN_WGN_1 | 2027-04-21 07:30 | 2027-04-23 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161180
NMA_220BS_A3 | pdm maint | 2027-04-21 07:30 | 2027-04-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161204
BPE_MTN_WGN_1 | Tower works x10 (B68, B78, B84-B85, B101, B109, B113, B119, B131, B154). | 2027-04-21 07:30 | 2027-04-23 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160333
WKM_220BS_C | WKM-DS-55 (MTI_2), WKM-DS-65 (OTA_1), WKM-DS-145 (G1), WKM-DS-155 (G2), WKM-DS-165 (G3), WKM-DS-297 (BC). | 2027-04-21 07:30 | 2027-04-22 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161805
WKM_TIE_1 | WKM-CVT-522, WKM-DS-335 | 2027-04-21 07:30 | 2027-04-22 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161811
WKM_CB_228 | Affected equipment of WKM_220BS_C, for WKM 6DS mtce. | 2027-04-21 07:30 | 2027-04-22 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161807
NMA_CB_718 | Affected Equipment of NMA_220BS_A3 pdm maint | 2027-04-21 07:30 | 2027-04-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161234
NMA_CB_708 | Affected Equipment of NMA_220BS_A3 pdm maint | 2027-04-21 07:30 | 2027-04-23 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161225
WKM_CB_288 | Affected equipment of WKM_220BS_C, for WKM 6DS mtce. | 2027-04-21 07:30 | 2027-04-22 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161809
BRB_CB_148 | BRB-CB-148 | 2027-04-22 07:30 | 2027-04-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160352
ROT_314_367 | ROT-BS-110-337-367 | 2027-04-22 07:30 | 2027-04-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161490
ROT_T3 | Affected equipment | 2027-04-22 07:30 | 2027-04-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161504
ROT_TRK_2 | Affected equipment ROT_314_367 & ROT_T2 & ROT_T3 & ROT_WHE_1 | 2027-04-22 07:30 | 2027-04-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161508
ROT_WHE_1 | ROT-M-CT312 | 2027-04-22 07:30 | 2027-04-23 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161509
ATI_OHK_1 | OHK-CT-92, OHK-CVT-92, OHK-DS-96, OHK-ES-99, OHK-P-CB-92 | 2027-04-22 07:30 | 2027-04-23 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160196
KAI_11BS_F | KAI-BS-11- FRONT | 2027-04-22 07:30 | 2027-04-23 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160881
KAI_SBK_2 | Affected Equipment of KAI_87_94 To Commission new Switchboard and T2 Protection and KAI CB62 Poles | 2027-04-23 07:30 | 2027-04-23 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005523
KAI_87_94 | To Commission new Switchboard and T2 Protection and KAI CB62 Poles | 2027-04-23 07:30 | 2027-04-23 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005522
KAI_74_87 | KAI-VT-VT1 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160883
KAI_SBK_1 | KAI-DS-76, KAI-ES-79, KAI-P-CB-72 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160886
OHB_TWZ_3 | OHB-CT-CT1102, OHB-CVT-VT112, OHB-DS-1106, OHB-ES-1109, OHB-P-CB-1102, TWZ-CT-CT2672, TWZ-CVT-CVT9, TWZ-DS-2676, TWZ-ES-2679 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161269
KIW_TMH_1 | NMA-TMH-A0303-10 NMA-TMH-A0304-10 NMA-TMH-A0305-10 NMA-TMH-A0310-10 NMA-TMH-A0312-10 NMA-TMH-A0313-10 NMA-TMH-A0314-10 NMA-TMH-A0315-10 NMA-TMH-A0316-10 NMA-TMH-A0317-10 NMA-TMH-A0318-10 NMA-TMH-A0319-10 NMA-TMH-A0320-10 NMA-TMH-A0323-10 NMA-TMH-A0324-10 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2006039
KAI_T1 | KAI-CBL-LS11, KAI-CBL-NER1, KAI-CBL-T1, KAI-RES-NER1, KAI-TF-LS11, KAI-TF-T1, KAI-VT-VT2812 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160887
TAK_T8 | Affected equipment TAK-P-TF-ET8, TAK-TF-T8 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161593
DRY_TAK_OTA_2 | HLY-OTA-A0150-20, HLY-OTA-A0167-20, HLY-OTA-A0172-20, HLY-OTA-A0177-20, HLY-OTA-A0179-20, HLY-OTA-A0191-20, HLY-OTA-A0196-20, HLY-OTA-A0210-20, HLY-OTA-A0213-20, OTA-CBL-1252-DRY2 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160451
GOR_T11 | Affected Equipment of NMA_GOR_TMH_1 NMA-TMH-A0303-10 NMA-TMH-A0304-10 NMA-TMH-A0305-10 NMA-TMH-A0310-10 NMA-TMH-A0312-10 NMA-TMH-A0313-10 NMA-TMH-A0314-10 NMA-TMH-A0315-10 NMA-TMH-A0316-10 NMA-TMH-A0317-10 NMA-TMH-A0318-10 NMA-TMH-A0319-10 NMA-TMH-A0320-10 NMA-TMH-A0323-10 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160528
HAY_UHT_2 | HAY_110BZ Stage 3G; Bay 190 - Upper Hutt cct 2. No other HAY work on days 1, 5, 6. No other work on associated equipment/lines on day 6 (commissioning). HAY-CT-192. Tower works x1 (A4). | 2027-04-28 07:00 | 2027-05-03 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1162025
INV_CB_712 | INV-P-CB-712 | 2027-04-28 07:30 | 2027-04-28 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160776
HAY_110CBF | HAY_110BZ Stage 3G; Bay 190 - Upper Hutt cct 2. | 2027-04-28 08:00 | 2027-04-28 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161995
HAY_110BZ | HAY_110BZ Stage 3G; Bay 190 - Upper Hutt cct 2. No work in HAY 110kV yard. | 2027-04-28 08:00 | 2027-04-28 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161949
KIK_STC_2B | KIK-CAPS-K12-C1, KIK-CAPS-K12-C2 | 2027-04-30 07:30 | 2027-04-30 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160930
HAY_110CBF | HAY_110BZ Stage 3G; Bay 190 - Upper Hutt cct 2. | 2027-05-02 08:00 | 2027-05-02 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161996
HAY_110BZ | HAY_110BZ Stage 3G; Bay 190 - Upper Hutt cct 2. No work in HAY 110kV yard. | 2027-05-02 08:00 | 2027-05-02 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161950
ISL_WPR_CUL_KIK_2 | CUL-DS-406, CUL-P-CB-402, ISL-KIK-B0021-0022-10, ISL-KIK-B0223-10, ISL-KIK-B0266-10, ISL-KIK-B0267-10, ISL-KIK-B0270-10, ISL-KIK-B0271-10, ISL-KIK-B0272-10, ISL-P-CB-562, KIK-CVT-VT342, KIK-DS-344, KIK-DS-354, KIK-P-CB-342, WPR-DS-436, WPR-P-CB-432 | 2027-05-03 06:30 | 2027-05-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160875
CUL_T22 | Affected Equipment of ISL_WPR_CUL_KIK_2 CUL-DS-406, CUL-P-CB-402, ISL-KIK-B0021-0022-10, ISL-KIK-B0223-10, ISL-KIK-B0266-10, ISL-KIK-B0267-10, ISL-KIK-B0270-10, ISL-KIK-B0271-10, ISL-KIK-B0272-10, ISL-P-CB-562, KIK-CVT-VT342, KIK-DS-344, KIK-DS-354, KIK-P-CB-342, WPR-DS-436, WPR-P-CB-432 | 2027-05-03 07:30 | 2027-05-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160428
OAM_87_66 | Affected Equipment of OAM_BPT_WTK_1 Affected equipment WTK_T24 | 2027-05-03 07:30 | 2027-05-07 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1163407
KAI_FDR_2822 | Affected equipment KAI_11BS_B & KAI_T1 | 2027-05-03 07:30 | 2027-05-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160884
KIK_STK_1 | KIK-DS-344 Disconnector & Earth Switch type Hapam SSB-III = Contact Alignment and Re-greasing (2019088) 500649328 ISL_WPR_CUL_KIK_2, KIK_STK_1 | 2027-05-03 07:30 | 2027-05-07 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1163094
KAI_FDR_2832 | Affected equipment KAI_11BS_B & KAI_T1 | 2027-05-03 07:30 | 2027-05-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160885
KAI_T1 | KAI-CBL-LS11, KAI-CBL-NER1, KAI-CBL-T1, KAI-RES-NER1, KAI-TF-LS11, KAI-TF-T1, KAI-VT-VT2812 | 2027-05-03 07:30 | 2027-05-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160888
HWA_T2 | OPE for the duration of HWA_SFD_1, to prevent recirculating currents through the HWA 33kV | 2027-05-03 07:30 | 2027-05-04 18:30 | Continuous | SNI | OPE - Open Ended | Approved | OW1160750
WTK_T24 | WTK-NCTD-T24 | 2027-05-03 07:30 | 2027-05-07 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161876
KAI_11BS_B | KAI-P-CB-38 | 2027-05-03 07:30 | 2027-05-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160880
OAM_T1 | Affected Equipment of OAM_BPT_WTK_1 Affected equipment WTK_T24 | 2027-05-03 07:30 | 2027-05-07 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161261
OAM_BPT_WTK_1 | Affected equipment WTK_T24 | 2027-05-03 07:30 | 2027-05-07 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161257
ALB_33CBF | Affected equipment | 2027-05-03 07:30 | 2027-05-04 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160124
SFD_T10 | SFD-DS-733 headgear refurbishment [CP_RA3_03F_0_00]. | 2027-05-03 07:30 | 2027-05-04 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161547
HWA_SFD_1 | OPE for the duration of SFD_T10, for post-contingent overloading prevention | 2027-05-03 07:30 | 2027-05-04 18:30 | Continuous | SNI | OPE - Open Ended | Approved | OW1160747
WPR_T12 | Affected Equipment of ISL_WPR_CUL_KIK_2 CUL-DS-406, CUL-P-CB-402, ISL-KIK-B0021-0022-10, ISL-KIK-B0223-10, ISL-KIK-B0266-10, ISL-KIK-B0267-10, ISL-KIK-B0270-10, ISL-KIK-B0271-10, ISL-KIK-B0272-10, ISL-P-CB-562, KIK-CVT-VT342, KIK-DS-344, KIK-DS-354, KIK-P-CB-342, WPR-DS-436, WPR-P-CB-432 | 2027-05-03 07:30 | 2027-05-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161829
ALB_33BZ_K | ALB-P-BZ-33 | 2027-05-03 07:30 | 2027-05-04 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160123
HAY_110BZ | HAY_110BZ Stage 3G; Bay 190 - Upper Hutt cct 2. No work in HAY 110kV yard. | 2027-05-03 08:00 | 2027-05-03 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161951
HAY_110CBF | HAY_110BZ Stage 3G; Bay 190 - Upper Hutt cct 2. | 2027-05-03 08:00 | 2027-05-03 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161997
HIN_44_64_124 | HIN-DS-124, HIN-DS-44, HIN-DS-64, HIN-VT-62 | 2027-05-03 08:00 | 2027-05-07 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160686
HIN_KPO_1 | HIN-KPO-A0001-00, HIN-KPO-A0069-0070-10 | 2027-05-03 08:00 | 2027-05-07 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160687
HIN_T1 | HIN-CB-62, HIN-CBL-T1-3122, HIN-CBL-T1-LS1, HIN-NER-1, HIN-P-TF-T1, HIN-TF-LST1 | 2027-05-03 08:00 | 2027-05-07 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160688
HIN_T2 | HIN-CB-42, HIN-CBL-T2-3222, HIN-CBL-T2-LS2, HIN-NER-2, HIN-P-TF-T2, HIN-TF-LST2, HIN-TF-T2R, HIN-TF-T2Y | 2027-05-03 08:00 | 2027-05-07 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160689
WDV_CB_132 | Affected equipment of WDV_67_147 | 2027-05-04 06:30 | 2027-05-04 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161763
WDV_67_147 | WDV_67_147 | 2027-05-04 06:30 | 2027-05-04 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161761
BPE_WDV_1 | BPE-P-CB-72, WDV-P-CB-112. Re-insulation x13. BPE_WDV_1/2 line protection replacement project [CP_BPE_02C_0_00]. Last day forcommissioning (no other work). | 2027-05-04 06:30 | 2027-05-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160348
BPE_LTN_2 | BPE-CB-892, BPE-CT-892, BPE-CVT-892, BPE-DS-893, BPE-DS-896, BPE-ES-899, LTN-DS-224, LTN-ES-229. Tower works x7 (A11, A20, A29,A35-A36, A46, A51). | 2027-05-04 06:30 | 2027-05-06 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160330
BPE_CB_918 | Affected equipment of BPE_797_907, for BPE-DS-893 (LTN-2) | 2027-05-04 06:30 | 2027-05-04 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160327
LTN_T2 | LTN-CVT-CVT222. Affected equipment of BPE_LTN_2. | 2027-05-04 06:30 | 2027-05-06 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161016
BPE_797_907 | BPE-DS-893 (LTN-2) | 2027-05-04 06:30 | 2027-05-04 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160321
INV_CB_642 | INV-CB-642, INV-CT-CT642, INV-P-CB-642 | 2027-05-04 07:30 | 2027-05-06 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160775
SBK_FDR_202 | SBK-CB-202 | 2027-05-04 07:30 | 2027-05-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161527
BLN_AVR_C1C2C3C4 | BLN-P-REG | 2027-05-04 07:30 | 2027-05-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160291
MPE_CB_252 | System split for BRB_HPI_1 | 2027-05-04 08:00 | 2027-05-04 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW2005196
BRB_HPI_1 | Attachment point, re-insulation and steel and bolts | 2027-05-04 08:00 | 2027-05-07 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005195
MPE_CB_292 | System split for BRB_HPI_1 | 2027-05-04 08:00 | 2027-05-04 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW2005199
MPE_CB_252 | System split for BRB_HPI_1 | 2027-05-05 06:00 | 2027-05-06 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW2005197
MPE_CB_292 | System split for BRB_HPI_1 | 2027-05-05 06:00 | 2027-05-06 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW2005200
MKE_CB_102 | MKE-DCB-102 | 2027-05-05 07:30 | 2027-05-07 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161057
ARI_KIN_1 | ARI-CB-212, ARI-CT-212, ARI-DS-216, ARI-ES-219 | 2027-05-05 07:30 | 2027-05-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160172
ONG_T1 | ONG-M-CT162, ONG-TF-T1B, ONG-TF-T1R, ONG-TF-T1SP, ONG-TF-T1Y | 2027-05-05 07:30 | 2027-05-06 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161299
SFD_177_222_232 | SFD-DS-187 | 2027-05-05 07:30 | 2027-05-07 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161532
SFD_T6 | SFD-NCT-6, SFD-P-TF-T6 | 2027-05-05 07:30 | 2027-05-07 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161548
SFD_T9 | SFD-CBL-T9-232 | 2027-05-05 07:30 | 2027-05-07 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161551
MNI_MKE_SFD_1 | MNI-DEV-A0169-20, MNI-DEV-A0170-20 | 2027-05-05 07:30 | 2027-05-07 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161093
GLN_220CBF | GLN-P-BZ-220 | 2027-05-05 07:30 | 2027-05-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160514
HWA_T2 | OPE for the duration of HWA_SFD_1, to prevent recirculating currents through the HWA 33kV. | 2027-05-05 07:30 | 2027-05-07 18:30 | Continuous | SNI | OPE - Open Ended | Approved | OW1160751
GLN_220BZ | GLN-P-BZ-220 | 2027-05-05 07:30 | 2027-05-06 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160513
HWA_SFD_1 | OPE for the duration of SFD_T9, for post-contingent overloadingprevention | 2027-05-05 07:30 | 2027-05-07 18:30 | Continuous | SNI | OPE - Open Ended | Approved | OW1160748
MPE_CB_292 | System split for BRB_HPI_1 | 2027-05-07 06:00 | 2027-05-07 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW2005201
MPE_CB_252 | System split for BRB_HPI_1 | 2027-05-07 06:00 | 2027-05-07 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW2005198
BPE_T9 | BPE-DS-553 motorisation [CP_RA4_02M_0_00]. | 2027-05-07 06:30 | 2027-05-07 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160342
BPE_CB_608 | Affected equipment of BPE_523_697, for BPE-DS-553 (T9) motorisation. | 2027-05-07 06:30 | 2027-05-07 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160325
BPE_523_697 | BPE-DS-553 (T9) motorisation [CP_RA4_02M_0_00] | 2027-05-07 06:30 | 2027-05-07 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160319
ASY_11BZ_A | ASY-P-BZ-11 | 2027-05-07 07:30 | 2027-05-07 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160193
ARG_KIK_1 | BLN-KIK-A0378-00, BLN-KIK-A0383-00, BLN-KIK-A0424-00, BLN-KIK-A0426-00, BLN-KIK-A0431-00, BLN-KIK-A0438-00, BLN-KIK-A0443-00, BLN-KIK-A0444-00, BLN-KIK-A0450-00, BLN-KIK-A0451-00, BLN-KIK-A0454-00, BLN-KIK-A0457-00, BLN-KIK-A0472-00, BLN-KIK-A0473-00, BLN-KIK-A0496-00, BLN-KIK-A0507-00, BLN-KIK-A0512-00, BLN-KIK-A0522-00, BLN-KIK-A0526-00, BLN-KIK-A0527-00, BLN-KIK-A0528-00, BLN-KIK-A0556-00 | 2027-05-10 06:30 | 2027-05-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160151
ISL_WPR_CUL_KIK_3 | Affected equipment KIK_220BS_C1 & KIK_CB_328 & KIK_STK_2 | 2027-05-10 06:30 | 2027-05-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160877
WPR_T13 | Affected Equipment of ISL_WPR_CUL_KIK_3 Affected equipment KIK_220BS_C1 & KIK_CB_328 & KIK_STK_2 | 2027-05-10 07:30 | 2027-05-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161833
OAM_T2 | OAM-CB-312, OAM-CB-82, OAM-DS-316, OAM-DS-87, OAM-M-CT312, OAM-M-VT2, OAM-P-TF-T2, OAM-TF-LS2, OAM-TF-T2, OAM-VT-VT2, OAM-VT-VT4 | 2027-05-10 07:30 | 2027-05-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161264
TGA_T2 | CB pole replacement TGA-CB-272, TGA-M-CT37 RM at end of outage after maintenance completed. | 2027-05-10 07:30 | 2027-05-15 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161604
WTK_T23 | WTK-NCTD-T23 | 2027-05-10 07:30 | 2027-05-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161875
STU_CB_62 | Affected equipment WTK_56_447 & LIV_WTK_1 & WTK_CB_438 & WTK_T23 & OAM_STU_BPD_WTK_2 & OAM_T2 | 2027-05-10 07:30 | 2027-05-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161567
OAM_STU_BPD_WTK_2 | BPD-P-CB-442, BPD-P-CB-482, GNY-TIM-A0364-00, GNY-TIM-A0385-00,GNY-WTK-A0080-0081-20, OAM-DS-86, OAM-ES-89, STU-DS-66, WTK-DS-56, WTK-ES-59 | 2027-05-10 07:30 | 2027-05-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161260
OAM_67_86 | OAM-CB-312, OAM-CB-82, OAM-DS-316, OAM-DS-87, OAM-M-CT312, OAM-M-VT2, OAM-P-TF-T2, OAM-TF-LS2, OAM-TF-T2, OAM-VT-VT2, OAM-VT-VT4 | 2027-05-10 07:30 | 2027-05-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1163408
EDG_TRK_1 | Reinsulation, Attachment Points, Line Maintenance | 2027-05-10 07:30 | 2027-05-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160481
CUL_T23 | Affected Equipment of ISL_WPR_CUL_KIK_3 Affected equipment KIK_220BS_C1 & KIK_CB_328 & KIK_STK_2 | 2027-05-10 07:30 | 2027-05-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160431
ROT_T3 | ROT-M-CT2792, ROT-M-VT2792 | 2027-05-10 07:30 | 2027-05-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161505
MTN_T2 | MTN-TF-T2 | 2027-05-10 07:30 | 2027-05-25 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161182
ROT_337_367 | ROT-DS-354, ROT-DS-357 | 2027-05-10 07:30 | 2027-05-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161491
ALB_587_597_637 | ALB-DS-594 | 2027-05-10 07:30 | 2027-05-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160125
ALB_C_2 | Affected equipment ALB_587_597_637 & ALB_SVL_1 | 2027-05-10 07:30 | 2027-05-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160127
OTA_ROS_2 | Attachment points, re-insulation & Steel and bolts | 2027-05-10 08:00 | 2027-05-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005228
ALB_SVL_1 | Tower Painting | 2027-05-10 08:00 | 2027-05-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142689
SVL_T1 | Affected Equipment Tower Painting | 2027-05-10 08:00 | 2027-05-14 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142690
KIK_220BS_C1 | KIK-DS-357, KIK-P-CB-358 | 2027-05-10 08:00 | 2027-05-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160918
KIK_CB_328 | KIK-P-CB-328 | 2027-05-10 08:00 | 2027-05-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160920
KIK_CB_358 | Affected equipment KIK_220BS_C1 & KIK_CB_328 & KIK_STK_2 | 2027-05-10 08:00 | 2027-05-13 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160922
WDV_CB_132 | Affected equipment of WDV_67_147 | 2027-05-11 06:30 | 2027-05-11 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161764
WDV_67_147 | WDV_67_147 | 2027-05-11 06:30 | 2027-05-11 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161762
HAY_UHT_1 | HAY_110BZ Stage 3H; Bay 210 - Upper Hutt cct 1. No other HAY work on days 1, 5, 6. No other work on associated equipment/lines on day 6 (commissioning). HAY-CT-212. Tower works x2 (A4-A5). | 2027-05-11 07:00 | 2027-05-16 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW1160634
HWA_WAA_1 | Affected equipment of HWA_CB_602, for HWA-P-DCB-602 | 2027-05-11 07:30 | 2027-05-11 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160752
HWA_CB_602 | HWA-P-DCB-602 | 2027-05-11 07:30 | 2027-05-11 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160743
DRY_220CBF_A_PROT1 | Affected equipment | 2027-05-11 08:00 | 2027-05-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160444
DRY_220BZ_A_PROT1 | DRY-P-BZ-220 | 2027-05-11 08:00 | 2027-05-12 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160443
HAY_110BZ | HAY_110BZ Stage 3H; Bay 210 - Upper Hutt cct 1. No work in HAY 110kV yard. | 2027-05-11 08:00 | 2027-05-11 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1160579
HAY_110CBF | HAY_110BZ Stage 3H; Bay 210 - Upper Hutt cct 1. | 2027-05-11 08:00 | 2027-05-11 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1160589
WPR_FDR_1132 | WPR-P-CB-1132 | 2027-05-12 07:30 | 2027-05-14 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161819
BPE_T3 | BPE-TNG prot upgrade Stage 10: BPE-T3 protection upgrade [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-05-12 07:30 | 2027-05-23 17:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161892
BPE_220CBF | Affected equipment of BPE_220BZ, for BPE-TNG prot upgrade Stage10 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-05-12 08:00 | 2027-05-12 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005600
BPE_220BZ | BPE-TNG prot upgrade Stage 10: BPE-T3 protection upgrade [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-05-12 08:00 | 2027-05-12 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005587
BPE_110BZ | BPE-TNG prot upgrade Stage 10: BPE-T3 protection upgrade [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-05-12 08:00 | 2027-05-12 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005588
BPE_110CBF | Affected equipment of BPE_110BZ, for BPE-TNG prot upgrade Stage10 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-05-12 08:00 | 2027-05-12 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005599
ALB_SVC_7 | ALB-P-PSUP-SVC7-UPS-1, ALB-P-TF-T7, ALB-SVC7-TCR7, ALB-SVC7-TSC7 | 2027-05-13 07:30 | 2027-05-14 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1160134
HAY_110BZ | HAY_110BZ Stage 3H; Bay 210 - Upper Hutt cct 1. No work in HAY 110kV yard. | 2027-05-15 08:00 | 2027-05-15 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1160580
HAY_110CBF | HAY_110BZ Stage 3H; Bay 210 - Upper Hutt cct 1. | 2027-05-15 08:00 | 2027-05-15 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1160590
HAY_110BZ | HAY_110BZ Stage 3H; Bay 210 - Upper Hutt cct 1. No work in HAY 110kV yard. | 2027-05-16 08:00 | 2027-05-16 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1160581
HAY_110CBF | HAY_110BZ Stage 3H; Bay 210 - Upper Hutt cct 1. | 2027-05-16 08:00 | 2027-05-16 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1160591
ARG_BLN_1 | BLN-KIK-A0200-00, BLN-KIK-A0366-00, structure replacements BLN-KIK-A0200-00, BLN-KIK-A0201-00, BLN-KIK-A0199-00, BLN-KIK-A0361 , BLN-KIK-A0366-00 under clearance | 2027-05-17 06:30 | 2027-05-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160148
ASY_SBK_1 | Affected equipment ASY_124_137_157, ASY-CB-152 | 2027-05-17 06:30 | 2027-05-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159792
ASY_124_137_157 | ASY-DS-137, ASY-DS-147, ASY-DS-154, ASY-DS-157, ASY-DS-124 Connect new Mainpower Feeder and Commission | 2027-05-17 06:30 | 2027-05-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159793
ASY_T3 | Affected equipment ASY_124_137_157 & ASY_SBK_1 | 2027-05-17 06:30 | 2027-05-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159794
ASY_CB_2722 | Affected equipment ASY_T3, ASY_124_137_157 & ASY_SBK_1 | 2027-05-17 06:30 | 2027-05-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159795
ASY_CB_2742 | CLO for ASY_T3 out with ASY_124_137_157 & ASY_SBK_1 | 2027-05-17 06:30 | 2027-05-21 18:30 | Continuous | SI | CLO - Close | Approved | OW1159796
ASY_157_167 | Affected equipment ASY-DS-157 | 2027-05-17 06:30 | 2027-05-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159797
ASY_CB_2632 | Affected equipment ASY_T3, ASY_124_137_157 & ASY_SBK_1 | 2027-05-17 06:30 | 2027-05-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1159799
ARI_CB_48 | Closed for the duration of HAM_T9 | 2027-05-17 07:00 | 2027-05-21 18:30 | Continuous | NNI | CLO - Close | Approved | OW1156743
KPO_TMU_1 | System split for the duration of HAM_T9 | 2027-05-17 07:00 | 2027-05-21 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1156742
HAY_UHT_1 | HAY-UHT-A 2027 reconductoring [CP_777_004_0_00] | 2027-05-17 07:00 | 2027-06-18 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2005536
ARI_HAM_2 | System split for the duration of HAM_T9 | 2027-05-17 07:00 | 2027-05-21 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1156741
ARI_HAM_1 | System split for the duration of HAM_T9 | 2027-05-17 07:00 | 2027-05-21 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW1156740
HAM_T9 | CT and ODJB replacement project. CP_HAM_001_0_00 | 2027-05-17 07:00 | 2027-05-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1156739
OKI_WRK_1 | OKI-DS-275, OKI-CT-272, OKI-ES-270, OKI-ES-279, OKI-P-CB-272, WRK-CB-142, WRK-CT-142, WRK-CVT-142, WRK-P-CB-142 | 2027-05-17 07:00 | 2027-05-21 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161291
OKI_RTU_1 | SMS & GPS replacements [CP_RA3_03C_0_00] | 2027-05-17 07:00 | 2027-05-17 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161290
OKI_CB_238 | OKI-DS-235, OKI-P-CB-238. Affected equipment of OKI_220BS_B. | 2027-05-17 07:00 | 2027-05-20 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161288
HAM_C_2 | Affected equipment HAM_T9 | 2027-05-17 07:00 | 2027-05-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160548
OKI_220BS_B | OKI-DS-235 (BC), OKI-DS-275 (WRK_1), OKI-DS-337, OKI-ES-330, OKI-ES-339 | 2027-05-17 07:00 | 2027-05-20 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161287
GOR_T11 | GOR-CB-752, GOR-CBL-T11-ET11, GOR-CT-CT612, GOR-CT-CT752, GOR-CT-NCT11, GOR-DCB-612, GOR-NCTD-T11, GOR-P-CB-752, GOR-P-TF-T11, GOR-TF-ET11, GOR-TF-T11 | 2027-05-17 07:30 | 2027-05-22 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160529
MPE_CB_292 | System split for the duration of BRB_HPI_1 | 2027-05-17 07:30 | 2027-05-17 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161163
HEN_467_514_524 | Head gear refurb HEN-DS-507 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160647
GOR_597_607_604 | GOR-DS-604, GOR-DS-607, GOR-P-CB-612, GOR-VT-VT617 | 2027-05-17 07:30 | 2027-05-22 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160523
HEN_CB_488 | Affected equipment HEN_467_514_524 & HEN_HPI_1 & HEN_SWN_1 & BRB_HPI_1 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160652
HEN_T5 | Affected equipment HEN_467_514_524 & HEN_HPI_1 & HEN_SWN_1 & BRB_HPI_1 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160670
HEN_T3 | Affected equipment HEN_467_514_524 & HEN_HPI_1 & HEN_SWN_1 & BRB_HPI_1 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160668
HEN_SWN_1 | HEN-CB-522, HEN-CVT-522, HEN-DS-526, HEN-ES-529, HEN-OTA-A0027-0028-20, HEN-OTA-A0034-20, HEN-OTA-A0037-20, HEN-OTA-A0052-20, HEN-OTA-A0091-20 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160664
HEN_HPI_1 | HEN-CB-512, HEN-MDN-A0001A-10, HEN-MDN-A0002-0003-10, HEN-MDN-A0007-10, HEN-MDN-A0013-10, HEN-MDN-A0036-00, HEN-MDN-A0036-10 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160660
GOR_T3 | GOR-TF-T3 | 2027-05-17 07:30 | 2027-05-22 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160537
MPE_CB_252 | System split for the duration of BRB_HPI_1 | 2027-05-17 07:30 | 2027-05-17 22:00 | Daily | NNI | OPE - Open Ended | Approved | OW1161128
KAI_T1 | KAI T1 Protection, term new 11kV Cables, Liven onto new Switchboard - KAI CB82 Pole Replacement | 2027-05-17 07:30 | 2027-06-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005525
KMO_TRK_2 | KMO-DS-386, KMO-ES-389 | 2027-05-17 08:00 | 2027-05-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160976
EDG_TRK_1 | EDG-TRK-A0067-10, EDG-TRK-A0092-10, EDG-TRK-A0100-10, EDG-TRK-A0105-10, EDG-TRK-A0106-10, EDG-TRK-A0108-10, EDG-TRK-A0109-10, EDG-TRK-A0110-10, EDG-TRK-A0112-10, EDG-TRK-A0114-10, EDG-TRK-A0120-10, EDG-TRK-A0124-10, EDG-TRK-A0131-10, EDG-TRK-A0132-10, EDG-TRK-A0133-10, EDG-TRK-A0138-10 | 2027-05-17 08:00 | 2027-05-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160482
TRK_357_627_607 | TRK-BS-220-357-607, TRK-DS-344 | 2027-05-17 08:00 | 2027-05-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161706
TRK_CB_618 | TRK-CB-618, TRK-CT-618 | 2027-05-17 08:00 | 2027-05-21 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161710
TRK_DIS_407 | Closed for the duration of KAW_357_627_607 | 2027-05-17 08:00 | 2027-05-21 18:30 | Continuous | NNI | CLO - Close | Approved | OW1161712
MPE_CB_252 | System split for the duration of BRB_HPI_1 | 2027-05-18 06:00 | 2027-05-20 22:00 | Continuous | NNI | OPE - Open Ended | Approved | OW1161129
MPE_CB_292 | System split for the duration of BRB_HPI_1 | 2027-05-18 06:00 | 2027-05-20 22:00 | Continuous | NNI | OPE - Open Ended | Approved | OW1161164
WRK_137_167 | WRK-DS-105 (CB_108) | 2027-05-18 07:00 | 2027-05-18 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161845
WRK_DIS_117 | CLO for the duration of WRK_137_167, to maintain a solid 220kV bus. | 2027-05-18 07:00 | 2027-05-18 18:30 | Daily | SNI | CLO - Close | Approved | OW1161858
PEN_LS1 | Affected equipment PEN_STC_1 | 2027-05-18 07:30 | 2027-05-19 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161423
PEN_STC_1 | PEN-CB-2412, PEN-CWU-STC1A, PEN-CWU-STC1B, PEN-P-PSUP-STC1-UPS-1, PEN-STC-1A, PEN-STC-1B | 2027-05-18 07:30 | 2027-05-19 18:30 | Continuous | HVDC | RS - Removal from Service | Approved | OW1161424
COL_HOR_3 | BKD-HOR-A0005-0006-20 | 2027-05-18 07:30 | 2027-05-18 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160392
COL_HOR_2 | BKD-HOR-A0006-0007-10 | 2027-05-19 07:30 | 2027-05-19 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160391
HAY_CB_2452 | HAY-CBL-CB2452-LS3 | 2027-05-19 07:30 | 2027-05-19 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160602
PTS_1873_INV_MAN | INV-C-PTSG-1873, MAN-C-PTSG-1873 | 2027-05-20 07:30 | 2027-05-20 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1161460
MPE_CB_252 | System split for the duration of BRB_HPI_1 | 2027-05-21 06:00 | 2027-05-21 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161130
MPE_CB_292 | System split for the duration of BRB_HPI_1 | 2027-05-21 06:00 | 2027-05-21 18:30 | Daily | NNI | OPE - Open Ended | Approved | OW1161165
OKI_220BS_A | OKI-DS-273 (WRK_1) | 2027-05-21 07:30 | 2027-05-21 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005252
OKI_CB_238 | Affected equipment of OKI_220BS_A, for OKI-DS-273 (WRK_1) | 2027-05-21 07:30 | 2027-05-21 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005250
BPE_110BZ | BPE-TNG prot upgrade Stage 10: BPE-T3 protection upgrade [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-05-22 08:00 | 2027-05-22 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005590
BPE_110CBF | Affected equipment of BPE_110BZ, for BPE-TNG prot upgrade Stage10 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-05-22 08:00 | 2027-05-22 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005602
BPE_220BZ | BPE-TNG prot upgrade Stage 10: BPE-T3 protection upgrade [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-05-22 08:00 | 2027-05-22 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005589
BPE_220CBF | Affected equipment of BPE_220BZ, for BPE-TNG prot upgrade Stage10 [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. | 2027-05-22 08:00 | 2027-05-22 16:00 | Daily | SNI | RS - Removal from Service | Approved | OW2005601
KIK_STK_3 | under clearance req | 2027-05-24 06:30 | 2027-05-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160934
OKI_CB_238 | Affected equipment of OKI_220BS_A | 2027-05-24 07:00 | 2027-05-27 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161289
NAP_OKI_2 | NAP-CT-CT182, OKI-DS-305, OKI-DS-306, OKI-ES-300 | 2027-05-24 07:00 | 2027-05-28 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161196
OKI_220BS_A | OKI-DS-233 (BC), OKI-DS-303 (NAP_2), OKI-DS-317, OKI-ES-310, OKI-ES-319 | 2027-05-24 07:00 | 2027-05-27 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161286
KAI_SBK_1 | Safety for new CB62 Pole Replacement | 2027-05-24 07:30 | 2027-05-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005526
KIW_GOR_NMA_1 | GOR-CVT-VT752, GOR-DS-756, GOR-ES-759, NMA-CT-CT832, | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2006037
KAI_74_87 | Safety for new CB62 Pole Replacement | 2027-05-24 07:30 | 2027-05-25 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005527
BEN_T34 | S1.P2-AL.T1 | 2027-05-24 07:30 | 2027-05-25 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160284
KUM_OTI_1 | CA Lifting inspections | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160999
GOR_T11 | GOR-CB-752, GOR-CBL-T11-ET11, GOR-CT-CT612, GOR-CT-CT752, GOR-CT-NCT11, GOR-DCB-612, GOR-NCTD-T11, GOR-P-CB-752, GOR-P-TF-T11, GOR-TF-ET11, GOR-TF-T11 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160530
WPR_T12 | WPR-CB-172, WPR-CT-CT432, WPR-CT-T12, WPR-P-TF-T12, WPR-TF-T12 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1161828
MGM_T2 | MGM-CB-1282, MGM-VT-12. MGM-M-CT1282 - metering days 2 + 3. | 2027-05-24 07:30 | 2027-05-26 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161052
KIN_367_394 | KIN-VT-377 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160939
KIN_T5 | KIN-CBL-36, KIN-CBL-T5-2232, KIN-CBL-T5-NER5, KIN-CT-392, KIN-DS-36, KIN-RES-NER5, KIN-TF-ET5, KIN-TF-T5, KIN-VT-2047, KIN-VT-2232, KIN-VT-30 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160947
KIN_CB_2072 | Closed for the duration of KIN T5 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | NNI | CLO - Close | Approved | OW1162251
HKK_OTI_2 | CA Lifting inspections | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160695
KIN_TRK_1 | LCH-KIN-A0739-0740-10 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160952
LFD_DIS_56 | Affected equipment KIN_367_394 & KIN_T5 & KIN_T6 & KIN_TRK_1 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161010
KIN_T6 | KIN-M-CT2932, KIN-M-VT2932 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160948
ALB_SVL_2 | Tower Painting | 2027-05-24 08:00 | 2027-05-28 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142691
SVL_T2 | Affected Equipment Tower Painting | 2027-05-24 08:00 | 2027-05-28 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1142692
HAY_MLG_2 | HAY_110BZ Stage 3C; Bay 180 - Melling cct 2 [CP_HAY_IN_00_00]. No other HAY work on days 1, 4, 5. No other work on associated equipment/lines on day 5 (commissioning). | 2027-05-25 07:00 | 2027-05-29 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2006095
MLG_T2 | Affected equipment of HAY_MLG_2, for HAY_110BZ Stage 3C; Bay 180 - Melling cct 2 [CP_HAY_IN_00_00] | 2027-05-25 07:00 | 2027-05-29 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2006096
MLG_T4 | Affected equipment of HAY_MLG_2, for HAY_110BZ Stage 3C; Bay 180 - Melling cct 2 [CP_HAY_IN_00_00] | 2027-05-25 07:00 | 2027-05-29 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2006097
DVK_T1 | Affected equipment of WDV_DVK_WPW_2. | 2027-05-25 07:30 | 2027-05-25 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160462
WDV_57_67_117 | WDV-P-CB-62 (BPE-2) | 2027-05-25 07:30 | 2027-05-25 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161759
WDV_DVK_WPW_2 | Affected equipment of WDV_57_67_117, for WDV-P-CB-62 (BPE-2) | 2027-05-25 07:30 | 2027-05-25 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161768
BEN_F_4 | S1.WA-Z1.F1.A, S1.WA-Z1.F1.B, S1.WA-Z1.F1.C, S1.WA-Z1.Q1, S1.WA-Z1.Q2, S1.WA-Z1.Z1.F1.A, S1.WA-Z1.Z1.F1.B, S1.WA-Z1.Z1.F1.C, S1.WA-Z1.Z1.R1A, S1.WA-Z1.Z1.R1B, S1.WA-Z1.Z1.R1C, S1.WA-Z1.Z2.F1.A, S1.WA-Z1.Z2.F1.B, S1.WA-Z1.Z2.F1.C, S1.WA-Z1.Z2.L1A, S1.WA-Z1.Z2.L1B, S1.WA-Z1.Z2.R1A, S1.WA-Z1.Z2.R1B, S1.WA-Z1.Z2.R1C | 2027-05-25 07:30 | 2027-05-26 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160272
WPW_T1 | Affected equipment of WDV_DVK_WPW_2. | 2027-05-25 07:30 | 2027-05-25 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161838
BPE_WDV_2 | BPE-P-CB-82, WDV-P-CB-62. Re-insulation x12. BPE_WDV_1/2 lineprotection replacement project [CP_BPE_02C_0_00]. Last day for commissioning (no other work). | 2027-05-25 07:30 | 2027-06-01 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160350
HAY_110CBF | HAY_110BZ Stage 3C; Bay 180 - Melling cct 2. | 2027-05-25 08:00 | 2027-05-25 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161968
HAY_110BZ | HAY_110BZ Stage 3C; Bay 180 - Melling cct 2. No work in HAY 110kV yard. | 2027-05-25 08:00 | 2027-05-25 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161922
PTS_2309_LFD_TRK | LFD-C-PTSG-2309A, TRK-C-PTSG-2309A | 2027-05-26 07:30 | 2027-05-26 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1161463
MGM_ACO_SPS | MGM-P-SPS-OTAS [CP_MGM_AC_00_00]. | 2027-05-26 07:30 | 2027-05-26 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161048
BDE_110BZ | BDE-P-BZ-110 | 2027-05-27 07:30 | 2027-05-28 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160205
BDE_110CBF | BDE-P-BZ-110 | 2027-05-27 07:30 | 2027-05-28 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160206
OKI_220BS_B | OKI-DS-305 (NAP_2) | 2027-05-28 07:30 | 2027-05-28 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005251
OKI_CB_238 | Affected equipment of OKI_220BS_B, for OKI-DS-305 (NAP_2) | 2027-05-28 07:30 | 2027-05-28 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW2005244
HAY_110CBF | HAY_110BZ Stage 3C; Bay 180 - Melling cct 2. | 2027-05-28 08:00 | 2027-05-28 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161969
HAY_110BZ | HAY_110BZ Stage 3C; Bay 180 - Melling cct 2. No work in HAY 110kV yard. | 2027-05-28 08:00 | 2027-05-28 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161923
HAY_110CBF | HAY_110BZ Stage 3C; Bay 180 - Melling cct 2. | 2027-05-29 08:00 | 2027-05-29 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161970
HAY_110BZ | HAY_110BZ Stage 3C; Bay 180 - Melling cct 2. No work in HAY 110kV yard. | 2027-05-29 08:00 | 2027-05-29 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161924
OKI_220BS_A | With Bus B. Maintenance on Contact DS-353, DS-373, ES-350. Aligned with OKI shut. | 2027-05-31 07:30 | 2027-06-01 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW2005264
ALB_CB_658 | ALB-CT-658, ALB-P-CB-658 | 2027-05-31 07:30 | 2027-06-01 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160128
OKI_220BS_B | With Bus A. Maintenance on Contact DS-355, DS-375, ES-370. Aligned with OKI shut. | 2027-05-31 07:30 | 2027-06-01 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW2005265
HTI_T1 | HTI-CBL-T1-2242, HTI-CBL-T1-LS1, HTI-TF-LS1, HTI-TF-T1B, HTI-TF-T1R, HTI-TF-T1Y | 2027-05-31 07:30 | 2027-06-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160731
BDE_C_2 | BDE-CAPS-C2, BDE-CBL-18, BDE-REA-C2 | 2027-05-31 07:30 | 2027-06-02 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160211
MGM_T3 | MGM-CB-1362, MGM-CBL-1362, MGM-TF-LS33, MGM-TF-T3, MGM-VT-13 | 2027-05-31 07:30 | 2027-06-02 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161053
MGM_MST_1 | Pole replacements x6. | 2027-05-31 07:30 | 2027-06-04 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161051
HEN_OTA_1 | Attachment points, re-insulation and steel and bolts. | 2027-05-31 08:00 | 2027-06-04 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005216
BLN_T2 | BLN-CB-92 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160307
BLN_FDR_2052 | Affected equipment BLN_33BS_A & BLN_C_1 & BLN_C_3 & BLN_CB_2028_CBL & BLN_T2 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160301
DVK_T1 | Affected equipment of WDV_DVK_WPW_2. | 2027-06-01 07:30 | 2027-06-01 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160463
WPW_T1 | Affected equipment of WDV_DVK_WPW_2. | 2027-06-01 07:30 | 2027-06-01 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161839
BLN_FDR_2042 | Affected equipment BLN_33BS_A & BLN_C_1 & BLN_C_3 & BLN_CB_2028_CBL & BLN_T2 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160300
BLN_FDR_2032 | Affected equipment BLN_33BS_A & BLN_C_1 & BLN_C_3 & BLN_CB_2028_CBL & BLN_T2 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160299
BLN_CB_2108 | Affected equipment BLN_33BS_A & BLN_C_1 & BLN_C_3 & BLN_CB_2028_CBL & BLN_T2 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160298
BLN_CB_2028_CBL | BLN-CB-2028 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160296
BLN_C_3 | BLN-CAPS-C3, BLN-CB-2072, BLN-CBL-C3, BLN-REA-C3-1, BLN-REA-C3-3, BLN-VT-C3-2 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160294
BLN_C_1 | BLN-CAPS-C1, BLN-CB-2082, BLN-CBL-C1, BLN-REA-C1-1, BLN-REA-C1-3, BLN-VT-C1-2 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160292
BLN_33BS_A | 1 yrs, BLN-VT-VT2067 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160288
WDV_DVK_WPW_2 | Affected equipment of WDV_57_67_117, for WDV-P-CB-62 (BPE-2) | 2027-06-01 07:30 | 2027-06-01 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161769
WDV_57_67_117 | WDV-P-CB-62 (BPE-2) | 2027-06-01 07:30 | 2027-06-01 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161760
WPW_T33 | WPW-TF-T33 (TENTATIVE OW - asset may be divested). | 2027-06-02 07:30 | 2027-06-03 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161843
BEN_T37 | S1.20T37-T37 | 2027-06-02 07:30 | 2027-06-03 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160286
WPW_DIS_36B | Affected equipment of WPW_T33, for WPW-TF-T33 (TENTATIVE OW - asset may be divested). | 2027-06-02 07:30 | 2027-06-03 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161836
WPW_DIS_36A | Affected equipment of WPW_T33, for WPW-TF-T33 (TENTATIVE OW - asset may be divested). | 2027-06-02 07:30 | 2027-06-03 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161835
BDE_EDN_1 | BDE-DEV-A0014-0015-00, GOR-INV-A0085-10, GOR-INV-A0113-00, GOR-INV-A0128-00 | 2027-06-03 07:30 | 2027-06-04 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160215
KAI_SBK_1 | Affected Equipment of KAI_74_87 To Commission new T1 Protection and CB82 Poles | 2027-06-04 07:30 | 2027-06-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005529
KAI_74_87 | To Commission new T1 Protection and CB82 Poles | 2027-06-04 07:30 | 2027-06-04 18:30 | Daily | SI | RS - Removal from Service | Approved | OW2005528
HAY_CB_258 | HAY-CT-258, HAY-P-CB-258 | 2027-06-07 07:30 | 2027-06-07 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160604
BDE_T1 | BDE-CBL-37, BDE-CT-T1, BDE-TF-LS1, BDE-TF-T1, BDE-VT-VT37 | 2027-06-08 07:30 | 2027-06-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160221
ISL_66BS_A | ISL-DS-293 Diagnostic inspection and service (DS0011) - Disconnector and Earth Switch: Canterbury Engineering (2045145) 500648116 HOR_KBY_ISL_1, ISL_66BS_A | 2027-06-08 07:30 | 2027-06-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160809
ISL_CB_708 | Affected Equipment of ISL_66BS_A ISL-DS-293 Diagnostic inspection and service (DS0011) - Disconnector and Earth Switch: Canterbury Engineering (2045145) 500648116 HOR_KBY_ISL_1, ISL_66BS_A | 2027-06-08 07:30 | 2027-06-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160838
HOR_KBY_ISL_1 | HOR-DS-66, HOR-ES-69, HOR-P-CB-62, ISL-CB-292, ISL-CBL-292, ISL-DS-293, ISL-DS-295, ISL-DS-296, ISL-ES-299, ISL-P-CB-292, ISL-VT-VT20, KBY-DS-4926, KBY-ES-4929, KBY-VT-VT4922 | 2027-06-08 07:30 | 2027-06-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160722
KBY_CB_4922 | Affected equipment HOR_KBY_ISL_1 | 2027-06-08 07:30 | 2027-06-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160915
ISL_CB_768 | ISL-P-CB-768 -Affected Equipment of ISL_66BS_A ISL-DS-293 Diagnostic inspection and service (DS0011) - Disconnector and EarthSwitch: Canterbury Engineering (2045145) 500648116 HOR_KBY_ISL_1, ISL_66BS_A | 2027-06-08 07:30 | 2027-06-09 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160844
ARI_110CBF | Affected equipment | 2027-06-08 07:30 | 2027-06-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160153
ARI_HAM_1 | ARI-HAM-B0005-00,, ARI-HAM-B0093-10, ARI-HAM-B0097-00, ARI-HAM-B0098-00, ARI-HAM-B0101-00, ARI-HAM-B0107-00, ARI-HAM-B0108-10, ARI-HAM-B0116-00, ARI-HAM-B0119-10, ARI-HAM-B0120-10, ARI-HAM-B0124-00, ARI-HAM-B0129-10, ARI-HAM-B0132-10, ARI-HAM-B0135-10, ARI-HAM-B0136-10, ARI-HAM-B0140-10 | 2027-06-08 07:30 | 2027-06-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160164
ARI_110BZ_A | ARI-P-BZ-110-A | 2027-06-08 07:30 | 2027-06-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160152
ATI_TRK_1 | ATI-CT-102, ATI-CVT-102, ATI-DS-106, ATI-ES-109, TRK-DS-566, TRK-P-CB-562, TRK-VT-CVT562 | 2027-06-08 07:30 | 2027-06-09 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160197
PEN_CB_8612 | Place PEN REA into service for the duration of HEN_SWN_1 | 2027-06-08 08:00 | 2027-06-11 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW2005218
HEN_SWN_1 | Attachment points, re-insulation & Steel and bolts | 2027-06-08 08:00 | 2027-06-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005217
PEN_T10 | System split for the duration of HEN_SWN_1 | 2027-06-08 08:00 | 2027-06-11 18:30 | Continuous | NNI | OPE - Open Ended | Approved | OW2005219
HAY_MLG_1 | HAY_110BZ Stage 3D; Bay 200 - Melling cct 1. No other HAY work on days 1, 5, 6. No other work on associated equipment/lines on day 6 (commissioning). | 2027-06-09 07:00 | 2027-06-13 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2006091
MLG_T1 | Affected equipment of HAY_MLG_1, for HAY_110BZ Stage 3D; Bay 200 - Melling cct 1 [CP_HAY_IN_00_00]. | 2027-06-09 07:00 | 2027-06-13 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2006092
MLG_T3 | Affected equipment of HAY_MLG_1, for HAY_110BZ Stage 3D; Bay 200 - Melling cct 1 [CP_HAY_IN_00_00]. | 2027-06-09 07:00 | 2027-06-13 18:00 | Continuous | SNI | RS - Removal from Service | Approved | OW2006094
BPE_CB_918 | Affected equipment of BPE_220BS_B | 2027-06-09 07:30 | 2027-06-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160328
HLY_CB_662 | HLY-P-CB-662 | 2027-06-09 07:30 | 2027-06-11 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160710
BPE_CB_648 | Affected equipment of BPE_220BS_B | 2027-06-09 07:30 | 2027-06-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160326
WRK_T29 | WRK-CB-182, WRK-M-VT2002, WRK-NCT-29, WRK-P-TF-T29, WRK-VT-2002 | 2027-06-09 07:30 | 2027-06-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161863
ALB_FDR_322 | ALB-CB-322, ALB-DS-326, ALB-ES-329 | 2027-06-09 07:30 | 2027-06-10 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160132
BPE_220BS_B | BPE-DS-667 (bus) headgear replacement [CP_RA4_03K_0_00] | 2027-06-09 07:30 | 2027-06-11 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1160316
HAY_110BZ | HAY_110BZ Stage 3D; Bay 200 - Melling cct 1. No work in HAY 110kV yard. | 2027-06-09 08:00 | 2027-06-09 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161925
HAY_110CBF | HAY_110BZ Stage 3D; Bay 200 - Melling cct 1. | 2027-06-09 08:00 | 2027-06-09 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161971
ISL_CB_748 | ISL-P-CB-748 | 2027-06-10 07:30 | 2027-06-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160841
WRK_FDR_2022 | WRK-CBL-2022-FDR | 2027-06-10 07:30 | 2027-06-10 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161860
ISL_CB_768 | Affected Equipment of ISL_66BS_B ISL-P-CB-748 | 2027-06-10 07:30 | 2027-06-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160845
ISL_66BS_B | ISL-P-CB-748 | 2027-06-10 07:30 | 2027-06-11 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160810
WRK_FDR_2042 | WRK-CBL-2042-FDR | 2027-06-11 07:30 | 2027-06-11 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161861
HAY_110CBF | HAY_110BZ Stage 3D; Bay 200 - Melling cct 1. | 2027-06-12 08:00 | 2027-06-12 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161972
HAY_110BZ | HAY_110BZ Stage 3D; Bay 200 - Melling cct 1. No work in HAY 110kV yard. | 2027-06-12 08:00 | 2027-06-12 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161926
HAY_110CBF | HAY_110BZ Stage 3D; Bay 200 - Melling cct 1. | 2027-06-13 08:00 | 2027-06-13 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161973
HAY_110BZ | HAY_110BZ Stage 3D; Bay 200 - Melling cct 1. No work in HAY 110kV yard. | 2027-06-13 08:00 | 2027-06-13 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1161927
GOR_T12 | GOR-CB-712, GOR-CBL-T12-ET12, GOR-CT-CT592, GOR-CT-CT712, GOR-CT-NCT12, GOR-DCB-592, GOR-DS-716, GOR-NCTD-T12, GOR-P-CB-712, GOR-P-TF-T12, GOR-TF-ET12, GOR-TF-T12 | 2027-06-14 07:30 | 2027-06-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160535
GOR_557_607 | GOR-DS-567, GOR-DS-574, GOR-DS-597, GOR-VT-VT597 | 2027-06-14 07:30 | 2027-06-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160522
GOR_T2 | GOR-P-TF-T2, GOR-TF-T2 | 2027-06-14 07:30 | 2027-06-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160536
BDE_GOR_1 | GOR-INV-A0014-00, GOR-INV-A0019-00, GOR-INV-A0039-00, GOR-INV-A0062-10 | 2027-06-14 07:30 | 2027-06-21 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160220
OPK_KPI_SFD_2 | SFD-P-CB-102. OPK-SFD-A0097-00. Benchmarking [CP_VAR_1B7_0_00]. | 2027-06-14 07:30 | 2027-06-15 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161300
CUL_FDR_142 | Prot upgrade | 2027-06-14 07:30 | 2027-06-30 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005530
HAM_PAO_WHU_1 | HAM-WHU-A0017A-00, HAM-WHU-A0024-10, HAM-WHU-A0025-10, HAM-WHU-A0027-10, HAM-WHU-A0028-10, HAM-WHU-A0029-10, HAM-WHU-A0030-10, HAM-WHU-A0031-10, HAM-WHU-A0033-10, HAM-WHU-A0036-10, HAM-WHU-A0037-10, HAM-WHU-A0039-10 | 2027-06-14 07:30 | 2027-06-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160565
HOR_FDR_52 | HOR-CB-52, HOR-P-CB-52 | 2027-06-14 07:30 | 2027-06-14 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160721
PAO_CB_212 | Affected equipment HAM_PAO_WHU_1 | 2027-06-14 07:30 | 2027-06-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161364
OTA_SWN_1 | Attachment points, re-insulation & Steel and bolts | 2027-06-14 08:00 | 2027-06-18 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005229
HEP_C_11 | HEP-CB-172 | 2027-06-15 07:30 | 2027-06-15 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160674
HOR_KBY_ISL_2 | HOR-ISL-EHORG23-10, ISL-CB-132 | 2027-06-15 07:30 | 2027-06-18 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160723
KBY_CB_4902 | Affected equipment HOR_KBY_ISL_2 | 2027-06-15 07:30 | 2027-06-18 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW1160914
PAK_CB_472 | Affected Equipment of PAK_220BS_A PAK 412 Siemens relay replacement | 2027-06-15 07:30 | 2027-06-15 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW2006323
PAK_220BS_A | PAK 412 Siemens relay replacement | 2027-06-15 07:30 | 2027-06-15 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW2006320
PAK_CB_502 | Affected Equipment of PAK_220BS_A PAK 412 Siemens relay replacement | 2027-06-15 07:30 | 2027-06-15 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW2006324
OPK_T4 | OPK-P-TF-T4, OPK-TF-T4. OPK_T4 LV bushing replacement [CP_OPK_00L_0_00]. Benchmarking [CP_VAR_1B7_0_00]. | 2027-06-15 07:30 | 2027-06-16 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161303
PAK_CB_452 | Affected Equipment of PAK_220BS_A PAK 412 Siemens relay replacement | 2027-06-15 07:30 | 2027-06-15 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW2006322
BPE_220BZ | BPE-P-BZ-220 | 2027-06-15 07:30 | 2027-06-15 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160317
BPE_220CBF | Affected equipment of BPE_220BZ, for BPE-P-BZ-220 | 2027-06-15 07:30 | 2027-06-15 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160318
PAK_R562 | Affected Equipment of PAK_220BS_A PAK 412 Siemens relay replacement | 2027-06-15 07:30 | 2027-06-15 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW2006325
OTA_PAK_3 | OTA-PAK-3 / OTA-CBL-512 - Project CP_OTA_01Z_0_00 - Cable Termination Retrofits OTA-PAK-3 / OTA-CBL-512 - Cable Termination Retrofits- Project CP_OTA_01Z_0_00 | 2027-06-15 07:30 | 2027-07-13 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005333
PAK_CB_412 | Affected Equipment of PAK_220BS_A PAK 412 Siemens relay replacement | 2027-06-15 07:30 | 2027-06-15 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW2006321
PAK_T3 | Affected Equipment of PAK_220BS_A PAK 412 Siemens relay replacement | 2027-06-15 07:30 | 2027-06-15 16:00 | Daily | NNI | RS - Removal from Service | Approved | OW2006326
HKK_KUM_1 | AHA-OTI-A0365-00, AHA-OTI-A0410-00 | 2027-06-16 06:30 | 2027-06-16 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160691
HEN_110BZ | HEN-P-BZ-110 | 2027-06-16 07:30 | 2027-06-17 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160639
HEN_110CBF | Affected equipment | 2027-06-16 07:30 | 2027-06-17 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160640
HAY_CB_2662 | HAY-CBL-CB2662-LS4 | 2027-06-16 07:30 | 2027-06-16 18:30 | Daily | HVDC | RS - Removal from Service | Approved | OW1160607
BPE_CB_918 | BPE-CB-918, BPE-CT-918, BPE-P-CB-918 | 2027-06-16 07:30 | 2027-06-16 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1160329
HKK_OTI_2 | AHA-OTI-A0365-00 | 2027-06-17 06:30 | 2027-06-17 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160696
WHI_R1 | WHI-CB-2862, WHI-CBL-1204-2862, WHI-P-CB-2862 | 2027-06-17 07:30 | 2027-06-17 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161782
OPK_SFD_1 | Affected equipment of OPK_T5, for OPK-P-TF-T5, OPK-TF-T5 | 2027-06-17 07:30 | 2027-06-18 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161302
HAM_CB_118 | HAM-CB-118 | 2027-06-17 07:30 | 2027-06-17 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160549
GLN_CB_658 | Affected equipment GLN_220BS_B | 2027-06-17 07:30 | 2027-06-17 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160517
OPK_T5 | OPK-P-TF-T5, OPK-TF-T5. OPK_T5 LV bushing replacement [CP_OPK_00L_0_00]. Benchmarking [CP_VAR_1B7_0_00]. | 2027-06-17 07:30 | 2027-06-18 18:30 | Continuous | SNI | RS - Removal from Service | Approved | OW1161304
GLN_220BS_B | Motor mech installation. GLN-BS-220-605-BUS-B, GLN-BS-220-615-BUS-B, GLN-BS-220-625-BUS-B, GLN-BS-220-635-BUS-B, GLN-BS-220-645-BUS-B, GLN-BS-220-B-CLEAN, GLN-DS-615, GLN-DS-635 | 2027-06-17 07:30 | 2027-06-17 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160512
HKK_KUM_1 | AHA-OTI-A0365-00, AHA-OTI-A0410-00 | 2027-06-18 06:30 | 2027-06-18 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1163795
EDG_KAW_1 | EDG-KAW-A0069-10, EDG-KAW-A0071-10, EDG-KAW-A0075-10, EDG-KAW-A0077-10, EDG-KAW-A0078-10, EDG-KAW-A0088-10 | 2027-06-21 06:30 | 2027-06-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160474
KUM_OTI_1 | OTI-CB-92 Pole Replacement | 2027-06-21 07:30 | 2027-06-24 18:30 | Continuous | SI | RS - Removal from Service | Approved | OW2005175
WHI_FDR_12 | WHI-CB-12 | 2027-06-21 07:30 | 2027-06-21 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161776
WKO_T1 | Affected equipment WKO_504_514_547 & WHU_WKO_2 | 2027-06-21 07:30 | 2027-06-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161814
WKO_504_514_547 | WKO-DS-504, WKO-DS-514, WKO-DS-524, WKO-DS-537, WKO-VT-2 | 2027-06-21 07:30 | 2027-06-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161813
KPU_367_VT10 | Affected equipment with WKO_504_514_547 | 2027-06-21 07:30 | 2027-06-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162253
KPU_T3 | Affected equipment with WKO_504_514_547 | 2027-06-21 07:30 | 2027-06-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1162252
KPU_WKO_2 | Affected equipment WKO_504_514_547 & WHU_WKO_2 | 2027-06-21 07:30 | 2027-06-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160996
WHU_WKO_2 | WHU-CT-102, WHU-DS-106, WHU-ES-109, WKO-CT-512, WKO-DS-516, WKO-ES-519 | 2027-06-21 07:30 | 2027-06-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161790
HEP_ROS_1 | Attachment point, re-insulation and steel and bolts | 2027-06-21 08:00 | 2027-06-24 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW2005157
WHI_FDR_13 | WHI-CB-13 | 2027-06-22 07:30 | 2027-06-22 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161777
EDN_110BZ_PROT1 | EDN-P-BZ-110 | 2027-06-23 07:30 | 2027-06-24 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160486
EDN_110CBF_PROT1 | EDN-P-BZ-110 | 2027-06-23 07:30 | 2027-06-24 18:30 | Daily | SI | RS - Removal from Service | Approved | OW1160487
WHI_FDR_14 | WHI-CB-14 | 2027-06-23 07:30 | 2027-06-23 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161778
BRB_CB_168 | BRB-CB-168 | 2027-06-23 07:30 | 2027-06-23 18:30 | Daily | NNI | RS - Removal from Service | Approved | OW1160354
WHI_FDR_15 | WHI-P-CB-15 | 2027-06-24 07:30 | 2027-06-24 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161779
ARI_KIN_2 | ARI-CT-202, ARI-DS-206, ARI-EDG-B0042-00, ARI-EDG-B0047-00, ARI-ES-209 | 2027-06-28 07:30 | 2027-06-29 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1160174
MTM_110CBF | Affected equipment | 2027-06-28 07:30 | 2027-06-30 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161177
MTM_110BZ | MTM-P-BZ-110-A | 2027-06-28 07:30 | 2027-06-30 18:30 | Continuous | NNI | RS - Removal from Service | Approved | OW1161176
WHI_FDR_2822 | WHI-CB-2822, WHI-P-CB-2822 | 2027-06-28 07:30 | 2027-06-28 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161780
WHI_FDR_2832 | WHI-CB-2832, WHI-P-CB-2832 | 2027-06-29 07:30 | 2027-06-29 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1161781
HAY_110BZ | HAY_110BZ Stage 3P; Bay 140 - Transformer T9. No work in HAY 110kV yard. | 2027-06-29 08:00 | 2027-06-29 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1160582
HAY_110CBF | HAY_110BZ Stage 3P; Bay 140 - Transformer T9. | 2027-06-29 08:00 | 2027-06-29 17:00 | Daily | SNI | RS - Removal from Service | Approved | OW1160592
WHI_FDR_2842 | WHI-CB-2842, WHI-P-CB-2842 | 2027-06-30 07:30 | 2027-06-30 18:30 | Daily | SNI | RS - Removal from Service | Approved | OW1162194