## Outage Window Advanced Find...
Outage Block | Planned Start Date/Time | Planned Finish Date/Time | Time Frame | Nature | Description of Work | Status
HKK_OTI_2 | 2026-07-01 06:30 | 2026-07-01 18:30 | Daily | RS - Removal from Service | Structure replacement CP_RA5_01N_0_00 | Lodged
IGH_KIK_1 | 2026-07-01 07:30 | 2026-07-01 18:30 | Daily | RS - Removal from Service | IGH-KIK-A0042-00, IGH-KIK-A0052-00, IGH-KIK-A0040-00, IGH-KIK-A0048-00, IGH-KIK-A0043-00, IGH-KIK-A0038-00, IGH-KIK-A0037-00, IGH-KIK-A0036-00, IGH-KIK-A0049-00, IGH-KIK-A0044-00, IGH-KIK-A0047-00, IGH-KIK-A0039-00, IGH-KIK-A0041-00, IGH-KIK-A0050-00, IGH-KIK-A0051-00 | Lodged
INV_MAN_2 | 2026-07-01 07:30 | 2026-07-01 18:30 | Daily | RS - Removal from Service | INV-MAN-A0337-00, INV-MAN-A0355-00, INV-MAN-A0354-00, INV-MAN-A0344-00, INV-MAN-A0122-00, INV-MAN-A0034-00, INV-MAN-A0123-00, INV-MAN-A0283-00, INV-MAN-A0033-00, INV-MAN-A0280-00, INV-MAN-A0028-00, INV-MAN-A0119-00, INV-MAN-A0036-00, INV-MAN-A0037-00, INV-MAN-A0035-00, INV-MAN-A0032-00, INV-MAN-A0120-00, INV-MAN-A0029-00, INV-MAN-A0282-00, INV-MAN-A0030-00, INV-MAN-A0031-00, INV-MAN-A0121-00, INV-MAN-A0279-00, INV-MAN-A0281-00 | Lodged
ISL_NWD_1 | 2026-07-01 07:30 | 2026-07-01 18:30 | Daily | RS - Removal from Service | ROX-ISL-A1056-00, ROX-ISL-A1069-00, ROX-ISL-A1068-00, ROX-ISL-A1064-00, ROX-ISL-A1060-00, ROX-ISL-A1062-00, ROX-ISL-A1063-00, ROX-ISL-A1066-00, ROX-ISL-A1065-00, ROX-ISL-A1067-00, ROX-ISL-A1061-00, ROX-ISL-A1059-00, ROX-ISL-A1058-00, ROX-ISL-A1055-00, ROX-ISL-A1057-00 | Lodged
MAN_NMA_1 | 2026-07-01 07:30 | 2026-07-01 18:30 | Daily | RS - Removal from Service | MAN-TWI-A0276-00, MAN-TWI-A0121-00, MAN-TWI-A0274-00, MAN-TWI-A0035-00, MAN-TWI-A0032-00, MAN-TWI-A0272-00, MAN-TWI-A0037-00, MAN-TWI-A0122-00, MAN-TWI-A0033-00, MAN-TWI-A0036-00, MAN-TWI-A0119-00, MAN-TWI-A0273-00, MAN-TWI-A0275-00, MAN-TWI-A0118-00, MAN-TWI-A0120-00, MAN-TWI-A0034-00, MAN-TWI-A0029-00, MAN-TWI-A0031-00, MAN-TWI-A0038-00, MAN-TWI-A0056-10 | Lodged
HAY_37_VT57 | 2026-07-02 06:30 | 2026-07-03 18:30 | Continuous | RS - Removal from Service | HAY_110BZ Stage 1C; VT57 JB replacement | Lodged
ASY_SBK_1 | 2026-07-02 07:30 | 2026-07-02 18:30 | Daily | RS - Removal from Service | ASY 66 kV CB Repl + Pole Refurb 25/26 | Lodged
BEN_220BZ | 2026-07-02 07:30 | 2026-07-02 18:30 | Daily | RS - Removal from Service | BEN 220BZ - T27 Migration | Lodged
BEN_220CBF | 2026-07-02 07:30 | 2026-07-02 18:30 | Daily | RS - Removal from Service | BEN 220BZ - T27 Migration | Lodged
IGH_ROB_1 | 2026-07-02 07:30 | 2026-07-02 18:30 | Daily | RS - Removal from Service | IGH-WPT-B0027-00, IGH-WPT-B0034-00, IGH-WPT-B0032-00, IGH-WPT-B0037-00, IGH-WPT-B0030-00, IGH-WPT-B0033-00, IGH-WPT-B0029-00, IGH-WPT-B0031-00, IGH-WPT-B0035-00, IGH-WPT-B0028-00, IGH-WPT-B0036-00 | Lodged
INV_T5 | 2026-07-02 07:30 | 2026-07-05 18:30 | Continuous | RS - Removal from Service | Invercargill Protection Replacements - x3 Transformer, Feeder, 33kV Bus Zone Protection & Arc flash | Lodged
MCH_RTU_1 | 2026-07-02 07:30 | 2026-07-05 18:30 | Continuous | RS - Removal from Service | SMS & GPS Replacements inc n-1 Improvements 25/27 (RSA5) | Lodged
CST_T2 | 2026-07-06 07:30 | 2026-07-08 18:30 | Continuous | RS - Removal from Service | CST-M-CT2132, CST-M-VT2132. CST-P-TF-T2 [CP_CST_00Q_0_00]. | Lodged
EDN_T1 | 2026-07-06 07:30 | 2026-07-08 18:30 | Continuous | RS - Removal from Service | EDN-CB-2052, EDN-M-CT2052, EDN-M-VT5 | Lodged
LFD_RTU_1 | 2026-07-06 07:30 | 2026-07-09 18:30 | Continuous | RS - Removal from Service | SMS Replacements inc n-1 Improvements 25/27 (RSA2) | Lodged
TWI_CB_468 | 2026-07-06 07:30 | 2026-07-06 18:30 | Daily | RS - Removal from Service | TWI-P-CB-468 | Lodged
ATU_DOB_1 | 2026-07-06 07:30 | 2026-07-09 18:30 | Continuous | RS - Removal from Service | Affected Equipment of DOB_RFN_IGH_1 BWR-IGH-A0398 | Lodged
DOB_RFN_IGH_1 | 2026-07-06 07:30 | 2026-07-09 18:30 | Continuous | RS - Removal from Service | BWR-IGH-A0398, BWR-IGH-A0420, BWR-IGH-A0472 IGH 110 kV CB412 Line Protection Replacement | Lodged
DOB_T12 | 2026-07-06 07:30 | 2026-07-09 18:30 | Continuous | RS - Removal from Service | Affected Equipment of DOB_RFN_IGH_1 BWR-IGH-A0398 | Lodged
COL_OTI_2 | 2026-07-07 07:30 | 2026-07-08 18:30 | Daily | RS - Removal from Service | Affected Equipment of OTI_67_46_56 OTI-VT-VT67 | Lodged
FHL_RTU_1 | 2026-07-07 07:30 | 2026-07-07 18:30 | Daily | RS - Removal from Service | SMS replacements [CP_RA4_03E_0_00] | Lodged
FHL_T3 | 2026-07-07 07:30 | 2026-07-07 18:30 | Daily | RS - Removal from Service | FHL-TF-T3 | Lodged
GOR_ROX_1 | 2026-07-07 07:30 | 2026-07-07 18:30 | Daily | RS - Removal from Service | GOR-ROX-A0095-00, GOR-ROX-A0098-00, GOR-ROX-A0108-00, GOR-ROX-A0120-00, GOR-ROX-A0121-00, GOR-ROX-A0127-00, GOR-ROX-A0143-00, GOR-ROX-A0153-00, GOR-ROX-A0159-00, GOR-ROX-A0216-00, GOR-ROX-A0232-10, GOR-ROX-A0244-00, GOR-ROX-A0252-00, GOR-ROX-A0286-00, GOR-ROX-A0397-10, GOR-ROX-A0400-10 | Lodged
HKK_OTI_2 | 2026-07-07 07:30 | 2026-07-08 18:30 | Daily | RS - Removal from Service | Affected Equipment of OTI_67_46_56 OTI-VT-VT67 | Lodged
OTI_67_46_56 | 2026-07-07 07:30 | 2026-07-08 18:30 | Daily | RS - Removal from Service | OTI-VT-VT67 OTI 66 kV CB/CT/VT Repl 27/28 | Lodged
TWI_CB_478 | 2026-07-07 07:30 | 2026-07-07 18:30 | Daily | RS - Removal from Service | TWI-P-CB-478 | Lodged
WEL_AUVLS | 2026-07-07 07:30 | 2026-07-08 18:30 | Continuous | RS - Removal from Service | WEL-P-UVLS | Lodged
TWI_CB_518 | 2026-07-08 07:30 | 2026-07-08 18:30 | Daily | RS - Removal from Service | TWI-P-CB-518 | Lodged
TWZ_220BZ_A_PROT1 | 2026-07-08 07:30 | 2026-07-08 18:30 | Daily | RS - Removal from Service | TWZ-P-BZ-220-A-P1 | Lodged
TWZ_220BZ_A_PROT2 | 2026-07-08 07:30 | 2026-07-08 18:30 | Daily | RS - Removal from Service | TWZ-P-BZ-220-A-P2 | Lodged
TWI_CB_428 | 2026-07-09 07:30 | 2026-07-09 18:30 | Daily | RS - Removal from Service | TWI-P-CB-428 | Lodged
TWZ_220BZ_B_PROT1 | 2026-07-09 07:30 | 2026-07-09 18:30 | Daily | RS - Removal from Service | TWZ-P-BZ-220-B-P1 | Lodged
TWZ_220BZ_B_PROT2 | 2026-07-09 07:30 | 2026-07-09 18:30 | Daily | RS - Removal from Service | TWZ-P-BZ-220-B-P2 | Lodged
KAI_T1 | 2026-07-13 07:30 | 2026-07-31 17:30 | Continuous | RS - Removal from Service | KAI-CBL-LS11, KAI-CBL-NER1, KAI-CBL-T1, KAI-RES-NER1, KAI-TF-T1, KAI-VT-VT2812, KAI-TF-LS11, KAI-CB-62 MP_RA5_031_0_00, KAI IDID and T1 T2 protection replacements; CP_KAI_84_00_00 | Lodged
WPR_FDR_132 | 2026-07-13 07:30 | 2026-07-17 18:30 | Continuous | RS - Removal from Service | WPR-P-CB-132 | Lodged
TMU_11BS_A1 | 2026-07-13 07:30 | 2026-07-15 18:30 | Continuous | RS - Removal from Service | TMU-BS-11-A1 | Lodged
TMU_CB_37 | 2026-07-13 07:30 | 2026-07-15 18:30 | Continuous | RS - Removal from Service | Affected equipment TMU_11BS_A1 & TMU_FDR_23 | Lodged
TMU_CB_38 | 2026-07-13 07:30 | 2026-07-15 18:30 | Continuous | RS - Removal from Service | Affected equipment TMU_11BS_A1 & TMU_FDR_23 | Lodged
TMU_FDR_22 | 2026-07-13 07:30 | 2026-07-15 18:30 | Continuous | RS - Removal from Service | Affected equipment TMU_11BS_A1 & TMU_FDR_23 | Lodged
TMU_FDR_23 | 2026-07-13 07:30 | 2026-07-15 18:30 | Continuous | RS - Removal from Service | TMU-P-CB-23 | Lodged
TMU_FDR_24 | 2026-07-13 07:30 | 2026-07-15 18:30 | Continuous | RS - Removal from Service | Affected equipment TMU_11BS_A1 & TMU_FDR_23 | Lodged
WRK_77_97 | 2026-07-13 07:31 | 2026-07-13 18:31 | Daily | RS - Removal from Service | WRK-DS-87, WRK-DS-194 (NAP_2) | Lodged
WRK_CB_108 | 2026-07-13 07:31 | 2026-07-13 18:31 | Daily | RS - Removal from Service | Affected equipment of WRK_77_97. | Lodged
WRK_DIS_117 | 2026-07-13 07:31 | 2026-07-13 18:31 | Daily | CLO - Close | CLO for the duration of WRK_77_97, to maintain a solid 220kV bus. | Lodged
NAP_WRK_2 | 2026-07-13 07:31 | 2026-07-15 18:31 | Continuous | RS - Removal from Service | OKI-ES-309, OKI-P-CB-302, WRK-CB-192, WRK-CVT-192, WRK-DS-196, WRK-ES-199, WRK-P-CB-192. Affected equipment of WRK_77_97. | Lodged
HAY_247_295 | 2026-07-14 06:30 | 2026-07-15 18:30 | Continuous | RS - Removal from Service | HAY_110BZ Stage 1D; VT267 JB replacement | Lodged
CST_T4 | 2026-07-14 07:30 | 2026-07-16 18:30 | Continuous | RS - Removal from Service | CST-M-CT2262, CST-M-VT2262. CST-P-TF-T4 [CP_CST_00Q_0_00]. | Lodged
EDN_T2 | 2026-07-14 07:30 | 2026-07-16 18:30 | Continuous | RS - Removal from Service | EDN-CB-2112, EDN-M-CT2112, EDN-M-VT6 | Lodged
GFD_CB_2188 | 2026-07-14 07:30 | 2026-07-14 18:30 | Daily | RS - Removal from Service | GFD-CBL-2188-2217 | Lodged
PAO_RTU_1 | 2026-07-14 07:30 | 2026-07-17 18:30 | Continuous | RS - Removal from Service | SMS Replacements inc n-1 Improvements 25/27 (RSA2) | Lodged
TIM_97_114_134 | 2026-07-14 07:30 | 2026-07-15 18:30 | Daily | RS - Removal from Service | TIM-CSA-98 | Lodged
TIM_CB_2752 | 2026-07-14 07:30 | 2026-07-15 18:30 | Daily | CLO - Close | Affected Equipment of TIM_97_114_134 TIM-CSA-98 | Lodged
TIM_T6 | 2026-07-14 07:30 | 2026-07-15 18:30 | Daily | RS - Removal from Service | Affected Equipment of TIM_97_114_134 TIM-CSA-98 | Lodged
TIM_T8 | 2026-07-14 07:30 | 2026-07-15 18:30 | Daily | RS - Removal from Service | Affected Equipment of TIM_97_114_134 TIM-CSA-98 | Lodged
MLG_CB_38 | 2026-07-15 07:00 | 2026-07-15 18:30 | Daily | RS - Removal from Service | MLG-CB-38, MLG-P-CB-38 | Lodged
FHL_110BZ | 2026-07-15 07:30 | 2026-07-15 18:30 | Daily | RS - Removal from Service | FHL-P-BZ-110 | Lodged
FHL_110CBF | 2026-07-15 07:30 | 2026-07-15 18:30 | Daily | RS - Removal from Service | Affected equipment of FHL_110BZ, for FHL-P-BZ-110 | Lodged
OTA_TIE_5 | 2026-07-15 07:30 | 2026-07-16 18:30 | Continuous | RS - Removal from Service | OTA-CT-552, OTA-DS-556, OTA-ES-559, OTA-P-CB-1302-CZP, OTA-P-CB-552 | Lodged
TGA_110BZ | 2026-07-15 07:30 | 2026-07-17 18:30 | Continuous | RS - Removal from Service | TGA-P-BZ-110-A | Lodged
TGA_110CBF | 2026-07-15 07:30 | 2026-07-17 18:30 | Continuous | RS - Removal from Service | TGA-P-BS-110 | Lodged
HAY_37_VT297 | 2026-07-16 06:30 | 2026-07-17 18:30 | Continuous | RS - Removal from Service | HAY_110BZ Stage 1E; VT297 JB replacement | Lodged
HAY_CB_258 | 2026-07-16 06:30 | 2026-07-17 18:30 | Continuous | RS - Removal from Service | Affected equipment of HAY_37_VT297 HAY_110BZ Stage 1E; VT297 JB replacement | Lodged
STU_67_76_T5 | 2026-07-16 07:30 | 2026-07-17 18:30 | Daily | RS - Removal from Service | Affected equipment STU_67_76_T5 & STU_TIM_1 | Lodged
STU_TIM_1 | 2026-07-16 07:30 | 2026-07-17 18:30 | Daily | RS - Removal from Service | GNY-TIM-A0032-00, GNY-TIM-A0068-00, GNY-TIM-A0111-00, GNY-TIM-A0122-00, GNY-TIM-A0127-00, GNY-TIM-A0277-00 | Lodged
TKR_33BZ_K | 2026-07-16 07:31 | 2026-07-17 18:31 | Daily | RS - Removal from Service | TKR-P-BZ-33 | Lodged
TKR_33BZ_L | 2026-07-16 07:31 | 2026-07-17 18:31 | Daily | RS - Removal from Service | TKR-P-BZ-33 | Lodged
TKR_33CBF | 2026-07-16 07:31 | 2026-07-17 18:31 | Daily | RS - Removal from Service | Affected equipment of TKR_33BZ_K/L, for TKR-P-BZ-33 | Lodged
SBK_FDR_152 | 2026-07-17 07:30 | 2026-07-17 18:30 | Daily | RS - Removal from Service | SBK-CB-152 | Lodged
HAY_STC_31 | 2026-07-20 07:30 | 2026-07-24 18:30 | Daily | RS - Removal from Service | S4.10F31-R1, S4.10J01-C1, S4.10J01-L1, S4.10J01-Q15, S4.10J01-Q2, S4.10J01-Q2-R1, S4.10J01-STC31, S4.10J01-T7, S4.10T31 | Lodged
MGM_MST_1 | 2026-07-20 07:30 | 2026-07-24 18:30 | Continuous | RS - Removal from Service | Pole replacements x11 (inc. 4x tagged poles). PDM-L AGS conductor clamp replacement and other PDM works | Lodged
MNI_CB_808 | 2026-07-20 07:30 | 2026-07-20 18:30 | Daily | RS - Removal from Service | MNI-P-CB-808 | Lodged
OTA_TIE_4 | 2026-07-20 07:30 | 2026-07-22 18:30 | Continuous | RS - Removal from Service | OTA-DS-405, OTA-DS-413, OTA-ES-419, OTA-P-CB-1222-CZP, OTA-CT-412, OTA-P-CB-412, OTA-CT-402, OTA-P-CB-402 | Lodged
ROS_110BZ | 2026-07-20 07:30 | 2026-07-21 18:30 | Daily | RS - Removal from Service | ROS-P-BZ-110 | Lodged
ROS_110CBF | 2026-07-20 07:30 | 2026-07-21 18:30 | Daily | RS - Removal from Service | ROS-P-BZ-110 | Lodged
STU_77_66_T6 | 2026-07-20 07:30 | 2026-07-22 18:30 | Continuous | RS - Removal from Service | STU-TF-T6B, STU-TF-T6R, STU-TF-T6Y | Lodged
TKR_CB_92_ITRIP | 2026-07-20 07:30 | 2026-07-20 18:30 | Daily | RS - Removal from Service | TKR-P-ITRP-CB-92-172 | Lodged
TMI_RTU_1 | 2026-07-20 07:30 | 2026-07-23 18:30 | Continuous | RS - Removal from Service | SMS Replacements inc n-1 Improvements 25/27 (RSA2) | Lodged
WDV_T1 | 2026-07-20 07:30 | 2026-07-21 18:30 | Continuous | RS - Removal from Service | WDV-M-CT2632, WDV-M-VT2632 | Lodged
OKI_WRK_1 | 2026-07-20 07:30 | 2026-07-27 18:30 | Continuous | RS - Removal from Service | OKI-CT-272 and WRK-CT-142 | Lodged
ROT_33BZ | 2026-07-20 07:30 | 2026-07-22 18:30 | Continuous | RS - Removal from Service | ROT-P-BZ-33 | Lodged
ROT_33CBF | 2026-07-20 07:30 | 2026-07-22 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
HUI_FDR_1262 | 2026-07-20 07:30 | 2026-07-20 18:30 | Daily | RS - Removal from Service | HUI-CB-1262 | Lodged
HUI_MNI_1 | 2026-07-20 07:30 | 2026-07-21 18:30 | Continuous | RS - Removal from Service | HUI-CVT-892, HUI-DS-896, HUI-ES-899, HUI-P-CB-892, MNI-BU-832, MNI-CVT-832, MNI-P-CB-832 | Lodged
DOB_GYM_1 | 2026-07-21 07:30 | 2026-07-23 18:30 | Continuous | RS - Removal from Service | AHA-DOB-A0243-00 RSA5 TL Pole 26-27 | Lodged
MNI_CB_848 | 2026-07-21 07:30 | 2026-07-21 18:30 | Daily | RS - Removal from Service | MNI-P-CB-848 | Lodged
PTS_2182_HWB_SDN | 2026-07-21 07:30 | 2026-07-21 18:00 | Daily | RS - Removal from Service | HWB-C-PTSG-2182, SDN-C-PTSG-2182 | Lodged
PTS_270598_MAN_ROX | 2026-07-21 07:30 | 2026-07-21 18:30 | Daily | RS - Removal from Service | MAN-C-PTSG-270598, ROX-C-PTSG-270598 | Lodged
EDN_INV_1 | 2026-07-21 07:30 | 2026-07-23 18:30 | Continuous | RS - Removal from Service | Affected equipment INV_707_604 | Lodged
INV_707_604 | 2026-07-21 07:30 | 2026-07-23 18:30 | Continuous | RS - Removal from Service | INV-DS-604 | Lodged
INV_CB_632 | 2026-07-21 07:30 | 2026-07-23 18:30 | Continuous | RS - Removal from Service | Affected equipment INV_707_604 | Lodged
INV_T1 | 2026-07-21 07:30 | 2026-07-23 18:30 | Continuous | RS - Removal from Service | Affected equipment INV_707_604 Invercargill Protection Replacements - x3 Transformer, Feeder, 33kV Bus Zone Protection & Arc flash | Lodged
HUI_FDR_1282 | 2026-07-21 07:30 | 2026-07-21 18:30 | Daily | RS - Removal from Service | HUI-CB-1282 | Lodged
PTS_1800_OTA_WIR | 2026-07-21 07:30 | 2026-07-21 18:30 | Daily | RS - Removal from Service | OTA-C-PTSG-1800A, WIR-C-PTSG-1800A | Lodged
CST_MNI_1 | 2026-07-22 07:30 | 2026-07-24 18:30 | Continuous | RS - Removal from Service | MNI-DEV-A0169-10, MNI-DEV-A0170-10 | Lodged
MNG_110BZ_A | 2026-07-22 07:30 | 2026-07-23 18:30 | Continuous | RS - Removal from Service | MNG-P-BZ-110 | Lodged
MNG_110BZ_B | 2026-07-22 07:30 | 2026-07-23 18:30 | Continuous | RS - Removal from Service | MNG-P-BZ-110 | Lodged
MNG_110CBF | 2026-07-22 07:30 | 2026-07-23 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
MNG_CB_248 | 2026-07-22 07:30 | 2026-07-23 18:30 | Continuous | RS - Removal from Service | MNG-P-CB-248 | Lodged
MNI_CB_858 | 2026-07-22 07:30 | 2026-07-22 18:30 | Daily | RS - Removal from Service | MNI-CB-858, MNI-P-CB-858 | Lodged
PTS_1517_ALB_HEN | 2026-07-22 07:30 | 2026-07-22 18:30 | Daily | RS - Removal from Service | ALB-C-PTSG-1517C, HEN-C-PTSG-1517C | Lodged
MNI_CB_898 | 2026-07-23 07:30 | 2026-07-23 18:30 | Daily | RS - Removal from Service | MNI-CB-898, MNI-P-CB-898 | Lodged
PEN_FDR_2512 | 2026-07-23 07:30 | 2026-07-23 18:30 | Daily | RS - Removal from Service | PEN-CB-2512, PEN-P-CB-2512 | Lodged
PTS_1290_HEN_MTO | 2026-07-23 07:30 | 2026-07-23 18:30 | Daily | RS - Removal from Service | MPE-C-PTSG-1290B | Lodged
PEN_FDR_2352 | 2026-07-24 07:30 | 2026-07-24 18:30 | Daily | RS - Removal from Service | PEN-CB-2352, PEN-P-CB-2352 | Lodged
PTS_1605_MPE_MTO | 2026-07-24 07:30 | 2026-07-24 18:30 | Daily | RS - Removal from Service | MPE-C-PTSG-1605A, MTO-C-PTSG-1605A | Lodged
PEN_FDR_2342 | 2026-07-26 07:30 | 2026-07-26 18:30 | Daily | RS - Removal from Service | PEN-CB-2342, PEN-P-CB-2342 | Lodged
BPE_WDV_1 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | Re-insulation x13 | Lodged
HAY_SC_1 | 2026-07-27 07:30 | 2026-08-07 18:30 | Continuous | RS - Removal from Service | HAY-SC1, HAY-SC1-CB-1A, HAY-SC1-EXC, HAY-SC1-NER | Lodged
PEN_FDR_2322 | 2026-07-27 07:30 | 2026-07-27 18:30 | Daily | RS - Removal from Service | PEN-P-CB-2322 | Lodged
IGH_ROB_1 | 2026-07-27 07:30 | 2026-08-01 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
KAW_77_87_107 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | KAW-DS-87, KAW-VT-97 . | Lodged
KAW_CB_78 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | Affected equipment KAW_77_87_107 & KAW_MAT_2 & KAW_T5 & KAW_T6 | Lodged
KAW_MAT_2 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | KAW-MAT-A0003-0004-20 | Lodged
KAW_T14 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | Affected equipment KAW_77_87_107 & KAW_MAT_2 & KAW_T5 & KAW_T6 | Lodged
KAW_T5 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | Affected equipment KAW_77_87_107 | Lodged
KAW_T6 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | Affected equipment KAW_77_87_107 | Lodged
INV_647_776_755 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | INV-DS-774 | Lodged
INV_CB_752 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | Affected equipment INV_727_776_755 & INV_NMA_1 | Lodged
INV_CB_762 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | Affected equipment INV_727_776_755 & INV_NMA_1 | Lodged
INV_CB_772 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | Affected equipment INV_727_776_755 & INV_NMA_1 | Lodged
INV_NMA_1 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | INV-DS-775, INV-DS-776, NMA-CT-CT642 | Lodged
INV_T3 | 2026-07-27 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | INV-DS-775, INV-DS-776, NMA-CT-CT642 Invercargill Protection Replacements - x3 Transformer, Feeder, 33kV Bus Zone Protection & Arc flash | Lodged
KMO_127_137 | 2026-07-27 07:31 | 2026-07-29 18:30 | Continuous | RS - Removal from Service | KMO-CB-138, KMO-P-CB-138 | Lodged
KMO_CB_138 | 2026-07-27 07:31 | 2026-07-29 18:30 | Continuous | RS - Removal from Service | KMO-CB-138, KMO-P-CB-138 | Lodged
MNI_11BS_K | 2026-07-27 07:31 | 2026-07-28 18:31 | Continuous | RS - Removal from Service | Affected equipment MNI_T4 | Lodged
MNI_CB_2732 | 2026-07-27 07:31 | 2026-07-28 18:31 | Continuous | RS - Removal from Service | Affected equipment MNI_T4 | Lodged
MNI_FDR_2712 | 2026-07-27 07:31 | 2026-07-28 18:31 | Continuous | RS - Removal from Service | Affected equipment MNI_T4 | Lodged
MNI_FDR_2722 | 2026-07-27 07:31 | 2026-07-28 18:31 | Continuous | RS - Removal from Service | Affected equipment MNI_T4 | Lodged
MNI_T4 | 2026-07-27 07:31 | 2026-07-28 18:31 | Continuous | RS - Removal from Service | MNI-NCT-4, MNI-P-TF-T4, MNI-RES-ER4, MNI-TF-ET4, MNI-TF-T4 | Lodged
GFD_HAY_1 | 2026-07-28 06:30 | 2026-07-28 18:30 | Daily | RS - Removal from Service | HAY_110BZ Stage 1F; Integrate/commission reference CT to CT_262 | Lodged
GFD_T6 | 2026-07-28 06:30 | 2026-07-28 18:30 | Daily | RS - Removal from Service | Affected equipment of GFD_HAY_1, for HAY_110BZ Stage 1F; Integrate/commission reference CT to CT_262 | Lodged
ISL_220BS_E | 2026-07-28 07:30 | 2026-07-29 18:30 | Continuous | RS - Removal from Service | ISL_DS_6527 | Lodged
ISL_CB_658 | 2026-07-28 07:30 | 2026-07-29 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_220BS_E ISL_DS_6527 | Lodged
ISL_CB_688 | 2026-07-28 07:30 | 2026-07-29 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_220BS_E ISL_DS_6527 | Lodged
KIK_220BS_A | 2026-07-28 07:30 | 2026-07-30 18:30 | Continuous | RS - Removal from Service | KIK-DS-367, KIK-DS-373, KIK-DS-393 | Lodged
KIK_CB_358 | 2026-07-28 07:30 | 2026-07-30 18:30 | Continuous | RS - Removal from Service | Affected equipment KIK_220BS_A | Lodged
KIK_CB_398 | 2026-07-28 07:30 | 2026-07-30 18:30 | Continuous | RS - Removal from Service | Affected equipment KIK_220BS_A | Lodged
PEN_CB_2498 | 2026-07-28 07:30 | 2026-07-28 18:30 | Daily | RS - Removal from Service | PEN-CB-2498, PEN-P-CB-2498 | Lodged
PEN_FDR_2222 | 2026-07-29 07:30 | 2026-07-29 18:30 | Daily | RS - Removal from Service | PEN-CB-2222, PEN-P-CB-2222 | Lodged
MNI_11BS_L | 2026-07-29 07:30 | 2026-07-30 18:30 | Continuous | RS - Removal from Service | Affected equipment MNI_T3 | Lodged
MNI_CB_2822 | 2026-07-29 07:30 | 2026-07-30 18:30 | Continuous | RS - Removal from Service | Affected equipment MNI_T3 | Lodged
MNI_FDR_2832 | 2026-07-29 07:30 | 2026-07-30 18:30 | Continuous | RS - Removal from Service | Affected equipment MNI_T3 | Lodged
MNI_FDR_2842 | 2026-07-29 07:30 | 2026-07-30 18:30 | Continuous | RS - Removal from Service | Affected equipment MNI_T3 | Lodged
MNI_T3 | 2026-07-29 07:30 | 2026-07-30 18:30 | Continuous | RS - Removal from Service | MNI-NCT-3, MNI-P-TF-T3, MNI-RES-ER3, MNI-TF-ET3, MNI-TF-T3 | Lodged
ISL_220BS_D | 2026-07-30 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | ISL-DS-425 | Lodged
ISL_C_21 | 2026-07-30 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | Affected equipment ISL_220BS_D & ISL_CB_658 | Lodged
ISL_CB_608 | 2026-07-30 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | Affected equipment ISL_220BS_D & ISL_CB_658 | Lodged
ISL_CB_658 | 2026-07-30 07:30 | 2026-07-31 18:30 | Continuous | RS - Removal from Service | ISL-CT-CT658, ISL-DS-6517, ISL-DS-6527 | Lodged
PEN_FDR_2422 | 2026-07-30 07:30 | 2026-07-30 18:30 | Daily | RS - Removal from Service | PEN-CB-2422, PEN-P-CB-2422 | Lodged
BPE_WDV_2 | 2026-08-03 06:30 | 2026-08-07 18:30 | Continuous | RS - Removal from Service | Re-insulation x13 | Lodged
HKK_OTI_2 | 2026-08-03 07:30 | 2026-08-07 18:30 | Continuous | RS - Removal from Service | Lines Maintenance | Lodged
HWB_FDR_2612 | 2026-08-03 07:30 | 2026-08-03 18:30 | Daily | RS - Removal from Service | HWB-CBL-2612 | Lodged
INV_ROX_1 | 2026-08-03 07:30 | 2026-08-07 18:30 | Continuous | RS - Removal from Service | INV-P-CB-692/722, INV-ROX-A0001-00, INV-ROX-A0009-00, INV-ROX-A0010-00, INV-ROX-A0027-00, INV-ROX-A0028-00, INV-ROX-A0029-00, INV-ROX-A0031-00, INV-ROX-A0032-00, INV-ROX-A0033-00, INV-ROX-A0035-00, INV-ROX-A0050-00, INV-ROX-A0078-00, INV-ROX-A0087-00, ROX-P-CB-492 | Lodged
ISL_FDR_112 | 2026-08-03 07:30 | 2026-08-05 18:30 | Continuous | RS - Removal from Service | ISL-CB-112, ISL-P-CB-112 | Lodged
KAW_587_674_657 | 2026-08-03 07:30 | 2026-08-05 18:30 | Continuous | RS - Removal from Service | KAW-BS-220-627-647 | Lodged
KAW_CB_608 | 2026-08-03 07:30 | 2026-08-05 18:30 | Continuous | RS - Removal from Service | KAW-CT-608, KAW-P-CB-608 | Lodged
KAW_DIS_617 | 2026-08-03 07:30 | 2026-08-05 18:30 | Continuous | CLO - Close | Closed for the duration of KAW bus outage | Lodged
KAW_OHK_1 | 2026-08-03 07:30 | 2026-08-07 18:30 | Continuous | RS - Removal from Service | KAW-CT-622, KAW-CVT-622, KAW-DS-626, KAW-ES-629, OHK-DS-1316, OHK-DS-86, OHK-ES-89. Tower Painting | Lodged
KAW_T14 | 2026-08-03 07:30 | 2026-08-05 18:30 | Continuous | RS - Removal from Service | Affected equipment KAW_587_674_657 & KAW_CB_608 & KAW_OHK_1 | Lodged
KUM_OTI_1 | 2026-08-03 07:30 | 2026-08-07 18:30 | Continuous | RS - Removal from Service | Lines Maintenance | Lodged
OTA_PAK_3 | 2026-08-03 07:30 | 2026-08-04 18:30 | Continuous | RS - Removal from Service | OTA-PAK-A0003-00 | Lodged
PEN_FDR_2432 | 2026-08-03 07:30 | 2026-08-04 18:30 | Continuous | RS - Removal from Service | PEN-CB-2432, PEN-CBL-2342-SP2, PEN-P-CB-2432 | Lodged
RDF_T1 | 2026-08-03 07:30 | 2026-08-17 18:30 | Continuous | RS - Removal from Service | RDF-TF-T1. Corrosive sulphur work. 12-hour heat soak on last day. | Lodged
NAP_OKI_2 | 2026-08-03 07:30 | 2026-08-07 18:30 | Continuous | RS - Removal from Service | OKI-CT-302 | Lodged
HOR_KBY_ISL_2 | 2026-08-03 07:30 | 2026-08-11 18:30 | Continuous | RS - Removal from Service | HOR-CB-102 66 KV CB Replacement | Lodged
HAY_CB_58 | 2026-08-04 07:00 | 2026-08-10 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 2A; CB_58 protection upgrade. No other work on days 1, 6, 7. No other work on associated equipment on day 7 (commissioning). HAY-CT-58, HAY-P-CB-58 | Lodged
HPI_CB_342 | 2026-08-04 07:30 | 2026-08-07 18:30 | Continuous | RS - Removal from Service | HPI-CB-342 Pole replacement project | Lodged
HWB_FDR_2552 | 2026-08-04 07:30 | 2026-08-05 18:30 | Daily | RS - Removal from Service | HWB-CBL-2552 | Lodged
OTA_T4 | 2026-08-04 07:30 | 2026-08-05 18:30 | Continuous | RS - Removal from Service | OTA-TF-T4 | Lodged
HAY_110BZ | 2026-08-04 08:00 | 2026-08-04 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 2A; CB_58 protection upgrade. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-08-04 08:00 | 2026-08-04 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 2A; CB_58 protection upgrade. | Lodged
HWB_FDR_2532 | 2026-08-05 07:30 | 2026-08-05 18:30 | Daily | RS - Removal from Service | HWB-CBL-2532 | Lodged
HWB_FDR_2602 | 2026-08-06 07:30 | 2026-08-07 18:30 | Daily | RS - Removal from Service | HWB-CBL-2602 | Lodged
OTA_T14 | 2026-08-06 07:30 | 2026-08-07 18:30 | Continuous | RS - Removal from Service | OTA-TF-T14 | Lodged
HWB_FDR_2592 | 2026-08-07 07:30 | 2026-08-07 18:30 | Daily | RS - Removal from Service | HWB-CBL-2592 | Lodged
HAY_110BZ | 2026-08-09 08:00 | 2026-08-09 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 2A; CB_58 protection upgrade. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-08-09 08:00 | 2026-08-09 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 2A; CB_58 protection upgrade. | Lodged
EDG_KAW_3 | 2026-08-10 07:30 | 2026-08-12 18:30 | Continuous | RS - Removal from Service | EDG-CB-502, KAW-CB-582, KAW-DEV-A0307-00 | Lodged
HAY_SC_2 | 2026-08-10 07:30 | 2026-08-14 18:30 | Continuous | RS - Removal from Service | 1 yrs, HAY-SC2, HAY-SC2-CB-2A, HAY-SC2-EXC, HAY-SC2-NER, HAY-SC2-R1, HAY-SC2-ST-2, HAY-SC2-XT-2 | Lodged
HKK_OTI_2 | 2026-08-10 07:30 | 2026-08-14 18:30 | Continuous | RS - Removal from Service | Lines Maintenance AHA-OTI-A0098-00, AHA-OTI-A0099-00 | Lodged
IGH_ROB_1 | 2026-08-10 07:30 | 2026-08-12 18:30 | Continuous | RS - Removal from Service | IGH-P-CB-342, ROB-P-CB-522 IGH-WPT-B0027-00, IGH-WPT-B0034-00, IGH-WPT-B0032-00, IGH-WPT-B0037-00, IGH-WPT-B0030-00, IGH-WPT-B0033-00, IGH-WPT-B0029-00, IGH-WPT-B0031-00, IGH-WPT-B0035-00, IGH-WPT-B0028-00, IGH-WPT-B0036-00 | Lodged
KAW_547_587_627 | 2026-08-10 07:30 | 2026-08-12 18:30 | Continuous | RS - Removal from Service | KAW-DS-584, KAW-DS-587 | Lodged
KAW_CB_608 | 2026-08-10 07:30 | 2026-08-12 18:30 | Continuous | RS - Removal from Service | KAW-CT-608, KAW-P-CB-608 | Lodged
KAW_DIS_617 | 2026-08-10 07:30 | 2026-08-12 18:30 | Continuous | CLO - Close | Closed for the duration of KAW_547_587_627 | Lodged
KUM_OTI_1 | 2026-08-10 07:30 | 2026-08-14 18:30 | Continuous | RS - Removal from Service | Lines Maintenance AHA-OTI-A0098-00, AHA-OTI-A0099-00 | Lodged
MAN_NMA_1 | 2026-08-10 07:30 | 2026-08-14 18:30 | Continuous | RS - Removal from Service | MAN-P-CB-272, MAN-TWI-A0010-10, MAN-TWI-A0216-0217-00, MAN-TWI-A0220-0221-00, MAN-TWI-A0258-0259-00, MAN-TWI-A0259-0260-00, MAN-TWI-A0260-0261-00, MAN-TWI-A0294-10, MAN-TWI-A0296-00, MAN-TWI-A0296-10, MAN-TWI-A0299-00, MAN-TWI-A0299-10, MAN-TWI-A0300-00, MAN-TWI-A0300-10, MAN-TWI-A0308-10, MAN-TWI-A0311-0312-10, MAN-TWI-A0313-0314-10, MAN-TWI-A0314-0315-10 | Lodged
NMA_220BS_A3 | 2026-08-10 07:30 | 2026-08-11 18:30 | Continuous | RS - Removal from Service | MAN-P-CB-272, MAN-TWI-A0010-10, MAN-TWI-A0216-0217-00, MAN-TWI-A0220-0221-00, MAN-TWI-A0258-0259-00, MAN-TWI-A0259-0260-00, MAN-TWI-A0260-0261-00, MAN-TWI-A0294-10, MAN-TWI-A0296-00, MAN-TWI-A0296-10, MAN-TWI-A0299-00, MAN-TWI-A0299-10, MAN-TWI-A0300-00, MAN-TWI-A0300-10, MAN-TWI-A0308-10, MAN-TWI-A0311-0312-10, MAN-TWI-A0313-0314-10, MAN-TWI-A0314-0315-10 | Lodged
OKI_RTU_1 | 2026-08-10 07:30 | 2026-08-10 18:30 | Daily | RS - Removal from Service | SMS & GPS replacements [CP_RA3_03C_0_00] | Lodged
OKI_WRK_1 | 2026-08-10 07:30 | 2026-08-14 18:30 | Continuous | RS - Removal from Service | OKI-DS-275, OKI-CT-272, OKI-ES-270, OKI-ES-279, OKI-P-CB-272, WRK-CB-142, WRK-CT-142, WRK-CVT-142, WRK-P-CB-142. OKI-CT-272 replacement [CP_OKI_001_0_00], WRK-CT-142 replacement [CP_WRK_002_0_00] (commissioning on last day of outage - no lines work). | Lodged
WRK_137_167 | 2026-08-10 07:30 | 2026-08-10 18:30 | Daily | RS - Removal from Service | WRK-DS-105 (CB_108) | Lodged
WRK_DIS_117 | 2026-08-10 07:30 | 2026-08-10 18:30 | Daily | CLO - Close | CLO for the duration of WRK_137_167, to maintain a solid 220kV bus. | Lodged
IGH_ROB_1 | 2026-08-10 07:30 | 2026-08-15 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
OKI_220BS_B | 2026-08-10 07:31 | 2026-08-14 18:31 | Continuous | RS - Removal from Service | OKI-DS-235 (BC), OKI-DS-275 (WRK_1), OKI-DS-305 (NAP_2), OKI-DS-337, OKI-DS-355 (T1), OKI-DS-375 (T2), OKI-ES-330, OKI-ES-339, OKI-ES-350, OKI-ES-370 | Lodged
OKI_CB_238 | 2026-08-10 07:31 | 2026-08-14 18:31 | Continuous | RS - Removal from Service | OKI-DS-235, OKI-P-CB-238. Affected equipment of OKI_220BS_B. | Lodged
NMA_CB_708 | 2026-08-10 07:31 | 2026-08-11 18:31 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A3 MAN-P-CB-272, MAN-TWI-A0010-10, MAN-TWI-A0216-0217-00, MAN-TWI-A0220-0221-00, MAN-TWI-A0258-0259-00, MAN-TWI-A0259-0260-00, MAN-TWI-A0260-0261-00, MAN-TWI-A0294-10, MAN-TWI-A0296-00, MAN-TWI-A0296-10, MAN-TWI-A0299-00, MAN-TWI-A0299-10, MAN-TWI-A0300-00, MAN-TWI-A0300-10, MAN-TWI-A0308-10, MAN-TWI-A0311-0312-10, MAN-TWI-A0313-0314-10, MAN-TWI-A0314-0315-10 | Lodged
NMA_CB_718 | 2026-08-10 07:31 | 2026-08-11 18:31 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A3 MAN-P-CB-272, MAN-TWI-A0010-10, MAN-TWI-A0216-0217-00, MAN-TWI-A0220-0221-00, MAN-TWI-A0258-0259-00, MAN-TWI-A0259-0260-00, MAN-TWI-A0260-0261-00, MAN-TWI-A0294-10, MAN-TWI-A0296-00, MAN-TWI-A0296-10, MAN-TWI-A0299-00, MAN-TWI-A0299-10, MAN-TWI-A0300-00, MAN-TWI-A0300-10, MAN-TWI-A0308-10, MAN-TWI-A0311-0312-10, MAN-TWI-A0313-0314-10, MAN-TWI-A0314-0315-10 | Lodged
BEN_220BS_A | 2026-08-10 08:00 | 2026-08-20 18:00 | Continuous | RS - Removal from Service | Affected Equipment of BEN_CB_408 BEN 220BZ - CB408 Migration | Lodged
BEN_220BZ | 2026-08-10 08:00 | 2026-08-10 18:00 | Daily | RS - Removal from Service | BEN 220BZ - CB408 Migration | Lodged
BEN_220CBF | 2026-08-10 08:00 | 2026-08-10 18:00 | Daily | RS - Removal from Service | BEN 220BZ - CB408 Migration | Lodged
BEN_CB_408 | 2026-08-10 08:00 | 2026-08-20 18:00 | Continuous | RS - Removal from Service | BEN 220BZ - CB408 Migration | Lodged
TAK_T5 | 2026-08-10 08:00 | 2026-08-15 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
HOR_T8 | 2026-08-11 07:30 | 2026-08-12 18:30 | Continuous | RS - Removal from Service | HOR-CT-NCT8 | Lodged
WIL_33BZ_K | 2026-08-11 07:30 | 2026-08-12 18:30 | Daily | RS - Removal from Service | WIL-P-BZ-33 | Lodged
WIL_33BZ_L | 2026-08-11 07:30 | 2026-08-12 18:30 | Daily | RS - Removal from Service | WIL-P-BZ-33 | Lodged
WIL_33CBF | 2026-08-11 07:30 | 2026-08-12 18:30 | Daily | RS - Removal from Service | Affected equipment of WIL_33BZ_K/L, for WIL-P-BZ-33 | Lodged
HLY_220BZ_A | 2026-08-12 07:30 | 2026-08-14 18:31 | Continuous | RS - Removal from Service | HLY-P-BZ-220-A | Lodged
HLY_220CBF | 2026-08-12 07:30 | 2026-08-14 18:31 | Continuous | RS - Removal from Service | Affected equipment HLY-P-BZ-220-A | Lodged
NMA_CB_738 | 2026-08-12 07:30 | 2026-08-14 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_687_835 MAN-P-CB-272, MAN-TWI-A0010-10, MAN-TWI-A0216-0217-00, MAN-TWI-A0220-0221-00, MAN-TWI-A0258-0259-00, MAN-TWI-A0259-0260-00, MAN-TWI-A0260-0261-00, MAN-TWI-A0294-10, MAN-TWI-A0296-00, MAN-TWI-A0296-10, MAN-TWI-A0299-00, MAN-TWI-A0299-10, MAN-TWI-A0300-00, MAN-TWI-A0300-10, MAN-TWI-A0308-10, MAN-TWI-A0311-0312-10, MAN-TWI-A0313-0314-10, MAN-TWI-A0314-0315-10 | Lodged
NMA_687_835 | 2026-08-12 07:31 | 2026-08-14 18:31 | Continuous | RS - Removal from Service | MAN-P-CB-272, MAN-TWI-A0010-10, MAN-TWI-A0216-0217-00, MAN-TWI-A0220-0221-00, MAN-TWI-A0258-0259-00, MAN-TWI-A0259-0260-00, MAN-TWI-A0260-0261-00, MAN-TWI-A0294-10, MAN-TWI-A0296-00, MAN-TWI-A0296-10, MAN-TWI-A0299-00, MAN-TWI-A0299-10, MAN-TWI-A0300-00, MAN-TWI-A0300-10, MAN-TWI-A0308-10, MAN-TWI-A0311-0312-10, MAN-TWI-A0313-0314-10, MAN-TWI-A0314-0315-10 | Lodged
NAP_220BZ | 2026-08-13 07:30 | 2026-08-13 18:30 | Daily | RS - Removal from Service | NAP-P-BZ-220 | Lodged
NAP_220CBF | 2026-08-13 07:30 | 2026-08-13 18:30 | Daily | RS - Removal from Service | Affected equipment of NAP_220BZ, for NAP-P-BZ-220. | Lodged
WIL_110BS_A_PROT1 | 2026-08-13 07:31 | 2026-08-14 18:31 | Daily | RS - Removal from Service | WIL-P-SPS-SPLIT | Lodged
WIL_110BS_A_PROT2 | 2026-08-13 07:31 | 2026-08-14 18:31 | Daily | RS - Removal from Service | WIL-P-SPS-SPLIT | Lodged
WIL_110BS_C_PROT1 | 2026-08-13 07:31 | 2026-08-14 18:31 | Daily | RS - Removal from Service | WIL-P-SPS-SPLIT | Lodged
WIL_110BS_C_PROT2 | 2026-08-13 07:31 | 2026-08-14 18:31 | Daily | RS - Removal from Service | WIL-P-SPS-SPLIT | Lodged
APS_OTI_1 | 2026-08-17 07:30 | 2026-08-19 18:30 | Continuous | RS - Removal from Service | Lines Maintenance | Lodged
COL_OTI_2 | 2026-08-17 07:30 | 2026-08-19 18:30 | Continuous | RS - Removal from Service | Lines Maintenance | Lodged
HAM_347_364_407 | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | RS - Removal from Service | Headgear replacement HAM-DS-367 | Lodged
HAM_CB_1522 | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | CLO - Close | Place T7 into service for duration of T8 | Lodged
HAM_T8 | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | RS - Removal from Service | CT replacement. HAM-CT-1532 | Lodged
MAN_NMA_3 | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | RS - Removal from Service | INV-MAN-A0289-20, INV-MAN-A0292-20, INV-MAN-A0297-20, INV-MAN-A0298-20, MAN-P-CB-222 | Lodged
NAP_OKI_2 | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | RS - Removal from Service | NAP-CT-CT182, OKI-DS-305, OKI-DS-306. OKI-CT-302 replacement project [CP_OKI_001_0_00] (commissioning on last day of outage - no lines work). | Lodged
NMA_220BS_A1 | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | RS - Removal from Service | INV-MAN-A0289-20, INV-MAN-A0292-20, INV-MAN-A0297-20, INV-MAN-A0298-20, MAN-P-CB-222 | Lodged
NMA_CB_688 | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A1 INV-MAN-A0289-20, INV-MAN-A0292-20, INV-MAN-A0297-20, INV-MAN-A0298-20, MAN-P-CB-222 | Lodged
NMA_CB_708 | 2026-08-17 07:30 | 2026-08-21 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A1 INV-MAN-A0289-20, INV-MAN-A0292-20, INV-MAN-A0297-20, INV-MAN-A0298-20, MAN-P-CB-222 | Lodged
TAK_T8 | 2026-08-17 08:00 | 2026-08-22 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
HAY_CB_258 | 2026-08-18 07:00 | 2026-08-24 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 2B; CB_258 protection upgrade. No other work on days 1, 6, 7. No other work on associated equipment on day 7 (commissioning). | Lodged
HAY_110BZ | 2026-08-18 08:00 | 2026-08-18 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 2B; CB_258 protection upgrade. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-08-18 08:00 | 2026-08-18 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 2B; CB_258 protection upgrade. | Lodged
DOB_RFN_IGH_1 | 2026-08-19 07:30 | 2026-08-21 18:30 | Continuous | RS - Removal from Service | DOB-BWR-A0042-10, DOB-BWR-A0198-10, DOB-CVT-562 | Lodged
DOB_T12 | 2026-08-19 07:30 | 2026-08-21 18:30 | Continuous | RS - Removal from Service | DOB-TF-ET12, DOB-TF-T12 DOB T12 and CB562 Protection Replacement | Lodged
DRY_GLN_1 | 2026-08-19 07:30 | 2026-08-20 18:30 | Daily | RS - Removal from Service | GLN-BS-220-DRY-GLN-1, GLN-CB-632, GLN-CVT-632, GLN-DS-636, GLN-ES-639 | Lodged
BEN_220BZ | 2026-08-19 08:00 | 2026-08-20 18:00 | Daily | RS - Removal from Service | BEN 220BZ - CB408 Migration | Lodged
BEN_220CBF | 2026-08-19 08:00 | 2026-08-20 18:00 | Daily | RS - Removal from Service | BEN 220BZ - CB408 Migration | Lodged
HAY_110BZ | 2026-08-23 08:00 | 2026-08-23 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 2B; CB_258 protection upgrade. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-08-23 08:00 | 2026-08-23 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 2B; CB_258 protection upgrade. | Lodged
ARG_KIK_1 | 2026-08-24 07:30 | 2026-08-28 18:30 | Continuous | RS - Removal from Service | Lines Maintenance | Lodged
CUL_FDR_1222 | 2026-08-24 07:30 | 2026-08-26 18:30 | Continuous | RS - Removal from Service | CUL-CB-1222, CUL-P-CB-1222 | Lodged
DRY_TAK_OTA_1 | 2026-08-24 07:30 | 2026-08-27 18:30 | Continuous | RS - Removal from Service | HLY-OTA-A0150-10, HLY-OTA-A0164-10, HLY-OTA-A0167-10, HLY-OTA-A0172-10, HLY-OTA-A0178-10, HLY-OTA-A0190-10, HLY-OTA-A0196-10, HLY-OTA-A0203-10, HLY-OTA-A0204-10, HLY-OTA-A0207-10, HLY-OTA-A0208-10, HLY-OTA-A0210-10, HLY-OTA-A0213-10 | Lodged
INV_NMA_1 | 2026-08-24 07:30 | 2026-08-26 18:30 | Continuous | RS - Removal from Service | Inv_ds_776 Headgear | Lodged
KIN_T7 | 2026-08-24 07:30 | 2026-08-25 18:30 | Continuous | RS - Removal from Service | KIN-M-CT2742, KIN-M-VT2742 | Lodged
KPU_357_VT367 | 2026-08-24 07:30 | 2026-08-26 18:30 | Continuous | RS - Removal from Service | KPU-VT-VT367 | Lodged
KPU_T4 | 2026-08-24 07:30 | 2026-08-26 18:30 | Continuous | RS - Removal from Service | KPU-P-AVR-T4 | Lodged
KPU_WKO_1 | 2026-08-24 07:30 | 2026-08-26 18:30 | Continuous | RS - Removal from Service | Affected equipment KPU_357_VT367 & KPU_T4 | Lodged
RDF_T2 | 2026-08-24 07:30 | 2026-09-09 18:30 | Continuous | RS - Removal from Service | RDF-CBL-ET2-NER2, RDF-CBL-T2-2462, RDF-CBL-T2-ET2, RDF-NCT-2, RDF-RES-NER2, RDF-TF-ET2, RDF-TF-T2. 12-hour heat soak on last day. | Lodged
TAK_T5 | 2026-08-24 07:30 | 2026-08-27 18:30 | Continuous | RS - Removal from Service | Mid-life refurbishment project. TAK-BS-220-302-T5, TAK-CB-2162A, TAK-CB-2162B, TAK-TF-T5 | Lodged
TNG_T11 | 2026-08-24 07:30 | 2026-08-28 18:30 | Continuous | RS - Removal from Service | TNG-CT-252 replacement [CP_TNG_001_0_00]. | Lodged
TNG_220BS_A | 2026-08-24 07:31 | 2026-08-25 18:31 | Continuous | RS - Removal from Service | TNG-DS-253 (T11) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-220 | Lodged
TNG_CB_288 | 2026-08-24 07:31 | 2026-08-25 18:31 | Continuous | RS - Removal from Service | Affected equipment of TNG_220BS_A, for TNG-DS-253 (T11), TNG-ES-220 | Lodged
BRB_CB_138 | 2026-08-26 07:30 | 2026-08-27 18:30 | Continuous | RS - Removal from Service | BRB-CB-138 | Lodged
RDF_TUI_1 | 2026-08-26 07:30 | 2026-08-27 18:30 | Continuous | RS - Removal from Service | RSA4 conductor repair [MP_RA4_03N_0_00]. | Lodged
TNG_FDR_2802 | 2026-08-26 07:30 | 2026-08-26 18:30 | Daily | RS - Removal from Service | TNG-CB-2802, TNG-P-CB-2802 (TENTATIVE OW - asset may be decommissioned). | Lodged
TUI_110BZ | 2026-08-26 07:31 | 2026-08-26 18:31 | Daily | RS - Removal from Service | TUI-P-BZ-110 | Lodged
TUI_110CBF | 2026-08-26 07:31 | 2026-08-26 18:31 | Daily | RS - Removal from Service | Affected equipment of TUI_110BZ, for TUI-P-BZ-110 | Lodged
TNG_220BS_B | 2026-08-26 07:31 | 2026-08-26 18:31 | Daily | RS - Removal from Service | TNG-DS-255 (T11) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-230 | Lodged
TNG_CB_288 | 2026-08-26 07:31 | 2026-08-26 18:31 | Daily | RS - Removal from Service | Affected equipment of TNG_220BS_B, for TNG-DS-255 (T11), TNG-ES-230 | Lodged
KIK_T1 | 2026-08-28 07:30 | 2026-08-28 18:30 | Daily | RS - Removal from Service | KIK-TF-T1B, KIK-TF-T1R, KIK-TF-T1Y | Lodged
ARG_KIK_1 | 2026-08-31 07:30 | 2026-09-04 18:30 | Continuous | RS - Removal from Service | Lines Maintenance | Lodged
BEN_220BZ | 2026-08-31 07:30 | 2026-08-31 18:30 | Daily | RS - Removal from Service | BEN-CT-CT418 BEN 220BZ - CB418 Migration | Lodged
BEN_CB_418 | 2026-08-31 07:30 | 2026-09-10 18:30 | Continuous | RS - Removal from Service | BEN-CT-CT418 BEN 220BZ - CB418 Migration | Lodged
FHL_TUI_1 | 2026-08-31 07:30 | 2026-09-01 18:30 | Continuous | RS - Removal from Service | FHL-CT-62, FHL-DS-66, FHL-ES-69, TUI-DS-146, TUI-VT-142. Last day for testing. NO LINES WORK. | Lodged
ISL_FDR_322 | 2026-08-31 07:30 | 2026-08-31 18:30 | Daily | RS - Removal from Service | ISL-P-CB-322 | Lodged
ISL_FDR_92 | 2026-08-31 07:30 | 2026-08-31 18:30 | Daily | RS - Removal from Service | ISL-CB-92, ISL-DS-96, ISL-P-CB-92 | Lodged
KPU_367_VT10 | 2026-08-31 07:30 | 2026-09-04 18:30 | Continuous | RS - Removal from Service | Affected equipment KPU_T3 | Lodged
KPU_T3 | 2026-08-31 07:30 | 2026-09-04 18:30 | Continuous | RS - Removal from Service | SF6 CB pole replacement. | Lodged
KPU_WKO_2 | 2026-08-31 07:30 | 2026-09-04 18:30 | Continuous | RS - Removal from Service | Affected equipment KPU_T3 | Lodged
ISL_TKB_1 | 2026-08-31 07:30 | 2026-09-04 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
MNG_287_VT2 | 2026-08-31 07:31 | 2026-09-06 18:30 | Continuous | RS - Removal from Service | CT replacement project MNG-M-VT2, MNG-VT-2 | Lodged
MNG_OTA_2 | 2026-08-31 07:31 | 2026-09-06 18:30 | Continuous | RS - Removal from Service | Affected equipment MNG_287_VT2 & MNG_ROS_2 | Lodged
MNG_ROS_2 | 2026-08-31 07:31 | 2026-09-06 18:30 | Continuous | RS - Removal from Service | MNG-ROS-A0034-20, ROS-CT-122, ROS-DS-126, ROS-ES-129, ROS-P-CB-122 | Lodged
BEN_220CBF | 2026-08-31 08:00 | 2026-08-31 18:00 | Daily | RS - Removal from Service | BEN-CT-CT418 BEN 220BZ - CB418 Migration | Lodged
MPE_CB_252 | 2026-08-31 08:00 | 2026-09-05 18:30 | Daily | OPE - Open Ended | system split for the duration of MDN_MPE_1 | Lodged
MPE_CB_292 | 2026-08-31 08:00 | 2026-09-05 18:30 | Daily | OPE - Open Ended | system split for the duration of MDN_MPE_1 | Lodged
MPE_CB_252 | 2026-09-01 06:00 | 2026-09-03 22:00 | Daily | OPE - Open Ended | system split for the duration of MDN_MPE_1 | Lodged
MPE_CB_292 | 2026-09-01 06:00 | 2026-09-03 22:00 | Daily | OPE - Open Ended | system split for the duration of MDN_MPE_1 | Lodged
HAY_SC_7_T7 | 2026-09-01 07:00 | 2026-09-06 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3N; Bay 100 - Transformer T7. No other work on days 1, 5, 6. No other work on associated equipment/lines on day 6 (commissioning). | Lodged
OTA_220BS_L | 2026-09-01 07:30 | 2026-09-04 18:30 | Continuous | RS - Removal from Service | Wall bushings maintenance | Lodged
OTA_220BS_N | 2026-09-01 07:30 | 2026-09-04 18:30 | Continuous | RS - Removal from Service | OTA-CT-CT1448A, OTA-DS-1415, OTA-DS-1425, OTA-DS-1447, OTA-ES-1420, OTA-ES-1449, OTA-P-CB-1448 | Lodged
OTA_C_30 | 2026-09-01 07:30 | 2026-09-04 18:30 | Continuous | RS - Removal from Service | OTA-CB-1422 | Lodged
OTA_C_31 | 2026-09-01 07:30 | 2026-09-04 18:30 | Continuous | RS - Removal from Service | OTA-CB-1412 | Lodged
OTA_CB_1448 | 2026-09-01 07:30 | 2026-09-04 18:30 | Continuous | RS - Removal from Service | Affected equipment OTA_220BS_N & OTA_CB_1412 & OTA_CB_1422 | Lodged
OTI_CB_1062 | 2026-09-01 07:30 | 2026-09-02 18:30 | Continuous | RS - Removal from Service | Affected equipment OTI_T6 | Lodged
OTI_LST_1 | 2026-09-01 07:30 | 2026-09-02 18:30 | Continuous | RS - Removal from Service | Affected equipment OTI_T6 | Lodged
OTI_T6 | 2026-09-01 07:30 | 2026-09-02 18:30 | Continuous | RS - Removal from Service | OTI-M-CT1062, OTI-M-VT1062, OTI-TF-T6 | Lodged
ASB_ISL_1 | 2026-09-01 07:30 | 2026-09-01 18:30 | Daily | RS - Removal from Service | insulator and earth wire | Lodged
HAY_110BZ | 2026-09-01 08:00 | 2026-09-01 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3N; Bay 100 - Transformer T7. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-09-01 08:00 | 2026-09-01 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3N; Bay 100 - Transformer T7. | Lodged
KAI_T2 | 2026-09-03 07:30 | 2026-09-03 18:30 | Daily | RS - Removal from Service | KAI-M-CT37, KAI-M-VT37, KAI T1 and T2 Transformer Protection, ODJB and 125V DC system Replacement | Lodged
MPE_CB_252 | 2026-09-04 06:00 | 2026-09-04 18:30 | Daily | OPE - Open Ended | system split for the duration of MDN_MPE_1 | Lodged
MPE_CB_292 | 2026-09-04 06:00 | 2026-09-04 18:30 | Daily | OPE - Open Ended | system split for the duration of MDN_MPE_1 | Lodged
PTS_1604_MPE_MTO | 2026-09-04 07:30 | 2026-09-04 18:30 | Daily | RS - Removal from Service | MPE-C-PTSG-1604A, MTO-C-PTSG-1604A | Lodged
HAY_110BZ | 2026-09-05 08:00 | 2026-09-05 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3N; Bay 100 - Transformer T7. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-09-05 08:00 | 2026-09-05 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3N; Bay 100 - Transformer T7. | Lodged
HAY_110BZ | 2026-09-06 08:00 | 2026-09-06 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3N; Bay 100 - Transformer T7. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-09-06 08:00 | 2026-09-06 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3N; Bay 100 - Transformer T7. | Lodged
KIK_STK_3 | 2026-09-07 06:30 | 2026-09-09 18:30 | Continuous | RS - Removal from Service | Under clearance works | Lodged
ASY_WPR_1 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WPR_127_134_174 WPR Project-Mt Cass Connections, upgrade DIS | Lodged
KMO_2157_2184 | 2026-09-07 07:30 | 2026-09-09 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
KMO_CB_2158 | 2026-09-07 07:30 | 2026-09-09 18:30 | Continuous | RS - Removal from Service | KMO-CB-2158, KMO-P-CB-2158 | Lodged
KMO_FDR_2172 | 2026-09-07 07:30 | 2026-09-09 18:30 | Continuous | RS - Removal from Service | KMO-CB-2172, KMO-P-CB-2172 | Lodged
KMO_FDR_2182 | 2026-09-07 07:30 | 2026-09-09 18:30 | Continuous | RS - Removal from Service | KMO-CB-2182, KMO-P-CB-2182 | Lodged
OTA_CB_478 | 2026-09-07 07:30 | 2026-09-07 18:30 | Daily | RS - Removal from Service | OTA-CT-478 | Lodged
SBK_WPR_1 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | Lodged
WPR_104_137 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | Lodged
WPR_127_134_174 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | WPR Project-Mt Cass Connections, upgrade DIS | Lodged
WPR_33BS | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | Lodged
WPR_FDR_1132 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | Lodged
WPR_FDR_1172 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | Lodged
WPR_FDR_1192 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | Lodged
WPR_FDR_132 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WPR_127_134_174 WPR Project-Mt Cass Connections, upgrade DIS | Lodged
WPR_FDR_82 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | Lodged
WPR_LST_30 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | Lodged
WPR_T12 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WPR_127_134_174 WPR Project-Mt Cass Connections, upgrade DIS | Lodged
WPR_T13 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | Lodged
WPR_T3 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WPR_104_137 WPR Project-Mt Cass Connections, upgrade DIS, entire 66kV bus outage req'd | Lodged
HKK_OTI_2 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | Lines Maintenance | Lodged
KUM_OTI_1 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | Lines Maintenance | Lodged
TNG_T12 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | TNG-CT-272 replacement [CP_TNG_001_0_00]. | Lodged
ISL_NWD_1 | 2026-09-07 07:30 | 2026-09-12 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
GOR_T12 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | GOR-CB-712, GOR-CBL-T12-ET12, GOR-CT-CT592, GOR-CT-CT712, GOR-CT-NCT12, GOR-DCB-592, GOR-DS-716, GOR-NCTD-T12, GOR-P-CB-712, GOR-P-TF-T12, GOR-TF-ET12, GOR-TF-T12 | Lodged
NMA_GOR_TMH_2 | 2026-09-07 07:30 | 2026-09-11 18:30 | Continuous | RS - Removal from Service | GOR-CVT-VT712, GOR-ES-719, NMA-DS-813, NMA-TMH-A0153-20, NMA-TMH-A0177-20, NMA-TMH-A0178-20, NMA-TMH-A0186-20, NMA-TMH-A0189-20, NMA-TMH-A0192-20, NMA-TMH-A0225-20, NMA-TMH-A0227-20, NMA-TMH-A0230-20, NMA-TMH-A0236-20, NMA-TMH-A0239-0240-20, NMA-TMH-A0240-0241-20 | Lodged
TNG_220BS_A | 2026-09-07 07:31 | 2026-09-08 18:31 | Continuous | RS - Removal from Service | TNG-DS-273 (T12) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-220 | Lodged
TNG_CB_288 | 2026-09-07 07:31 | 2026-09-08 18:31 | Continuous | RS - Removal from Service | Affected equipment of TNG_220BS_A, for TNG-DS-273 (T12), TNG-ES-220 | Lodged
ALB_HEN_3 | 2026-09-07 08:00 | 2026-09-12 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
MPE_CB_252 | 2026-09-07 08:00 | 2026-09-12 18:30 | Daily | OPE - Open Ended | System split for the duration MDN_MPE_2 | Lodged
MPE_CB_292 | 2026-09-07 08:00 | 2026-09-12 18:30 | Daily | OPE - Open Ended | System split for the duration MDN_MPE_2 | Lodged
MPE_CB_252 | 2026-09-08 06:00 | 2026-09-10 22:00 | Daily | OPE - Open Ended | System split for the duration MDN_MPE_2 | Lodged
MPE_CB_292 | 2026-09-08 06:00 | 2026-09-10 22:00 | Daily | OPE - Open Ended | System split for the duration MDN_MPE_2 | Lodged
CML_FDR_1102 | 2026-09-08 07:30 | 2026-09-10 18:30 | Continuous | RS - Removal from Service | CML-DS-1106, CML-ES-1109, CML-P-CB-1102 | Lodged
OTA_CB_488 | 2026-09-08 07:30 | 2026-09-08 18:30 | Daily | RS - Removal from Service | OTA-CT-488 | Lodged
BEN_220BS_B | 2026-09-08 08:00 | 2026-09-08 18:00 | Daily | RS - Removal from Service | BEN-CT-CT418 BEN 220BZ - CB418 Migration | Lodged
SVL_FDR_2822 | 2026-09-09 07:30 | 2026-09-09 18:30 | Daily | RS - Removal from Service | SVL-CBL-2822 | Lodged
TNG_FDR_2772 | 2026-09-09 07:30 | 2026-09-09 18:30 | Daily | RS - Removal from Service | TNG-CB-2772, TNG-P-CB-2772 (TENTATIVE OW - asset may be decommissioned). | Lodged
TNG_220BS_B | 2026-09-09 07:31 | 2026-09-10 18:31 | Continuous | RS - Removal from Service | TNG-DS-275 (T12) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-230 | Lodged
TNG_CB_288 | 2026-09-09 07:31 | 2026-09-10 18:31 | Continuous | RS - Removal from Service | Affected equipment of TNG_220BS_B, for TNG-DS-275 (T12), TNG-ES-230 | Lodged
BEN_220BZ | 2026-09-09 08:00 | 2026-09-10 18:00 | Daily | RS - Removal from Service | BEN-CT-CT418 BEN 220BZ - CB418 Migration | Lodged
BEN_220CBF | 2026-09-09 08:00 | 2026-09-10 18:00 | Daily | RS - Removal from Service | BEN-CT-CT418 BEN 220BZ - CB418 Migration | Lodged
HEP_FDR_2222 | 2026-09-10 07:30 | 2026-09-10 18:30 | Daily | RS - Removal from Service | HEP-CB-2222, HEP-P-CB-2222 | Lodged
KMO_FDR_2132 | 2026-09-10 07:30 | 2026-09-10 18:30 | Daily | RS - Removal from Service | KMO-CB-2132, KMO-P-CB-2132 | Lodged
TNG_FDR_2792 | 2026-09-10 07:30 | 2026-09-10 18:30 | Daily | RS - Removal from Service | TNG-CB-2792, TNG-P-CB-2792 (TENTATIVE OW - asset may be decommissioned). | Lodged
MPE_CB_252 | 2026-09-11 06:00 | 2026-09-11 18:30 | Daily | OPE - Open Ended | System split for the duration MDN_MPE_2 | Lodged
MPE_CB_292 | 2026-09-11 06:00 | 2026-09-11 18:30 | Daily | OPE - Open Ended | System split for the duration MDN_MPE_2 | Lodged
KMO_FDR_2122 | 2026-09-11 07:30 | 2026-09-11 18:30 | Daily | RS - Removal from Service | KMO-CB-2122, KMO-P-CB-2122 | Lodged
ISL_SBK_1 | 2026-09-14 06:30 | 2026-10-02 18:30 | Continuous | RS - Removal from Service | ISL-SBK A line reconductoring | Lodged
ISL_SBK_2 | 2026-09-14 06:30 | 2026-10-02 18:30 | Continuous | RS - Removal from Service | ISL-SBK A line reconductoring | Lodged
DOB_RFN_IGH_1 | 2026-09-14 07:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | Protection project RFN CB332, IGH CB412 Line Protection Replacement CP_RFN_06_00_00, CP_IGH_40_00_00 | Lodged
DOB_T12 | 2026-09-14 07:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | Affected Equipment of DOB_RFN_IGH_1 Protection project RFN CB332, IGH CB412 Line Protection Replacement CP_RFN_06_00_00, CP_IGH_40_00_00 | Lodged
ISL_SBK_1 | 2026-09-14 07:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | reconductoring | Lodged
ISL_SBK_2 | 2026-09-14 07:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | ISL-CB-362 | Lodged
KPU_367_VT10 | 2026-09-14 07:30 | 2026-09-17 18:30 | Continuous | RS - Removal from Service | Affected equipment KPU_T3 | Lodged
KPU_T3 | 2026-09-14 07:30 | 2026-09-17 18:30 | Continuous | RS - Removal from Service | KPU-CB-342, KPU-CT-342, KPU-TF-T3, KPU-VT-VT1062 | Lodged
KPU_WKO_2 | 2026-09-14 07:30 | 2026-09-17 18:30 | Continuous | RS - Removal from Service | Affected Equipment of KPU_367_VT10 | Lodged
OHW_OTA_1 | 2026-09-14 07:30 | 2026-09-18 18:30 | Continuous | RS - Removal from Service | Spacer replacement project. OTA-WKM-C0310-0311-10 | Lodged
OTA_C_29 | 2026-09-14 07:30 | 2026-09-18 18:30 | Continuous | RS - Removal from Service | OTA-CB-5812, OTA-DS-5814 | Lodged
TNG_220BS_A | 2026-09-14 07:30 | 2026-09-15 18:30 | Continuous | RS - Removal from Service | TNG-DS-223 (T2) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-220 | Lodged
TNG_CB_288 | 2026-09-14 07:30 | 2026-09-15 18:30 | Continuous | RS - Removal from Service | Affected equipment of TNG_220BS_A, for TNG-DS-223 (T2), TNG-ES-220 | Lodged
TNG_T2 | 2026-09-14 07:30 | 2026-09-18 18:30 | Continuous | RS - Removal from Service | TNG-CT-1562, TNG-DS-1566, TNG-ES-1569, TNG-SA-2, TNG-TF-T2, TNG-VT-1562. TNG-CT-222 replacement [CP_TNG_001_0_00]. TNG-TF-T2 [CP_TNG_BG_00_00]. Reinhausen work. | Lodged
RDF_WTU_1 | 2026-09-14 07:31 | 2026-09-18 18:31 | Continuous | RS - Removal from Service | RDF-CB-652, RDF-CT-652, RDF-CVT-652, RDF-DS-653, RDF-DS-655, RDF-DS-656, RDF-ES-659, RDF-P-CB-652, WTU-CVT-4, WTU-DS-846, WTU-ES-849. RDF-CB-652 line protection & ODJB [CP_RDF_00E_0_00]. | Lodged
WTU_T4 | 2026-09-14 07:31 | 2026-09-18 18:31 | Continuous | RS - Removal from Service | WTU-P-TF-T4 [CP_WTU_009_0_00]. Affected equipment of RDF_WTU_1. | Lodged
TAK_T5 | 2026-09-14 08:00 | 2026-09-18 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
HEN_HPI_1 | 2026-09-14 08:00 | 2026-09-19 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
BRB_HPI_1 | 2026-09-14 08:00 | 2026-09-19 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
MPE_CB_252 | 2026-09-14 08:00 | 2026-09-19 18:30 | Daily | OPE - Open Ended | System split for the duration of HEN_HPI_1 | Lodged
MPE_CB_292 | 2026-09-14 08:00 | 2026-09-19 18:30 | Daily | OPE - Open Ended | System split for the duration of HEN_HPI_1 | Lodged
MPE_CB_252 | 2026-09-15 06:00 | 2026-09-17 22:00 | Daily | OPE - Open Ended | System split for the duration of HEN_HPI_1 | Lodged
MPE_CB_292 | 2026-09-15 06:00 | 2026-09-17 22:00 | Daily | OPE - Open Ended | System split for the duration of HEN_HPI_1 | Lodged
HAY_SC_8_T8 | 2026-09-15 07:00 | 2026-09-20 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3O; Bay 120 - Transformer T8. No other work on days 1, 4, 5. No other work on associated equipment/lines on day 5 (commissioning). | Lodged
KIK_STC_2 | 2026-09-15 07:30 | 2026-09-16 18:30 | Continuous | RS - Removal from Service | KIK-STC-2A, KIK-STC-2B, KIK-TF-LS6-K13-T6 | Lodged
KIK_T2 | 2026-09-15 07:30 | 2026-09-16 18:30 | Continuous | RS - Removal from Service | KIK-P-TF-T2, KIK-TF-T2 | Lodged
WTK_11BS_B | 2026-09-15 07:31 | 2026-09-17 18:31 | Continuous | RS - Removal from Service | Affected equipment WTK_T22 | Lodged
WTK_FDR_28 | 2026-09-15 07:31 | 2026-09-17 18:31 | Continuous | RS - Removal from Service | Affected equipment WTK_T22 | Lodged
WTK_LST_32 | 2026-09-15 07:31 | 2026-09-17 18:31 | Continuous | RS - Removal from Service | Affected equipment WTK_T22 | Lodged
WTK_T22 | 2026-09-15 07:31 | 2026-09-17 18:31 | Continuous | RS - Removal from Service | WTK-CBL-T22-ET32, WTK-CBL-T22-T32, WTK-CT-CT22, WTK-CT-CT462, WTK-ES-290, WTK-P-AVR-T32, WTK-P-TF-T22, WTK-RES-T22-N, WTK-TF-ET32, WTK-TF-T22, WTK-TF-T32, WTK-VT-VT22, WTK-VT-VT32 | Lodged
HAY_110BZ | 2026-09-15 08:00 | 2026-09-15 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3O; Bay 120 - Transformer T8. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-09-15 08:00 | 2026-09-15 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3O; Bay 120 - Transformer T8. | Lodged
CUL_T22 | 2026-09-16 07:30 | 2026-09-18 18:30 | Continuous | RS - Removal from Service | CUL-CBL-LS22, CUL-CBL-NER22, CUL-CBL-T22, CUL-P-TF-T22, CUL-RES-NER22, CUL-TF-LS22, CUL-TF-T22 | Lodged
TNG_220BS_B | 2026-09-16 07:31 | 2026-09-16 18:31 | Daily | RS - Removal from Service | TNG-DS-225 (T2) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-230 | Lodged
TNG_CB_288 | 2026-09-16 07:31 | 2026-09-16 18:31 | Daily | RS - Removal from Service | Affected Equipment of TNG_220BS_B TNG-DS-225 (T2), TNG-ES-230 | Lodged
KPU_LST_1 | 2026-09-17 07:30 | 2026-09-17 18:30 | Daily | RS - Removal from Service | KPU-TF-LS | Lodged
MPE_FDR_242 | 2026-09-17 07:30 | 2026-09-18 18:30 | Continuous | RS - Removal from Service | Revenue metering. MPE-M-CT242 | Lodged
MPE_CB_252 | 2026-09-18 06:00 | 2026-09-18 18:30 | Daily | OPE - Open Ended | System split for the duration of HEN_HPI_1 | Lodged
MPE_CB_292 | 2026-09-18 06:00 | 2026-09-18 18:30 | Daily | OPE - Open Ended | System split for the duration of HEN_HPI_1 | Lodged
HAY_110BZ | 2026-09-19 08:00 | 2026-09-19 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3O; Bay 120 - Transformer T8. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-09-19 08:00 | 2026-09-19 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3O; Bay 120 - Transformer T8. | Lodged
HAY_110BZ | 2026-09-20 08:00 | 2026-09-20 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3O; Bay 120 - Transformer T8. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-09-20 08:00 | 2026-09-20 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3O; Bay 120 - Transformer T8. | Lodged
BRK_SFD_3 | 2026-09-21 07:30 | 2026-09-25 18:30 | Continuous | RS - Removal from Service | SFD-DS-653, SFD-DS-665. Tower steel replacements. Tower painting x49 [CP_760_005_0_00]. | Lodged
HEP_FDR_2232 | 2026-09-21 07:30 | 2026-09-21 18:30 | Daily | RS - Removal from Service | HEP-CB-2232, HEP-P-CB-2232 | Lodged
ISL_TKB_1 | 2026-09-21 07:30 | 2026-09-25 18:30 | Daily | RS - Removal from Service | BEN-ISL-A0393-10, BEN-ISL-A0678-10 | Lodged
OHW_OTA_1 | 2026-09-21 07:30 | 2026-09-24 18:30 | Continuous | RS - Removal from Service | Sub conductor spacers project | Lodged
ROX_644_635_633_636 | 2026-09-21 07:30 | 2026-09-25 18:30 | Continuous | RS - Removal from Service | ROX-DS-636 | Lodged
ROX_TMH_2 | 2026-09-21 07:30 | 2026-09-25 18:30 | Continuous | RS - Removal from Service | ROX-ES-639, ROX-TMH-A0078-0079-20, TMH-CB-552, TMH-CT-CT552, TMH-CVT-VT9, TMH-DS-555, TMH-DS-556, TMH-ES-559 | Lodged
TMH_220BS_A3 | 2026-09-21 07:30 | 2026-09-23 18:30 | Continuous | RS - Removal from Service | TMH-DS-553, TMH-DS-603 | Lodged
TMH_CB_538 | 2026-09-21 07:30 | 2026-09-23 18:30 | Continuous | RS - Removal from Service | Affected equipment TMH_220BS_A3 | Lodged
ISL_NWD_1 | 2026-09-21 07:30 | 2026-09-26 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
RDF_WTU_2 | 2026-09-21 07:30 | 2026-09-25 18:30 | Continuous | RS - Removal from Service | RDF-CB-672 line protection & ODJB [CP_RDF_00E_0_00]. | Lodged
WTU_T3 | 2026-09-21 07:30 | 2026-09-25 18:30 | Continuous | RS - Removal from Service | WTU-CBL-LS3, WTU-CBL-T3-2152, WTU-NER-3, WTU-SA-3A, WTU-TF-LS3, WTU-TF-T3. WTU-P-TF-T3 [CP_WTU_009_0_00]. Affected equipment of RDF_WTU_2. | Lodged
RDF_703_627_673 | 2026-09-21 07:31 | 2026-09-21 18:31 | Daily | RS - Removal from Service | RDF-BS-220-587-627, RDF-BS-220-617-673. | Lodged
RDF_CB_628 | 2026-09-21 07:31 | 2026-09-21 18:31 | Daily | RS - Removal from Service | Affected equipment RDF_587_617_627 | Lodged
BEN_220BZ | 2026-09-21 08:00 | 2026-09-21 18:00 | Daily | RS - Removal from Service | BEN 220BZ - CB428 Migration | Lodged
BEN_220CBF | 2026-09-21 08:00 | 2026-09-21 18:00 | Daily | RS - Removal from Service | BEN 220BZ - CB428 Migration | Lodged
BEN_CB_428 | 2026-09-21 08:00 | 2026-10-02 18:00 | Continuous | RS - Removal from Service | BEN 220BZ - CB428 Migration | Lodged
TAK_T8 | 2026-09-21 08:00 | 2026-09-25 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
MPE_CB_252 | 2026-09-21 08:00 | 2026-09-25 18:30 | Daily | OPE - Open Ended | System split for the duration of MDN_MPE_1 | Lodged
MPE_CB_292 | 2026-09-21 08:00 | 2026-09-25 18:30 | Daily | OPE - Open Ended | System split for the duration of MDN_MPE_1 | Lodged
MPE_CB_252 | 2026-09-22 06:00 | 2026-09-24 22:00 | Daily | OPE - Open Ended | System split for the duration of MDN_MPE_1 | Lodged
MPE_CB_292 | 2026-09-22 06:00 | 2026-09-24 22:00 | Daily | OPE - Open Ended | System split for the duration of MDN_MPE_1 | Lodged
HAY_F_8 | 2026-09-22 07:30 | 2026-09-24 18:30 | Continuous | RS - Removal from Service | S4.10E22-FB8, S4.10E22.B-C1A, S4.10E22.B-C1B, S4.10E22.B-C1C, S4.10E22.B-L1A, S4.10E22.B-L1B, S4.10E22.B-L1C, S4.10E22.B-R1A, S4.10E22.B-R1B, S4.10E22.B-R1C | Lodged
RDF_597_703 | 2026-09-22 07:30 | 2026-09-22 18:30 | Daily | RS - Removal from Service | RDF-BS-220-587-703 | Lodged
SVL_FDR_2782 | 2026-09-22 07:30 | 2026-09-22 18:30 | Daily | RS - Removal from Service | SVL-CBL-2782 | Lodged
OTA_220BS_K | 2026-09-22 07:31 | 2026-09-25 18:30 | Continuous | RS - Removal from Service | Wall bushings maintenance | Lodged
OTA_220BS_M | 2026-09-22 07:31 | 2026-09-25 18:30 | Continuous | RS - Removal from Service | OTA-CT-CT1438A, OTA-DS-1413, OTA-DS-1423, OTA-DS-1437, OTA-ES-1410, OTA-ES-1439, OTA-P-CB-1438 | Lodged
OTA_C_30 | 2026-09-22 07:31 | 2026-09-25 18:30 | Continuous | RS - Removal from Service | OTA-CB-1422 | Lodged
OTA_C_31 | 2026-09-22 07:31 | 2026-09-25 18:30 | Continuous | RS - Removal from Service | OTA-CB-1412 | Lodged
OTA_CB_1438 | 2026-09-22 07:31 | 2026-09-25 18:30 | Continuous | RS - Removal from Service | Affected equipment OTA_220BS_M & OTA_CB_1412 & OTA_CB_1422 | Lodged
HAY_11BS_F | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | RS - Removal from Service | Affected equipment HAY_T22 | Lodged
HAY_11BS_G | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | RS - Removal from Service | Affected equipment HAY_T22 | Lodged
HAY_T22 | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | RS - Removal from Service | HAY-CT-822 | Lodged
HAY_T34 | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | RS - Removal from Service | Affected equipment HAY_T22 | Lodged
HAY_T37 | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | RS - Removal from Service | Affected equipment HAY_T22 | Lodged
OHW_C_2 | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | RS - Removal from Service | OWH-NER-2 | Lodged
RDF_220BS_B | 2026-09-23 07:30 | 2026-09-23 18:30 | Daily | RS - Removal from Service | RDF-BS-220-627-705 | Lodged
PEN_FDR_2232 | 2026-09-24 07:30 | 2026-09-24 18:30 | Daily | RS - Removal from Service | PEN-CB-2232, PEN-P-CB-2232 | Lodged
TMK_T1 | 2026-09-24 07:30 | 2026-09-24 18:30 | Daily | RS - Removal from Service | Affected Equipment of TMK_TIM_1_TMK_T1 ASH-TIM-A0422-00, ASH-TIM-A0423-00, ASH-TIM-A0456-10, ASH-TIM-A0459-00, TMK-CVT-CVT132 | Lodged
TMH_220BS_B | 2026-09-24 07:30 | 2026-09-25 18:30 | Continuous | RS - Removal from Service | TMH-DS-605 | Lodged
TMH_CB_538 | 2026-09-24 07:30 | 2026-09-25 18:30 | Continuous | RS - Removal from Service | Affected equipment TMH_220BS_B | Lodged
MPE_CB_252 | 2026-09-25 06:00 | 2026-09-25 18:30 | Daily | OPE - Open Ended | System split for the duration of MDN_MPE_1 | Lodged
MPE_CB_292 | 2026-09-25 06:00 | 2026-09-25 18:30 | Daily | OPE - Open Ended | System split for the duration of MDN_MPE_1 | Lodged
BRK_CB_572 | 2026-09-28 07:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | BRK-P-CB-572. Affected equipment of BRK_SFD_3. | Lodged
BRK_SFD_3 | 2026-09-28 07:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | SFD-DS-653, SFD-DS-665. Tower steel replacements. Tower painting x49 [CP_760_005_0_00]. | Lodged
PEN_697_847 | 2026-09-28 07:30 | 2026-09-29 18:30 | Continuous | RS - Removal from Service | PEN-CBL-698-848, PEN-ES-690, PEN-ES-850 | Lodged
PEN_CB_698 | 2026-09-28 07:30 | 2026-09-29 18:30 | Continuous | RS - Removal from Service | PEN-P-CB-698 | Lodged
PEN_CB_848 | 2026-09-28 07:30 | 2026-09-29 18:30 | Continuous | RS - Removal from Service | PEN-CB-848 | Lodged
TNG_220BS_A | 2026-09-28 07:30 | 2026-09-28 18:30 | Daily | RS - Removal from Service | TNG-DS-343 (T3) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-220 | Lodged
TNG_CB_288 | 2026-09-28 07:30 | 2026-09-28 18:30 | Daily | RS - Removal from Service | Affected Equipment of TNG_220BS_A TNG-DS-343 (T3), TNG-ES-220 | Lodged
TNG_T3 | 2026-09-28 07:30 | 2026-10-02 18:30 | Continuous | RS - Removal from Service | TNG-CT-1572, TNG-CT-342, TNG-DS-1576, TNG-ES-1579, TNG-TF-T3, TNG-VT-1572. TNG-CT-342 replacement [CP_TNG_001_0_00]. | Lodged
CML_FKN_2 | 2026-09-28 07:31 | 2026-10-02 18:31 | Continuous | RS - Removal from Service | Affected Equipment of CML_T8 Affected equipment CYD_CML_TWZ_2 | Lodged
CML_T8 | 2026-09-28 07:31 | 2026-10-02 18:31 | Continuous | RS - Removal from Service | Affected equipment CYD_CML_TWZ_2 | Lodged
CYD_CML_TWZ_2 | 2026-09-28 07:31 | 2026-10-02 18:31 | Continuous | RS - Removal from Service | ROX-TWZ-A0143-20, ROX-TWZ-A0145-20, ROX-TWZ-A0146-20, ROX-TWZ-A0147-20, ROX-TWZ-A0148-20, ROX-TWZ-A0149-20, ROX-TWZ-A0150-20, ROX-TWZ-A0151-20, ROX-TWZ-A0152-20, ROX-TWZ-A0153-20, ROX-TWZ-A0154-20, ROX-TWZ-A0155-20, ROX-TWZ-A0156-20, ROX-TWZ-A0157-20 | Lodged
FKN_T3 | 2026-09-28 07:31 | 2026-10-02 18:31 | Continuous | RS - Removal from Service | Affected equipment CYD_CML_TWZ_2 | Lodged
MPE_CB_252 | 2026-09-28 08:00 | 2026-10-02 18:30 | Daily | OPE - Open Ended | System split for the duration of MDN_MPE_2 | Lodged
MPE_CB_292 | 2026-09-28 08:00 | 2026-10-02 18:30 | Daily | OPE - Open Ended | System split for the duration of MDN_MPE_2 | Lodged
ALB_WRD_4 | 2026-09-29 07:30 | 2026-10-02 18:30 | Continuous | RS - Removal from Service | ALB-WRD-C-CBL-SHEATH, WRD-VT-VT152. MP_ALB_01F_0_00 | Lodged
DVK_FDR_2622 | 2026-09-29 07:31 | 2026-09-29 18:31 | Daily | RS - Removal from Service | DVK-P-CB-2622 [CP_DVK_70_00_00]. | Lodged
TNG_220BS_B | 2026-09-29 07:31 | 2026-09-29 18:31 | Daily | RS - Removal from Service | TNG-DS-345 (T3) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-230 | Lodged
TNG_CB_288 | 2026-09-29 07:31 | 2026-09-29 18:31 | Daily | RS - Removal from Service | Affected Equipment of TNG_220BS_B TNG-DS-345 (T3), TNG-ES-230 | Lodged
BEN_220BS_C | 2026-09-29 08:00 | 2026-09-29 18:00 | Daily | RS - Removal from Service | BEN 220BZ - CB428 Migration | Lodged
OTA_PEN_5 | 2026-09-30 07:30 | 2026-10-02 18:30 | Continuous | RS - Removal from Service | OTA-CVT-1192, OTA-P-CB-1192/1202 | Lodged
PEN_CB_8612 | 2026-09-30 07:30 | 2026-10-02 18:30 | Continuous | OPE - Open Ended | Open for the duration of OTA_PEN_5 & PEN_T10 to place PEN REA into service | Lodged
PEN_T10 | 2026-09-30 07:30 | 2026-10-02 18:30 | Continuous | OPE - Open Ended | Open whilst PEN REA is in service | Lodged
DVK_FDR_2642 | 2026-09-30 07:31 | 2026-09-30 18:31 | Daily | RS - Removal from Service | DVK-P-CB-2642 [CP_DVK_70_00_00]. | Lodged
BEN_220BS_D | 2026-09-30 08:00 | 2026-09-30 18:00 | Daily | RS - Removal from Service | BEN 220BZ - CB428 Migration | Lodged
CLH_11BS | 2026-10-01 07:30 | 2026-10-01 18:30 | Daily | RS - Removal from Service | Affected Equipment of CLH_T1 CLH-TF-RT1 | Lodged
CLH_FDR_672 | 2026-10-01 07:30 | 2026-10-01 18:30 | Daily | RS - Removal from Service | Affected Equipment of CLH_T1 CLH-TF-RT1 | Lodged
CLH_FDR_692 | 2026-10-01 07:30 | 2026-10-01 18:30 | Daily | RS - Removal from Service | Affected Equipment of CLH_T1 CLH-TF-RT1 | Lodged
CLH_T1 | 2026-10-01 07:30 | 2026-10-01 18:30 | Daily | RS - Removal from Service | CLH-TF-RT1 | Lodged
ISL_C_22 | 2026-10-01 07:30 | 2026-10-02 18:30 | Daily | RS - Removal from Service | Affected equipment ISL_T2 | Lodged
ISL_T2 | 2026-10-01 07:30 | 2026-10-02 18:30 | Daily | RS - Removal from Service | ISL-M-CT2112, ISL-M-VT2112, ISL-NCTD-T2 | Lodged
DVK_FDR_2662 | 2026-10-01 07:31 | 2026-10-01 18:31 | Daily | RS - Removal from Service | DVK-P-CB-2662 [CP_DVK_70_00_00]. | Lodged
BEN_220BZ | 2026-10-01 08:00 | 2026-10-02 18:00 | Daily | RS - Removal from Service | BEN 220BZ - CB428 Migration | Lodged
BEN_220CBF | 2026-10-01 08:00 | 2026-10-02 18:00 | Daily | RS - Removal from Service | BEN 220BZ - CB428 Migration | Lodged
DVK_FDR_2682 | 2026-10-02 07:31 | 2026-10-02 18:31 | Daily | RS - Removal from Service | DVK-P-CB-2682 [CP_DVK_70_00_00]. | Lodged
KIN_CB_2222 | 2026-10-04 01:30 | 2026-10-05 07:29 | Continuous | OPE - Open Ended | Open for the duration of KIN T9 | Lodged
KIN_CB_2232 | 2026-10-04 01:30 | 2026-10-11 02:00 | Continuous | CLO - Close | Closed for the duration of KIN T9 | Lodged
IGH_MCH_1 | 2026-10-04 07:30 | 2026-10-04 18:30 | Daily | RS - Removal from Service | Affected equipment MCH_110BS & KIK_MCH_1 & MCH_T1 | Lodged
KIK_MCH_1 | 2026-10-04 07:30 | 2026-10-04 18:30 | Daily | RS - Removal from Service | KIK-CB-82 | Lodged
MCH_110BS | 2026-10-04 07:30 | 2026-10-04 18:30 | Daily | RS - Removal from Service | MCH-DS-64 | Lodged
MCH_11BS | 2026-10-04 07:30 | 2026-10-04 18:30 | Daily | RS - Removal from Service | Affected equipment MCH_110BS & KIK_MCH_1 & MCH_T1 | Lodged
MCH_CB_32 | 2026-10-04 07:30 | 2026-10-04 18:30 | Daily | RS - Removal from Service | Affected Equipment of MCH_T1 Affected equipment MCH_110BS & KIK_MCH_1 & MCH_T1 | Lodged
MCH_T1 | 2026-10-04 07:30 | 2026-10-04 18:30 | Daily | RS - Removal from Service | MCH-TF-T1 | Lodged
ISL_SBK_2 | 2026-10-05 06:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | ISL-SBK A line reconductoring | Lodged
ISL_SBK_1 | 2026-10-05 06:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | ISL-SBK A line reconductoring | Lodged
ARI_HAM_1 | 2026-10-05 07:30 | 2026-10-11 18:30 | Continuous | OPE - Open Ended | System split for the duration of HAM T6 | Lodged
ARI_HAM_2 | 2026-10-05 07:30 | 2026-10-11 18:30 | Continuous | OPE - Open Ended | System split for the duration of HAM T6 | Lodged
HAM_T6 | 2026-10-05 07:30 | 2026-10-11 18:30 | Continuous | RS - Removal from Service | HAM T6 CCC and WTI replacement project. HAM-TF-T6 | Lodged
ISL_FDR_262 | 2026-10-05 07:30 | 2026-10-06 18:30 | Daily | RS - Removal from Service | ISL-CB-262 | Lodged
KPO_TMU_1 | 2026-10-05 07:30 | 2026-10-11 18:30 | Continuous | OPE - Open Ended | System split for the duration of HAM T6 | Lodged
MAN_NMA_2 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | MAN-P-CB-252, MAN-TWI-A0010-20, MAN-TWI-A0038-20, MAN-TWI-A0039-20, MAN-TWI-A0042-20, MAN-TWI-A0043-20, MAN-TWI-A0046-20, MAN-TWI-A0049-20, MAN-TWI-A0056-20, MAN-TWI-A0060-20, MAN-TWI-A0061-20, MAN-TWI-A0062-20, MAN-TWI-A0063-20, MAN-TWI-A0294-20, MAN-TWI-A0296-20, MAN-TWI-A0299-20, MAN-TWI-A0300-20, MAN-TWI-A0308-20, MAN-TWI-A0311-0312-20, MAN-TWI-A0313-0314-20, MAN-TWI-A0314-0315-20, NMA-CT-CT762 | Lodged
MLG_T1 | 2026-10-05 07:30 | 2026-10-16 18:30 | Continuous | RS - Removal from Service | SS pipework replacement. 12-hour soak on last day. | Lodged
OKI_220BS_A | 2026-10-05 07:30 | 2026-10-08 18:30 | Continuous | RS - Removal from Service | OKI-DS-233 (BC), OKI-DS-273 (WRK), OKI-DS-303 (NAP_2), OKI-DS-317, OKI-DS-353 (T1), OKI-DS-373 (T2), OKI-ES-300, OKI-ES-310, OKI-ES-319 | Lodged
OKI_CB_238 | 2026-10-05 07:30 | 2026-10-08 18:30 | Continuous | RS - Removal from Service | Affected equipment of OKI_220BS_A | Lodged
PEN_T10 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | PEN-CBL-T10-LV-N, PEN-CT-782, PEN-CT-NCT10, PEN-P-TF-T10, PEN-TF-T10 | Lodged
INV_TWI_1 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
CPK_T3 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | Affected equipment of CPK_WWD_WIL_3. No cable works. | Lodged
CPK_WWD_WIL_3 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | WWD-TEE-A0111-WWDG1-10 | Lodged
TKR_WIL_2 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | Re-insulation x2. Attachment points. Affected equipment of WIL_128_VT57. | Lodged
WIL_128_VT57 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | WIL-DCB-118, WIL-DCB-52 | Lodged
KIN_11BS_D | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | KIN-VT-2057, SM KIN 2042, 2052, 2072 | Lodged
KIN_317_368 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | KIN-DCB-338 | Lodged
KIN_CB_2042 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | KIN-CB-2042 | Lodged
KIN_CB_338 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | Affected equipment KIN_317_368 | Lodged
KIN_FDR_2052 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | KIN-NER-2052 | Lodged
KIN_FDR_2062 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | Affected equipment KIN_CB_2042 & KIN_FDR_2052 | Lodged
KIN_T9 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | KIN-CBL-2072-ET9A, KIN-CBL-ET9B-NER9, KIN-CBL-T9-2072, KIN-CBL-T9-2222, KIN-CBL-T9-ET9B, KIN-CT-322, KIN-RES-NER9, KIN-TF-ET9A, KIN-TF-ET9B, KIN-TF-T9. KIN-M-VT2222 | Lodged
NMA_220BS_A4 | 2026-10-05 07:30 | 2026-10-06 18:30 | Continuous | RS - Removal from Service | MAN-P-CB-252, MAN-TWI-A0010-20, MAN-TWI-A0038-20, MAN-TWI-A0039-20, MAN-TWI-A0042-20, MAN-TWI-A0043-20, MAN-TWI-A0046-20, MAN-TWI-A0049-20, MAN-TWI-A0056-20, MAN-TWI-A0060-20, MAN-TWI-A0061-20, MAN-TWI-A0062-20, MAN-TWI-A0063-20, MAN-TWI-A0294-20, MAN-TWI-A0296-20, MAN-TWI-A0299-20, MAN-TWI-A0300-20, MAN-TWI-A0308-20, MAN-TWI-A0311-0312-20, MAN-TWI-A0313-0314-20, MAN-TWI-A0314-0315-20, NMA-CT-CT762 | Lodged
NMA_CB_718 | 2026-10-05 07:30 | 2026-10-06 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A4 MAN-P-CB-252, MAN-TWI-A0010-20, MAN-TWI-A0038-20, MAN-TWI-A0039-20, MAN-TWI-A0042-20, MAN-TWI-A0043-20, MAN-TWI-A0046-20, MAN-TWI-A0049-20, MAN-TWI-A0056-20, MAN-TWI-A0060-20, MAN-TWI-A0061-20, MAN-TWI-A0062-20, MAN-TWI-A0063-20, MAN-TWI-A0294-20, MAN-TWI-A0296-20, MAN-TWI-A0299-20, MAN-TWI-A0300-20, MAN-TWI-A0308-20, MAN-TWI-A0311-0312-20, MAN-TWI-A0313-0314-20, MAN-TWI-A0314-0315-20, NMA-CT-CT762 | Lodged
NMA_CB_738 | 2026-10-05 07:30 | 2026-10-06 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A4 MAN-P-CB-252, MAN-TWI-A0010-20, MAN-TWI-A0038-20, MAN-TWI-A0039-20, MAN-TWI-A0042-20, MAN-TWI-A0043-20, MAN-TWI-A0046-20, MAN-TWI-A0049-20, MAN-TWI-A0056-20, MAN-TWI-A0060-20, MAN-TWI-A0061-20, MAN-TWI-A0062-20, MAN-TWI-A0063-20, MAN-TWI-A0294-20, MAN-TWI-A0296-20, MAN-TWI-A0299-20, MAN-TWI-A0300-20, MAN-TWI-A0308-20, MAN-TWI-A0311-0312-20, MAN-TWI-A0313-0314-20, MAN-TWI-A0314-0315-20, NMA-CT-CT762 | Lodged
DVK_CB_2698 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | DVK-P-CB-2698 [CP_DVK_70_00_00]. | Lodged
DVK_FDR_2702 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | DVK-P-CB-2702 [CP_DVK_70_00_00]. Affected equipment of DVK_T2 + DVK_CB_2698. | Lodged
DVK_FDR_2722 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | DVK-P-CB-2722 [CP_DVK_70_00_00]. Affected equipment of DVK_T2 + DVK_CB_2698. | Lodged
DVK_FDR_2742 | 2026-10-05 07:30 | 2026-10-09 18:30 | Daily | RS - Removal from Service | DVK-P-CB-2742 [CP_DVK_70_00_00]. Affected equipment of DVK_T2 + DVK_CB_2698. | Lodged
DVK_FDR_2762 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | DVK-P-CB-2762 [CP_DVK_70_00_00]. Affected equipment of DVK_T2 + DVK_CB_2698. | Lodged
DVK_T2 | 2026-10-05 07:30 | 2026-10-06 18:30 | Continuous | RS - Removal from Service | DVK-P-TF-T2, DVK-TF-T2 [CP_DVK_70_00_00]. | Lodged
DVK_WPW_1 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | Tower works x7 (A244, A246, A258, A273, A286, A302, A315). | Lodged
WPW_T2 | 2026-10-05 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | WPW-P-TF-T2 [CP_WPW_00L_0_00]. Affected equipment of DVK_WPW_1. | Lodged
CML_FKN_1 | 2026-10-05 07:31 | 2026-10-09 18:31 | Continuous | RS - Removal from Service | Affected equipment CYD_CML_TWZ_1 & CML_T5 | Lodged
CML_T5 | 2026-10-05 07:31 | 2026-10-09 18:31 | Continuous | RS - Removal from Service | CML-TF-T5A, CML-TF-T5B | Lodged
CYD_CML_TWZ_1 | 2026-10-05 07:31 | 2026-10-09 18:31 | Continuous | RS - Removal from Service | ROX-TWZ-A0143-10, ROX-TWZ-A0145-10, ROX-TWZ-A0146-10, ROX-TWZ-A0147-10, ROX-TWZ-A0148-10, ROX-TWZ-A0149-10, ROX-TWZ-A0150-10, ROX-TWZ-A0151-10, ROX-TWZ-A0152-10, ROX-TWZ-A0153-10, ROX-TWZ-A0154-10, ROX-TWZ-A0155-10, ROX-TWZ-A0156-10, ROX-TWZ-A0157-10 | Lodged
FKN_T1 | 2026-10-05 07:31 | 2026-10-09 18:31 | Continuous | RS - Removal from Service | Affected equipment CYD_CML_TWZ_1 & CML_T5 | Lodged
ALB_HEN_3 | 2026-10-05 08:00 | 2026-10-10 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
BOB_T4 | 2026-10-05 08:00 | 2026-10-10 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
OKI_WRK_1 | 2026-10-06 07:30 | 2026-10-06 18:30 | Daily | RS - Removal from Service | OKI-DS-273 | Lodged
ASB_397_427 | 2026-10-07 07:30 | 2026-10-08 18:30 | Continuous | RS - Removal from Service | ASB-DS-404 | Lodged
ASB_FDR_62 | 2026-10-07 07:30 | 2026-10-08 18:30 | Continuous | RS - Removal from Service | Affected equipment ASB_397_427 | Lodged
ASB_T9 | 2026-10-07 07:30 | 2026-10-08 18:30 | Continuous | RS - Removal from Service | Affected equipment ASB_397_427 | Lodged
BLN_33BS_B | 2026-10-07 07:30 | 2026-10-08 18:30 | Continuous | RS - Removal from Service | 1 yrs, BLN-VT-VT2147 | Lodged
BLN_C_2 | 2026-10-07 07:30 | 2026-10-08 18:30 | Continuous | RS - Removal from Service | BLN-CAPS-C2, BLN-CB-2122, BLN-CBL-C2, BLN-REA-C2-1, BLN-REA-C2-3, BLN-VT-C2-2 | Lodged
BLN_C_4 | 2026-10-07 07:30 | 2026-10-08 18:30 | Continuous | RS - Removal from Service | BLN-CAPS-C4, BLN-CB-2132, BLN-CBL-C4, BLN-REA-C4-1, BLN-REA-C4-3, BLN-VT-C4-2 | Lodged
BLN_CB_2108 | 2026-10-07 07:30 | 2026-10-08 18:30 | Continuous | RS - Removal from Service | Affected equipment BLN_33BS_B & BLN_C_2 & BLN_C_4 | Lodged
BLN_FDR_2152 | 2026-10-07 07:30 | 2026-10-08 18:30 | Continuous | RS - Removal from Service | Affected equipment BLN_33BS_B & BLN_C_2 & BLN_C_4 | Lodged
BLN_FDR_2162 | 2026-10-07 07:30 | 2026-10-08 18:30 | Continuous | RS - Removal from Service | Affected equipment BLN_33BS_B & BLN_C_2 & BLN_C_4 | Lodged
BLN_FDR_2172 | 2026-10-07 07:30 | 2026-10-08 18:30 | Continuous | RS - Removal from Service | Affected equipment BLN_33BS_B & BLN_C_2 & BLN_C_4 | Lodged
BLN_T1 | 2026-10-07 07:30 | 2026-10-08 18:30 | Continuous | RS - Removal from Service | Affected equipment BLN_33BS_B & BLN_C_2 & BLN_C_4 | Lodged
TRK_407_417_437 | 2026-10-07 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | TRK-BS-220-417-437, TRK-DS-417 | Lodged
WHU_110BZ | 2026-10-07 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | WHU-P-BZ-110-A | Lodged
WHU_110CBF | 2026-10-07 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
NMA_687_835 | 2026-10-07 07:31 | 2026-10-09 18:31 | Continuous | RS - Removal from Service | MAN-P-CB-252, MAN-TWI-A0010-20, MAN-TWI-A0038-20, MAN-TWI-A0039-20, MAN-TWI-A0042-20, MAN-TWI-A0043-20, MAN-TWI-A0046-20, MAN-TWI-A0049-20, MAN-TWI-A0056-20, MAN-TWI-A0060-20, MAN-TWI-A0061-20, MAN-TWI-A0062-20, MAN-TWI-A0063-20, MAN-TWI-A0294-20, MAN-TWI-A0296-20, MAN-TWI-A0299-20, MAN-TWI-A0300-20, MAN-TWI-A0308-20, MAN-TWI-A0311-0312-20, MAN-TWI-A0313-0314-20, MAN-TWI-A0314-0315-20, NMA-CT-CT762 | Lodged
NMA_CB_738 | 2026-10-07 07:31 | 2026-10-09 18:31 | Continuous | RS - Removal from Service | Affected Equipment of NMA_687_835 MAN-P-CB-252, MAN-TWI-A0010-20, MAN-TWI-A0038-20, MAN-TWI-A0039-20, MAN-TWI-A0042-20, MAN-TWI-A0043-20, MAN-TWI-A0046-20, MAN-TWI-A0049-20, MAN-TWI-A0056-20, MAN-TWI-A0060-20, MAN-TWI-A0061-20, MAN-TWI-A0062-20, MAN-TWI-A0063-20, MAN-TWI-A0294-20, MAN-TWI-A0296-20, MAN-TWI-A0299-20, MAN-TWI-A0300-20, MAN-TWI-A0308-20, MAN-TWI-A0311-0312-20, MAN-TWI-A0313-0314-20, MAN-TWI-A0314-0315-20, NMA-CT-CT762 | Lodged
ISL_C_16 | 2026-10-08 07:30 | 2026-10-08 18:30 | Daily | RS - Removal from Service | ISL-CB-372 | Lodged
ISL_T8 | 2026-10-08 07:30 | 2026-10-08 18:30 | Daily | RS - Removal from Service | ISL-TF-T8 | Lodged
OTA_220BZ_K_2 | 2026-10-08 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | OTA-P-BZ-2-220-K | Lodged
OTA_220CBF_K_2 | 2026-10-08 07:30 | 2026-10-09 18:30 | Continuous | RS - Removal from Service | Affected equipment. OTA-P-BZ-2-220-K | Lodged
GFD_HAY_2 | 2026-10-12 07:00 | 2026-10-16 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3E; Bay 240 - Gracefield cct 2. No other HAY work on days 1, 5, 6. No other work on associated equipment/lines on day 6 (commissioning). | Lodged
GFD_T5 | 2026-10-12 07:00 | 2026-10-16 18:00 | Continuous | RS - Removal from Service | GFD-CBL-2242-LS5, GFD-CBL-T5-2242, GFD-CBL-T5-NER5, GFD-CBL-TS-T5, GFD-RES-NER5, GFD-TF-LS-LS5, GFD-TF-T5, GFD-VT-72. Affected equipment of GFD_HAY_2, for HAY_110BZ Stage 3E; Bay 240 - Gracefield cct 2. | Lodged
ARI_BOB_1 | 2026-10-12 07:30 | 2026-10-17 18:30 | Continuous | RS - Removal from Service | Attachment Points, Reinsulation | Lodged
CYD_ROX_1 | 2026-10-12 07:30 | 2026-10-16 18:30 | Continuous | RS - Removal from Service | ROX-CVT-VT69, ROX-DS-556, ROX-DS-564, ROX-ES-559 | Lodged
GOR_T12 | 2026-10-12 07:30 | 2026-10-16 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_GOR_TMH_2 pdm maint | Lodged
HAY_F_3 | 2026-10-12 07:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | 8 yrs, S4.WA-Z2.Q1, S4.WA-Z2.Z1.Q1, S4.WA-Z2.Z1.R1A, S4.WA-Z2.Z1.R1B, S4.WA-Z2.Z1.R1C, S4.WA-Z2.Z2.Q1, S4.WA-Z2.Z2.R1A, S4.WA-Z2.Z2.R1B, S4.WA-Z2.Z2.R1C, HVDC HAY-DC Pole 2 Era AC Disconnector/Earth Switch Refurbishments | Lodged
NMA_220BS_A4 | 2026-10-12 07:30 | 2026-10-13 18:30 | Continuous | RS - Removal from Service | pdm maint. | Lodged
NMA_CB_718 | 2026-10-12 07:30 | 2026-10-13 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A4 pdm maint. | Lodged
NMA_CB_738 | 2026-10-12 07:30 | 2026-10-13 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A4 pdm maint. | Lodged
NMA_GOR_TMH_2 | 2026-10-12 07:30 | 2026-10-16 18:30 | Continuous | RS - Removal from Service | pdm maint includes Lines | Lodged
PEN_220BS_C | 2026-10-12 07:30 | 2026-10-14 18:30 | Continuous | RS - Removal from Service | PEN-DS-804, PEN-DS-807, PEN-DS-814, PEN-DS-827, PEN-ES-810, PEN-ES-820 | Lodged
PEN_CB_2332A | 2026-10-12 07:30 | 2026-10-14 18:30 | Continuous | CLO - Close | Place T8 into service for the duration of PEN_T11 | Lodged
PEN_CB_2332B | 2026-10-12 07:30 | 2026-10-14 18:30 | Continuous | CLO - Close | Place T8 into service for the duration of PEN_T11 | Lodged
PEN_CB_798 | 2026-10-12 07:30 | 2026-10-14 18:30 | Continuous | RS - Removal from Service | PEN-CT-798, PEN-P-CB-798 | Lodged
PEN_CB_812 | 2026-10-12 07:30 | 2026-10-14 18:30 | Continuous | RS - Removal from Service | Affected equipment PEN_220BS_C & PEN_CB_798 & PEN_CB_828 & PEN_T11 | Lodged
PEN_CB_828 | 2026-10-12 07:30 | 2026-10-14 18:30 | Continuous | RS - Removal from Service | PEN-CB-828 | Lodged
PEN_T11 | 2026-10-12 07:30 | 2026-10-14 18:30 | Continuous | RS - Removal from Service | PEN-TF-ET11 | Lodged
ROX_220BS_B | 2026-10-12 07:30 | 2026-10-13 18:30 | Continuous | RS - Removal from Service | ROX-DS-553, ROX-DS-555 | Lodged
ROX_564_555_553_556 | 2026-10-12 07:30 | 2026-10-16 18:30 | Continuous | RS - Removal from Service | ROX-DS-553, ROX-DS-555 | Lodged
ROX_CB_698 | 2026-10-12 07:30 | 2026-10-13 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ROX_220BS_B ROX-DS-553, ROX-DS-555 | Lodged
ROX_CB_708 | 2026-10-12 07:30 | 2026-10-13 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ROX_220BS_B ROX-DS-553, ROX-DS-555 | Lodged
WHI_WRK_1 | 2026-10-12 07:30 | 2026-10-16 18:30 | Continuous | RS - Removal from Service | WRK-CB-172, WRK-CT-172. WHI-DS-516 headgear refurbishment [CP_RA4_03K_0_00]. Tower works x14 (A12, A63-A64, A68, A100-A101, A104-A105, A122, A155-A156, A158-A160). RSA4 re-insulation x1. | Lodged
TNG_CB_288 | 2026-10-12 07:30 | 2026-10-16 18:30 | Continuous | RS - Removal from Service | TNG-CT-288 replacement [CP_TNG_001_0_00]. | Lodged
INV_TWI_2 | 2026-10-12 07:30 | 2026-10-16 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
WHI_514_524_537 | 2026-10-12 07:31 | 2026-10-14 18:31 | Daily | RS - Removal from Service | WHI-DS-514 headgear refurbishment [CP_RA4_03K_0_00]. | Lodged
WHI_T1 | 2026-10-12 07:31 | 2026-10-14 18:31 | Daily | RS - Removal from Service | Affected equipment of WHI_514_524_537 | Lodged
TNG_220BS_B | 2026-10-12 07:31 | 2026-10-13 18:31 | Continuous | RS - Removal from Service | TNG-DS-285 (BC) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-230 | Lodged
BEN_220BZ | 2026-10-12 08:00 | 2026-10-12 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 3 Migration | Lodged
BEN_220CBF | 2026-10-12 08:00 | 2026-10-12 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 3 Migration | Lodged
BEN_F_3 | 2026-10-12 08:00 | 2026-10-22 18:00 | Continuous | RS - Removal from Service | BEN 220BZ - Filter 3 Migration | Lodged
MPE_CB_252 | 2026-10-12 08:00 | 2026-10-12 22:00 | Daily | OPE - Open Ended | System split for HEN_HPI_1 | Lodged
MPE_CB_292 | 2026-10-12 08:00 | 2026-10-12 22:00 | Daily | OPE - Open Ended | System split for HEN_HPI_1 | Lodged
BOB_T5 | 2026-10-12 08:00 | 2026-10-17 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
HEN_HPI_1 | 2026-10-12 08:00 | 2026-10-17 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
BRB_HPI_1 | 2026-10-12 08:00 | 2026-10-17 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
MPE_CB_252 | 2026-10-13 06:00 | 2026-10-15 22:00 | Continuous | OPE - Open Ended | System split for HEN_HPI_1 | Lodged
MPE_CB_292 | 2026-10-13 06:00 | 2026-10-15 22:00 | Continuous | OPE - Open Ended | System split for HEN_HPI_1 | Lodged
HAM_T2 | 2026-10-13 07:30 | 2026-10-14 18:30 | Continuous | RS - Removal from Service | Revenue metering HAM-M-CT2872 | Lodged
HTI_CB_2188 | 2026-10-13 07:30 | 2026-10-15 18:30 | Continuous | RS - Removal from Service | HTI-CBL-2188-2217 | Lodged
HAY_110BZ | 2026-10-13 08:00 | 2026-10-13 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3E; Bay 240 - Gracefield cct 2. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-10-13 08:00 | 2026-10-13 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3E; Bay 240 - Gracefield cct 2. | Lodged
MAN_220BZ | 2026-10-14 07:30 | 2026-10-14 18:30 | Daily | RS - Removal from Service | MAN-P-BZ-220 | Lodged
NMA_220BS_A3 | 2026-10-14 07:30 | 2026-10-16 18:30 | Continuous | RS - Removal from Service | pdm maint. | Lodged
NMA_CB_708 | 2026-10-14 07:30 | 2026-10-16 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A3 pdm maint. | Lodged
NMA_CB_718 | 2026-10-14 07:30 | 2026-10-16 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A3 pdm maint. | Lodged
ROX_220BS_C | 2026-10-14 07:30 | 2026-10-16 18:30 | Continuous | RS - Removal from Service | ROX-DS-553, ROX-DS-555 | Lodged
ROX_CB_658 | 2026-10-14 07:30 | 2026-10-16 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ROX_220BS_C ROX-DS-553, ROX-DS-555 | Lodged
ROX_CB_708 | 2026-10-14 07:30 | 2026-10-16 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ROX_220BS_C ROX-DS-553, ROX-DS-555 | Lodged
TNG_220BS_A | 2026-10-14 07:30 | 2026-10-14 18:30 | Daily | RS - Removal from Service | TNG-DS-283 (BC) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-220 | Lodged
ISL_FDR_202 | 2026-10-15 07:30 | 2026-10-16 18:30 | Continuous | RS - Removal from Service | ISL-CB-202, ISL-P-CB-202 | Lodged
PEN_FDR_2252 | 2026-10-15 07:30 | 2026-10-15 18:30 | Daily | RS - Removal from Service | PEN-CB-2252, PEN-P-CB-2252 | Lodged
MPE_CB_252 | 2026-10-16 06:00 | 2026-10-16 18:30 | Daily | OPE - Open Ended | System split for HEN_HPI_1 | Lodged
MPE_CB_292 | 2026-10-16 06:00 | 2026-10-16 18:30 | Daily | OPE - Open Ended | System split for HEN_HPI_1 | Lodged
HAY_CB_2622 | 2026-10-16 07:30 | 2026-10-16 18:30 | Daily | RS - Removal from Service | HAY-CBL-CB2622-ST10 | Lodged
PEN_FDR_2502 | 2026-10-16 07:30 | 2026-10-16 18:30 | Daily | RS - Removal from Service | PEN-CB-2502, PEN-P-CB-2502 | Lodged
HAY_110BZ | 2026-10-16 08:00 | 2026-10-16 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3E; Bay 240 - Gracefield cct 2. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-10-16 08:00 | 2026-10-16 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3E; Bay 240 - Gracefield cct 2. | Lodged
HAY_110BZ | 2026-10-17 08:00 | 2026-10-17 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3E; Bay 240 - Gracefield cct 2. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-10-17 08:00 | 2026-10-17 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3E; Bay 240 - Gracefield cct 2. | Lodged
KIK_CB_37 | 2026-10-18 07:30 | 2026-10-18 18:30 | Daily | RS - Removal from Service | KIK-P-TF-RT1, KIK-TF-RT1 | Lodged
ISL_CB_708 | 2026-10-19 06:30 | 2026-10-20 18:30 | Continuous | RS - Removal from Service | Affected Equipment ISL-DS-95, ISL-DS-145. CY4 Re-planned. | Lodged
ISL_CB_728 | 2026-10-19 06:30 | 2026-10-20 18:30 | Continuous | RS - Removal from Service | Affected Equipment ISL-DS-95, ISL-DS-145. CY4 Re-planned. | Lodged
BOB_T5 | 2026-10-19 07:30 | 2026-10-20 18:30 | Continuous | RS - Removal from Service | Affected Equipment of DRY_BOB_HLY_2 Lines maintenance | Lodged
DRY_BOB_HLY_2 | 2026-10-19 07:30 | 2026-10-20 18:30 | Continuous | RS - Removal from Service | Lines maintenance | Lodged
EDG_T4 | 2026-10-19 07:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | EDG-CB-412, EDG-CBL-ET4-NER4, EDG-CBL-T4-2162, EDG-CBL-TS-ET4, EDG-CT-412, EDG-NCT-4, EDG-RES-NER4, EDG-TF-ET4, EDG-TF-T4 | Lodged
ISL_CB_768 | 2026-10-19 07:30 | 2026-10-20 18:30 | Daily | RS - Removal from Service | ISL-P-CB-768 | Lodged
MAN_NMA_2 | 2026-10-19 07:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | MAN-TWI-A0038-20 MAN-TWI-A0039-20 MAN-TWI-A0042-20 MAN-TWI-A0043-20 MAN-TWI-A0046-20 MAN-TWI-A0049-20 MAN-TWI-A0056-20 MAN-TWI-A0060-20 MAN-TWI-A0061-20 MAN-TWI-A0062-20 MAN-TWI-A0063-20 MAN-TWI-A0294-20 MAN-TWI-A0296-20 MAN-TWI-A0299-20 MAN-TWI-A0300-20 MAN-TWI-A0308-20 | Lodged
PEN_110BS_A | 2026-10-19 07:30 | 2026-10-22 18:30 | Continuous | RS - Removal from Service | PEN-DS-44, PEN-DS-54, PEN-DS-64, PEN-DS-94, PEN-DS-97, PEN-VT-47 | Lodged
PEN_C_11 | 2026-10-19 07:30 | 2026-10-22 18:30 | Continuous | RS - Removal from Service | PEN-CB-52 | Lodged
PEN_C_13 | 2026-10-19 07:30 | 2026-10-22 18:30 | Continuous | RS - Removal from Service | Affected equipment PEN_110BS_A & PEN_C_11 & PEN_FDR_62 | Lodged
PEN_CB_118 | 2026-10-19 07:30 | 2026-10-22 18:30 | Continuous | RS - Removal from Service | Affected equipment PEN_110BS_A & PEN_C_11 & PEN_FDR_62 | Lodged
PEN_FDR_62 | 2026-10-19 07:30 | 2026-10-22 18:30 | Continuous | RS - Removal from Service | PEN-CT-62, PEN-DS-66, PEN-ES-69, PEN-P-CB-62 | Lodged
PEN_T6 | 2026-10-19 07:30 | 2026-10-22 18:30 | Continuous | RS - Removal from Service | Affected equipment PEN_110BS_A & PEN_C_11 & PEN_FDR_62 | Lodged
CPK_T4 | 2026-10-19 07:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | Affected equipment of CPK_WWD_WIL_2 | Lodged
CPK_WWD_WIL_2 | 2026-10-19 07:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | WWD-CB-242, WWD-CT-242, WWD-CVT-242, WWD-DS-246, WWD-ES-249. WWD-TEE-A0108-0109-00, WWD-TEE-A0109-0110-00, WWD-TEE-A0111-WWDG2-10 | Lodged
RDF_WHI_1 | 2026-10-19 07:31 | 2026-10-21 18:31 | Continuous | RS - Removal from Service | Affected equipment of WHI_567_634_644, for DS headgear refurbishment | Lodged
WHI_567_634_644 | 2026-10-19 07:31 | 2026-10-21 18:31 | Continuous | RS - Removal from Service | WHI-DS-584 headgear refurbishment [CP_RA4_03K_0_00]. | Lodged
TWH_33BS_A | 2026-10-19 07:31 | 2026-10-24 18:31 | Continuous | RS - Removal from Service | Protection replacement project. TWH-P-BZ-33-A | Lodged
TWH_CB_2808 | 2026-10-19 07:31 | 2026-10-24 18:31 | Continuous | RS - Removal from Service | TWH-P-CB-2808 | Lodged
TWH_FDR_2722 | 2026-10-19 07:31 | 2026-10-24 18:31 | Continuous | RS - Removal from Service | TWH-P-CB-2722 | Lodged
TWH_FDR_2742 | 2026-10-19 07:31 | 2026-10-24 18:31 | Continuous | RS - Removal from Service | TWH-P-CB-2742 | Lodged
TWH_FDR_2762 | 2026-10-19 07:31 | 2026-10-24 18:31 | Continuous | RS - Removal from Service | TWH-P-CB-2762 | Lodged
TWH_FDR_2782 | 2026-10-19 07:31 | 2026-10-24 18:31 | Continuous | RS - Removal from Service | TWH-P-CB-2782 | Lodged
TWH_T1 | 2026-10-19 07:31 | 2026-10-24 18:31 | Continuous | RS - Removal from Service | TWH-P-TF-T1, TWH-TF-T1 | Lodged
HEP_FDR_2202 | 2026-10-20 07:30 | 2026-10-20 18:30 | Daily | RS - Removal from Service | HEP-CB-2202, HEP-P-CB-2202 | Lodged
ROX_624_615_613_616 | 2026-10-20 07:30 | 2026-10-22 18:30 | Continuous | RS - Removal from Service | ROX-DS-616 | Lodged
ROX_TMH_1 | 2026-10-20 07:30 | 2026-10-22 18:30 | Continuous | RS - Removal from Service | ROX-TMH-A0078-0079-10 | Lodged
TIM_CB_2752 | 2026-10-20 07:31 | 2026-10-22 18:31 | Continuous | RS - Removal from Service | Affected equipment TIM_T6 | Lodged
TIM_T6 | 2026-10-20 07:31 | 2026-10-22 18:31 | Continuous | RS - Removal from Service | TIM-CBL-T6-CB2932, TIM-CBL-T6-LS6, TIM-CBL-T6-NER6, TIM-RES-NER6, TIM-TF-LS6, TIM-TF-T6, TIM-VT-VT2932 | Lodged
ISL_CB_708 | 2026-10-21 06:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | Affected Equipment ISL-DS-143. CY4 Re-planned. | Lodged
ISL_CB_768 | 2026-10-21 06:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | Affected Equipment ISL-DS-143. CY4 Re-planned. | Lodged
HAM_STC_3 | 2026-10-21 07:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | HAM-BU-STC3, HAM-COOL-STC3, HAM-STC-3 | Lodged
ISL_FDR_142 | 2026-10-21 07:30 | 2026-10-22 18:30 | Continuous | RS - Removal from Service | ISL-CB-142, ISL-P-CB-142 | Lodged
BEN_220BZ | 2026-10-21 08:00 | 2026-10-22 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 3 Migration | Lodged
BEN_220CBF | 2026-10-21 08:00 | 2026-10-22 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 3 Migration | Lodged
SVL_FDR_2882 | 2026-10-22 07:30 | 2026-10-23 18:30 | Continuous | RS - Removal from Service | SVL-CBL-2882 | Lodged
PTS_2027_ARI_HTI | 2026-10-23 07:30 | 2026-10-23 18:30 | Daily | RS - Removal from Service | ARI-C-PTSG-2027, HTI-C-PTSG-2027 | Lodged
KAW_OHK_1 | 2026-10-26 08:00 | 2026-10-31 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
GOR_T12 | 2026-10-27 07:30 | 2026-10-30 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_GOR_TMH_2 includes Lines | Lodged
HAY_CB_962 | 2026-10-27 07:30 | 2026-10-30 18:30 | Continuous | RS - Removal from Service | S4.10DC96-Q0 | Lodged
HTI_97_87_VT57 | 2026-10-27 07:30 | 2026-10-28 18:30 | Continuous | RS - Removal from Service | HTI-M-VT57 | Lodged
HTI_DIS_54 | 2026-10-27 07:30 | 2026-10-28 18:30 | Continuous | RS - Removal from Service | Affected equipment HTI_97_87_VT57 | Lodged
HTI_TMU_1 | 2026-10-27 07:30 | 2026-10-28 18:30 | Continuous | RS - Removal from Service | Affected equipment HTI_97_87_VT57 | Lodged
MLG_T2 | 2026-10-27 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | SS pipework replacement. 12-hour soak on last day. | Lodged
NMA_GOR_TMH_2 | 2026-10-27 07:30 | 2026-10-30 18:30 | Continuous | RS - Removal from Service | includes Lines | Lodged
WPR_T12 | 2026-10-27 07:30 | 2026-10-30 18:30 | Continuous | RS - Removal from Service | WPR-CB-172, WPR-CT-CT432, WPR-CT-T12, WPR-P-TF-T12, WPR-TF-T12 | Lodged
OWH_97_104_114 | 2026-10-27 07:30 | 2026-10-31 18:31 | Continuous | RS - Removal from Service | OWH-BS-110-107-114, OWH-DS-104, OWH-DS-107, OWH-DS-114, OWH-VT-VT107 | Lodged
OWH_T2 | 2026-10-27 07:30 | 2026-10-31 18:31 | Continuous | RS - Removal from Service | OWH-TF-T2 | Lodged
OWH_TMI_TRK_1 | 2026-10-27 07:30 | 2026-10-31 18:31 | Continuous | RS - Removal from Service | ARI-EDG-B0268-00, ARI-EDG-B0279-00, ARI-EDG-B0302-00, TRK-CT-142, TRK-DS-146, TRK-ES-149, TRK-P-CB-142 | Lodged
PEN_220BS_B | 2026-10-27 07:31 | 2026-10-31 18:31 | Continuous | RS - Removal from Service | PEN-DS-774, PEN-ES-7749, PEN-DS-767, PEN-DS-777, PEN-DS-784, PEN-DS-797, PEN-ES-760, PEN-ES-790 | Lodged
PEN_CB_2332A | 2026-10-27 07:31 | 2026-10-31 18:31 | Continuous | CLO - Close | Place PEN T8 into service for the duration of T9 outage | Lodged
PEN_CB_2332B | 2026-10-27 07:31 | 2026-10-31 18:31 | Continuous | CLO - Close | Place PEN T8 into service for the duration of T9 outage | Lodged
PEN_CB_758 | 2026-10-27 07:31 | 2026-10-31 18:31 | Continuous | RS - Removal from Service | PEN-P-CB-758 | Lodged
PEN_CB_772 | 2026-10-27 07:31 | 2026-10-31 18:31 | Continuous | RS - Removal from Service | Affected equipment PEN_220BS_B & PEN_CB_758 & PEN_CB_798 & PEN_T10 | Lodged
PEN_CB_798 | 2026-10-27 07:31 | 2026-10-31 18:31 | Continuous | RS - Removal from Service | PEN-CT-798, PEN-P-CB-798 | Lodged
PEN_T10 | 2026-10-27 07:31 | 2026-10-31 18:31 | Continuous | RS - Removal from Service | Affected equipment | Lodged
PEN_T9 | 2026-10-27 07:31 | 2026-10-31 18:31 | Continuous | RS - Removal from Service | Affected equipment PEN_220BS_B & PEN_CB_758 & PEN_CB_798 & PEN_T10 | Lodged
GFD_HAY_1 | 2026-10-28 07:00 | 2026-11-01 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3F; Bay 260 - Gracefield cct 1. No other HAY work on days 1, 4, 5. No other work on associated equipment/lines on day 5 (commissioning). | Lodged
GFD_T6 | 2026-10-28 07:00 | 2026-11-01 18:00 | Continuous | RS - Removal from Service | Reinhausen work. Affected equipment of GFD_HAY_1, for HAY_110BZ Stage 3F; Bay 260 - Gracefield cct 1. | Lodged
WHI_WRK_1 | 2026-10-28 07:30 | 2026-10-30 18:30 | Continuous | RS - Removal from Service | Additional outage for tower works x14 (A12, A63-A64, A68, A100-A101, A104-A105, A122, A155-A156, A158-A160). RSA4 re-insulation x1. WHI-DS-516, WRK-CB-172, WRK-CT-172. | Lodged
ABY_TIM_1 | 2026-10-28 07:30 | 2026-10-29 18:30 | Daily | RS - Removal from Service | ABY-CB-72, TIM-P-CB-132, TKA-TIM-A0314-00, TKA-TIM-A0320-00, TKA-TIM-A0386-00, TKA-TIM-A0399-00, TKA-TIM-A0410-00, TKA-TIM-A0450-00, TKA-TIM-A0454-00, TKA-TIM-A0463-10 | Lodged
ABY_TKA_1 | 2026-10-28 07:30 | 2026-10-29 18:30 | Daily | RS - Removal from Service | TKA-TIM-A0191-00 | Lodged
ABY_11BS | 2026-10-28 07:30 | 2026-10-29 18:30 | Daily | RS - Removal from Service | Affected equipment ABY_T2 | Lodged
ABY_FDR_2722 | 2026-10-28 07:30 | 2026-10-29 18:30 | Daily | RS - Removal from Service | Affected Equipment of ABY_11BS Affected equipment ABY_T2 | Lodged
ABY_FDR_2732 | 2026-10-28 07:30 | 2026-10-29 18:30 | Daily | RS - Removal from Service | ABY-CB-2732, ABY-P-CB-2732, ABY-VT-VT2732 | Lodged
ABY_FDR_2742 | 2026-10-28 07:30 | 2026-10-29 18:30 | Daily | RS - Removal from Service | ABY-CB-2742, ABY-P-CB-2742, ABY-VT-VT2742 | Lodged
ABY_T2 | 2026-10-28 07:30 | 2026-10-29 18:30 | Daily | RS - Removal from Service | ABY-CB-62, ABY-CT-CT62, ABY-VT-VT62 | Lodged
HEN_287_297_334 | 2026-10-28 07:31 | 2026-10-29 18:31 | Continuous | RS - Removal from Service | HEN-DS-294, HEN-DS-297, HEN-DS-304, HEN-DS-314, HEN-DS-324, HEN-VT-2 | Lodged
HEN_CB_288 | 2026-10-28 07:31 | 2026-10-29 18:31 | Continuous | RS - Removal from Service | Affected equipment HEN_287_297_334 | Lodged
HEN_HEP_3 | 2026-10-28 07:31 | 2026-10-29 18:31 | Continuous | RS - Removal from Service | Affected equipment HEN_287_297_334 | Lodged
HEN_HEP_4 | 2026-10-28 07:31 | 2026-10-29 18:31 | Continuous | RS - Removal from Service | Affected equipment HEN_287_297_334 | Lodged
HEN_T5 | 2026-10-28 07:31 | 2026-10-29 18:31 | Continuous | RS - Removal from Service | Affected equipment HEN_287_297_334 | Lodged
HEN_WEL_1 | 2026-10-28 07:31 | 2026-10-29 18:31 | Continuous | RS - Removal from Service | Affected equipment HEN_287_297_334 | Lodged
HEN_WEL_2 | 2026-10-28 07:31 | 2026-10-29 18:31 | Continuous | RS - Removal from Service | Affected equipment HEN_287_297_334 | Lodged
HAY_110BZ | 2026-10-28 08:00 | 2026-10-28 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3F; Bay 260 - Gracefield cct 1. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-10-28 08:00 | 2026-10-28 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3F; Bay 260 - Gracefield cct 1. | Lodged
ISL_FDR_152 | 2026-10-29 07:30 | 2026-10-30 18:30 | Continuous | RS - Removal from Service | ISL-CB-152, ISL-P-CB-152 | Lodged
HAY_110BZ | 2026-10-31 08:00 | 2026-10-31 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3F; Bay 260 - Gracefield cct 1. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-10-31 08:00 | 2026-10-31 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3F; Bay 260 - Gracefield cct 1. | Lodged
HAY_110BZ | 2026-11-01 08:00 | 2026-11-01 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3F; Bay 260 - Gracefield cct 1. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-11-01 08:00 | 2026-11-01 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3F; Bay 260 - Gracefield cct 1. | Lodged
HEP_FDR_2262 | 2026-11-02 07:30 | 2026-11-02 18:30 | Daily | RS - Removal from Service | HEP-CB-2262, HEP-P-CB-2262 | Lodged
HWB_ROX_1 | 2026-11-02 07:30 | 2026-11-13 18:30 | Continuous | RS - Removal from Service | HWB-ROX-A0135-00, HWB-ROX-A0145A-00, HWB-ROX-A0150-00, HWB-ROX-A0153-00, HWB-ROX-A0160-00, HWB-ROX-A0173-00, HWB-ROX-A0312-10, HWB-ROX-A0344-10, HWB-ROX-A0346-10, HWB-ROX-A0347-10 | Lodged
HWB_ROX_2 | 2026-11-02 07:30 | 2026-11-13 18:30 | Continuous | RS - Removal from Service | HWB-ROX-A0201-20, HWB-ROX-A0203A-10, HWB-ROX-A0204A-10, | Lodged
OTA_CB_188 | 2026-11-02 07:30 | 2026-11-03 18:30 | Continuous | RS - Removal from Service | OTA-P-CB-188 | Lodged
PEN_FDR_2452 | 2026-11-02 07:30 | 2026-11-03 18:30 | Continuous | RS - Removal from Service | PEN-CB-2452, PEN-P-CB-2452 | Lodged
SFD_TMN_1 | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | RSA3 lines works. | Lodged
TMN_396_457 | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | Affected Equipment of SFD_TMN_1 RSA3 lines works. | Lodged
TMN_CB_458 | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | Affected Equipment of SFD_TMN_1 RSA3 lines works. | Lodged
TMN_T5 | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | Affected Equipment of SFD_TMN_1 RSA3 lines works. | Lodged
CLH_COL_1 | 2026-11-02 07:30 | 2026-11-07 18:30 | Continuous | RS - Removal from Service | COL-OTI-A0031-00, COL-OTI-A0045-00 | Lodged
COL_OTI_2 | 2026-11-02 07:30 | 2026-11-07 18:30 | Continuous | RS - Removal from Service | COL-OTI-A0031-00, COL-OTI-A0045-00 | Lodged
ISL_KIK_1 | 2026-11-02 07:30 | 2026-11-07 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
CPK_T5 | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | Reinhausen work. Affected equipment of CPK_WIL_1, for line works | Lodged
CPK_WIL_1 | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | CPK-WIL-A0001-00, CPK-WIL-A0001-0002-10, CPK-WIL-A0002-0003-10, CPK-WIL-A0004-0005-00, CPK-WIL-A0004-0005-10, CPK-WIL-A0007-00, CPK-WIL-A0007-0008-00, CPK-WIL-A0007-0008-10, CPK-WIL-A0008-0009-10, CPK-WIL-A0009-00, CPK-WIL-A0009-0010-10, CPK-WIL-A0014-0015-00, CPK-WIL-A0014-0015-10, CPK-WIL-B0027-0028-00, CPK-WIL-B0028-0029-00 | Lodged
TWH_33BS_B | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | Transformer, feeder and BZ protection replacement. TWH-P-BZ-33-B | Lodged
TWH_CB_2808 | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | TWH-P-CB-2808 | Lodged
TWH_FDR_2822 | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | TWH-P-CB-2822 | Lodged
TWH_FDR_2842 | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | TWH-P-CB-2842 | Lodged
TWH_FDR_2862 | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | TWH-P-CB-2862 | Lodged
TWH_FDR_2882 | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | TWH-DS-2884 | Lodged
TWH_T2 | 2026-11-02 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | Protection replacement TWH-P-TF-T2, TWH-TF-T2 | Lodged
KMO_110BZ | 2026-11-02 07:31 | 2026-11-04 18:31 | Continuous | RS - Removal from Service | KMO-P-BZ-110-C | Lodged
KMO_110CBF | 2026-11-02 07:31 | 2026-11-04 18:31 | Continuous | RS - Removal from Service | Affected equipment | Lodged
KWA_CB_14 | 2026-11-02 07:31 | 2026-11-06 18:31 | Continuous | RS - Removal from Service | Affected equipment KWA_T3 & KWA_WIL_2 | Lodged
KWA_T3 | 2026-11-02 07:31 | 2026-11-06 18:31 | Continuous | RS - Removal from Service | KWA-P-TF-T3. Affected equipment of KWA_WIL_2. | Lodged
KWA_WIL_2 | 2026-11-02 07:31 | 2026-11-06 18:31 | Continuous | RS - Removal from Service | KWA-CBL-62-WIL2, KWA-ES-69, WIL-CT-CT222, WIL-P-CB-222 | Lodged
OTA_110BZ | 2026-11-02 07:31 | 2026-11-05 18:31 | Continuous | RS - Removal from Service | OTA-P-BZ-110 | Lodged
OTA_110CBF | 2026-11-02 07:31 | 2026-11-05 18:31 | Continuous | RS - Removal from Service | OTA-P-BS-110 | Lodged
ISL_SVC_3 | 2026-11-02 07:31 | 2026-11-06 18:31 | Continuous | RS - Removal from Service | ISL-CAPS-C1, ISL-CAPS-C3, ISL-CWU-SVC3, ISL-SVC-3 | Lodged
ISL_T3 | 2026-11-02 07:31 | 2026-11-06 18:31 | Continuous | RS - Removal from Service | ISL-CB-162, ISL-TF-T3B, ISL-TF-T3R | Lodged
WIL_178_VT217 | 2026-11-02 07:31 | 2026-11-06 18:31 | Continuous | RS - Removal from Service | WIL-DCB-188, WIL-DCB-192, WIL-DCB-202, WIL-DCB-222, WIL-VT-VT217 | Lodged
WIL_T8 | 2026-11-02 07:31 | 2026-11-06 18:31 | Continuous | RS - Removal from Service | Reinhausen work. WIL CB, CBL, CT, NCT, NER and TF mtce. Affected equipment of WIL_178_VT217. | Lodged
BEN_220BZ | 2026-11-02 08:00 | 2026-11-02 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 4 Migration | Lodged
BEN_220CBF | 2026-11-02 08:00 | 2026-11-02 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 4 Migration | Lodged
BEN_F_4 | 2026-11-02 08:00 | 2026-11-12 18:00 | Continuous | RS - Removal from Service | BEN 220BZ - Filter 4 Migration | Lodged
HTU_T1 | 2026-11-02 08:00 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
PEN_CB_8612 | 2026-11-02 08:00 | 2026-11-07 18:30 | Continuous | OPE - Open Ended | Place PEN REA into service for the duration of OTA_PEN_5 | Lodged
PEN_T10 | 2026-11-02 08:00 | 2026-11-07 18:30 | Continuous | OPE - Open Ended | Open for duration of OTA_PEN_5 | Lodged
KAW_T12 | 2026-11-04 07:30 | 2026-11-05 18:30 | Continuous | RS - Removal from Service | KAW-CT-592, KAW-NCT-12 | Lodged
OHC_TWZ_4 | 2026-11-04 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | Affected equipment TWZ_2616_2417 & TWZ_T19 | Lodged
OTA_CB_178 | 2026-11-04 07:30 | 2026-11-05 18:30 | Continuous | RS - Removal from Service | OTA-P-CB-178 | Lodged
TWZ_2616_2417 | 2026-11-04 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | TWZ-DS-2564 | Lodged
TWZ_CB_2442 | 2026-11-04 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | Affected equipment TWZ_2616_2417 & TWZ_T19 | Lodged
TWZ_CB_2562 | 2026-11-04 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | Affected equipment TWZ_2616_2417 & TWZ_T19 | Lodged
TWZ_T19 | 2026-11-04 07:30 | 2026-11-06 18:30 | Continuous | RS - Removal from Service | TWZ-CBL-LS19-2162, TWZ-CBL-T19-2162, TWZ-CBL-T19-NER19, TWZ-RES-NER-19, TWZ-TF-LS19 | Lodged
ARG_BLN_1 | 2026-11-04 07:31 | 2026-11-06 18:31 | Continuous | RS - Removal from Service | Affected Equipment of BLN_64_74_87 BLN-DS-64 BLN-DS-67 | Lodged
BLN_64_74_87 | 2026-11-04 07:31 | 2026-11-06 18:31 | Continuous | RS - Removal from Service | BLN-DS-64 BLN-DS-67 | Lodged
BLN_T1 | 2026-11-04 07:31 | 2026-11-06 18:31 | Continuous | RS - Removal from Service | Affected Equipment of BLN_64_74_87 BLN-DS-64 BLN-DS-67 | Lodged
SVL_FDR_2902 | 2026-11-05 07:30 | 2026-11-05 18:30 | Daily | RS - Removal from Service | SVL-CBL-2902 | Lodged
HAY_SC_7_T7 | 2026-11-06 07:30 | 2026-11-17 18:30 | Continuous | RS - Removal from Service | HAY-SC7, HAY-SC7-EXC, HAY-SC7-NCT-7, HAY-SC7-NER, HAY-TF-T7 | Lodged
HLY_SFD_1 | 2026-11-07 07:30 | 2026-11-15 18:30 | Continuous | RS - Removal from Service | NZGP - Protection upgrade on HLY-SFD to enable TKU_WKM_2 duplexing (Both Sat / Sun are primarily for the protection work if this work is do earlier (May 26) these days can be removed. | Lodged
EDG_WAI_2 | 2026-11-08 07:30 | 2026-11-08 18:30 | Daily | RS - Removal from Service | Annual shut | Lodged
WAI_104_114 | 2026-11-08 07:30 | 2026-11-08 18:30 | Daily | RS - Removal from Service | Annual shut | Lodged
WAI_CB_1362 | 2026-11-08 07:30 | 2026-11-08 18:30 | Daily | RS - Removal from Service | Affected Equipment of WAI_T2 Annual shut | Lodged
WAI_T1 | 2026-11-08 07:30 | 2026-11-08 18:30 | Daily | RS - Removal from Service | WAI-CB-102, WAI-CT-102, Annual shut | Lodged
WAI_T2 | 2026-11-08 07:30 | 2026-11-08 18:30 | Daily | RS - Removal from Service | Annual shut | Lodged
WAI_T5 | 2026-11-08 07:30 | 2026-11-08 18:30 | Daily | RS - Removal from Service | WAI-CB-2752, WAI-CB-92, WAI-CBL-2752-2756, WAI-CBL-2752-T5, WAI-DS-2756, WAI-DS-96, WAI-M-CT92, WAI-M-VT92, WAI-TF-T5, WAI-VT-92 | Lodged
WAI_964_2726 | 2026-11-08 07:31 | 2026-11-08 18:31 | Daily | RS - Removal from Service | WAI-DS-2726, WAI-DS-961, WAI-DS-962, WAI-DS-963, WAI-DS-964, WAI-VT-5 | Lodged
WAI_CB_2722 | 2026-11-08 07:31 | 2026-11-08 18:31 | Daily | RS - Removal from Service | WAI-CB-2722, WAI-CBL-2722 | Lodged
MLG_T2 | 2026-11-09 07:00 | 2026-11-14 18:00 | Continuous | RS - Removal from Service | MLG-CB-37, MLG-CBL-37, MLG-NCT-T2, MLG-TF-T2, MLG-VT-37. Affected equipment of HAY_MLG_2, for HAY_110BZ Stage 3C; Bay 180 - Melling cct 2 [CP_HAY_IN_00_00]. | Lodged
FHL_RDF_1 | 2026-11-09 07:30 | 2026-11-11 18:30 | Continuous | RS - Removal from Service | FHL-CB-142, FHL-CT-142, FHL-DS-146, FHL-ES-149, FHL-P-CB-142. RDF-P-CB-92. Pole replacement x1. Re-insulation x2. | Lodged
HAY_SC_9_T9 | 2026-11-09 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | HAY-CBL-T9-C9, HAY-CBL-T9-XT9, HAY-CBL-XT9-VT9A, HAY-SC9, HAY-SC9-EXC, HAY-SC9-NER, HAY-SC9-VT-9A | Lodged
INV_CB_722 | 2026-11-09 07:30 | 2026-11-13 18:30 | Continuous | RS - Removal from Service | INV-P-CB-722 | Lodged
MTM_C_1 | 2026-11-09 07:30 | 2026-11-11 18:30 | Continuous | RS - Removal from Service | Repaint MTM REA 1 | Lodged
ROS_FDR_162 | 2026-11-09 07:30 | 2026-11-14 18:30 | Continuous | RS - Removal from Service | Protection replacement project, ROS-P-CB-162 | Lodged
WIL_T5 | 2026-11-09 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | Reinhausen work. WIL-CBL-852 (T5). Testing 18th + 19th, 12-hour heat soak on 20th. | Lodged
RPO_TNG_1 | 2026-11-09 07:31 | 2026-11-13 18:31 | Continuous | RS - Removal from Service | RPO-DS-333 (bus A), RPO-DS-335 (bus B). RPO-CBL-626-639. Affected equipment of TNG_220BS_A/B. | Lodged
TNG_220BS_A | 2026-11-09 07:31 | 2026-11-09 18:31 | Daily | RS - Removal from Service | TNG-DS-333 (RPO-1) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-220 | Lodged
HTU_T2 | 2026-11-09 08:00 | 2026-11-13 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
OTA_487_547 | 2026-11-09 08:00 | 2026-11-13 18:31 | Continuous | RS - Removal from Service | OTA-DS-523 Headgear refurb | Lodged
OTA_CB_488 | 2026-11-09 08:00 | 2026-11-13 18:31 | Continuous | RS - Removal from Service | Affected Equipment of OTA_487_547 OTA-DS-523 Headgear refurb | Lodged
OTA_CB_538 | 2026-11-09 08:00 | 2026-11-13 18:31 | Continuous | RS - Removal from Service | Affected Equipment of OTA_487_547 OTA-DS-523 Headgear refurb | Lodged
KAW_OHK_1 | 2026-11-09 08:00 | 2026-11-14 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
BOB_T4 | 2026-11-09 08:00 | 2026-11-14 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
PEN_CB_8612 | 2026-11-09 08:00 | 2026-11-14 18:30 | Continuous | OPE - Open Ended | Place PEN REA into service for the duration of OTA_PEN_6 | Lodged
PEN_T10 | 2026-11-09 08:00 | 2026-11-14 18:30 | Continuous | OPE - Open Ended | Open for duration of OTA_PEN_6 | Lodged
HAY_MLG_2 | 2026-11-10 07:00 | 2026-11-14 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3C; Bay 180 - Melling cct 2. No other HAY work on days 1, 4, 5. No other work on associated equipment/lines on day 5 (commissioning). Tower works x3 (B16, B19, B30). | Lodged
MLG_54_94 | 2026-11-10 07:00 | 2026-11-14 18:00 | Continuous | RS - Removal from Service | Affected equipment of HAY_MLG_2, for HAY_110BZ Stage 3C; Bay 180 - Melling cct 2. | Lodged
MLG_T4 | 2026-11-10 07:00 | 2026-11-14 18:00 | Continuous | RS - Removal from Service | Affected equipment of HAY_MLG_2, for HAY_110BZ Stage 3C; Bay 180 - Melling cct 2. | Lodged
AVI_BEN_2 | 2026-11-10 07:30 | 2026-11-11 18:30 | Daily | RS - Removal from Service | BEN-CT-CT532, BEN-CVT-VT9, BEN-DS-536, BEN-ES-539 | Lodged
KPO_TMU_1 | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | RS - Removal from Service | Affected Equipment of TMU_54_48_94 TMU-CAPS-C1, TMU-ES-69, TMU-P-CAPS-C1, TMU-REA-R1 | Lodged
STK_33BS_C1 | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | RS - Removal from Service | STK-CB-2392 does this need entire Bus? | Lodged
STK_C_34 | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | RS - Removal from Service | Affected Equipment of STK_33BS_C1 STK-CB-2392 does this need entire Bus? | Lodged
STK_CB_2248_2374 | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | RS - Removal from Service | Affected Equipment of STK_33BS_C1 STK-CB-2392 does this need entire Bus? | Lodged
STK_CB_2408 | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | RS - Removal from Service | Affected Equipment of STK_33BS_C1 STK-CB-2392 does this need entire Bus? | Lodged
STK_FDR_2352 | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | RS - Removal from Service | Affected Equipment of STK_33BS_C1 STK-CB-2392 does this need entire Bus? | Lodged
TMU_54_48_94 | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | RS - Removal from Service | TMU-CAPS-C1, TMU-ES-69, TMU-P-CAPS-C1, TMU-REA-R1 | Lodged
TMU_C_1 | 2026-11-10 07:30 | 2026-11-13 18:30 | Continuous | RS - Removal from Service | TMU-CAPS-C1, TMU-ES-69, TMU-P-CAPS-C1, TMU-REA-R1 | Lodged
TMU_C_2 | 2026-11-10 07:30 | 2026-11-13 18:30 | Continuous | RS - Removal from Service | TMU-CAPS-C2, TMU-ES-119, TMU-P-CAPS-C2, TMU-REA-R2 | Lodged
TMU_T2 | 2026-11-10 07:30 | 2026-11-10 18:30 | Daily | RS - Removal from Service | Affected Equipment of TMU_54_48_94 TMU-CAPS-C1, TMU-ES-69, TMU-P-CAPS-C1, TMU-REA-R1 | Lodged
TNG_220BS_B | 2026-11-10 07:31 | 2026-11-10 18:31 | Daily | RS - Removal from Service | TNG-DS-335 (RPO-1) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-350 | Lodged
HAY_110BZ | 2026-11-10 08:00 | 2026-11-10 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3C; Bay 180 - Melling cct 2. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-11-10 08:00 | 2026-11-10 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3C; Bay 180 - Melling cct 2. | Lodged
ISL_C_26 | 2026-11-11 07:30 | 2026-11-12 18:30 | Daily | RS - Removal from Service | Affected equipment ISL_T6 | Lodged
ISL_T6 | 2026-11-11 07:30 | 2026-11-12 18:30 | Daily | RS - Removal from Service | ISL-DS-503, ISL-DS-505 | Lodged
RPO_626_634 | 2026-11-11 07:30 | 2026-11-11 18:31 | Daily | RS - Removal from Service | RPO-P-CB-632-CZP | Lodged
BEN_220BZ | 2026-11-11 08:00 | 2026-11-12 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 4 Migration | Lodged
BEN_220CBF | 2026-11-11 08:00 | 2026-11-12 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 4 Migration | Lodged
ATI_WKM_1 | 2026-11-12 07:30 | 2026-11-12 18:30 | Daily | RS - Removal from Service | ATI-CVT-132, ATI-DS-136, ATI-ES-139. Tower works x1 (A114). | Lodged
FHL_RDF_2 | 2026-11-12 07:30 | 2026-11-13 18:30 | Continuous | RS - Removal from Service | FHL-DS-126, FHL-ES-129, FHL-P-CB-122. RDF-P-CB-62. Re-insulation x2. | Lodged
PEN_FDR_2302 | 2026-11-12 07:30 | 2026-11-12 18:30 | Daily | RS - Removal from Service | PEN-CB-2302, PEN-P-CB-2302 | Lodged
HAY_CB_2432 | 2026-11-13 07:30 | 2026-11-13 18:30 | Daily | RS - Removal from Service | HAY-CBL-CB2432-ST7 | Lodged
ISL_FDR_192 | 2026-11-13 07:30 | 2026-11-13 18:30 | Daily | RS - Removal from Service | ISL-CB-192 | Lodged
HAY_110BZ | 2026-11-13 08:00 | 2026-11-13 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3C; Bay 180 - Melling cct 2. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-11-13 08:00 | 2026-11-13 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3C; Bay 180 - Melling cct 2. | Lodged
HAY_110BZ | 2026-11-14 08:00 | 2026-11-14 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3C; Bay 180 - Melling cct 2. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-11-14 08:00 | 2026-11-14 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3C; Bay 180 - Melling cct 2. | Lodged
BPE_687_723 | 2026-11-16 06:30 | 2026-11-16 18:30 | Daily | RS - Removal from Service | Affected equipment of BPE_TKU_2. | Lodged
BPE_TKU_2 | 2026-11-16 06:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | Tower painting x21 (B53-B54, B55A, B56-B73). Affected equipment of TKU_64_67_107. | Lodged
STK_T7 | 2026-11-16 06:30 | 2026-12-11 18:30 | Continuous | RS - Removal from Service | STK T7 Transformer Protection Replacement, MP_STK_00S_0_00 | Lodged
ISL_C_26 | 2026-11-16 06:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | Affected Equipment ISL-CB-252 Pole Replacement, MP_RA5_031_0_00. CY4 Scheduled Maintenance Re-planned. | Lodged
BPE_T15 | 2026-11-16 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | Reinhausen work. BPE CB, CT, DS, ER, ES, NCT, TF, VT mtce. | Lodged
HEN_244_287_297 | 2026-11-16 07:30 | 2026-11-17 18:30 | Continuous | RS - Removal from Service | HEN-DS-254, HEN-DS-274, HEN-DS-287, HEN-VT-1 | Lodged
HEN_CB_288 | 2026-11-16 07:30 | 2026-11-17 18:30 | Continuous | RS - Removal from Service | Affected equipment HEN_244_287_297 & HEN_T1 | Lodged
HEN_HEP_1 | 2026-11-16 07:30 | 2026-11-17 18:30 | Continuous | RS - Removal from Service | Affected equipment HEN_244_287_297 & HEN_T1 | Lodged
HEN_HEP_2 | 2026-11-16 07:30 | 2026-11-17 18:30 | Continuous | RS - Removal from Service | Affected equipment HEN_244_287_297 & HEN_T1 | Lodged
HEN_T1 | 2026-11-16 07:30 | 2026-11-17 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
HLY_TWH_1 | 2026-11-16 07:30 | 2026-11-19 18:30 | Continuous | RS - Removal from Service | Headgear refurbishment project. HLY-CVT-582, HLY-DS-583, HLY-DS-586, HLY-DS-605, HLY-ES-589, HLY-TMN-A0032-20, HLY-TMN-A0039-20 | Lodged
INV_TWI_2 | 2026-11-16 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | Lines extra outage resource heavy | Lodged
PEN_T10 | 2026-11-16 07:30 | 2026-11-18 18:30 | Continuous | RS - Removal from Service | PEN-CBL-T10-LV-N, PEN-CT-782, PEN-CT-NCT10, PEN-P-TF-T10, PEN-TF-T10 | Lodged
CPK_T4 | 2026-11-16 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | CPK-DS-84, CPK-ES-89 | Lodged
CPK_WWD_WIL_2 | 2026-11-16 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | WIL-CT-CT142 (no lines on day 1). WWD-TEE-A0108-0109-00, WWD-TEE-A0109-0110-00, WWD-TEE-A0111-WWDG2-10 | Lodged
KWA_CB_8 | 2026-11-16 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | Affected equipment of KWA_T2 & KWA_WIL_1 | Lodged
KWA_T2 | 2026-11-16 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | KWA-P-TF-T2 | Lodged
KWA_WIL_1 | 2026-11-16 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | KWA-DS-56, KWA-ES-59, WIL-P-CB-162 | Lodged
TKR_WIL_1 | 2026-11-16 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | WIL-CT-CT152. Re-insulation x2. Attachment points. | Lodged
WIL_118_188 | 2026-11-16 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | WIL-CT-CT178, WIL-DCB-128, WIL-DCB-142, WIL-DCB-152, WIL-DCB-162, WIL-DCB-178, WIL-P-CB-178-188, WIL-VT-VT137 | Lodged
TKU_64_67_107 | 2026-11-16 07:31 | 2026-11-16 18:31 | Daily | RS - Removal from Service | TKU-DS-64 (BPE_2) | Lodged
TKU_WKM_2 | 2026-11-16 07:31 | 2026-11-16 18:31 | Daily | RS - Removal from Service | Affected equipment of TKU_64_67_107. | Lodged
BOB_T5 | 2026-11-16 08:00 | 2026-11-21 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
TWH_427_444_454 | 2026-11-17 07:30 | 2026-11-19 18:30 | Continuous | RS - Removal from Service | TWH-CB-428 | Lodged
TWH_CB_428 | 2026-11-17 07:30 | 2026-11-19 18:30 | Continuous | RS - Removal from Service | Affected equipment TWH_427_444_454 & HLY_TWH_1 & TWH_T2 | Lodged
TWH_T2 | 2026-11-17 07:30 | 2026-11-19 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
NPK_T1 | 2026-11-17 07:30 | 2026-11-26 18:30 | Continuous | RS - Removal from Service | NPK_T1 protection replacement [CP_NPK_002_0_00]. Affected equipment of OKN_NPK_ONG_1. | Lodged
OKN_NPK_ONG_1 | 2026-11-17 07:30 | 2026-11-26 18:30 | Continuous | RS - Removal from Service | RSA3 conductor repairs [MP_RA3_03H_0_00]. BPE-ONG-A0366-0367-10, BPE-ONG-A0406-0407-10 | Lodged
TKU_DIS_137 | 2026-11-17 07:31 | 2026-11-26 18:31 | Continuous | OPE - Open Ended | OPE for duration of TKU_T21, to ensure high-tension CB protection to TKU_T22 | Lodged
TKU_DIS_147 | 2026-11-17 07:31 | 2026-11-26 18:31 | Continuous | OPE - Open Ended | OPE for duration of TKU_T21, to ensure high-tension CB protection to TKU_T22 | Lodged
TKU_FDR_1062 | 2026-11-17 07:31 | 2026-11-26 18:31 | Continuous | RS - Removal from Service | TKU-M-CT1062 | Lodged
TKU_T21 | 2026-11-17 07:31 | 2026-11-26 18:31 | Continuous | RS - Removal from Service | TKU-M-VT21, TKU-P-TF-T21 | Lodged
TKU_T22 | 2026-11-17 07:31 | 2026-11-26 18:31 | Continuous | CLO - Close | CLO for the duration of TKU_T21, to maintain TKU 33kV supply. | Lodged
DOB_RFN_IGH_2 | 2026-11-18 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | Affected Equipment of IGH_387_377_344 IGH-VT-VT367 | Lodged
DOB_T11 | 2026-11-18 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | Affected Equipment of IGH_387_377_344 IGH-VT-VT367 | Lodged
DOB_T11_RFN_IGH_2 | 2026-11-18 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | Affected Equipment of IGH_387_377_344 IGH-VT-VT367 | Lodged
IGH_387_377_344 | 2026-11-18 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | IGH-VT-VT367 | Lodged
IGH_KIK_2 | 2026-11-18 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | Affected Equipment of IGH_387_377_344 IGH-VT-VT367 | Lodged
ISL_FDR_122 | 2026-11-18 07:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | ISL-CB-122, ISL-P-CB-122 | Lodged
MPE_FDR_302 | 2026-11-18 07:30 | 2026-11-18 18:30 | Daily | RS - Removal from Service | Revenue metering. MPE-M-CT302 | Lodged
ISL_220BS_D | 2026-11-19 06:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | ISL-DS-505. CY4 Scheduled Maintenance Re-planned. | Lodged
ISL_CB_608 | 2026-11-19 06:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | Affected Equipment ISL-DS-505. CY4 Scheduled Maintenance Re-planned. | Lodged
ISL_CB_658 | 2026-11-19 06:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | Affected Equipment ISL-DS-505. CY4 Scheduled Maintenance Re-planned. | Lodged
ISL_C_21 | 2026-11-19 06:30 | 2026-11-20 18:30 | Continuous | RS - Removal from Service | Affected Equipment ISL-DS-505. CY4 Scheduled Maintenance Re-planned. | Lodged
PEN_CB_2318 | 2026-11-19 07:30 | 2026-11-19 18:30 | Daily | RS - Removal from Service | PEN-CB-2318, PEN-P-CB-2318 | Lodged
ROS_2012_2042_2058 | 2026-11-19 07:30 | 2026-11-19 18:30 | Daily | RS - Removal from Service | Revenue metering. ROS-M-VT23 | Lodged
ROS_CB_2058 | 2026-11-19 07:30 | 2026-11-19 18:30 | Daily | RS - Removal from Service | Affected equipment ROS_2012_2042_2058 | Lodged
ROS_FDR_2012 | 2026-11-19 07:30 | 2026-11-19 18:30 | Daily | RS - Removal from Service | Affected equipment ROS_2012_2042_2058 | Lodged
ROS_FDR_2022 | 2026-11-19 07:30 | 2026-11-19 18:30 | Daily | RS - Removal from Service | Affected equipment ROS_2012_2042_2058 | Lodged
ROS_FDR_2032 | 2026-11-19 07:30 | 2026-11-19 18:30 | Daily | RS - Removal from Service | Affected equipment ROS_2012_2042_2058 | Lodged
ROS_T2 | 2026-11-19 07:30 | 2026-11-19 18:30 | Daily | RS - Removal from Service | Affected equipment ROS_2012_2042_2058 | Lodged
BPE_T10 | 2026-11-20 07:30 | 2026-11-22 18:30 | Continuous | RS - Removal from Service | Reinhausen work. | Lodged
PEN_FDR_2242 | 2026-11-20 07:30 | 2026-11-20 18:30 | Daily | RS - Removal from Service | PEN-CB-2242, PEN-P-CB-2242 | Lodged
HWA_WVY_1 | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | RS - Removal from Service | Affected equipment of WVY site shut (alternate date 29/11/26) | Lodged
WVY_47_134 | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | RS - Removal from Service | Affected equipment of WVY site shut (alternate date 29/11/26) | Lodged
WVY_57_94 | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | RS - Removal from Service | Affected equipment of WVY site shut (alternate date 29/11/26) | Lodged
WVY_CB_112 | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | RS - Removal from Service | Affected equipment of WVY site shut (alternate date 29/11/26) | Lodged
WVY_CB_42 | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | RS - Removal from Service | Affected equipment of WVY site shut (alternate date 29/11/26) | Lodged
WVY_FDR_242 | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | RS - Removal from Service | Affected equipment of WVY site shut (alternate date 29/11/26) | Lodged
WVY_FDR_262 | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | RS - Removal from Service | Affected equipment of WVY site shut (alternate date 29/11/26) | Lodged
WVY_FDR_282 | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | RS - Removal from Service | Affected equipment of WVY site shut (alternate date 29/11/26) | Lodged
WVY_LST_1 | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | RS - Removal from Service | Affected equipment of WVY site shut (alternate date 29/11/26) | Lodged
WVY_RTU_1 | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | RS - Removal from Service | SMS & GPS replacements [CP_RA3_03C_0_00] | Lodged
WVY_T1 | 2026-11-22 09:00 | 2026-11-22 16:00 | Daily | RS - Removal from Service | WVY site shut (alternate date 29/11/26). WVY-TF-T1. | Lodged
MLG_T1 | 2026-11-23 07:00 | 2026-11-28 18:00 | Continuous | RS - Removal from Service | MLG-CB-39, MLG-CBL-39, MLG-TF-T1, MLG-VT-39. MLG T1/T2 CCC & WTI replacement [CP_MLG_00G_0_00]. Affected equipment of HAY_MLG_1, for HAY_110BZ Stage 3D; Bay 200 - Melling cct 1 [CP_HAY_IN_00_00]. | Lodged
HAY_MLG_1 | 2026-11-23 07:00 | 2026-11-28 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3D; Bay 200 - Melling cct 1. No other HAY work on days 1, 5, 6. No other work on associated equipment/lines on day 6 (commissioning). HAY-CB-202. Tower works x6 (B5, B8, B11, B16, B28, B30). | Lodged
MLG_T3 | 2026-11-23 07:00 | 2026-11-28 18:00 | Continuous | RS - Removal from Service | Affected equipment of HAY_MLG_1, for HAY_110BZ Stage 3D; Bay 200 - Melling cct 1. | Lodged
CST_SFD_2 | 2026-11-23 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | SFD-CBL-222-CST2. Tower painting x6 (A99A - A100A, A101-A104) [CP_752_002_0_00]. Tower recoating x13 (A56-A68) [CP_752_005_0_00]. | Lodged
HAY_T24 | 2026-11-23 07:30 | 2026-11-25 18:30 | Continuous | RS - Removal from Service | Reinhausen work. HAY-TF-T24 | Lodged
HTU_T1 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | Affected equipment OTA_HTU_WKM_1 | Lodged
INV_MAN_2 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | INV-MAN-A0277-0278-00, INV-MAN-A0297-10, INV-MAN-A0298-10, INV-MAN-A0348-0349-20, INV-P-CB-632/642, MAN-CB-202, MAN-P-CB-202 | Lodged
NMA_615_737 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | INV-MAN-A0277-0278-00, INV-MAN-A0297-10, INV-MAN-A0298-10, INV-MAN-A0348-0349-20, INV-P-CB-632/642, MAN-CB-202, MAN-P-CB-202 | Lodged
NMA_CB_688 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_615_737 INV-MAN-A0277-0278-00, INV-MAN-A0297-10, INV-MAN-A0298-10, INV-MAN-A0348-0349-20, INV-P-CB-632/642, MAN-CB-202, MAN-P-CB-202 | Lodged
PEN_FDR_2262 | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | RS - Removal from Service | PEN-CB-2262, PEN-P-CB-2262 | Lodged
WIL_T3 | 2026-11-23 07:30 | 2026-12-03 18:30 | Continuous | RS - Removal from Service | WIL CBL mtce. | Lodged
WRK_44_57_197 | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | RS - Removal from Service | WRK-DS-57 (bus), WRK-DS-64 (T3) | Lodged
WRK_CB_198 | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | RS - Removal from Service | Affected equipment of WRK_44_57_197 | Lodged
WRK_FDR_2082 | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | RS - Removal from Service | WRK-CBL-2082-FDR | Lodged
DOB_RFN_IGH_2 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | ca lifting inspect | Lodged
DOB_T11 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | Affected Equipment of DOB_RFN_IGH_2 ca lifting inspect | Lodged
TGA_33BS_A | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | RS - Removal from Service | TGA-BS-33-A | Lodged
TGA_CB_2188 | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | RS - Removal from Service | Affected equipment TGA_33BS_A | Lodged
TGA_CB_2208 | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | RS - Removal from Service | Affected equipment TGA_33BS_A | Lodged
TGA_FDR_2132 | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | RS - Removal from Service | Affected equipment TGA_33BS_A | Lodged
TGA_FDR_2142 | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | RS - Removal from Service | Affected equipment TGA_33BS_A | Lodged
TGA_FDR_2162 | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | RS - Removal from Service | Affected equipment TGA_33BS_A | Lodged
TGA_FDR_2172 | 2026-11-23 07:30 | 2026-11-23 18:30 | Daily | RS - Removal from Service | Affected equipment TGA_33BS_A | Lodged
DVK_T2 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | Affected equipment of WDV_DVK_WPW_1 | Lodged
WDV_DVK_WPW_1 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | Pole replacements x4 | Lodged
WPW_T2 | 2026-11-23 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | Affected equipment of WDV_DVK_WPW_1 | Lodged
KMO_TGA_1 | 2026-11-23 07:30 | 2026-11-25 18:30 | Continuous | RS - Removal from Service | HAI-TGA-ATGAS1-00, HAI-TGA-ATGAS2-00, HAI-TGA-ATGAS3-00, KMO-DS-116, KMO-ES-119 | Lodged
TGA_237_244_264 | 2026-11-23 07:30 | 2026-11-25 18:30 | Continuous | RS - Removal from Service | TGA-BS-110-247-244, TGA-DS-244, TGA-DS-247, TGA-DS-264, TGA-VT-2 | Lodged
TGA_T3 | 2026-11-23 07:30 | 2026-11-25 18:30 | Continuous | RS - Removal from Service | Affected equipment TGA_33BS_A | Lodged
WKM_WRK_1 | 2026-11-23 07:30 | 2026-11-24 18:31 | Continuous | RS - Removal from Service | WRK-DS-114 (WKM_1). Affected equipment of WRK_47_67 | Lodged
WRK_CB_112 | 2026-11-23 07:30 | 2026-11-24 18:31 | Continuous | RS - Removal from Service | WRK-CB-112 (WKM_1) pole replacement [CP_WRK_00U_0_00]. Affected equipment of WKM_WRK_1. | Lodged
BEN_220BZ | 2026-11-23 08:00 | 2026-11-23 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 5 Migration | Lodged
BEN_220CBF | 2026-11-23 08:00 | 2026-11-23 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 5 Migration | Lodged
BEN_F_5 | 2026-11-23 08:00 | 2026-11-27 18:00 | Continuous | RS - Removal from Service | BEN 220BZ - Filter 5 Migration | Lodged
KAW_OHK_1 | 2026-11-23 08:00 | 2026-11-28 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
BPE_TNG_1 | 2026-11-24 07:30 | 2026-12-01 18:30 | Continuous | RS - Removal from Service | BPE-P-CB-752, TNG-DS-316, TNG-ES-319. Protection upgrade [CP_BPE_EH_00_00 + CP_TNG_001_0_00]. Tower painting x23 (A50-A72). | Lodged
MLG_64_104 | 2026-11-24 07:30 | 2026-11-28 18:30 | Continuous | RS - Removal from Service | MLG-DS-104, MLG-DS-64, MLG-ES-79, MLG-VT-67. Affected equipment of HAY_MLG_1. | Lodged
TNG_220BS_A | 2026-11-24 07:31 | 2026-11-24 18:31 | Daily | RS - Removal from Service | TNG-DS-313 (BPE-1) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-220 | Lodged
HAY_110BZ | 2026-11-24 08:00 | 2026-11-24 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3D; Bay 200 - Melling cct 1. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-11-24 08:00 | 2026-11-24 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3D; Bay 200 - Melling cct 1. | Lodged
OTA_PEN_2 | 2026-11-25 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
PEN_110BS_B | 2026-11-25 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | PEN-DS-117, PEN-DS-124, PEN-DS-134, PEN-DS-144, PEN-DS-164, PEN-DS-174, PEN-VT-177 | Lodged
PEN_C_12 | 2026-11-25 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | Affected equipment PEN_110BS_B & OTA_PEN_2 & PEN_C_14 & PEN_T10 | Lodged
PEN_CB_118 | 2026-11-25 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | Affected equipment PEN_110BS_B & OTA_PEN_2 & PEN_C_14 & PEN_T10 | Lodged
PEN_FDR_122 | 2026-11-25 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | Affected equipment PEN_110BS_B & OTA_PEN_2 & PEN_C_14 & PEN_T10 | Lodged
PEN_T10 | 2026-11-25 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
THI_WRK_1 | 2026-11-25 07:30 | 2026-11-26 18:30 | Continuous | RS - Removal from Service | WRK-CT-112, WRK-DS-116, WRK-ES-119 | Lodged
TNG_220BS_B | 2026-11-25 07:31 | 2026-11-25 18:31 | Daily | RS - Removal from Service | TNG-DS-315 (BPE-1) headgear refurbishment [CP_RA3_03F_0_00]. TNG-ES-230 | Lodged
CBG_206_224_236 | 2026-11-26 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | CBG-DS-224, CBG-DS-236 | Lodged
ISL_220BZ | 2026-11-26 07:30 | 2026-11-26 18:30 | Daily | RS - Removal from Service | ISL-P-BZ-220 | Lodged
KPO_BUS_A1 | 2026-11-26 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | KPO-DCB-198, KPO-VT-VT187 | Lodged
KPO_CB_198 | 2026-11-26 07:30 | 2026-11-27 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
CBG_T3 | 2026-11-26 07:31 | 2026-11-27 18:31 | Continuous | RS - Removal from Service | Affected equipment CBG_206_224_236 & HAM_KPO_2 | Lodged
HAM_KPO_2 | 2026-11-26 07:31 | 2026-11-27 18:31 | Continuous | RS - Removal from Service | CBG-DS-206, CBG-ES-209, CBG-ES-239, HAM-ES-139, HAM-KPO-A2-Z-CBL-SHEATH, HAM-P-CB-132 | Lodged
KPO_TMU_1 | 2026-11-26 07:31 | 2026-11-27 18:31 | Continuous | RS - Removal from Service | KPO-TMU-A0019-00, KPO-TMU-A0070-00, TMU-VT-92 | Lodged
BEN_220BZ | 2026-11-26 08:00 | 2026-11-27 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 5 Migration | Lodged
BEN_220CBF | 2026-11-26 08:00 | 2026-11-27 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 5 Migration | Lodged
FHL_T2 | 2026-11-27 07:30 | 2026-12-12 18:30 | Continuous | RS - Removal from Service | FHL-TF-T2. 12-hour heat soak on last day. | Lodged
HAY_110BZ | 2026-11-27 08:00 | 2026-11-27 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3D; Bay 200 - Melling cct 1. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-11-27 08:00 | 2026-11-27 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3D; Bay 200 - Melling cct 1. | Lodged
OTA_PEN_6 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | RS - Removal from Service | OTA-CB-522, OTA-CT-522, PEN-CB-752, PEN-CT-752, PEN-CVT-752, PEN-DS-756, PEN-ES-759, PEN-P-CB-752 | Lodged
PEN_220BS_A | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | RS - Removal from Service | PEN-DS-697, PEN-DS-704, PEN-DS-714, PEN-DS-734, PEN-DS-744, PEN-DS-754, PEN-DS-757, PEN-DS-764, PEN-ES-750 | Lodged
PEN_C_1 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | RS - Removal from Service | PEN-CAPS-C1, PEN-CB-732, PEN-CT-C1, PEN-ES-739, PEN-REA-C1 | Lodged
PEN_CB_698 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | RS - Removal from Service | PEN-P-CB-698 | Lodged
PEN_CB_758 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | RS - Removal from Service | PEN-P-CB-758 | Lodged
PEN_CB_848 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | RS - Removal from Service | PEN-CB-848 | Lodged
PEN_CB_8612 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | OPE - Open Ended | Place PEN REA into service for the duration of OTA_PEN_6 | Lodged
PEN_T5 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | RS - Removal from Service | Affected equipment PEN_220BS_A & OTA_PEN_6 & PEN_C_1 & PEN_CB_698 & PEN_CB_758 & PEN_CB_848 & PEN_T10 | Lodged
PEN_T6 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | RS - Removal from Service | Affected equipment PEN_220BS_A & OTA_PEN_6 & PEN_C_1 & PEN_CB_698 & PEN_CB_758 & PEN_CB_848 & PEN_T10 | Lodged
PEN_T7 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | RS - Removal from Service | Affected equipment PEN_220BS_A & OTA_PEN_6 & PEN_C_1 & PEN_CB_698 & PEN_CB_758 & PEN_CB_848 & PEN_T10, PEN-CB-2482B, PEN-CB-2482A | Lodged
PEN_T8 | 2026-11-28 07:30 | 2026-11-29 18:30 | Continuous | RS - Removal from Service | PEN-CB-2332A, PEN_220BS_A & OTA_PEN_6 & PEN_C_1 & PEN_CB_698 & PEN_CB_758 & PEN_CB_848 & PEN_T10, PEN-CB-2332B | Lodged
HAY_110BZ | 2026-11-28 08:00 | 2026-11-28 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3D; Bay 200 - Melling cct 1. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-11-28 08:00 | 2026-11-28 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3D; Bay 200 - Melling cct 1. | Lodged
CBG_T4 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | CBG-CBL-T4-2752, CBG-CBL-T4-LS4, CBG-TF-LS4, CBG-TF-T4, CBG-VT-242, CBG-VT-2822 | Lodged
HAM_KPO_1 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | HAM-KPO-A0051-00, HAM-KPO-A1-Z-CBL-SHEATH, HAM-P-CB-112 | Lodged
HAY_F_4 | 2026-11-30 07:30 | 2026-12-11 18:30 | Continuous | RS - Removal from Service | S4.WA-Z1.Q1, S4.WA-Z1.Z1.Q1, S4.WA-Z1.Z1.R1A, S4.WA-Z1.Z1.R1B, S4.WA-Z1.Z1.R1C, S4.WA-Z1.Z2.Q1, S4.WA-Z1.Z2.R1A, S4.WA-Z1.Z2.R1B, S4.WA-Z1.Z2.R1C HVDC HAY-DC Pole 2 Era AC Disconnector/Earth Switch Refurbishments | Lodged
HIN_44_64_124 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | HIN-DS-124, HIN-DS-44, HIN-DS-64, HIN-VT-62 | Lodged
HIN_KPO_1 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | HIN-KPO-A0001-00, HIN-KPO-A0069-0070-10 | Lodged
HIN_T1 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | HIN-CB-62, HIN-CBL-T1-3122, HIN-CBL-T1-LS1, HIN-NER-1, HIN-P-TF-T1, HIN-TF-LST1 | Lodged
HIN_T2 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | HIN-CB-42, HIN-CBL-T2-3222, HIN-CBL-T2-LS2, HIN-NER-2, HIN-P-TF-T2, HIN-TF-LST2, HIN-TF-T2R, HIN-TF-T2Y | Lodged
HTU_T2 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | Affected equipment OTA_HTU_WKM_2 | Lodged
NMA_T2 | 2026-11-30 07:30 | 2026-12-11 18:30 | Continuous | RS - Removal from Service | NMA-CB-722, NMA-CBL-1132, NMA-CT-CT722, NMA-DS-723, NMA-TF-T2, NMA-VT-VT2 | Lodged
TMN_454_466_494 | 2026-11-30 07:30 | 2026-12-02 18:30 | Continuous | RS - Removal from Service | TMN-DS-466 (TWH-1) headgear refurbishment [CP_RA3_03F_0_00]. TMN 220kV bus insulator replacements [CP_TMN_001_0_00]. | Lodged
TMN_CB_458 | 2026-11-30 07:30 | 2026-12-02 18:30 | Continuous | RS - Removal from Service | Affected equipment of TMN_454_466_494 | Lodged
TMN_T8 | 2026-11-30 07:30 | 2026-12-02 18:30 | Continuous | RS - Removal from Service | TMN-TF-T8 [CP_TMN_77_00_00]. Reinhausen work. Affected equipment of TMN_454_466_494 [CP_RA3_03F_0_00, CP_TMN_001_0_00]. | Lodged
CPK_FDR_2832 | 2026-11-30 07:30 | 2026-12-03 18:30 | Continuous | RS - Removal from Service | Affected equipment of CPK_T12 | Lodged
CPK_T12 | 2026-11-30 07:30 | 2026-12-03 18:30 | Continuous | RS - Removal from Service | CPK-CBL-2212, CPK-CBL-LK2827-LS12, CPK-CBL-T12-LK2827, CPK-NCT-T12, CPK-TF-LS12, CPK-TF-T12 | Lodged
FHL_WPW_1 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | FHL-CT-152, FHL-DS-156, FHL-ES-159, FHL-P-CB-152. WPW-ES-79. Pole replacements x12. Condition assessments. | Lodged
ALB_HEN_3 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | ALB-HPI-A0403-20, ALB-HPI-A0405-0406-20, ALB-HPI-A0416-00, ALB-HPI-A0435-0436-20, ALB-HPI-A0435-30, HEN-DS-456, HEN-MDN-A0013-20, HEN-MDN-A0018-0019-20, HEN-MDN-A0029-00 | Lodged
HEN_414_447_487 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | Headgear refurbishment project. HEN-DS-467 | Lodged
HEN_C_1 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | Affected equipment HEN_414_447_487 & ALB_HEN_3 & HEN_OTA_1 & HEN_T1 | Lodged
HEN_CB_488 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | Affected equipment HEN_414_447_487 & ALB_HEN_3 & HEN_OTA_1 & HEN_T1 | Lodged
HEN_OTA_1 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | HEN-CB-462, HEN-CT-462, HEN-CVT-462, HEN-DS-466, HEN-ES-469, HEN-OTA-A0003-00, HEN-OTA-A0004-00, HEN-OTA-A0005-00, HEN-OTA-A0006-00, HEN-OTA-A0007-00, HEN-OTA-A0009-00, HEN-OTA-A0010-00, HEN-OTA-A0010-10, HEN-OTA-A0011-00, HEN-OTA-A0012-00, HEN-OTA-A0013-00, HEN-OTA-A0013-10, HEN-OTA-A0014-00, HEN-OTA-A0020-00, HEN-OTA-A0022-00, HEN-OTA-A0024-00, HEN-OTA-A0028-00, HEN-OTA-A0029-00, HEN-OTA-A0031-00, HEN-OTA-A0034-10, HEN-OTA-A0037-10, HEN-OTA-A0052-00, HEN-OTA-A0056-10, HEN-, OTA-VT-VT1272 | Lodged
HEN_T1 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | HEN-CB-432 | Lodged
HEN_T2 | 2026-11-30 07:30 | 2026-12-04 18:30 | Continuous | RS - Removal from Service | Affected equipment HEN_414_447_487 & ALB_HEN_3 & HEN_OTA_1 & HEN_T1 | Lodged
HLY_CB_462 | 2026-11-30 07:31 | 2026-12-04 18:31 | Continuous | RS - Removal from Service | Headgear refurbishment HLY-DS-603 | Lodged
NMA_687_835 | 2026-11-30 07:31 | 2026-12-04 18:31 | Continuous | RS - Removal from Service | NMA-DS-737 | Lodged
NMA_CB_738 | 2026-11-30 07:31 | 2026-12-04 18:31 | Continuous | RS - Removal from Service | Affected equipment NMA_687_835 | Lodged
BEN_220BZ | 2026-11-30 08:00 | 2026-11-30 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 6 Migration | Lodged
BEN_220CBF | 2026-11-30 08:00 | 2026-11-30 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 6 Migration | Lodged
BEN_F_6 | 2026-11-30 08:00 | 2026-12-04 18:00 | Continuous | RS - Removal from Service | BEN 220BZ - Filter 6 Migration | Lodged
TMN_TWH_1 | 2026-12-02 07:30 | 2026-12-11 18:30 | Continuous | RS - Removal from Service | HLY-TMN-A0070-20, HLY-TMN-A0078-20, HLY-TMN-A0168-20, HLY-TMN-A0170-20, HLY-TMN-A0173-20, HLY-TMN-A0174-20, HLY-TMN-A0176-20, HLY-TMN-A0178-20, HLY-TMN-A0179-20, HLY-TMN-A0181-20, HLY-TMN-A0183-20, HLY-TMN-A0186-20, HLY-TMN-A0191-20, HLY-TMN-A0193-20, HLY-TMN-A0194-20, HLY-TMN-A0196-20, HLY-TMN-A0200-20 | Lodged
CPK_T3 | 2026-12-03 07:30 | 2026-12-03 18:30 | Daily | RS - Removal from Service | CPK-CBL-2252 [CP_CPK_00L_0_00] | Lodged
BEN_220BZ | 2026-12-03 08:00 | 2026-12-04 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 6 Migration | Lodged
BEN_220CBF | 2026-12-03 08:00 | 2026-12-04 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 6 Migration | Lodged
BPE_PRM_HAY_2 | 2026-12-07 07:30 | 2026-12-12 18:30 | Continuous | RS - Removal from Service | HAY CT maintenance. Tower painting (B5-B7) [CP_768_002_0_00]. Tower recoating (B280-B288, B290) [CP_768_004_0_00]. | Lodged
CST_SFD_3 | 2026-12-07 07:30 | 2026-12-18 18:30 | Continuous | RS - Removal from Service | SFD-CBL-82-CST3. Tower painting x6 (A99-A100, A101-A104) [CP_752_002_0_00]. Tower recoating x13 (A56-A68) [CP_752_005_0_00]. | Lodged
NMA_220BS_A3 | 2026-12-07 07:30 | 2026-12-10 18:30 | Continuous | RS - Removal from Service | pdm maint. | Lodged
NMA_CB_708 | 2026-12-07 07:30 | 2026-12-10 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A3 pdm maint. | Lodged
NMA_CB_718 | 2026-12-07 07:30 | 2026-12-10 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A3 pdm maint. | Lodged
OTA_ROS_2 | 2026-12-07 07:30 | 2026-12-11 18:30 | Continuous | RS - Removal from Service | OTA-CT-172, OTA-P-CB-172, OTA-PEN-B0002A-0003-20, OTA-PEN-B0003-0004-20, OTA-PEN-B0004-0005A-10, OTA-PEN-B0011A-0012-10, OTA-PEN-B0012-0013-20, OTA-PEN-B0013-0014-20, OTA-PEN-B0015-0016-20, OTA-PEN-B0016-0017-20, OTA-PEN-B0017-0018-20, OTA-PEN-B0018-0019-20, OTA-PEN-B0019-0020-20, OTA-PEN-B2-Z-CBL-SHEATH, PEN-ROS-A0025-20, PEN-ROS-A0037-20, ROS-P-CB-82 | Lodged
PRM_T2 | 2026-12-07 07:30 | 2026-12-12 19:29 | Continuous | RS - Removal from Service | PRM-M-CT2242, PRM-M-VT2242. Affected equipment of BPE_PRM_HAY_2. | Lodged
SVL_FDR_2742 | 2026-12-07 07:30 | 2026-12-07 18:30 | Daily | RS - Removal from Service | SVL-CBL-2742 | Lodged
KIK_STK_2 | 2026-12-07 07:30 | 2026-12-11 18:30 | Continuous | RS - Removal from Service | reinsulating KIK-STK-A0064-20, KIK-STK-A0065-20, KIK-STK-A0066-20, KIK-STK-A0067-20, KIK-STK-A0068-20, KIK-STK-A0069-20, KIK-STK-A0079-20, KIK-STK-A0080-20, KIK-STK-A0082-20, KIK-STK-A0092-20, KIK-STK-A0096-20, KIK-STK-A0098-20 | Lodged
ISL_KIK_1 | 2026-12-07 07:30 | 2026-12-12 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
ISL_CB_668 | 2026-12-07 07:30 | 2026-12-11 18:30 | Continuous | RS - Removal from Service | ISL-DS-667, ISL-DS-677, ISL-P-CB-668 | Lodged
ISL_FDR_172 | 2026-12-07 07:30 | 2026-12-11 18:30 | Continuous | RS - Removal from Service | ISL-CB-172 | Lodged
ISL_FDR_272 | 2026-12-07 07:30 | 2026-12-11 18:30 | Continuous | RS - Removal from Service | ISL-CB-272, ISL-DS-273, ISL-DS-275, ISL-DS-276 | Lodged
ISL_220BS_A | 2026-12-07 07:30 | 2026-12-09 18:30 | Continuous | RS - Removal from Service | affected equipment ISL-DS-667, ISL-DS-677, ISL-P-CB-668 | Lodged
ISL_66BS_A | 2026-12-07 07:30 | 2026-12-09 18:30 | Continuous | RS - Removal from Service | ISL-CB-272, ISL-DS-273, ISL-DS-275, ISL-DS-276 | Lodged
ISL_CB_708 | 2026-12-07 07:30 | 2026-12-09 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_66BS_A ISL-CB-272, ISL-DS-273, ISL-DS-275, ISL-DS-276 | Lodged
ISL_CB_768 | 2026-12-07 07:30 | 2026-12-09 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_66BS_A ISL-CB-272, ISL-DS-273, ISL-DS-275, ISL-DS-276 | Lodged
DVK_T1 | 2026-12-07 07:31 | 2026-12-11 18:31 | Continuous | RS - Removal from Service | DVK-P-TF-T1, DVK-TF-T1 [CP_DVK_70_00_00]. Affected equipment of WDV_DVK_WPW_2. | Lodged
WDV_DVK_WPW_2 | 2026-12-07 07:31 | 2026-12-11 18:31 | Continuous | RS - Removal from Service | Pole replacements x4 [CP_RA4_01T_0_00]. | Lodged
WPW_T1 | 2026-12-07 07:31 | 2026-12-11 18:31 | Continuous | RS - Removal from Service | WPW-P-TF-T1 [CP_WPW_00L_0_00]. Affected equipment of WDV_DVK_WPW_2. | Lodged
BEN_220BZ | 2026-12-07 08:00 | 2026-12-07 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 7 Migration | Lodged
BEN_220CBF | 2026-12-07 08:00 | 2026-12-07 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 7 Migration | Lodged
BEN_F_7 | 2026-12-07 08:00 | 2026-12-12 18:00 | Continuous | RS - Removal from Service | BEN 220BZ - Filter 7 Migration | Lodged
HEN_HPI_1 | 2026-12-07 08:00 | 2026-12-11 18:30 | Continuous | RS - Removal from Service | Lines maintenance | Lodged
MPE_CB_252 | 2026-12-07 08:00 | 2026-12-07 22:00 | Daily | OPE - Open Ended | System split for the duration of BRB_HPI_1 | Lodged
MPE_CB_292 | 2026-12-07 08:00 | 2026-12-07 22:00 | Daily | OPE - Open Ended | System split for the duration of BRB_HPI_1 | Lodged
BRB_HPI_1 | 2026-12-07 08:00 | 2026-12-12 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
KAW_OHK_1 | 2026-12-07 08:00 | 2026-12-12 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
MPE_CB_252 | 2026-12-08 06:00 | 2026-12-10 22:00 | Daily | OPE - Open Ended | System split for the duration of BRB_HPI_1 | Lodged
MPE_CB_292 | 2026-12-08 06:00 | 2026-12-10 22:00 | Daily | OPE - Open Ended | System split for the duration of BRB_HPI_1 | Lodged
BPE_110BS_B | 2026-12-08 06:30 | 2026-12-08 18:30 | Daily | RS - Removal from Service | BPE_110BS_B | Lodged
BPE_CB_48 | 2026-12-08 06:30 | 2026-12-08 18:30 | Daily | RS - Removal from Service | Affected equipment of BPE_110BS_B | Lodged
BPE_T2 | 2026-12-08 06:30 | 2026-12-15 18:30 | Continuous | RS - Removal from Service | BPE-TF-T2 (CP_BPE_EH_00_00) | Lodged
HAY_R1 | 2026-12-08 07:00 | 2026-12-15 18:00 | Continuous | RS - Removal from Service | Affected equipment of HAY_T1, for HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. | Lodged
HAY_SC_1 | 2026-12-08 07:00 | 2026-12-15 18:00 | Continuous | RS - Removal from Service | Affected equipment of HAY_T1, for HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. | Lodged
HAY_T1 | 2026-12-08 07:00 | 2026-12-15 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3I; Bay 70 - Interconnector T1 (CP_HAY_IN_00_00). No other HAY work on days 1, 7, 8. No other work on associated equipment on day 8 (commissioning). HAY 11kV surge arrestor replacement (CP_RA4_03C_0_00). HAY-CT-442, HAY-CT-72, HAY-SA-1C, HAY-TF-T1, HAY-VT-VT14R. | Lodged
IGH_KIK_2 | 2026-12-08 07:30 | 2026-12-10 18:30 | Continuous | RS - Removal from Service | KIK-CB-122 GH-WPT-B0022-00, IGH-WPT-B0020-00, IGH-WPT-B0023-00, IGH-WPT-B0024-00, IGH-WPT-B0026-00, IGH-WPT-B0025-00, IGH-WPT-B0021-00 | Lodged
SVL_FDR_2762 | 2026-12-08 07:30 | 2026-12-08 18:30 | Daily | RS - Removal from Service | SVL-CBL-2762 | Lodged
TIM_T3 | 2026-12-08 07:30 | 2026-12-10 18:30 | Continuous | RS - Removal from Service | TIM-CB-2752, TIM-CBL-T3-CB2752, TIM-CBL-T3-NER3, TIM-CT-CT92, TIM-P-TF-T3, TIM-RES-NER3, TIM-TF-T3, TIM-VT-VT2752 | Lodged
WHU_T3 | 2026-12-08 07:30 | 2026-12-09 18:30 | Continuous | RS - Removal from Service | WHU-TF-T3 | Lodged
WHU_WKO_1 | 2026-12-08 07:30 | 2026-12-09 18:30 | Continuous | RS - Removal from Service | WKO-CB-552 | Lodged
WRD_T7 | 2026-12-08 07:30 | 2026-12-10 18:30 | Continuous | RS - Removal from Service | WRD-CBL-ET7-NER7, WRD-CBL-T7-ET7, WRD-CBL-T7-H27, WRD-CT-NCT7, WRD-NCTD-T7, WRD-RES-NER7, WRD-TF-ET7, WRD-TF-T7 | Lodged
HAY_110BZ | 2026-12-08 08:00 | 2026-12-08 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-12-08 08:00 | 2026-12-08 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. | Lodged
ISL_220BS_F | 2026-12-10 07:30 | 2026-12-11 18:30 | Continuous | RS - Removal from Service | affected equipment ISL-DS-667, ISL-DS-677, ISL-P-CB-668 | Lodged
ISL_66BS_C | 2026-12-10 07:30 | 2026-12-11 18:30 | Continuous | RS - Removal from Service | ISL-CB-272, ISL-DS-273, ISL-DS-275, ISL-DS-276 | Lodged
ISL_CB_728 | 2026-12-10 07:30 | 2026-12-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_66BS_C ISL-CB-272, ISL-DS-273, ISL-DS-275, ISL-DS-276 | Lodged
ISL_CB_748 | 2026-12-10 07:30 | 2026-12-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_66BS_C ISL-CB-272, ISL-DS-273, ISL-DS-275, ISL-DS-276 | Lodged
MPE_CB_252 | 2026-12-11 06:00 | 2026-12-11 18:30 | Daily | OPE - Open Ended | System split for the duration of BRB_HPI_1 | Lodged
MPE_CB_292 | 2026-12-11 06:00 | 2026-12-11 18:30 | Daily | OPE - Open Ended | System split for the duration of BRB_HPI_1 | Lodged
BEN_220BZ | 2026-12-11 08:00 | 2026-12-12 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 7 Migration | Lodged
BEN_220CBF | 2026-12-11 08:00 | 2026-12-12 18:00 | Daily | RS - Removal from Service | BEN 220BZ - Filter 7 Migration | Lodged
BPE_PRM_HAY_2 | 2026-12-14 07:30 | 2026-12-17 18:30 | Continuous | RS - Removal from Service | HAY CT maintenance. Tower painting (B5-B7) [CP_768_002_0_00]. Tower recoating (B280-B288, B290) [CP_768_004_0_00]. | Lodged
EDG_OWH_2 | 2026-12-14 07:30 | 2026-12-18 18:30 | Continuous | RS - Removal from Service | ARI-EDG-A0387-00, ARI-EDG-A0403-00, ARI-EDG-A0443-00, ARI-EDG-A0454-00, ARI-EDG-A0465-00, ARI-EDG-B0438-00, ARI-EDG-B0468-00, ARI-EDG-B0492-00, OWH-DEV-A0616-00 | Lodged
INV_NMA_1 | 2026-12-14 07:30 | 2026-12-18 18:30 | Continuous | RS - Removal from Service | Change to INV_NMA_1 for 5 Days - INV-DS-775, 776 DS Headgear Project | Lodged
OWH_82_92_107 | 2026-12-14 07:30 | 2026-12-18 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
OWH_T1 | 2026-12-14 07:30 | 2026-12-18 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
PRM_T2 | 2026-12-14 07:30 | 2026-12-17 18:30 | Continuous | RS - Removal from Service | Affected equipment of BPE_PRM_HAY_2. | Lodged
KIK_STK_2 | 2026-12-14 07:30 | 2026-12-17 18:30 | Continuous | RS - Removal from Service | KIK-CVT-VT332, KIK-DS-336, KIK-ES-339, KIK-P-CB-332, KIK-STK-A0064-20, KIK-STK-A0065-20, KIK-STK-A0066-20, KIK-STK-A0067-20, KIK-STK-A0068-20, KIK-STK-A0069-20, KIK-STK-A0079-20, KIK-STK-A0080-20, KIK-STK-A0082-20, KIK-STK-A0092-20, KIK-STK-A0096-20, KIK-STK-A0098-20, KIK-STK-A0100-20, KIK-STK-A0102-20, KIK-STK-A0104-20, KIK-STK-A0115-20, STK-CVT-VT772, STK-DS-776, STK-ES-779, STK-P-CB-772 | Lodged
FHL_WPW_2 | 2026-12-14 07:31 | 2026-12-18 18:31 | Continuous | RS - Removal from Service | FHL-CT-132, FHL-DS-136, FHL-ES-139, FHL-P-CB-132. Pole replacements x5. Condition assessments. | Lodged
HOB_PEN_1 | 2026-12-14 07:31 | 2026-12-17 18:30 | Continuous | RS - Removal from Service | HOB-VT-VT182, PEN-DS-866, PEN-ES-8649, PEN-ES-8669, PEN-ES-869, PEN-REA-862, PEN-VT-CVT862 | Lodged
PAK_PEN_3 | 2026-12-14 07:31 | 2026-12-17 18:30 | Continuous | RS - Removal from Service | PEN-DS-856, PEN-ES-8549, PEN-ES-859, PEN-VT-CVT852 | Lodged
PEN_220BS_D | 2026-12-14 07:31 | 2026-12-17 18:30 | Continuous | RS - Removal from Service | PEN-DS-724, PEN-DS-837, PEN-DS-847, PEN-DS-854, PEN-DS-864, PEN-ES-830, PEN-ES-840, PEN-ES-8470 | Lodged
PEN_CB_698 | 2026-12-14 07:31 | 2026-12-17 18:30 | Continuous | RS - Removal from Service | PEN-P-CB-698 | Lodged
PEN_CB_828 | 2026-12-14 07:31 | 2026-12-17 18:30 | Continuous | RS - Removal from Service | PEN-CB-828 | Lodged
PEN_CB_848 | 2026-12-14 07:31 | 2026-12-17 18:30 | Continuous | RS - Removal from Service | PEN-CB-848 | Lodged
PEN_CB_8612 | 2026-12-14 07:31 | 2026-12-17 18:30 | Continuous | RS - Removal from Service | Affected equipment PEN_220BS_D & HOB_PEN_1 & PAK_PEN_3 & PEN_CB_698 & PEN_CB_828 & PEN_CB_848 & PEN_T10 | Lodged
PEN_T10 | 2026-12-14 07:31 | 2026-12-17 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
ARI_HAM_1 | 2026-12-14 07:31 | 2026-12-18 18:31 | Continuous | OPE - Open Ended | System split for the duration of HAM_WKM_1 | Lodged
ARI_HAM_2 | 2026-12-14 07:31 | 2026-12-18 18:31 | Continuous | OPE - Open Ended | System split for the duration of HAM_WKM_1 | Lodged
HAM_417_437_497 | 2026-12-14 07:31 | 2026-12-18 18:31 | Continuous | RS - Removal from Service | HAM-DS-437 | Lodged
HAM_DIS_447 | 2026-12-14 07:31 | 2026-12-18 18:31 | Continuous | CLO - Close | Closed for the duration of HAM 417_437_497 bus outage | Lodged
HAM_WKM_1 | 2026-12-14 07:31 | 2026-12-18 18:31 | Continuous | RS - Removal from Service | HAM-CT-412, HAM-CVT-2, HAM-DEV-A0509-20, HAM-DEV-A0512-20, HAM-DS-416, HAM-ES-419, HAM-SA-412, OTA-WKM-C0188-00, OTA-WKM-C0194-00 | Lodged
KPO_TMU_1 | 2026-12-14 07:31 | 2026-12-18 18:31 | Continuous | OPE - Open Ended | System split for the duration of HAM_WKM_1 | Lodged
MDN_257_267_297 | 2026-12-14 08:00 | 2026-12-16 18:30 | Continuous | RS - Removal from Service | MDN-DS-267, MDN-DS-274, MDN-DS-294, MDN-DS-297 | Lodged
MDN_CB_308 | 2026-12-14 08:00 | 2026-12-16 18:30 | Continuous | RS - Removal from Service | Affected equipment MDN_257_267_297 & MDN_MPE_1 | Lodged
MDN_MPE_1 | 2026-12-14 08:00 | 2026-12-16 18:30 | Continuous | RS - Removal from Service | MDN-CT-292, MDN-DS-296, MDN-ES-299, MDN-MPE-A0012-0013-00, MDN-MPE-A0013-0014-00, MDN-MPE-A0054-0055-00, MDN-MPE-A0074-0075-10, MDN-MPE-A0075-0076-10, MDN-MPE-A0076-0077-10, MDN-MPE-A0079-0080-10, MDN-MPE-A0082-0083-10, MDN-MPE-A0084-MPEG5-10, MDN-P-CB-292, MDN-VT-VT292, MPE-DS-316, MPE-ES-319, MPE-P-CB-312 | Lodged
MDN_T5 | 2026-12-14 08:00 | 2026-12-16 18:30 | Continuous | RS - Removal from Service | Affected equipment MDN_257_267_297 & MDN_MPE_1 | Lodged
MPE_CB_252 | 2026-12-14 08:00 | 2026-12-14 22:00 | Daily | OPE - Open Ended | System split for HPI_MDN | Lodged
MPE_CB_292 | 2026-12-14 08:00 | 2026-12-14 22:00 | Daily | OPE - Open Ended | System split for HPI_MDN | Lodged
HAY_110BZ | 2026-12-14 08:00 | 2026-12-14 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-12-14 08:00 | 2026-12-14 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. | Lodged
HPI_MDN_1 | 2026-12-14 08:00 | 2026-12-19 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
MPE_CB_252 | 2026-12-15 06:00 | 2026-12-17 22:00 | Continuous | OPE - Open Ended | System split for HPI_MDN | Lodged
MPE_CB_292 | 2026-12-15 06:00 | 2026-12-17 22:00 | Continuous | OPE - Open Ended | System split for HPI_MDN | Lodged
KIK_STC_2A | 2026-12-15 07:30 | 2026-12-15 18:30 | Daily | RS - Removal from Service | KIK-CAPS-K11-C1, KIK-CAPS-K11-C2 | Lodged
HAY_110BZ | 2026-12-15 08:00 | 2026-12-15 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2026-12-15 08:00 | 2026-12-15 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3I; Bay 70 - Interconnector T1. | Lodged
KMO_127_167_177 | 2026-12-16 07:30 | 2026-12-18 18:31 | Continuous | RS - Removal from Service | KMO-CB-178, KMO-CT-178 | Lodged
KMO_CB_138 | 2026-12-16 07:30 | 2026-12-18 18:31 | Continuous | RS - Removal from Service | Affected equipment KMO_127_167_177 & KMO_MTM_TGA_2 | Lodged
KMO_CB_178 | 2026-12-16 07:30 | 2026-12-18 18:31 | Continuous | RS - Removal from Service | Affected equipment KMO_127_167_177 & KMO_MTM_TGA_2 | Lodged
KMO_MTM_TGA_2 | 2026-12-16 07:30 | 2026-12-18 18:31 | Continuous | RS - Removal from Service | HAI-MTM-B0020-0021-10 | Lodged
MPE_CB_252 | 2026-12-18 06:00 | 2026-12-18 18:30 | Daily | OPE - Open Ended | System split for HPI_MDN | Lodged
MPE_CB_292 | 2026-12-18 06:00 | 2026-12-18 18:30 | Daily | OPE - Open Ended | System split for HPI_MDN | Lodged
IGH_ROB_2 | 2026-12-21 07:30 | 2026-12-22 18:30 | Daily | RS - Removal from Service | IGH-P-CB-382, ROB-P-CB-502 | Lodged
LIV_NWD_1 | 2026-12-21 07:30 | 2026-12-23 18:30 | Continuous | RS - Removal from Service | CA lifting | Lodged
HAY_CB_2472 | 2026-12-23 07:30 | 2026-12-24 18:30 | Daily | RS - Removal from Service | HAY-CBL-CB2472-ST8 | Lodged
HAY_R5 | 2027-01-05 07:30 | 2027-01-07 18:30 | Continuous | RS - Removal from Service | HAY-CB-R52, HAY-ES-R559, HAY-ES-R59, HAY-REA-R5 | Lodged
HWB_SDN_1 | 2027-01-05 07:30 | 2027-01-12 18:30 | Continuous | RS - Removal from Service | HWB-SDN-A0003-00, HWB-SDN-A0003-10, HWB-SDN-A0004-00, HWB-SDN-A0004-10, HWB-SDN-A0019-00, HWB-SDN-A0021-00, HWB-SDN-A0023-00, HWB-SDN-A0025-00, HWB-SDN-A0031-00, HWB-SDN-A0032-00 | Lodged
TKU_WKM_1 | 2027-01-11 07:00 | 2027-05-14 18:30 | Continuous | RS - Removal from Service | TKU-WKM Duplexing project. (CP_VAR_1DF_0_00) | Lodged
BRY_C_7A | 2027-01-11 07:30 | 2027-01-15 18:30 | Continuous | RS - Removal from Service | Affected equipment BRY_T7 | Lodged
BRY_T7 | 2027-01-11 07:30 | 2027-01-15 18:30 | Continuous | RS - Removal from Service | BRY-CB-2002, BRY-DS-574, BRY-DS-884, BRY-DS-887, BRY-P-CAPS-C7A, BRY-REA-C7A | Lodged
CST_HUI_1 | 2027-01-11 07:30 | 2027-01-22 18:30 | Continuous | RS - Removal from Service | Tower recoating x10 (A1-A10) [CP_750_001_0_00]. | Lodged
HLY_357_524_644 | 2027-01-11 07:30 | 2027-01-12 18:30 | Continuous | RS - Removal from Service | HLY-DS-644 | Lodged
HLY_CB_522 | 2027-01-11 07:30 | 2027-01-12 18:30 | Continuous | RS - Removal from Service | Affected equipment HLY_357_524_644 | Lodged
HLY_CB_582 | 2027-01-11 07:30 | 2027-01-12 18:30 | Continuous | RS - Removal from Service | Affected equipment HLY_357_524_644 | Lodged
HLY_CB_642 | 2027-01-11 07:30 | 2027-01-12 18:30 | Continuous | RS - Removal from Service | Affected equipment HLY_357_524_644 | Lodged
GFD_T6 | 2027-01-12 07:00 | 2027-02-01 18:00 | Continuous | RS - Removal from Service | GFD-CBL-2152-LS6, GFD-CBL-T6-2152, GFD-CBL-T6-NER6, GFD-CBL-TS-T6, GFD-DS-94, GFD-ES-99, GFD-RES-NER6, GFD-TF-LS-LS6, GFD-TF-T6, GFD-VT-92 | Lodged
GFD_HAY_1 | 2027-01-12 07:00 | 2027-02-01 18:00 | Continuous | RS - Removal from Service | Affected Equipment of GFD_T6 GFD-CBL-2152-LS6, GFD-CBL-T6-2152, GFD-CBL-T6-NER6, GFD-CBL-TS-T6, GFD-DS-94, GFD-ES-99, GFD-RES-NER6, GFD-TF-LS-LS6, GFD-TF-T6, GFD-VT-92 | Lodged
HAY_SC_2 | 2027-01-12 07:00 | 2027-01-19 18:00 | Continuous | RS - Removal from Service | Affected Equipment of HAY_T2, for HAY_110BZ Stage 3J; Bay 110 - Interconnector T2. | Lodged
HAY_T2 | 2027-01-12 07:00 | 2027-01-19 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3J; Bay 110 - Interconnector T2 (CP_HAY_IN_00_00). No other HAY work on days 1, 7, 8. No other work on associated equipment on day 8 (commissioning). HAY 11kV surge arrestor replacement (CP_RA4_03C_0_00). HAY-CT-112, HAY-CT-462, HAY-SA-2C, HAY-TF-T2. | Lodged
BPE_PRM_HAY_1 | 2027-01-12 07:30 | 2027-01-16 18:30 | Continuous | RS - Removal from Service | HAY CT, DS maintenance. Tower painting (A4-A9) [CP_767_001_0_00]. | Lodged
HRP_TAB_1 | 2027-01-12 07:30 | 2027-01-15 18:30 | Continuous | RS - Removal from Service | Tower works x21 (A57, A63-A64, A68, A88, A99, A101, A104-A105, A111-A112, A119, A122, A129, A141, A156, A158-A160). RSA4 Re-insulation x3. | Lodged
KOE_MPE_1 | 2027-01-12 07:30 | 2027-01-15 18:30 | Continuous | RS - Removal from Service | KOE-CT-162, KOE-DS-166, KOE-ES-169, KOE-MPE-A0024-00, KOE-MPE-A0048-00, KOE-MPE-A0062-10, KOE-MPE-A0070-10, KOE-MPE-A0084-10, KOE-MPE-A0088-00, KOE-MPE-A0126-10, KOE-P-CB-162, MPE-CT-322, MPE-DS-326, MPE-ES-329, MPE-P-CB-322 | Lodged
PRM_T1 | 2027-01-12 07:30 | 2027-01-16 18:30 | Continuous | RS - Removal from Service | PRM-M-CT2162, PRM-M-VT2162. Affected equipment of BPE_PRM_HAY_1. | Lodged
SWN_T2 | 2027-01-12 07:30 | 2027-01-14 18:30 | Continuous | RS - Removal from Service | SWN-CBL-T2-NER2, SWN-DS-254, SWN-DS-3046, SWN-ES-3049, SWN-P-TF-T2, SWN-RES-NER2, SWN-TF-T2, SWN-VT-VT3042 | Lodged
ISL_33BS_A | 2027-01-12 07:30 | 2027-01-13 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_T1 ISL-NCTD-T1 | Lodged
ISL_CB_2058 | 2027-01-12 07:30 | 2027-01-13 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_T1 ISL-NCTD-T1 | Lodged
ISL_FDR_1022 | 2027-01-12 07:30 | 2027-01-13 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_T1 ISL-NCTD-T1 | Lodged
ISL_FDR_1032 | 2027-01-12 07:30 | 2027-01-13 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_T1 ISL-NCTD-T1 | Lodged
ISL_T1 | 2027-01-12 07:30 | 2027-01-13 18:30 | Continuous | RS - Removal from Service | ISL-NCTD-T1 | Lodged
HAY_110BZ | 2027-01-12 08:00 | 2027-01-12 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3J; Bay 110 - Interconnector T2. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-01-12 08:00 | 2027-01-12 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3J; Bay 110 - Interconnector T2. No work in HAY 110kV yard. | Lodged
WAI_CB_1362 | 2027-01-13 07:30 | 2027-01-15 18:30 | Continuous | RS - Removal from Service | Affected equipment WAI_T2 | Lodged
WAI_T2 | 2027-01-13 07:30 | 2027-01-15 18:30 | Continuous | RS - Removal from Service | 5 yrs, WAI-CB-112, WAI-CB-2742, WAI-CBL-2742, WAI-CT-112, WAI-TF-T2B, WAI-VT-2742 | Lodged
MLG_FDR_8 | 2027-01-13 07:30 | 2027-01-13 18:30 | Daily | RS - Removal from Service | MLG-CB-8, MLG-P-CB-8 | Lodged
HWB_TMH_1 | 2027-01-14 07:30 | 2027-01-15 18:30 | Continuous | RS - Removal from Service | HWB-SDN-A0003-20, HWB-SDN-A0004-20 | Lodged
BPE_T3 | 2027-01-14 07:30 | 2027-01-21 18:30 | Continuous | RS - Removal from Service | BPE-TF-T3 (CP_BPE_EH_00_00) | Lodged
MLG_FDR_9 | 2027-01-14 07:30 | 2027-01-14 18:30 | Daily | RS - Removal from Service | MLG-CB-9, MLG-P-CB-9 | Lodged
GOR_T12 | 2027-01-15 07:30 | 2027-02-24 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_GOR_TMH_2 includes Lines | Lodged
SVL_FDR_2842 | 2027-01-15 07:30 | 2027-01-15 18:30 | Daily | RS - Removal from Service | SVL-CBL-2842 | Lodged
TKA_T1 | 2027-01-15 07:30 | 2027-01-15 18:30 | Daily | RS - Removal from Service | TKA-CT-CT1042, TKA-CT-T1 | Lodged
TMI_LST_1 | 2027-01-15 07:30 | 2027-01-15 18:30 | Daily | RS - Removal from Service | TMI-TF-LS1 | Lodged
MLG_FDR_11 | 2027-01-15 07:30 | 2027-01-15 18:30 | Daily | RS - Removal from Service | MLG-CB-11, MLG-P-CB-11 | Lodged
BAL_GOR_1 | 2027-01-18 07:30 | 2027-01-22 18:30 | Continuous | RS - Removal from Service | GOR-HWB-A0014-00, GOR-HWB-A0044-00, GOR-HWB-A0060-00, GOR-HWB-A0077-00, GOR-HWB-A0101-0102-10, GOR-HWB-A0116-00, GOR-HWB-A0117-00, GOR-HWB-A0120-00, GOR-HWB-A0128-00, GOR-HWB-A0139-00, GOR-HWB-A0189-00, GOR-HWB-A0196-00, GOR-HWB-A0213-00, GOR-HWB-A0218-00, GOR-HWB-A0249-00, GOR-HWB-A0250-00 | Lodged
BEN_T36 | 2027-01-18 07:30 | 2027-01-20 18:30 | Continuous | RS - Removal from Service | S1.20T36-T36 | Lodged
BPE_BRK_2 | 2027-01-18 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | BPE-DS-786 (BRK_2), BRK-CT-622, BRK-CVT-622, BRK-DS-613 (BPE_2), BRK-DS-625 (BPE_2), BRK-DS-626 (BPE_2), BRK-ES-629, BRK-P-CB-612/622. 1 day lines-free. Tower recoating (A68-A73, A75-A76). | Lodged
BRY_ISL_1 | 2027-01-18 07:30 | 2027-01-24 18:30 | Continuous | RS - Removal from Service | BRY-ISL-A0044-0045-20, BRY-ISL-A0057-0057A-20, ISL-DS-435, dampers and spacers | Lodged
HAY_SC_8_T8 | 2027-01-18 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | HAY-SC8, HAY-SC8-EXC, HAY-SC8-NER, HAY_110BZ Stage 3O; Bay 120 - Transformer T8. No other work on days 1, 4, 5. No other work on associated equipment/lines on day 5 (commissioning). | Lodged
KAW_T5 | 2027-01-18 07:30 | 2027-01-22 18:30 | Continuous | RS - Removal from Service | KAW T5 protection replacement. KAW-P-TF-T5, KAW-TF-T5 | Lodged
TKB_TWZ_1 | 2027-01-18 07:30 | 2027-01-20 18:30 | Continuous | RS - Removal from Service | CA Lifting | Lodged
MAN_NMA_1 | 2027-01-18 07:30 | 2027-01-23 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
MLG_FDR_12 | 2027-01-18 07:30 | 2027-01-18 18:30 | Daily | RS - Removal from Service | MLG-CB-12, MLG-P-CB-12 | Lodged
HAM_PAO_WHU_2 | 2027-01-18 07:31 | 2027-01-22 18:31 | Continuous | RS - Removal from Service | HAM-WHU-A0014-20, HAM-WHU-A0019-20, HAM-WHU-A0020-20, HAM-WHU-A0021-20, HAM-WHU-A0025-20, HAM-WHU-A0027-20, HAM-WHU-A0028-20, HAM-WHU-A0029-20, HAM-WHU-A0030-20, HAM-WHU-A0031-20, HAM-WHU-A0033-20, HAM-WHU-A0036-20, HAM-WHU-A0037-20, HAM-WHU-A0039-20, HAM-WHU-A0070-20, HAM-WHU-A0077-20, HAM-WHU-A0080-20, HAM-WHU-A0085-20, PAO-DCB-232 | Lodged
PAO_CB_232 | 2027-01-18 07:31 | 2027-01-22 18:31 | Continuous | RS - Removal from Service | Affected equipment HAM_PAO_WHU_2 | Lodged
ALB_204_297_317 | 2027-01-18 07:31 | 2027-01-22 18:31 | Continuous | RS - Removal from Service | ALB-DS-264, ALB-VT-2, ALB-DS-204, ALB-DS-277, ALB-DS-297 | Lodged
ALB_C_1 | 2027-01-18 07:31 | 2027-01-22 18:31 | Continuous | RS - Removal from Service | ALB-CAPS-C1, ALB-CAPS-C2, ALB-CT-1, ALB-CT-202, ALB-ES-209 | Lodged
ALB_FDR_262 | 2027-01-18 07:31 | 2027-01-22 18:31 | Continuous | RS - Removal from Service | ALB-M-CT262 | Lodged
ALB_FDR_302 | 2027-01-18 07:31 | 2027-01-22 18:30 | Continuous | RS - Removal from Service | ALB-CB-302, ALB-CT-302, ALB-DS-306, ALB-ES-309, ALB-DS-304 | Lodged
OTA_WIR_1 | 2027-01-18 07:31 | 2027-01-19 18:31 | Continuous | RS - Removal from Service | BOB-OTA-A0117B-00 | Lodged
WIR_T2 | 2027-01-18 07:31 | 2027-01-20 18:31 | Continuous | RS - Removal from Service | Affected equipment | Lodged
MPE_CB_252 | 2027-01-18 08:00 | 2027-01-18 22:00 | Daily | OPE - Open Ended | System split for the duration of BRB_HPI | Lodged
MPE_CB_292 | 2027-01-18 08:00 | 2027-01-18 22:00 | Daily | OPE - Open Ended | System split for the duration of BRB_HPI | Lodged
HAY_110BZ | 2027-01-18 08:00 | 2027-01-18 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3J; Bay 110 - Interconnector T2. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-01-18 08:00 | 2027-01-18 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3J; Bay 110 - Interconnector T2. | Lodged
MPE_CB_252 | 2027-01-19 06:00 | 2027-01-21 22:00 | Continuous | OPE - Open Ended | System split for the duration of BRB_HPI | Lodged
MPE_CB_292 | 2027-01-19 06:00 | 2027-01-21 22:00 | Continuous | OPE - Open Ended | System split for the duration of BRB_HPI | Lodged
BEN_F_5 | 2027-01-19 07:30 | 2027-01-21 18:30 | Continuous | RS - Removal from Service | S1.20DB72-FB5, S1.20DB72-Q02 | Lodged
TKU_T22 | 2027-01-19 07:30 | 2027-01-28 18:30 | Continuous | RS - Removal from Service | TKU-M-VT22, TKU-P-TF-T22 | Lodged
HAY_110BZ | 2027-01-19 08:00 | 2027-01-19 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3J; Bay 110 - Interconnector T2. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-01-19 08:00 | 2027-01-19 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3J; Bay 110 - Interconnector T2. | Lodged
BRB_HPI_1 | 2027-01-19 08:00 | 2027-01-23 18:30 | Continuous | RS - Removal from Service | Tower painting | Lodged
ALB_CB_818 | 2027-01-20 07:30 | 2027-01-20 18:30 | Daily | RS - Removal from Service | ALB-P-CB-818 | Lodged
ARI_STH_RNBACK_PROT1 | 2027-01-20 07:30 | 2027-01-22 18:30 | Continuous | RS - Removal from Service | ARI-P-SPS-SOUTH-OL | Lodged
BEN_BGR_1 | 2027-01-20 07:30 | 2027-01-21 18:30 | Daily | RS - Removal from Service | S1.WN-F1 | Lodged
BEN_BIPOLE | 2027-01-20 07:30 | 2027-01-21 18:30 | Daily | RS - Removal from Service | FTB-BLDG-SBG, S1.P2-Q41 | Lodged
BEN_HAY_2 | 2027-01-20 07:30 | 2027-01-21 18:30 | Daily | RS - Removal from Service | BEN-HAY-A0827-20, BEN-HAY-A0828-20, BEN-HAY-A0834-20, BEN-HAY-A1482-20, BEN-HAY-A1513-20, BEN-HAY-A1526-20, FTB-P-P2-CSI, FTB-P2-BU-1, OTB-HAY-A0002-20, OTB-HAY-A0004-20, OTB-HAY-A0064A-30, OTB-P2-SA-3 | Lodged
BEN_POLE_2 | 2027-01-20 07:30 | 2027-01-21 18:30 | Daily | RS - Removal from Service | S1.P2-F1, S1.P2-F2, S1.P2-FP3, S1.P2-FP8, S1.P2-L1, S1.P2-T1.F1.A, S1.P2-T1.F1.B, S1.P2-T1.F1.C, S1.P2-T1.N.F1.A, S1.P2-T1.N.F1.B, S1.P2-T1.N.F1.C, S1.P2-T1.Q1, S1.P2-T1.T1A, S1.P2-T1.T1B, S1.P2-T1.T1C, S1.P2-T1.Z1.L1A, S1.P2-T1.Z1.L1B, S1.P2-T1.Z1.L1C, S1.P2-T1.Z1.Z1A, S1.P2-T1.Z1.Z1B, S1.P2-T1.Z1.Z1C, S1.P2-T1.Z1.Z2A, S1.P2-T1.Z1.Z2B, S1.P2-T1.Z1.Z2C, S1.P2-T1.Z1.Z3A, S1.P2-T1.Z1.Z3B, | Lodged
MLG_FDR_10 | 2027-01-20 07:30 | 2027-01-21 18:30 | Continuous | RS - Removal from Service | MLG-CB-10, MLG-P-CB-10 | Lodged
ISL_TKB_1 | 2027-01-21 07:30 | 2027-01-22 18:30 | Continuous | RS - Removal from Service | CA lifting | Lodged
MPE_CB_252 | 2027-01-22 06:00 | 2027-01-22 18:30 | Daily | OPE - Open Ended | System split for the duration of BRB_HPI | Lodged
MPE_CB_292 | 2027-01-22 06:00 | 2027-01-22 18:30 | Daily | OPE - Open Ended | System split for the duration of BRB_HPI | Lodged
STK_C_32 | 2027-01-22 07:30 | 2027-01-22 18:30 | Daily | RS - Removal from Service | STK-CAPS-C32, STK-CBL-2192-C32, STK-REA-C32 | Lodged
TIM_11TIE_A_C | 2027-01-22 07:30 | 2027-01-22 18:30 | Daily | RS - Removal from Service | TIM-CBL-CB2728-2968, TIM-VT-VT2968 | Lodged
ASB_BRY_1 | 2027-01-25 06:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | Affected Equipment BRY-DS-884. CY4 Maintenance Re-planned. | Lodged
BRY_CB_878 | 2027-01-25 06:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | Affected Equipment BRY-DS-884. CY4 Maintenance Re-planned. | Lodged
BRY_C_7A | 2027-01-25 06:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | Affected Equipment BRY-DS-884. CY4 Maintenance Re-planned. | Lodged
BRY_T7 | 2027-01-25 06:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | Affected Equipment BRY-DS-884. CY4 Maintenance Re-planned. | Lodged
APS_CLH_1 | 2027-01-25 07:30 | 2027-01-28 18:30 | Continuous | RS - Removal from Service | COL-OTI-A0240-00, COL-OTI-A0241-00, COL-OTI-A0242-00, COL-OTI-A0361-0362-10, COL-OTI-A0382-00, COL-OTI-A0396-00 | Lodged
ASB_BRY_1 | 2027-01-25 07:30 | 2027-01-31 18:30 | Continuous | RS - Removal from Service | ASB-DS-386, BRY-P-CB-892, CHH-TWZ-A0306-00, CHH-TWZ-A0307-00, CHH-TWZ-A0308-00, CHH-TWZ-A0308-10 | Lodged
BAL_GOR_1 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | GOR-HWB-A0101-0102-10 GOR-HWB-A0196-00 GOR-HWB-A0213-00 GOR-HWB-A0218-00 GOR-HWB-A0249-00 GOR-HWB-A0250-00 | Lodged
BDE_11BZ | 2027-01-25 07:30 | 2027-01-26 18:30 | Daily | RS - Removal from Service | BDE-P-BZ-11 | Lodged
BDE_11CBF | 2027-01-25 07:30 | 2027-01-26 18:30 | Daily | RS - Removal from Service | BDE-P-BZ-11 | Lodged
COL_OTI_2 | 2027-01-25 07:30 | 2027-01-28 18:30 | Continuous | RS - Removal from Service | Affected equipment APS_CLH_1 | Lodged
CST_HUI_2 | 2027-01-25 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | Tower recoating x10 (A1-A10) [CP_750_001_0_00]. | Lodged
KAW_T6 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | KAW T6 Protection replacement. KAW-DS-1097, KAW-NCT-ET6, KAW-P-TF-T6 | Lodged
NMA_220BS_A4 | 2027-01-25 07:30 | 2027-01-26 18:30 | Continuous | RS - Removal from Service | MAN-TWI-A0324-0325-20, MAN-TWI-A0354-20, MAN-TWI-A0359-20, MAN-TWI-A0360-20, MAN-TWI-A0373-20, MAN-TWI-A0379-20, MAN-TWI-A0388-20, MAN-TWI-A0389-0390-20, MAN-TWI-A0394-20, MAN-TWI-A0396-0397-20, MAN-TWI-A0397-0398-20, NMA-CT-CT752, TWI-SA-3, FM3 roller door servicing | Lodged
NMA_CB_718 | 2027-01-25 07:30 | 2027-01-26 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A4 MAN-TWI-A0324-0325-20, MAN-TWI-A0354-20, MAN-TWI-A0359-20, MAN-TWI-A0360-20, MAN-TWI-A0373-20, MAN-TWI-A0379-20, MAN-TWI-A0388-20, MAN-TWI-A0389-0390-20, MAN-TWI-A0394-20, MAN-TWI-A0396-0397-20, MAN-TWI-A0397-0398-20, NMA-CT-CT752, TWI-SA-3, FM3 roller door servicing | Lodged
NMA_CB_738 | 2027-01-25 07:30 | 2027-01-26 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A4 MAN-TWI-A0324-0325-20, MAN-TWI-A0354-20, MAN-TWI-A0359-20, MAN-TWI-A0360-20, MAN-TWI-A0373-20, MAN-TWI-A0379-20, MAN-TWI-A0388-20, MAN-TWI-A0389-0390-20, MAN-TWI-A0394-20, MAN-TWI-A0396-0397-20, MAN-TWI-A0397-0398-20, NMA-CT-CT752, TWI-SA-3, FM3 roller door servicing | Lodged
NMA_TWI_2 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | MAN-TWI-A0324-0325-20, MAN-TWI-A0354-20, MAN-TWI-A0359-20, MAN-TWI-A0360-20, MAN-TWI-A0373-20, MAN-TWI-A0379-20, MAN-TWI-A0388-20, MAN-TWI-A0389-0390-20, MAN-TWI-A0394-20, MAN-TWI-A0396-0397-20, MAN-TWI-A0397-0398-20, NMA-CT-CT752, TWI-SA-3, FM3 roller door servicing | Lodged
ROT_DIS_357 | 2027-01-25 07:30 | 2027-02-05 18:30 | Continuous | CLO - Close | Closed for the duration of ROT_TRK_1 | Lodged
ROT_DIS_367 | 2027-01-25 07:30 | 2027-02-05 18:30 | Continuous | CLO - Close | Closed for the duration of ROT_TRK_1 | Lodged
ROT_TRK_1 | 2027-01-25 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | Line Protection replacement and bus zone installation TRK-P-CB-162 | Lodged
TMU_CB_2812 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | TMU-CB-2812 | Lodged
TMU_T2 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | TMU-TF-T2 | Lodged
MAN_NMA_2 | 2027-01-25 07:30 | 2027-01-30 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
ALB_SVL_1 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | ALB-CVT-592, ALB-DS-596, ALB-ES-599, ALB-SVL-A0002-20, ALB-SVL-A0004-10, ALB-SVL-A0005-00, ALB-SVL-A0005-10, ALB-SVL-A0010-10, ALB-SVL-A0013-00, ALB-SVL-A0016-00, ALB-SVL-A0018-10, ALB-SVL-A0020-00, ALB-SVL-A0021-00, ALB-SVL-A0022-00, ALB-SVL-A0025-00, ALB-SVL-A0028-10, ALB-SVL-A0029-00, Tower painting | Lodged
SVL_33BS_A | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | Feeder Protection upgrade | Lodged
SVL_CB_2808 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | Affected Equipment of SVL_33BS_A | Lodged
SVL_FDR_2742 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | Affected Equipment of SVL_33BS_A | Lodged
SVL_FDR_2762 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | Affected Equipment of SVL_33BS_A | Lodged
SVL_FDR_2782 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | Affected Equipment of SVL_33BS_A | Lodged
SVL_T1 | 2027-01-25 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | Affected equipment ALB_587_597_637 & ALB_SVL_1 | Lodged
TAB_WRK_1 | 2027-01-25 07:30 | 2027-01-26 18:30 | Continuous | RS - Removal from Service | WRK-CB-162, WRK-CT-162, WRK-DS-166, WRK-ES-169. Tower work x1 (A20). Affected equipment of WRK_97_127_164. | Lodged
WRK_97_127_164 | 2027-01-25 07:30 | 2027-01-26 18:30 | Continuous | RS - Removal from Service | WRK 2DS mtce | Lodged
RPO_WRK_1 | 2027-01-25 07:31 | 2027-01-27 18:31 | Continuous | RS - Removal from Service | RPO-CBL-526-539. Affected equipment of WRK_97_127_164. | Lodged
MPE_CB_252 | 2027-01-25 08:00 | 2027-01-25 22:00 | Daily | OPE - Open Ended | System split with HPI_MDN | Lodged
MPE_CB_292 | 2027-01-25 08:00 | 2027-01-25 22:00 | Daily | OPE - Open Ended | System split with HPI_MDN | Lodged
HPI_MDN_1 | 2027-01-25 08:00 | 2027-01-30 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
MPE_CB_252 | 2027-01-26 06:00 | 2027-01-28 22:00 | Continuous | OPE - Open Ended | System split with HPI_MDN | Lodged
MPE_CB_292 | 2027-01-26 06:00 | 2027-01-28 22:00 | Continuous | OPE - Open Ended | System split with HPI_MDN | Lodged
MLG_FDR_6 | 2027-01-26 07:00 | 2027-01-27 18:30 | Continuous | RS - Removal from Service | MLG-CB-6, MLG-P-CB-6. | Lodged
MTN_T1 | 2027-01-26 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | MTN-TF-T1. 12-hour heat soak on last day. | Lodged
DVK_T2 | 2027-01-26 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | Affected equipment of WDV_DVK_WPW_1 | Lodged
WDV_DVK_WPW_1 | 2027-01-26 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | Pole replacements x4 | Lodged
WPW_T2 | 2027-01-26 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | Affected equipment of WDV_DVK_WPW_1 | Lodged
HAY_R5 | 2027-01-27 07:00 | 2027-02-03 18:00 | Continuous | RS - Removal from Service | Affected equipment of HAY_T5, for HAY_110BZ Stage 3K; Bay 290 - Interconnector T5. | Lodged
HAY_SC_3 | 2027-01-27 07:00 | 2027-02-03 18:00 | Continuous | RS - Removal from Service | Affected equipment of HAY_T5, for HAY_110BZ Stage 3K; Bay 290 - Interconnector T5. | Lodged
HAY_SC_4 | 2027-01-27 07:00 | 2027-02-03 18:00 | Continuous | RS - Removal from Service | Affected equipment of HAY_T5, for HAY_110BZ Stage 3K; Bay 290 - Interconnector T5. | Lodged
HAY_T5 | 2027-01-27 07:00 | 2027-02-03 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3K; Bay 290 - Interconnector T5 (CP_HAY_IN_00_00). No other HAY work on days 1, 7, 8. No other work on associated equipment on day 8 (commissioning). HAY 11kV surge arrestor replacement (CP_RA4_03C_0_00). HAY-CT-292, HAY-CT-622, HAY-SA-5C, HAY-TF-T5 | Lodged
NMA_687_835 | 2027-01-27 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | MAN-TWI-A0324-0325-20, MAN-TWI-A0354-20, MAN-TWI-A0359-20, MAN-TWI-A0360-20, MAN-TWI-A0373-20, MAN-TWI-A0379-20, MAN-TWI-A0388-20, MAN-TWI-A0389-0390-20, MAN-TWI-A0394-20, MAN-TWI-A0396-0397-20, MAN-TWI-A0397-0398-20, NMA-CT-CT752, TWI-SA-3, FM3 roller door servicing | Lodged
NMA_CB_738 | 2027-01-27 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_687_835 MAN-TWI-A0324-0325-20, MAN-TWI-A0354-20, MAN-TWI-A0359-20, MAN-TWI-A0360-20, MAN-TWI-A0373-20, MAN-TWI-A0379-20, MAN-TWI-A0388-20, MAN-TWI-A0389-0390-20, MAN-TWI-A0394-20, MAN-TWI-A0396-0397-20, MAN-TWI-A0397-0398-20, NMA-CT-CT752, TWI-SA-3, FM3 roller door servicing | Lodged
ROT_11BS_A | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | RS - Removal from Service | ROT-M-CT2742, ROT-M-VT2742 | Lodged
ROT_CB_2778 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | RS - Removal from Service | Affected Equipment of ROT_11BS_A ROT-M-CT2742, ROT-M-VT2742 | Lodged
ROT_FDR_2702 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | RS - Removal from Service | Affected Equipment of ROT_11BS_A ROT-M-CT2742, ROT-M-VT2742 | Lodged
ROT_FDR_2712 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | RS - Removal from Service | Affected Equipment of ROT_11BS_A ROT-M-CT2742, ROT-M-VT2742 | Lodged
ROT_FDR_2722 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | RS - Removal from Service | Affected Equipment of ROT_11BS_A ROT-M-CT2742, ROT-M-VT2742 | Lodged
ROT_FDR_2732 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | RS - Removal from Service | Affected Equipment of ROT_11BS_A ROT-M-CT2742, ROT-M-VT2742 | Lodged
ROT_FDR_2752 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | RS - Removal from Service | Affected Equipment of ROT_11BS_A ROT-M-CT2742, ROT-M-VT2742 | Lodged
ROT_FDR_2762 | 2027-01-27 07:30 | 2027-01-27 18:30 | Daily | RS - Removal from Service | Affected Equipment of ROT_11BS_A ROT-M-CT2742, ROT-M-VT2742 | Lodged
ROT_T4 | 2027-01-27 07:30 | 2027-01-28 18:30 | Continuous | RS - Removal from Service | ROT-M-CT2742, ROT-M-VT2742 | Lodged
HAY_110BZ | 2027-01-27 08:00 | 2027-01-27 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3K; Bay 290 - Interconnector T5. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-01-27 08:00 | 2027-01-27 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3K; Bay 290 - Interconnector T5. | Lodged
MLG_FDR_7 | 2027-01-28 07:00 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | MLG-CB-7, MLG-P-CB-7. | Lodged
PAK_WKM_1 | 2027-01-28 07:30 | 2027-01-29 18:30 | Continuous | RS - Removal from Service | BHL-PAK-A-CBL-SHEATH, WKM-CVT-502 | Lodged
PEN_FDR_2362 | 2027-01-28 07:30 | 2027-01-28 18:30 | Daily | RS - Removal from Service | PEN-CB-2362, PEN-P-CB-2362 | Lodged
MPE_CB_252 | 2027-01-29 06:00 | 2027-01-29 18:30 | Daily | OPE - Open Ended | System split with HPI_MDN | Lodged
MPE_CB_292 | 2027-01-29 06:00 | 2027-01-29 18:30 | Daily | OPE - Open Ended | System split with HPI_MDN | Lodged
PEN_FDR_2542 | 2027-01-29 07:30 | 2027-01-29 18:30 | Daily | RS - Removal from Service | PEN-CB-2542, PEN-P-CB-2542 | Lodged
BDE_C_5 | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | BDE-CAPS-C5, BDE-CBL-21, BDE-REA-C5 | Lodged
BDE_FDR_25 | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | Affected equipment BDE_11BS_B & BDE_C_4 & BDE_C_5 | Lodged
BPE_BRK_1 | 2027-02-01 07:30 | 2027-02-12 18:30 | Continuous | RS - Removal from Service | BPE-DS-526, BRK-CT-652, BRK-CVT-652, BRK-DS-643, BRK-DS-655, BRK-DS-656, BRK-ES-659, BRK-P-CB-652. Tower recoating (A68-A73, A75-A76). | Lodged
BRK_CB_642 | 2027-02-01 07:30 | 2027-02-12 18:30 | Continuous | RS - Removal from Service | BRK-CB-642, BRK-CT-642, BRK-P-CB-642. Affected equipment of BPE_BRK_1. | Lodged
BWK_HWB_1 | 2027-02-01 07:30 | 2027-02-03 18:30 | Continuous | RS - Removal from Service | GOR-HWB-A0612-10, GOR-HWB-A0665-00, GOR-HWB-A0713-00 | Lodged
GOR_ROX_1 | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | GOR-ROX-A0095-00 GOR-ROX-A0098-00 GOR-ROX-A0108-00 GOR-ROX-A0120-00 GOR-ROX-A0121-00 GOR-ROX-A0127-00 GOR-ROX-A0143-00 GOR-ROX-A0153-00 GOR-ROX-A0159-00 GOR-ROX-A0216-00 | Lodged
NMA_TWI_1 | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | MAN-TWI-A0324-0325-10, MAN-TWI-A0354-10, MAN-TWI-A0379-10, MAN-TWI-A0386-00, MAN-TWI-A0388-0389-10, MAN-TWI-A0388-10, MAN-TWI-A0393-00, MAN-TWI-A0394-10, MAN-TWI-A0396-0397-00, MAN-TWI-A0396-0397-10, MAN-TWI-A0397-0398-00, MAN-TWI-A0399-00, NMA-CT-CT792, TWI-SA-4, FM3 roller door servicing | Lodged
IGH_MCH_1 | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
BDE_11BS_B | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | BDE-M-CT-BUS-B, BDE-M-VT20 | Lodged
BDE_FDR_23 | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | Affected equipment BDE_11BS_B & BDE_C_4 & BDE_C_5 | Lodged
BDE_C_4 | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | BDE-CAPS-C4, BDE-CBL-20, BDE-REA-C4 | Lodged
BDE_CB_38 | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | Affected equipment BDE_11BS_B & BDE_C_4 & BDE_C_5 | Lodged
BDE_FDR_24 | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | Affected equipment BDE_11BS_B & BDE_C_4 & BDE_C_5 | Lodged
BDE_T2 | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | Affected equipment BDE_11BS_B & BDE_C_4 & BDE_C_5 | Lodged
FHL_WPW_1 | 2027-02-01 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | Pole replacements x12. Condition assessments. | Lodged
HAY_SC_10_T10 | 2027-02-02 07:30 | 2027-02-12 18:30 | Continuous | RS - Removal from Service | HAY-CBL-T10-C10, HAY-CBL-T10-XT10, HAY-CBL-XT10-VT10A, HAY-SC10, HAY-SC10-EXC, HAY-SC10-NER, HAY-SC10-VT-10A | Lodged
OHW_WKM_1 | 2027-02-02 07:30 | 2027-02-04 18:30 | Continuous | RS - Removal from Service | Spacer replacement project. OTA-WKM-C0298-0299-20, OTA-WKM-C0300-0301-20 | Lodged
OTA_C_11 | 2027-02-02 07:30 | 2027-02-02 18:30 | Daily | RS - Removal from Service | OTA-CB-262 | Lodged
THI_WKM_1 | 2027-02-02 07:30 | 2027-02-04 18:30 | Continuous | RS - Removal from Service | Maintenance works, broken insulator, u-Bolts, birds nests, earthwire works, loose strands back span, bulging joint. | Lodged
KWA_AVR_T2 | 2027-02-02 07:30 | 2027-02-03 18:30 | Continuous | RS - Removal from Service | Affected equipment of KWA_WIL_1 | Lodged
KWA_CB_8 | 2027-02-02 07:30 | 2027-02-03 18:30 | Continuous | RS - Removal from Service | Affected equipment of KWA_WIL_1 | Lodged
KWA_T2 | 2027-02-02 07:30 | 2027-02-03 18:30 | Continuous | RS - Removal from Service | Affected Equipment of KWA_WIL_1 KWA_WIL_1 | Lodged
KWA_WIL_1 | 2027-02-02 07:30 | 2027-02-03 18:30 | Continuous | RS - Removal from Service | KWA-DS-56, KWA-ES-59 | Lodged
EDG_KAW_2 | 2027-02-02 07:30 | 2027-02-05 18:31 | Continuous | RS - Removal from Service | EDG-KAW-B0076-10, EDG-KAW-B0078-10, EDG-KAW-B0080-10, EDG-KAW-B0084-10, KAW-CT-112, KAW-P-CB-112 | Lodged
KAW_97_VT107 | 2027-02-02 07:30 | 2027-02-05 18:31 | Continuous | RS - Removal from Service | KAW-DS-107, KAW-VT-107 | Lodged
KAW_T7 | 2027-02-02 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | Protection upgrade. KAW-CT-102, KAW-DS-1103, KAW-DS-1107, KAW-ES-109, KAW-NCT-7, KAW-NCT-ET7, KAW-P-TF-T7, KAW-TF-ET7, KAW-TF-T7 | Lodged
OTA_220BZ_B_1 | 2027-02-02 07:31 | 2027-02-04 18:30 | Continuous | RS - Removal from Service | OTA-P-BZ-1-220-B | Lodged
OTA_220CBF_1 | 2027-02-02 07:31 | 2027-02-04 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
HAY_110BZ | 2027-02-02 08:00 | 2027-02-02 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3K; Bay 290 - Interconnector T5. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-02-02 08:00 | 2027-02-02 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3K; Bay 290 - Interconnector T5. | Lodged
HLY_CB_242 | 2027-02-03 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | HLY-P-CB-242 | Lodged
OHC_1307_1506 | 2027-02-03 07:30 | 2027-02-03 18:30 | Daily | RS - Removal from Service | OHC-DS-1414 | Lodged
OHC_1506_1507 | 2027-02-03 07:30 | 2027-02-03 18:30 | Daily | RS - Removal from Service | OHC-DS-1514 | Lodged
OHC_CB_1358 | 2027-02-03 07:30 | 2027-02-03 18:30 | Daily | RS - Removal from Service | Affected equipment OHC_1307_1506 | Lodged
OHC_TWZ_4 | 2027-02-03 07:30 | 2027-02-03 18:30 | Daily | RS - Removal from Service | Affected equipment OHC_1506_1507 | Lodged
OTA_C_12 | 2027-02-03 07:30 | 2027-02-03 18:30 | Daily | RS - Removal from Service | OTA-CB-272 | Lodged
HAY_110BZ | 2027-02-03 08:00 | 2027-02-03 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3K; Bay 290 - Interconnector T5. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-02-03 08:00 | 2027-02-03 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3K; Bay 290 - Interconnector T5. | Lodged
BAL_BWK_1 | 2027-02-04 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | BAL-DEV-A0010-00, BAL-DEV-A0013-00, BAL-DEV-A0030-00, BWK-CB-192, GOR-HWB-A0440-00 | Lodged
BEN_OHB_1 | 2027-02-04 07:30 | 2027-02-04 18:30 | Daily | RS - Removal from Service | Affected equipment OHB_806_1007 | Lodged
KIN_FDR_2242 | 2027-02-04 07:30 | 2027-02-05 18:30 | Continuous | RS - Removal from Service | KIN-CB-2242, KIN-P-CB-2242 | Lodged
OHB_806_1007 | 2027-02-04 07:30 | 2027-02-04 18:30 | Daily | RS - Removal from Service | OHB-DS-914 | Lodged
MAN_220BS_B | 2027-02-05 07:30 | 2027-02-05 18:30 | Daily | RS - Removal from Service | MAN-P-CB-238, MAN-P-CB-248 | Lodged
MAN_CB_238 | 2027-02-05 07:30 | 2027-02-05 18:30 | Daily | RS - Removal from Service | Affected equipment MAN_220BS_B | Lodged
MAN_CB_248 | 2027-02-05 07:30 | 2027-02-05 18:30 | Daily | RS - Removal from Service | Affected equipment MAN_220BS_B | Lodged
OHB_807_806 | 2027-02-05 07:30 | 2027-02-05 18:30 | Daily | RS - Removal from Service | OHB-DS-814 | Lodged
KIK_STK_1 | 2027-02-08 07:31 | 2027-02-12 18:31 | Continuous | RS - Removal from Service | KIK-DS-344 Disconnector & Earth Switch type Hapam SSB-III = Contact Alignment and Re-greasing (2019088) 500649328 ISL_WPR_CUL_KIK_2, KIK_STK_1 KIK-DS-354 Disconnector & Earth Switch type Hapam SSB-III = Contact Alignment and Re-greasing (2019090) 500649327 ISL_WPR_CUL_KIK_2, KIK_STK_1 | Lodged
HAY_CB_2892 | 2027-02-09 07:00 | 2027-02-14 18:00 | Continuous | RS - Removal from Service | Affected equipment of HAY_T11, for HAY_110BZ Stage 3L; Bay 130 - Transformer T11. | Lodged
HAY_FDR_1012 | 2027-02-09 07:00 | 2027-02-14 18:00 | Continuous | RS - Removal from Service | Affected equipment of HAY_T11, for HAY_110BZ Stage 3L; Bay 130 - Transformer T11. | Lodged
HAY_T11 | 2027-02-09 07:00 | 2027-02-14 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3L; Bay 130 - Transformer T11. No other HAY work on days 1, 5, 6. No other work on associated equipment/lines on day 6 (commissioning). | Lodged
BRK_SFD_1 | 2027-02-09 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | BRK-CB-632, BRK-CT-632, BRK-P-CB-632, BRK-P-CB-632/642, SFD-CVT-21, SFD-DS-743, SFD-DS-755, SFD-DS-756, SFD-ES-759. (CVT requires no other work for 1/2 day). Tower recoating x10 (A165-A174) [CP_758_003_0_00]. | Lodged
GOR_ROX_1 | 2027-02-09 07:30 | 2027-02-12 18:30 | Continuous | RS - Removal from Service | GOR-ROX-A0244-00 GOR-ROX-A0252-00 GOR-ROX-A0286-00 | Lodged
HAM_CB_458 | 2027-02-09 07:30 | 2027-02-14 18:30 | Continuous | RS - Removal from Service | HAM-CT-458 replacement | Lodged
HAM_DIS_447 | 2027-02-09 07:30 | 2027-02-14 18:30 | Continuous | CLO - Close | Closed for the duration of HAM CB 458. HAM CT 458 replacement | Lodged
HAY_WIL_LTN_1 | 2027-02-09 07:30 | 2027-02-09 18:29 | Daily | RS - Removal from Service | HAY-DS-576. Tower works x1 (A307). Remove droppers on JFD_LTN_1 for tower painting [CP_770_007_0_00]. | Lodged
INV_TWI_1 | 2027-02-09 07:30 | 2027-02-12 18:30 | Continuous | RS - Removal from Service | INV-TWI-A0002-10 INV-TWI-A0005-10 INV-TWI-A0006-10 INV-TWI-A0017-10 INV-TWI-A0017-10 INV-TWI-A0019-10 INV-TWI-A0020-10 INV-TWI-A0020-10 INV-TWI-A0023-10 INV-TWI-A0023-10 INV-TWI-A0031-10 INV-TWI-A0031-10 | Lodged
ISL_T7 | 2027-02-09 07:30 | 2027-02-12 18:30 | Continuous | RS - Removal from Service | ISL-CB-312, ISL-P-TF-T7, ISL-TF-T7B, ISL-TF-T7R, ISL-TF-T7Y | Lodged
KAW_MAT_1 | 2027-02-09 07:30 | 2027-02-11 18:30 | Continuous | RS - Removal from Service | KAW-MAT-A0002-0003-00, KAW-MAT-A0003-00, KAW-MAT-A0003-0004-10, KAW-MAT-A0009-00, KAW-MAT-A0014-00 | Lodged
NMA_220BS_A1 | 2027-02-09 07:30 | 2027-02-12 18:30 | Continuous | RS - Removal from Service | NMA-CBL-1092, NMA-TF-T1 | Lodged
NMA_CB_688 | 2027-02-09 07:30 | 2027-02-12 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A1 NMA-CBL-1092, NMA-TF-T1 | Lodged
NMA_CB_708 | 2027-02-09 07:30 | 2027-02-12 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A1 NMA-CBL-1092, NMA-TF-T1 | Lodged
NMA_T1 | 2027-02-09 07:30 | 2027-02-20 18:30 | Continuous | RS - Removal from Service | NMA-CBL-1092, NMA-TF-T1 | Lodged
OTB_SMK_1 | 2027-02-09 07:30 | 2027-02-11 18:30 | Daily | RS - Removal from Service | OTB-TF-LS21 | Lodged
HAM_CB_458 | 2027-02-09 07:30 | 2027-02-14 18:30 | Continuous | RS - Removal from Service | HAM CT 458 replacement project | Lodged
HAM_DIS_447 | 2027-02-09 07:30 | 2027-02-14 18:30 | Continuous | CLO - Close | Closed for the duration of HAM_CB_458. HAM CT 458 replacement project | Lodged
HAY_110BZ | 2027-02-09 08:00 | 2027-02-09 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3L; Bay 130 - Transformer T11. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-02-09 08:00 | 2027-02-09 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3L; Bay 130 - Transformer T11. | Lodged
JFD_LTN_1 | 2027-02-09 18:30 | 2027-02-26 07:29 | Continuous | RS - Removal from Service | Tower works x8 (A83, A85, A96-A97, A135-A137, A274). Tower painting x19 (A57-A75) [CP_770_007_0_00]. JFD_LTN_1 droppers removed to leave HAY_WIL_1 in-service. | Lodged
ARI_BOB_1 | 2027-02-10 07:30 | 2027-02-12 18:30 | Continuous | RS - Removal from Service | Pole Replacement, Reinsulation, Attachment Points, CAs on outage | Lodged
OWH_11BZ_K | 2027-02-10 07:30 | 2027-02-12 18:30 | Continuous | RS - Removal from Service | OWH-P-BZ-11 | Lodged
OWH_11CBF | 2027-02-10 07:30 | 2027-02-12 18:30 | Continuous | RS - Removal from Service | OWH-P-BZ-11 | Lodged
PNI_214_224_277 | 2027-02-10 07:30 | 2027-02-11 18:30 | Continuous | RS - Removal from Service | PNI-BS-33-214-237 | Lodged
PNI_FDR_212 | 2027-02-10 07:30 | 2027-02-11 18:30 | Continuous | RS - Removal from Service | Affected equipment PNI_214_257 & PNI_T1 | Lodged
PNI_LST_1 | 2027-02-10 07:30 | 2027-02-11 18:30 | Continuous | RS - Removal from Service | Affected equipment of PNI_214_224_277, for PNI-BS-33-214-237 | Lodged
PNI_T1 | 2027-02-10 07:30 | 2027-02-22 18:30 | Continuous | RS - Removal from Service | PNI-M-VT222, PNI-TF-T1R. 33kV droppers to be removed to allow 12-hour heat soak and metering concurrently on last day. | Lodged
PNI_TKR_1 | 2027-02-10 07:30 | 2027-02-11 18:30 | Continuous | RS - Removal from Service | Affected equipment PNI_214_257 & PNI_T1 | Lodged
GLN_220BS_A | 2027-02-11 07:31 | 2027-02-11 18:31 | Daily | RS - Removal from Service | GLN-BS-220-603-BUS-A, GLN-BS-220-613-BUS-A, GLN-BS-220-623-BUS-A, GLN-BS-220-633-BUS-A, GLN-BS-220-643-BUS-A, GLN-BS-220-A-CLEAN, GLN-DS-613, GLN-DS-653 | Lodged
GLN_CB_658 | 2027-02-11 07:31 | 2027-02-11 18:31 | Daily | RS - Removal from Service | Affected equipment GLN_220BS_A | Lodged
HAY_110BZ | 2027-02-13 08:00 | 2027-02-13 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3L; Bay 130 - Transformer T11. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-02-13 08:00 | 2027-02-13 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3L; Bay 130 - Transformer T11. | Lodged
HAY_110BZ | 2027-02-14 08:00 | 2027-02-14 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3L; Bay 130 - Transformer T11. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-02-14 08:00 | 2027-02-14 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3L; Bay 130 - Transformer T11. | Lodged
GLN_T5 | 2027-02-15 07:30 | 2027-02-21 18:30 | Continuous | RS - Removal from Service | Surge arrestor, bushing replacements, GLN-BS-220-T5-CLEAN, GLN-BS-33-T5-CLEAN, GLN-CT-622, GLN-SA-5A, GLN-SA-5B, GLN-TF-T5 | Lodged
HTI_T2 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | SF6 CB pole replacement project HTI-CB-132, HTI-CBL-T2-2152, HTI-CBL-T2-LS2, HTI-CT-132, HTI-NCT-2, HTI-TF-LS2, HTI-TF-T2B, HTI-TF-T2R, HTI-TF-T2SP, HTI-TF-T2Y | Lodged
ISL_220BS_F | 2027-02-15 07:30 | 2027-02-16 18:30 | Continuous | RS - Removal from Service | ISL-DS-803 ISL-DS-813 | Lodged
ISL_C_14 | 2027-02-15 07:30 | 2027-02-15 18:30 | Daily | RS - Removal from Service | ISL-REA-C14 | Lodged
ISL_C_27 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | ISL-DS-803, ISL-DS-805, ISL-P-CAPS-C27 | Lodged
ISL_CB_668 | 2027-02-15 07:30 | 2027-02-16 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_220BS_F ISL-DS-803 ISL-DS-813 | Lodged
ISL_CB_688 | 2027-02-15 07:30 | 2027-02-16 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_220BS_F ISL-DS-803 ISL-DS-813 | Lodged
ISL_FDR_222 | 2027-02-15 07:30 | 2027-02-15 18:30 | Daily | RS - Removal from Service | ISL-CT-CT222, ISL-ES-229 | Lodged
ISL_SVC_9 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | ISL-CAPS-K0-C1, ISL-CT-CT812-D0-T1, ISL-CT-TCR9-K1-T2, ISL-CWU-SVC9, ISL-DS-813, ISL-DS-815, ISL-NCTD-T9, ISL-SVC-9, ISL-VT-VT812-D0-T5 | Lodged
KAW_T2 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | KAW T2 protection replacement KAW-P-TF-T2, KAW-TF-T2 | Lodged
NMA_GOR_TMH_2 | 2027-02-15 07:30 | 2027-02-24 18:30 | Continuous | RS - Removal from Service | CP_EDN_00E_0_00 Powernet EDN New 220kV GXP Build | Lodged
STK_T10 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | STK-CB-822, STK-CBL-ET10, STK-CBL-NER10, STK-CBL-T10-2442, STK-CT-CT822, STK-CT-T10HV, STK-TF-ET10, STK-TF-T10 | Lodged
MAN_NMA_1 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
IGH_KIK_2 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
SVL_33BS_B | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | Feeder protection upgrade | Lodged
SVL_CB_2808 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | Affected Equipment of SVL_33BS_B | Lodged
SVL_FDR_2822 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | Affected Equipment of SVL_33BS_B | Lodged
SVL_FDR_2842 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | Affected Equipment of SVL_33BS_B | Lodged
SVL_FDR_2862 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | Affected Equipment of SVL_33BS_B | Lodged
SVL_FDR_2882 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | Affected Equipment of SVL_33BS_B | Lodged
SVL_FDR_2902 | 2027-02-15 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | Affected Equipment of SVL_33BS_B | Lodged
NMA_615_737 | 2027-02-15 07:30 | 2027-02-18 18:30 | Continuous | RS - Removal from Service | NMA-CBL-1092, NMA-TF-T1 | Lodged
NMA_CB_688 | 2027-02-15 07:30 | 2027-02-18 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_615_737 NMA-CBL-1092, NMA-TF-T1 | Lodged
FHL_WPW_2 | 2027-02-15 07:31 | 2027-02-19 18:31 | Continuous | RS - Removal from Service | Pole replacements x5. Condition assessments. | Lodged
HWA_SFD_1 | 2027-02-15 07:31 | 2027-02-17 18:31 | Continuous | OPE - Open Ended | OPE for the duration of SFD_T9, for post-contingent overloading prevention | Lodged
HWA_T2 | 2027-02-15 07:31 | 2027-02-17 18:31 | Continuous | OPE - Open Ended | OPE for the duration of HWA_SFD_1, to prevent recirculating currents through the HWA 33kV | Lodged
SFD_727_754 | 2027-02-15 07:31 | 2027-02-17 18:31 | Continuous | RS - Removal from Service | SFD-DS-754 headgear refurbishment [CP_RA3_03F_0_00]. | Lodged
SFD_CB_752 | 2027-02-15 07:31 | 2027-02-17 18:31 | Continuous | RS - Removal from Service | SFD-DS-754, SFD-DS-755 headgear refurbishments [CP_RA3_03F_0_00]. Affected equipment of SFD_727_754 & BRK_SFD_1. | Lodged
SFD_T9 | 2027-02-15 07:31 | 2027-02-17 18:31 | Continuous | RS - Removal from Service | Affected equipment of SFD_727_754 | Lodged
KMO_167_177_204 | 2027-02-15 07:31 | 2027-02-17 18:30 | Continuous | RS - Removal from Service | KMO-DS-177, KMO-DS-184, KMO-DS-194, KMO-DS-204, KMO-VT-177 | Lodged
KMO_CB_178 | 2027-02-15 07:31 | 2027-02-17 18:30 | Continuous | RS - Removal from Service | Affected equipment KMO_167_177_204 & KMO_MTM_1 & KMO_TMI_1 | Lodged
KMO_MTM_1 | 2027-02-15 07:31 | 2027-02-17 18:30 | Continuous | RS - Removal from Service | HAI-MTM-B0038-0039-10, KMO-DS-196, KMO-ES-199 | Lodged
KMO_T4 | 2027-02-15 07:31 | 2027-02-17 18:30 | Continuous | RS - Removal from Service | Affected equipment KMO_167_177_204 & KMO_MTM_1 & KMO_TMI_1 | Lodged
KMO_TMI_1 | 2027-02-15 07:31 | 2027-02-17 18:30 | Continuous | RS - Removal from Service | KMO-CT-202, KMO-ES-209, KMO-P-CB-202, TMI-CB-132 | Lodged
ARA_44_76 | 2027-02-15 07:31 | 2027-02-17 18:31 | Continuous | RS - Removal from Service | ARA 1DS mtce | Lodged
ARA_WRK_1 | 2027-02-15 07:31 | 2027-02-17 18:31 | Continuous | RS - Removal from Service | ARA 1DS mtce. Affected equipment of ARA_44_76. | Lodged
WRK_57_103_87 | 2027-02-15 07:31 | 2027-02-17 18:31 | Continuous | RS - Removal from Service | WRK 6DS mtce | Lodged
WRK_CB_108 | 2027-02-15 07:31 | 2027-02-17 18:31 | Continuous | RS - Removal from Service | Affected equipment of WRK_67_103_87. | Lodged
WRK_DIS_117 | 2027-02-15 07:31 | 2027-02-17 18:31 | Continuous | CLO - Close | CLO for the duration of WRK_57_103_87, to maintain a solid 220kV bus. | Lodged
HEN_MPE_2 | 2027-02-15 07:31 | 2027-02-19 18:31 | Continuous | RS - Removal from Service | HEN-CB-322, HEN-CT-322, HEN-DS-326, HEN-ES-329, HEN-MPE-A0027-20, HEN-MPE-A0043-20, HEN-MPE-A0079-20, HEN-MPE-A0082-0083-20, HEN-MPE-A0085-0086-20, HEN-MPE-A0086-20, HEN-MPE-A0108-0109-20, HEN-MPE-A0126-0127-20, HEN-MPE-A0132-0133-20, HEN-MPE-A0134-20, HEN-MPE-A0137-0138-20, HEN-MPE-A0156-20, HEN-MPE-A0162-20, HEN-MPE-A0163-20, HEN-MPE-A0183B-00, HEN-MPE-A0275-20, HEN-MPE-A0278-20, HEN-MPE-A0280-20, HEN-MPE-A0289-20, HEN-P-CB-322, MPE-P-CB-252 | Lodged
MTO_T2 | 2027-02-15 07:31 | 2027-02-19 18:31 | Continuous | RS - Removal from Service | Affected equipment HEN_MPE_2 & WEL_T1 | Lodged
WEL_T1 | 2027-02-15 07:31 | 2027-02-19 18:31 | Continuous | RS - Removal from Service | WEL-TF-T1B, WEL-TF-T1R | Lodged
BPE_MTR_1 | 2027-02-15 09:00 | 2027-02-27 18:30 | Continuous | RS - Removal from Service | MTR-REA-R92. Tower painting (A122-A130). | Lodged
ARI_BOB_1 | 2027-02-16 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | Pole Replacement | Lodged
ISL_66BZ | 2027-02-16 07:30 | 2027-02-16 18:30 | Daily | RS - Removal from Service | ISL-P-BZ-66 | Lodged
ISL_C_25 | 2027-02-16 07:30 | 2027-02-16 18:30 | Daily | RS - Removal from Service | ISL-CB-1492 | Lodged
ISL_220BS_E | 2027-02-17 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | ISL-DS-805 | Lodged
ISL_CB_658 | 2027-02-17 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_220BS_E ISL-DS-805 | Lodged
ISL_CB_688 | 2027-02-17 07:30 | 2027-02-19 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_220BS_E ISL-DS-805 | Lodged
HEN_220BZ_A1 | 2027-02-17 07:30 | 2027-02-18 18:30 | Daily | RS - Removal from Service | Affected equipment with HEN_220CBF | Lodged
HEN_220BZ_A2 | 2027-02-17 07:30 | 2027-02-18 18:30 | Daily | RS - Removal from Service | Affected equipment with HEN_220CBF | Lodged
HEN_220CBF | 2027-02-17 07:30 | 2027-02-18 18:30 | Daily | RS - Removal from Service | HEN-P-BZ-220 | Lodged
HAY_R1 | 2027-02-18 07:30 | 2027-02-18 18:30 | Daily | RS - Removal from Service | Affected equipment HAY_T1 & HAY_SC_1 | Lodged
HAY_T35 | 2027-02-18 07:30 | 2027-02-18 18:30 | Daily | RS - Removal from Service | S4.P2-AL.T2 | Lodged
OPK_SFD_1 | 2027-02-18 07:30 | 2027-02-18 18:30 | Daily | RS - Removal from Service | SFD-P-CB-162. Benchmarking [CP_VAR_1B7_0_00]. | Lodged
SFD_137_187 | 2027-02-18 07:30 | 2027-02-18 18:30 | Daily | RS - Removal from Service | SFD-DS-164, SFD-DS-167, SFD-DS-177 | Lodged
SFD_CB_148 | 2027-02-18 07:30 | 2027-02-18 18:30 | Daily | RS - Removal from Service | Affected equipment SFD_137_187 | Lodged
HAM_11KV_BS_A | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | RS - Removal from Service | HAM-M-VT2752 | Lodged
HAM_CB_2818 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | RS - Removal from Service | Affected Equipment of HAM_11KV_BS_A HAM-M-VT2752 | Lodged
HAM_FDR_2722 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | RS - Removal from Service | Affected Equipment of HAM_11KV_BS_A HAM-M-VT2752 | Lodged
HAM_FDR_2742 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | RS - Removal from Service | Affected Equipment of HAM_11KV_BS_A HAM-M-VT2752 | Lodged
HAM_FDR_2762 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | RS - Removal from Service | Affected Equipment of HAM_11KV_BS_A HAM-M-VT2752 | Lodged
HAM_FDR_2782 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | RS - Removal from Service | Affected Equipment of HAM_11KV_BS_A HAM-M-VT2752 | Lodged
HAM_FDR_2802 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | RS - Removal from Service | Affected Equipment of HAM_11KV_BS_A HAM-M-VT2752 | Lodged
HAM_T1 | 2027-02-19 07:30 | 2027-02-19 18:30 | Daily | RS - Removal from Service | HAM-M-VT2752 | Lodged
SFD_117_167 | 2027-02-19 07:31 | 2027-02-19 18:31 | Daily | RS - Removal from Service | SFD-DS-134, SFD-DS-137 | Lodged
SFD_CB_122 | 2027-02-19 07:31 | 2027-02-19 18:31 | Daily | OPE - Open Ended | OPE for the duration of SFD_117_167, to leave CST_JRD_1 leg in-service. | Lodged
SFD_CB_148 | 2027-02-19 07:31 | 2027-02-19 18:31 | Daily | RS - Removal from Service | SFD-DS-137. Affected equipment of SFD_117_167. | Lodged
SFD_T8 | 2027-02-19 07:31 | 2027-02-19 18:31 | Daily | RS - Removal from Service | SFD-DS-134. Affected equipment of SFD_117_167. | Lodged
FTB_OTB_CBL_4 | 2027-02-20 07:30 | 2027-02-21 18:30 | Continuous | RS - Removal from Service | FTB-P2-CBLT-4, FTB-P2-SA-3, OTB-P2-CBLT-4 | Lodged
FTB_OTB_CBL_5 | 2027-02-20 07:30 | 2027-02-21 18:30 | Continuous | RS - Removal from Service | FTB-P2/3-CBLT-5, FTB-P2/3-SA-2, OTB-P2/3-CBLT-5, OTB-P2/3-SA-2 | Lodged
FTB_OTB_CBL_6 | 2027-02-20 07:30 | 2027-02-21 18:30 | Continuous | RS - Removal from Service | FTB-P3-CBLT-6, FTB-P3-SA-1, OTB-P3-CBLT-6, OTB-P3-SA-1 | Lodged
HAY_THW_1A | 2027-02-20 07:30 | 2027-02-21 18:30 | Continuous | RS - Removal from Service | OTB-HAY-A0045-20, OTB-HAY-A0050A-20, OTB-HAY-A0065A-20, OTB-HAY-A0073-20 | Lodged
HAY_THW_1B | 2027-02-20 07:30 | 2027-02-21 18:30 | Daily | RS - Removal from Service | OTB-HAY-A0045-40, OTB-HAY-A0065A-40, OTB-HAY-A0073-40, OTB-HAY-A0076-40 | Lodged
ARI_HTI_1 | 2027-02-22 07:30 | 2027-02-26 18:30 | Continuous | RS - Removal from Service | CA Lift | Lodged
BRB_T3 | 2027-02-22 07:30 | 2027-02-25 18:30 | Continuous | RS - Removal from Service | BRB-CBL-182, BRB-TF-T3 | Lodged
BRK_CB_612 | 2027-02-22 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | BRK-CB-612, BRK-CT-612, BRK-P-CB-612. Affected equipment of BRK_SFD_2. | Lodged
BRK_SFD_2 | 2027-02-22 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | BRK-CB-602, BRK-CT-602, BRK-CVT-602, BRK-DS-603, BRK-DS-606, BRK-DS-615, BRK-ES-609, BRK-P-CB-602, BRK-P-CB-602/612, BRK-P-CB-642/652, SFD-CB-692, SFD-DS-683, SFD-DS-695, SFD-DS-696. (CVT requires no other work for 1/2 day). Tower recoating x10 (A165-A174) [CP_758_003_0_00]. | Lodged
BRY_C_5A | 2027-02-22 07:30 | 2027-02-26 18:30 | Continuous | RS - Removal from Service | Affected equipment BRY_T5 | Lodged
BRY_T5 | 2027-02-22 07:30 | 2027-02-26 18:30 | Continuous | RS - Removal from Service | BRY-REA-C5A, BRY-VT-VT492 | Lodged
GLN_T4 | 2027-02-22 07:30 | 2027-02-28 18:30 | Continuous | RS - Removal from Service | Surge arrestor & bushings replacement PJ, GLN-BS-220-T4-CLEAN, GLN-BS-33-T4-CLEAN, GLN-SA-4A, GLN-SA-4B, GLN-TF-T4 | Lodged
HAM_T7 | 2027-02-22 07:30 | 2027-02-26 18:30 | Continuous | RS - Removal from Service | CT replacement project. HAM-CT-1522 HAM T7 Traction Transformer Replace Bushing, Corrosion Repaint and Life Extension | Lodged
HKK_C7C8C9 | 2027-02-22 07:30 | 2027-02-22 18:30 | Daily | RS - Removal from Service | HKK-CB-1402 | Lodged
OHW_CB_312 | 2027-02-22 07:30 | 2027-02-27 18:30 | Continuous | RS - Removal from Service | OHW-CB-312, OHW-ES-3069, OHW-ES-3169 | Lodged
OHW_OTA_2 | 2027-02-22 07:30 | 2027-02-27 18:30 | Continuous | RS - Removal from Service | OHW-DS-296, OHW-DS-306, OHW-ES-299, OHW-VT-CVT292, OTA-WKM-C0306-0307-20, , OTA-WKM-C0363-0364-20, OTA-WKM-C0364-0365-20, OTA-WKM-C0365-0366-20, OTA-WKM-C0391-0392-20, OTA-WKM-C0449-0450-20, OTA-WKM-C0453-0454-20, OTA-WKM-C0455-0456-20, OTA-WKM-C0456-0457-20, OTA-WKM-C0488-0489-20 OHW-ES-2949, OHW-ES-2969, OHW-P-CB-292 | Lodged
MAN_NMA_2 | 2027-02-22 07:30 | 2027-02-27 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
IGH_ROB_1 | 2027-02-22 07:30 | 2027-02-26 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
EDG_217_207_324 | 2027-02-22 07:30 | 2027-02-24 18:30 | Continuous | RS - Removal from Service | EDG-DS-207, EDG-VT-VT207 | Lodged
EDG_KAW_2 | 2027-02-22 07:30 | 2027-02-24 18:30 | Continuous | RS - Removal from Service | EDG-KAW-B0076-10, EDG-KAW-B0078-10, EDG-KAW-B0080-10, EDG-KAW-B0084-10, KAW-CT-112, KAW-P-CB-112 | Lodged
HEN_MPE_1 | 2027-02-22 07:31 | 2027-02-26 18:31 | Continuous | RS - Removal from Service | HEN-MPE-A0001-0002-10, HEN-MPE-A0001-10, HEN-MPE-A0003-0004-10, HEN-MPE-A0005-0006-10, HEN-MPE-A0008-0009-10, HEN-MPE-A0022-00, HEN-MPE-A0043-10, HEN-MPE-A0080-00, HEN-MPE-A0088-00, HEN-MPE-A0092-10, HEN-MPE-A0105-00, HEN-MPE-A0111-00, HEN-MPE-A0111-10, HEN-MPE-A0112-0113-10, HEN-MPE-A0113-00, HEN-MPE-A0114-00, HEN-MPE-A0115-00, HEN-MPE-A0116-00, HEN-MPE-A0119-00, HEN-MPE-A0120-00, HEN-MPE-A0121-00, HEN-MPE-A0122-00, HEN-MPE-A0123-00, HEN-MPE-A0125-00, HEN-MPE-A0129-00, HEN-, HEN-P-CB-302, MPE-P-CB-292 | Lodged
MTO_T1 | 2027-02-22 07:31 | 2027-02-26 18:31 | Continuous | RS - Removal from Service | MTO-CB-1292, MTO-NCT-1, MTO-P-TF-T1, MTO-TF-LS1, MTO-TF-T1, MTO-VT-11 | Lodged
WEL_T2 | 2027-02-22 07:31 | 2027-02-26 18:31 | Continuous | RS - Removal from Service | Affected equipment HEN_MPE_1 & MTO_T1 | Lodged
WRK_CB_112 | 2027-02-23 07:30 | 2027-02-23 18:30 | Daily | RS - Removal from Service | WRK-CB-112 (WKM_1) pole replacement [CP_WRK_00U_0_00]. Affected equipment of WKM_WRK_1. | Lodged
WRK_44_57_197 | 2027-02-23 07:31 | 2027-02-23 18:31 | Daily | RS - Removal from Service | WRK 2DS mtce | Lodged
WRK_CB_198 | 2027-02-23 07:31 | 2027-02-23 18:31 | Daily | RS - Removal from Service | Affected equipment of WRK_44_57_197 | Lodged
WRK_T30 | 2027-02-23 07:31 | 2027-02-23 18:31 | Daily | RS - Removal from Service | WRK 1TF mtce. Affected equipment of WRK_44_57_197, for 2DS mtce. | Lodged
SFD_617_647 | 2027-02-23 07:31 | 2027-02-25 18:31 | Continuous | RS - Removal from Service | SFD-DS-614. LOC to SPL. | Lodged
SFD_CB_612 | 2027-02-23 07:31 | 2027-02-25 18:31 | Continuous | RS - Removal from Service | SFD-CT-612, SFD-CVT-22, SFD-DS-616, SFD-ES-619, SFD-P-CB-612. Affected equipment of SFD_617_647. | Lodged
KMO_T2 | 2027-02-24 07:30 | 2027-02-26 18:30 | Continuous | RS - Removal from Service | KMO-CBL-T2-ET2, KMO-TF-ET2, KMO-TF-T2 | Lodged
SFD_524_617 | 2027-02-24 07:31 | 2027-02-24 18:31 | Daily | RS - Removal from Service | SFD-DS-554. LOC to G22. | Lodged
SFD_CB_552 | 2027-02-24 07:31 | 2027-02-24 18:31 | Daily | RS - Removal from Service | SFD-DS-554. LOC to G22. Affected equipment of SFD_524_617. | Lodged
SFD_CB_582 | 2027-02-24 07:31 | 2027-02-24 18:31 | Daily | RS - Removal from Service | Affected equipment of SFD_524_617, for SFD-DS-554 | Lodged
BEN_220BS_A | 2027-02-25 07:30 | 2027-02-25 18:30 | Daily | RS - Removal from Service | Affected Equipment of BEN_CB_408 BEN-CT-CT408 | Lodged
BEN_CB_408 | 2027-02-25 07:30 | 2027-02-25 18:30 | Daily | RS - Removal from Service | BEN-CT-CT408 | Lodged
HAY_WIL_LTN_1 | 2027-02-26 07:30 | 2027-02-26 18:30 | Daily | RS - Removal from Service | Reinstate droppers on JFD_LTN_1 [CP_770_007_0_00]. | Lodged
TKA_T6 | 2027-02-26 07:30 | 2027-02-26 18:30 | Daily | RS - Removal from Service | TKA-TF-T6 | Lodged
MTR_OKN_1 | 2027-02-28 07:30 | 2027-02-28 18:30 | Daily | RS - Removal from Service | Affected equipment of OKN site shut (alternate date 7/03/27) | Lodged
OKN_72_82_92 | 2027-02-28 07:30 | 2027-02-28 18:30 | Daily | RS - Removal from Service | Affected equipment of OKN site shut (alternate date 7/03/27) | Lodged
OKN_CB_38 | 2027-02-28 07:30 | 2027-02-28 18:30 | Daily | RS - Removal from Service | Affected equipment of OKN site shut (alternate date 7/03/27) | Lodged
OKN_CB_39 | 2027-02-28 07:30 | 2027-02-28 18:30 | Daily | RS - Removal from Service | Affected equipment of OKN site shut (alternate date 7/03/27) | Lodged
OKN_CB_72 | 2027-02-28 07:30 | 2027-02-28 18:30 | Daily | OPE - Open Ended | OPE for OKN site shut (alternate date 7/03/27), to leave NPK_ONG_1 leg in-service | Lodged
OKN_T2 | 2027-02-28 07:30 | 2027-02-28 18:30 | Daily | RS - Removal from Service | OKN site shut (alternate date 7/03/27). OKN-TF-T2. | Lodged
ARI_HTI_ONG_1 | 2027-03-01 07:30 | 2027-03-12 18:30 | Continuous | RS - Removal from Service | Tower painting x10 (B231-B240) [CP_708_002_0_00] | Lodged
BPE_TKU_1 | 2027-03-01 07:30 | 2027-05-14 18:30 | Continuous | RS - Removal from Service | BPE-TKU-A/B TTU project. Tower works x8 (A11-12, A14-A17, A32, A36). Tower painting x20 (A52-A72) [CP_716_004_0_00]. | Lodged
GLN_CB_2348 | 2027-03-01 07:30 | 2027-03-07 18:30 | Continuous | CLO - Close | Closed for the duration of GLN T6 outage | Lodged
GLN_DIS_2347 | 2027-03-01 07:30 | 2027-03-07 18:30 | Continuous | CLO - Close | Closed for the duration of GLN T6 outage | Lodged
GLN_T6 | 2027-03-01 07:30 | 2027-03-07 18:30 | Continuous | RS - Removal from Service | Surge arrestor & bushings replacement PJ, GLN-BS-220-T6-CLEAN, GLN-BS-33-T6-CLEAN, GLN-SA-6A, GLN-SA-6B, GLN-TF-T6 | Lodged
HAY_WIL_LTN_2 | 2027-03-01 07:30 | 2027-03-02 18:29 | Continuous | RS - Removal from Service | HAY-CT-532, WIL-CB-882. Tower painting x19 (A57-A75). Remove JFD_LTN_2 droppers for tower painting [CP_770_007_0_00]. | Lodged
MDN_STC_6 | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | MDN-P-PSUP-STC6-UPS-1, MDN-STC-6, MDN-STC6-VCS | Lodged
MTI_RTU_1 | 2027-03-01 07:30 | 2027-03-01 18:30 | Daily | RS - Removal from Service | SMS & GPS replacements [CP_RA3_03C_0_00] | Lodged
MTI_WKM_2 | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | WKM CT maintenance. Tower painting x6 (B1-B3, B15, B23-B24) [CP_704_001_0_00]. | Lodged
MTI_WPA_1 | 2027-03-01 07:30 | 2027-03-12 18:30 | Continuous | RS - Removal from Service | MTI-P-CB-92 [CP_MTI_002_0_00]. Tower painting x13 (A1-A13) [CP_702_001_0_00]. | Lodged
NMA_220BS_A3 | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | pdm maint. | Lodged
NMA_CB_708 | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A3 pdm maint. | Lodged
NMA_CB_718 | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A3 pdm maint. | Lodged
WPR_T13 | 2027-03-01 07:30 | 2027-03-03 18:30 | Continuous | RS - Removal from Service | WPR-P-TF-T13, WPR-TF-T13 | Lodged
IGH_ROB_1 | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | CA Lifting INSPECTIONS | Lodged
IGH_MCH_1 | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
INV_MAN_2 | 2027-03-01 07:30 | 2027-03-06 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
PNI_237_294 | 2027-03-01 07:30 | 2027-03-02 18:30 | Continuous | RS - Removal from Service | PNI-BS-33-237-294 | Lodged
PNI_FDR_292 | 2027-03-01 07:30 | 2027-03-02 18:30 | Continuous | RS - Removal from Service | Affected equipment PNI_237_294 & PNI_T2 | Lodged
PNI_LST_1 | 2027-03-01 07:30 | 2027-03-02 18:30 | Continuous | RS - Removal from Service | Affected equipment PNI_237_294 & PNI_T2 | Lodged
PNI_T2 | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | PNI-CB-282, PNI-CB-92, PNI-CT-92, PNI-DS-94, PNI-ES-99, PNI-NCT-T2, PNI-P-TF-T2, PNI-TF-T2, PNI-VT-282, PNI-VT-94. Corrosive sulphur work. No metering. | Lodged
PNI_TKR_2 | 2027-03-01 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | Affected equipment PNI_237_294 & PNI_T2 | Lodged
TRK_220BZ_A | 2027-03-01 07:30 | 2027-03-03 18:30 | Continuous | RS - Removal from Service | TRK-P-BZ-220-A | Lodged
TRK_220CBF | 2027-03-01 07:30 | 2027-03-03 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
BRB_MDN_1 | 2027-03-01 07:31 | 2027-03-05 18:31 | Continuous | RS - Removal from Service | BRB-DEV-A0406-0407-20, BRB-DEV-A0411-BRBB2-10, BRB-SA-172, HEN-MDN-A0331-00, MDN-CVT-CVT472, MDN-DS-476, MDN-ES-479, MDN-P-CB-472 | Lodged
MDN_297_237_257 | 2027-03-01 07:31 | 2027-03-05 18:31 | Continuous | RS - Removal from Service | MDN-DS-237 | Lodged
MDN_457_494_497 | 2027-03-01 07:31 | 2027-03-05 18:31 | Continuous | RS - Removal from Service | MDN-DS-467, MDN-DS-474, MDN-DS-494, MDN-DS-497 | Lodged
MDN_CB_308 | 2027-03-01 07:31 | 2027-03-05 18:31 | Continuous | RS - Removal from Service | Affected equipment MDN_297_237_257 & MDN_MPE_2 & MDN_T6 & MDN_STC_6 | Lodged
MDN_CB_508 | 2027-03-01 07:31 | 2027-03-05 18:31 | Continuous | RS - Removal from Service | Affected equipment MDN_457_494_497 & BRB_MDN_1 & MDN_T6 & MDN_STC_6 | Lodged
MDN_LST_6B | 2027-03-01 07:31 | 2027-03-05 18:31 | Continuous | RS - Removal from Service | Affected equipment MDN_457_494_497 & BRB_MDN_1 & MDN_T6 & MDN_STC_6 | Lodged
MDN_MPE_2 | 2027-03-01 07:31 | 2027-03-05 18:31 | Continuous | RS - Removal from Service | MDN-CT-252, MDN-DS-256, MDN-ES-259, MDN-MPE-A0012-0013-20, MDN-MPE-A0013-0014-20, MDN-MPE-A0084-MPEG3-10, MDN-P-CB-252, MDN-VT-VT252, MPE-P-CB-272 | Lodged
MDN_T6 | 2027-03-01 07:31 | 2027-03-05 18:31 | Continuous | RS - Removal from Service | MDN-P-CB-232 | Lodged
MPE_CB_252 | 2027-03-01 07:31 | 2027-03-01 22:00 | Daily | OPE - Open Ended | System split for the duration of MDN_MPE_2 | Lodged
MPE_CB_292 | 2027-03-01 07:31 | 2027-03-01 22:00 | Daily | OPE - Open Ended | System split for the duration of MDN_MPE_2 | Lodged
MPE_CB_252 | 2027-03-02 06:00 | 2027-03-04 22:00 | Continuous | OPE - Open Ended | System split for the duration of MDN_MPE_2 | Lodged
MPE_CB_292 | 2027-03-02 06:00 | 2027-03-04 22:00 | Continuous | OPE - Open Ended | System split for the duration of MDN_MPE_2 | Lodged
HAY_CB_2772 | 2027-03-02 07:00 | 2027-03-07 18:00 | Continuous | RS - Removal from Service | Affected equipment of HAY_T12, for HAY_110BZ Stage 3M; Bay 270 - Transformer T12. | Lodged
HAY_FDR_1052 | 2027-03-02 07:00 | 2027-03-07 18:00 | Continuous | RS - Removal from Service | Affected equipment of HAY_T12, for HAY_110BZ Stage 3M; Bay 270 - Transformer T12. | Lodged
HAY_T12 | 2027-03-02 07:00 | 2027-03-07 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3M; Bay 270 - Transformer T12. No other HAY work on days 1, 5, 6. No other work on associated equipment/lines on day 6 (commissioning). | Lodged
SFD_637_667 | 2027-03-02 07:31 | 2027-03-04 18:31 | Continuous | RS - Removal from Service | SFD-DS-634. LOC to SPL. | Lodged
SFD_667_697 | 2027-03-02 07:31 | 2027-03-04 18:31 | Continuous | RS - Removal from Service | SFD-DS-664, SFD-DS-697 headgear refurbishments [CP_RA3_03F_0_00]. | Lodged
SFD_CB_612 | 2027-03-02 07:31 | 2027-03-04 18:31 | Continuous | RS - Removal from Service | SFD-CT-612, SFD-CVT-22, SFD-DS-616, SFD-ES-619, SFD-P-CB-612. Affected equipment of SFD_637_667. | Lodged
SFD_CB_662 | 2027-03-02 07:31 | 2027-03-04 18:31 | Continuous | RS - Removal from Service | Affected equipment of SFD_667_727, for SFD-DS-664, SFD-DS-697. | Lodged
HAY_110BZ | 2027-03-02 08:00 | 2027-03-02 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3M; Bay 270 - Transformer T12. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-03-02 08:00 | 2027-03-02 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3M; Bay 270 - Transformer T12. | Lodged
JFD_LTN_2 | 2027-03-02 18:30 | 2027-03-19 07:29 | Continuous | RS - Removal from Service | Tower painting x19 (A57-A75) [CP_770_007_0_00]. JFD_LTN_2 droppers removed to leave HAY_WIL_2 in-service. | Lodged
APS_FDR_622 | 2027-03-03 07:30 | 2027-03-04 18:30 | Continuous | RS - Removal from Service | Affected equipment APS_T1 | Lodged
APS_T1 | 2027-03-03 07:30 | 2027-03-04 18:30 | Continuous | RS - Removal from Service | APS-TF-T1B, APS-TF-T1R, APS-TF-T1Y | Lodged
BEN_T29 | 2027-03-03 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | BEN-CB-852, BEN-NCTD-T29, BEN-TF-T29 | Lodged
WKM_TIE_1 | 2027-03-03 07:30 | 2027-03-04 18:30 | Continuous | RS - Removal from Service | WKM-CVT-522, WKM-DS-335 | Lodged
ISL_220BS_C | 2027-03-03 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | ISL-DS-423 | Lodged
ISL_C_22 | 2027-03-03 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | Affected equipment ISL_220BS_C | Lodged
ISL_CB_608 | 2027-03-03 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | Affected equipment ISL_220BS_C | Lodged
ISL_CB_628 | 2027-03-03 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | Affected equipment ISL_220BS_C | Lodged
ISL_T2 | 2027-03-03 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | Affected equipment ISL_220BS_C | Lodged
EDG_427_437_447 | 2027-03-03 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | Headgear refurbishment EDG-DS-437 | Lodged
EDG_T5 | 2027-03-03 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | Affected equipment EDG_427_437_447 & EDG_TRK_2 | Lodged
EDG_TRK_2 | 2027-03-03 07:30 | 2027-03-05 18:30 | Continuous | RS - Removal from Service | EDG-TRK-A0048-20, EDG-TRK-A0067-20, EDG-TRK-A0079-20, EDG-TRK-A0092-20, EDG-TRK-A0100-0101-20, EDG-TRK-A0100-20, EDG-TRK-A0105-20, EDG-TRK-A0106-20, EDG-TRK-A0108-20, EDG-TRK-A0109-20, EDG-TRK-A0110-20, EDG-TRK-A0112-20, EDG-TRK-A0114-20, EDG-TRK-A0124-20, EDG-TRK-A0131-20, EDG-TRK-A0133-20, EDG-TRK-A0138-20, TRK-DS-366 | Lodged
WKM_220BS_C | 2027-03-03 07:31 | 2027-03-04 18:31 | Continuous | RS - Removal from Service | WKM-DS-55 (MTI_2), WKM-DS-65 (OTA_1), WKM-DS-145 (G1), WKM-DS-155 (G2), WKM-DS-165 (G3), WKM-DS-297 (BC). | Lodged
WKM_CB_228 | 2027-03-03 07:31 | 2027-03-04 18:31 | Continuous | RS - Removal from Service | Affected equipment of WKM_220BS_C, for WKM 6DS mtce. | Lodged
WKM_CB_288 | 2027-03-03 07:31 | 2027-03-04 18:31 | Continuous | RS - Removal from Service | Affected equipment of WKM_220BS_C, for WKM 6DS mtce. | Lodged
MPE_CB_252 | 2027-03-05 06:00 | 2027-03-05 18:30 | Daily | OPE - Open Ended | System split for the duration of MDN_MPE_2 | Lodged
MPE_CB_292 | 2027-03-05 06:00 | 2027-03-05 18:30 | Daily | OPE - Open Ended | System split for the duration of MDN_MPE_2 | Lodged
HAY_110BZ | 2027-03-06 08:00 | 2027-03-06 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3M; Bay 270 - Transformer T12. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-03-06 08:00 | 2027-03-06 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3M; Bay 270 - Transformer T12. | Lodged
MGM_MST_1 | 2027-03-07 07:30 | 2027-03-12 18:30 | Continuous | RS - Removal from Service | MGM-CB-172, MGM-CT-172, MGM-DS-176, MGM-ES-179, MGM-P-CB-172, MGM-VT-172. Last day for VT testing - no lines. Pole replacements x6. | Lodged
HAY_110BZ | 2027-03-07 08:00 | 2027-03-07 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3M; Bay 270 - Transformer T12. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-03-07 08:00 | 2027-03-07 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3M; Bay 270 - Transformer T12. | Lodged
ISL_FDR_192 | 2027-03-08 06:30 | 2027-03-12 18:30 | Continuous | RS - Removal from Service | ISL-CB-192, ISL-CT-CT192, ISL-DS-196, ISL-DS-193, ISL-DS-195. CY4 Re-planned. | Lodged
ISL_CB_708 | 2027-03-08 06:30 | 2027-03-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment ISL-DS-193 and Hot-end hardware corroded. CY4 Re-planned. | Lodged
ISL_CB_768 | 2027-03-08 06:30 | 2027-03-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment ISL-DS-193 and Hot-end hardware corroded. CY4 Re-planned. | Lodged
ABY_TIM_1 | 2027-03-08 07:30 | 2027-03-12 18:30 | Continuous | RS - Removal from Service | TKA-TIM-A0314-00 TKA-TIM-A0320-00 TKA-TIM-A0386-00 TKA-TIM-A0399-00 TKA-TIM-A0410-00 | Lodged
APS_OTI_1 | 2027-03-08 07:30 | 2027-03-13 18:30 | Continuous | RS - Removal from Service | structure replacement COL-OTI-A0467-00, COL-OTI-A0468-00, COL-OTI-A0469-00, COL-OTI-A0470-00, COL-OTI-A0472-00, COL-OTI-A0473-00, COL-OTI-A0474-00, COL-OTI-A0475-00, COL-OTI-A0476-00, COL-OTI-A0477-00, COL-OTI-A0478-00, COL-OTI-A0524-00, COL-OTI-A0505A, COL-OTI-A0505A-0507A-10, COL-OTI-A0486-0487-10 | Lodged
COL_OTI_2 | 2027-03-08 07:30 | 2027-03-13 18:30 | Continuous | RS - Removal from Service | structure replacement COL-OTI-A0467-00, COL-OTI-A0468-00, COL-OTI-A0469-00, COL-OTI-A0470-00, COL-OTI-A0472-00, COL-OTI-A0473-00, COL-OTI-A0474-00, COL-OTI-A0475-00, COL-OTI-A0476-00, COL-OTI-A0477-00, COL-OTI-A0478-00, COL-OTI-A0524-00, COL-OTI-A0505A, COL-OTI-A0505A-0507A-10, COL-OTI-A0486-0487-10 | Lodged
MTI_WKM_1 | 2027-03-08 07:30 | 2027-03-12 18:30 | Continuous | RS - Removal from Service | Tower painting x7 (A1-A3, A16, A23-A25) [CP_703_001_0_00]. | Lodged
ROS_FDR_62 | 2027-03-08 07:30 | 2027-03-12 18:30 | Continuous | RS - Removal from Service | Protection replacement ROS-P-CB-62 | Lodged
MAN_NMA_3 | 2027-03-08 07:30 | 2027-03-13 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
WKM_220BS_C | 2027-03-08 07:30 | 2027-03-08 18:30 | Daily | RS - Removal from Service | WKM-DS-45 (MTI_1), WKM-DS-75 (OTA_2), WKM-DS-325 (TIE_2). | Lodged
WKM_CB_228 | 2027-03-08 07:30 | 2027-03-08 18:30 | Daily | RS - Removal from Service | Affected equipment of WKM_220BS_C, for WKM 3DS mtce. | Lodged
WKM_CB_288 | 2027-03-08 07:30 | 2027-03-08 18:30 | Daily | RS - Removal from Service | Affected equipment of WKM_220BS_C, for WKM 3DS mtce. | Lodged
BOB_T4 | 2027-03-08 07:31 | 2027-03-12 18:31 | Continuous | RS - Removal from Service | BOB-TF-T4 | Lodged
DRY_BOB_HLY_1 | 2027-03-08 07:31 | 2027-03-12 18:31 | Continuous | RS - Removal from Service | Attachment point replacements PJ. HLY-OTA-A0063-10, HLY-OTA-A0092-10, HLY-OTA-A0095-10, HLY-OTA-A0099-10, HLY-OTA-A0100-10, HLY-OTA-A0104-10, HLY-OTA-A0106-10, HLY-OTA-A0107-10, HLY-OTA-A0111-10, HLY-OTA-A0118-10 | Lodged
MTO_T1 | 2027-03-08 08:00 | 2027-03-13 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
WEL_T2 | 2027-03-08 08:00 | 2027-03-13 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
ARI_BOB_1 | 2027-03-09 07:30 | 2027-03-13 18:30 | Continuous | RS - Removal from Service | Pole Replacement | Lodged
EDG_220BZ | 2027-03-09 07:30 | 2027-03-11 18:30 | Continuous | RS - Removal from Service | EDG-P-BZ-220 | Lodged
EDG_220CBF | 2027-03-09 07:30 | 2027-03-11 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
HOB_WRD_1 | 2027-03-10 07:30 | 2027-03-12 18:30 | Continuous | RS - Removal from Service | HOB-VT-VT152, WRD-CT-NCT182A, WRD-CT-NCT182B, WRD-REA-R182, WRD-VT-VT182. HOB-WRD-A-CBL-13 Yph Sheath Repair MP_649_002_0_00 | Lodged
PEN_1678_2213_2215 | 2027-03-10 07:30 | 2027-03-10 18:30 | Daily | RS - Removal from Service | PEN-CBL-1678-2213/2215 | Lodged
SVL_FDR_2862 | 2027-03-10 07:30 | 2027-03-10 18:30 | Daily | RS - Removal from Service | SVL-CBL-2862 | Lodged
KMO_TRK_1 | 2027-03-10 07:30 | 2027-03-12 18:30 | Continuous | RS - Removal from Service | Affected equipment TRK_567_607_627 & TRK_CB_618 | Lodged
TRK_567_607_627 | 2027-03-10 07:30 | 2027-03-12 18:30 | Continuous | RS - Removal from Service | TRK-DS-607 | Lodged
TRK_CB_618 | 2027-03-10 07:30 | 2027-03-12 18:30 | Continuous | RS - Removal from Service | TRK-CB-618, TRK-CT-618 | Lodged
TRK_DIS_407 | 2027-03-10 07:30 | 2027-03-12 18:30 | Continuous | CLO - Close | Closed for the duration of TRK_CB_618 | Lodged
BEN_F_7 | 2027-03-10 08:00 | 2027-03-12 18:00 | Continuous | RS - Removal from Service | S1.20DB80-FB7, S1.20DB80-Q02 | Lodged
ISL_CB_728 | 2027-03-12 06:30 | 2027-03-12 18:30 | Daily | RS - Removal from Service | Affected Equipment ISL-DS-195. CY4 Re-planned. | Lodged
ISL_CB_748 | 2027-03-12 06:30 | 2027-03-12 18:30 | Daily | RS - Removal from Service | Affected Equipment ISL-DS-195. CY4 Re-planned. | Lodged
BDE_GOR_1 | 2027-03-14 07:30 | 2027-03-21 18:30 | Continuous | RS - Removal from Service | GOR-INV-A0014-00 GOR-INV-A0019-00 GOR-INV-A0039-00 | Lodged
BPE_MTR_1 | 2027-03-14 07:31 | 2027-03-14 18:31 | Daily | RS - Removal from Service | Affected equipment of MTR site shut (alternate date 21/03/27) | Lodged
MTR_1064_1074_1114 | 2027-03-14 07:31 | 2027-03-14 18:31 | Daily | RS - Removal from Service | Affected equipment of MTR site shut (alternate date 21/03/27) | Lodged
MTR_54_94 | 2027-03-14 07:31 | 2027-03-14 18:31 | Daily | RS - Removal from Service | Affected equipment of MTR site shut (alternate date 21/03/27) | Lodged
MTR_FDR_1072 | 2027-03-14 07:31 | 2027-03-14 18:31 | Daily | RS - Removal from Service | Affected equipment of MTR site shut (alternate date 21/03/27) | Lodged
MTR_FDR_1092 | 2027-03-14 07:31 | 2027-03-14 18:31 | Daily | RS - Removal from Service | Affected equipment of MTR site shut (alternate date 21/03/27) | Lodged
MTR_FDR_1112 | 2027-03-14 07:31 | 2027-03-14 18:31 | Daily | RS - Removal from Service | Affected equipment of MTR site shut (alternate date 21/03/27) | Lodged
MTR_LST_1 | 2027-03-14 07:31 | 2027-03-14 18:31 | Daily | RS - Removal from Service | Affected equipment of MTR site shut (alternate date 21/03/27) | Lodged
MTR_OKN_1 | 2027-03-14 07:31 | 2027-03-14 18:31 | Daily | RS - Removal from Service | Affected equipment of MTR site shut (alternate date 21/03/27) | Lodged
MTR_T2 | 2027-03-14 07:31 | 2027-03-14 18:31 | Daily | RS - Removal from Service | MTR site shut (alternate date 21/03/27). MTR-TF-T2B, MTR-TF-T2R, MTR-TF-T2Y. | Lodged
ABY_TIM_1 | 2027-03-15 07:30 | 2027-03-17 18:30 | Continuous | RS - Removal from Service | TKA-TIM-A0450-00 TKA-TIM-A0454-00 | Lodged
ALB_T8 | 2027-03-15 07:30 | 2027-03-19 18:30 | Continuous | RS - Removal from Service | ALB T8 Transformer Protection Replacement | Lodged
APS_CLH_1 | 2027-03-15 07:30 | 2027-03-19 18:30 | Continuous | RS - Removal from Service | STRUCTURE REPLACEMENTS | Lodged
ARI_HAM_2 | 2027-03-15 07:30 | 2027-03-20 18:30 | Continuous | RS - Removal from Service | ARI-HAM-B0061-20, ARI-HAM-B0062-20, ARI-HAM-B0072-20, ARI-HAM-B0073-20, ARI-HAM-B0074-20, ARI-HAM-B0080-20, ARI-HAM-B0081-20, ARI-HAM-B0082-20, ARI-HAM-B0093-20, ARI-HAM-B0108-20, ARI-HAM-B0119-20, ARI-HAM-B0120-20, ARI-HAM-B0129-20, ARI-HAM-B0132-20, ARI-HAM-B0135-20, ARI-HAM-B0136-20, ARI-HAM-B0140-20 | Lodged
BPE_TWC_LTN_1 | 2027-03-15 07:30 | 2027-03-16 18:30 | Continuous | RS - Removal from Service | LTN-CVT-CVT262. BPE-WIL-A0050-10. No lines work day 1. | Lodged
COL_OTI_2 | 2027-03-15 07:30 | 2027-03-19 18:30 | Continuous | RS - Removal from Service | STRUCTURE REPLACEMENTS COL-OTI-A0241-00, COL-OTI-A0242-00, COL-OTI-A0382-00, COL-OTI-A0361-0362-10 | Lodged
EDG_TRK_2 | 2027-03-15 07:30 | 2027-03-20 18:30 | Continuous | RS - Removal from Service | Attachment Points | Lodged
INV_ROX_2 | 2027-03-15 07:30 | 2027-03-19 18:30 | Continuous | RS - Removal from Service | INV-ROX-B0027-00, INV-ROX-B0028-00, INV-ROX-B0029-00, INV-ROX-B0030-00, INV-ROX-B0031-00, INV-ROX-B0032-00, INV-ROX-B0036-00, INV-ROX-B0042-00, INV-ROX-B0043-00, INV-ROX-B0046-00, INV-ROX-B0048-00, INV-ROX-B0050-00, INV-ROX-B0051-00 | Lodged
LTN_AVR_T3 | 2027-03-15 07:30 | 2027-03-16 18:30 | Continuous | RS - Removal from Service | Affected equipment of LTN_T3. | Lodged
LTN_T3 | 2027-03-15 07:30 | 2027-03-16 18:30 | Continuous | RS - Removal from Service | Affected equipment of BPE_TWC_LTN_1. | Lodged
NMA_CB_718 | 2027-03-15 07:30 | 2027-03-19 18:30 | Continuous | RS - Removal from Service | NMA-CT-CT718 | Lodged
OTA_ROS_1 | 2027-03-15 07:30 | 2027-03-16 18:30 | Continuous | RS - Removal from Service | 2 yrs, OTA-PEN-B0002A-0003-10, OTA-PEN-B1-Z-CBL-SHEATH | Lodged
RDF_T4 | 2027-03-15 07:30 | 2027-03-25 18:30 | Continuous | RS - Removal from Service | RDF-TF-T4 | Lodged
IGH_ROB_1 | 2027-03-15 07:30 | 2027-03-19 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
HAM_T4 | 2027-03-15 07:30 | 2027-03-19 18:30 | Continuous | RS - Removal from Service | HAM CT replacement project | Lodged
HAM_387_404_447 | 2027-03-15 07:31 | 2027-03-16 18:31 | Continuous | RS - Removal from Service | HAM-DS-404, HAM-DS-407, HAM-DS-427 | Lodged
HAM_T4 | 2027-03-15 07:31 | 2027-03-19 18:31 | Continuous | RS - Removal from Service | HAM-CBL-ET4-NER4, HAM-CBL-T4-2242, HAM-CBL-T4-ET4, HAM-CT-402, HAM-NCT-4, HAM-P-TF-T4, HAM-RES-NER4, HAM-TF-ET4, HAM-TF-T4 | Lodged
MTO_T2 | 2027-03-15 08:00 | 2027-03-20 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
WEL_T1 | 2027-03-15 08:00 | 2027-03-20 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
HAY_TKR_2 | 2027-03-16 07:00 | 2027-03-20 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3A; Bay 60 - Takapu Rd cct 2. No other HAY work on days 1, 4, 5. No other work on associated equipment/lines on day 5 (commissioning). | Lodged
BEN_F_3 | 2027-03-16 07:30 | 2027-03-18 18:30 | Continuous | RS - Removal from Service | S1.WA-Z2.Q1, S1.WA-Z2.Q2, S1.WA-Z2.Z1.L1A, S1.WA-Z2.Z1.L1B, S1.WA-Z2.Z1.L1C, S1.WA-Z2.Z1.L2A, S1.WA-Z2.Z1.L2B, S1.WA-Z2.Z1.L2C, S1.WA-Z2.Z2.L1A, S1.WA-Z2.Z2.L1B, S1.WA-Z2.Z2.L1C, S1.WA-Z2.Z2.R1A, S1.WA-Z2.Z2.R1B | Lodged
CUL_FDR_142 | 2027-03-16 07:30 | 2027-03-19 18:30 | Continuous | RS - Removal from Service | CUL-CB-142, CUL-P-CB-142 | Lodged
OHB_1007_1107 | 2027-03-16 07:30 | 2027-03-16 18:30 | Daily | RS - Removal from Service | OHB-DS-1014 | Lodged
PNI_T2 | 2027-03-16 07:30 | 2027-03-19 18:29 | Continuous | RS - Removal from Service | Metering only required if not completed in 2026. Affected equipment of PNI_TKR_2. | Lodged
PNI_TKR_2 | 2027-03-16 07:30 | 2027-03-19 18:29 | Continuous | RS - Removal from Service | Affected equipment of TKR_127_174_184 | Lodged
TKR_127_174_184 | 2027-03-16 07:30 | 2027-03-19 18:30 | Continuous | RS - Removal from Service | TKR-DS-147, TKR-DS-164, TKR-DS-174, TKR-VT-1 | Lodged
TKR_CB_172_ITRIP | 2027-03-16 07:30 | 2027-03-19 18:30 | Continuous | RS - Removal from Service | TKR-P-ITRP-CB-92-172 | Lodged
TKR_T1 | 2027-03-16 07:30 | 2027-03-19 18:30 | Continuous | RS - Removal from Service | Affected equipment of TKR_127_174_184 | Lodged
TKR_WIL_2 | 2027-03-16 07:30 | 2027-03-19 18:30 | Continuous | RS - Removal from Service | Re-insulation x2. Attachment points. Affected equipment of TKR_127_174_184. | Lodged
TKR_FDR_2272 | 2027-03-16 07:31 | 2027-03-17 18:31 | Continuous | RS - Removal from Service | Reinsulation x2 structures | Lodged
HAY_110BZ | 2027-03-16 08:00 | 2027-03-16 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3A; Bay 60 - Takapu Rd cct 2. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-03-16 08:00 | 2027-03-16 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3A; Bay 60 - Takapu Rd cct 2. | Lodged
AVI_BEN_1 | 2027-03-17 07:30 | 2027-03-18 18:30 | Daily | RS - Removal from Service | AVI-BEN-A0002-00, AVI-BEN-A0041-00 | Lodged
OHB_1106_1107 | 2027-03-17 07:30 | 2027-03-17 18:30 | Daily | RS - Removal from Service | OHB-DS-1114 | Lodged
SBK_66BZ | 2027-03-17 07:30 | 2027-03-17 18:30 | Daily | RS - Removal from Service | SBK-P-BZ-66 | Lodged
ABY_TKA_1 | 2027-03-18 07:30 | 2027-03-19 18:30 | Continuous | RS - Removal from Service | TKA-TIM-A0191-00 | Lodged
ROS_AUVLS | 2027-03-18 07:30 | 2027-03-18 18:30 | Daily | RS - Removal from Service | ROS-P-UVLS | Lodged
TKA_T6 | 2027-03-18 07:30 | 2027-03-19 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ABY_TKA_1 TKA-TIM-A0191-00 | Lodged
HAM_T8 | 2027-03-18 07:30 | 2027-03-19 18:30 | Continuous | RS - Removal from Service | CT stability checks HAM CT replacement project | Lodged
HAM_CB_1522 | 2027-03-18 07:30 | 2027-03-19 18:30 | Continuous | CLO - Close | Place HAM T7 into service for the duration of T8 outage. CT stability checks HAM CT replacement project | Lodged
TKR_FDR_2142 | 2027-03-18 07:31 | 2027-03-19 18:31 | Continuous | RS - Removal from Service | KHD-TKR-A0037-00, TKR gantry reinsulation/attachment points. | Lodged
HAM_CB_1522 | 2027-03-18 07:31 | 2027-03-19 18:31 | Continuous | CLO - Close | Place T7 into service for duration of T8 | Lodged
HAM_T8 | 2027-03-18 07:31 | 2027-03-19 18:31 | Continuous | RS - Removal from Service | Ref CT for stability tests | Lodged
HAY_WIL_LTN_2 | 2027-03-19 07:30 | 2027-03-19 18:30 | Daily | RS - Removal from Service | Reinstate JFD_LTN_2 droppers [CP_770_007_0_00]. | Lodged
PEN_FDR_2442 | 2027-03-19 07:30 | 2027-03-19 18:30 | Daily | RS - Removal from Service | PEN-CB-2442, PEN-P-CB-2442 | Lodged
PTS_1608_HEN_MPE | 2027-03-19 07:30 | 2027-03-19 18:30 | Daily | RS - Removal from Service | HEN-C-PTSG-1608B | Lodged
HAY_110BZ | 2027-03-19 08:00 | 2027-03-19 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3A; Bay 60 - Takapu Rd cct 2. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-03-19 08:00 | 2027-03-19 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3A; Bay 60 - Takapu Rd cct 2. | Lodged
HAY_110BZ | 2027-03-20 08:00 | 2027-03-20 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3A; Bay 60 - Takapu Rd cct 2. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-03-20 08:00 | 2027-03-20 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3A; Bay 60 - Takapu Rd cct 2. | Lodged
CLH_COL_1 | 2027-03-22 07:30 | 2027-03-24 18:30 | Continuous | RS - Removal from Service | COL-OTI-A0031-00, COL-OTI-A0045-00, COL-OTI-A0119-00 | Lodged
COL_OTI_2 | 2027-03-22 07:30 | 2027-03-24 18:30 | Continuous | RS - Removal from Service | COL-OTI-A0031-00, COL-OTI-A0045-00, COL-OTI-A0119-00 | Lodged
HLY_CB_682 | 2027-03-22 07:30 | 2027-03-24 18:30 | Continuous | RS - Removal from Service | HLY-P-CB-682 | Lodged
HLY_OHW_2 | 2027-03-22 07:30 | 2027-03-24 18:30 | Continuous | RS - Removal from Service | HLY-DS-223, HLY-DS-226, HLY-DS-245, HLY-ES-229 | Lodged
HPI_MDN_1 | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | RS - Removal from Service | CB Pole replacement, conductor repairs projects. HPI-CB-372, MDN-CVT-452, MDN-DS-456, MDN-ES-459, MDN-P-CB-452 | Lodged
MDN_437_457_467 | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | RS - Removal from Service | MDN-DS-434, MDN-DS-437, MDN-DS-454, MDN-DS-457 | Lodged
MDN_CB_508 | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | RS - Removal from Service | Affected equipment MDN_437_457_467 & HPI_MDN_1 | Lodged
MDN_STC_5 | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | RS - Removal from Service | MDN-P-PSUP-STC5-UPS-1, MDN-STC-5, MDN-STC5-VCS | Lodged
MDN_T5 | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | RS - Removal from Service | Affected equipment MDN_437_457_467 & HPI_MDN_1 | Lodged
MPE_CB_252 | 2027-03-22 07:30 | 2027-03-22 22:00 | Daily | OPE - Open Ended | System split for the duration of HPI_MDN_1 | Lodged
MPE_CB_292 | 2027-03-22 07:30 | 2027-03-22 22:00 | Daily | OPE - Open Ended | System split for the duration of HPI_MDN_1 | Lodged
TMK_TIM_1_TMK_T1 | 2027-03-22 07:30 | 2027-03-25 18:30 | Continuous | RS - Removal from Service | ASH-TIM-A0422-00, ASH-TIM-A0423-00, ASH-TIM-A0456-10, ASH-TIM-A0459-00, TMK-CVT-CVT132 | Lodged
INV_MAN_2 | 2027-03-22 07:30 | 2027-03-27 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
MPE_CB_252 | 2027-03-23 06:00 | 2027-03-24 22:00 | Continuous | OPE - Open Ended | System split for the duration of HPI_MDN_1 | Lodged
MPE_CB_292 | 2027-03-23 06:00 | 2027-03-24 22:00 | Continuous | OPE - Open Ended | System split for the duration of HPI_MDN_1 | Lodged
DRY_220BZ_A | 2027-03-23 07:30 | 2027-03-24 18:30 | Daily | RS - Removal from Service | DRY-P-BZ-220 | Lodged
DRY_220CBF | 2027-03-23 07:30 | 2027-03-24 18:30 | Daily | RS - Removal from Service | Affected equipment | Lodged
MPE_CB_252 | 2027-03-25 06:00 | 2027-03-25 18:30 | Daily | OPE - Open Ended | System split for the duration of HPI_MDN_1 | Lodged
MPE_CB_292 | 2027-03-25 06:00 | 2027-03-25 18:30 | Daily | OPE - Open Ended | System split for the duration of HPI_MDN_1 | Lodged
MAN_NMA_3 | 2027-03-29 07:30 | 2027-04-04 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
HAM_T9 | 2027-03-29 07:30 | 2027-04-02 18:30 | Continuous | RS - Removal from Service | CT and ODJB replacement project. CP_HAM_001_0_00 | Lodged
ARI_HAM_1 | 2027-03-29 07:30 | 2027-04-02 18:30 | Continuous | OPE - Open Ended | System split for the duration of HAM_T9 | Lodged
ARI_HAM_2 | 2027-03-29 07:30 | 2027-04-02 18:30 | Continuous | OPE - Open Ended | System split for the duration of HAM_T9 | Lodged
KPO_TMU_1 | 2027-03-29 07:30 | 2027-04-02 18:30 | Continuous | OPE - Open Ended | System split for the duration of HAM_T9 | Lodged
ARI_CB_48 | 2027-03-29 07:30 | 2027-04-02 18:30 | Continuous | CLO - Close | Closed for the duration of HAM_T9 | Lodged
BEN_TWZ_1 | 2027-03-30 07:30 | 2027-03-31 18:30 | Daily | RS - Removal from Service | BEN-CT-CT472, BEN-CVT-VT3, BEN-DS-473, BEN-DS-476, BEN-ES-479, TWZ-CT-CT2562, TWZ-CVT-CVT2562, TWZ-DS-2565, TWZ-DS-2566, TWZ-DS-2573, TWZ-ES-2569, TWZ-P-CB-2562 | Lodged
KOE_MPE_2 | 2027-03-30 07:30 | 2027-04-02 18:30 | Continuous | RS - Removal from Service | KOE-CB-102, KOE-CT-102, KOE-DS-106, KOE-ES-109, KOE-MPE-A0086-20, KOE-MPE-A0089-20, KOE-P-CB-102 | Lodged
OTA_SWN_1 | 2027-03-30 07:30 | 2027-04-02 18:30 | Continuous | RS - Removal from Service | OTA-DS-575, OTA-DS-573, HEN-OTA-A0013-20, OTA-CT-572, OTA-CVT-572, OTA-DS-576, OTA-ES-579, OTA-P-CB-572 | Lodged
STK_727_777 | 2027-03-30 07:30 | 2027-04-02 18:30 | Continuous | RS - Removal from Service | STK-DS-704, STK-DS-707 | Lodged
STK_AVR_T6 | 2027-03-30 07:30 | 2027-04-02 18:30 | Continuous | RS - Removal from Service | Affected equipment STK_727_777 & STK_T6 | Lodged
STK_DIS_807 | 2027-03-30 07:30 | 2027-04-02 18:30 | Continuous | RS - Removal from Service | Affected equipment STK_727_777 & STK_T6 | Lodged
STK_T6 | 2027-03-30 07:30 | 2027-04-02 18:30 | Continuous | RS - Removal from Service | STK-CBL-ET6, STK-CBL-NER6, STK-CBL-T6-2132, STK-CT-2132, STK-CT-CT702, STK-CT-T6HV, STK-TF-ET6, STK-TF-T6 | Lodged
BPE_MHO_2 | 2027-03-30 07:30 | 2027-04-11 18:30 | Continuous | RS - Removal from Service | Shelterbelt tree works. Conductor repairs x2 spans [MP_RA4_03N_0_00]. Affected equipment of MHO_T4 | Lodged
MHO_T4 | 2027-03-30 07:30 | 2027-04-11 18:30 | Continuous | RS - Removal from Service | MHO-TF-T4 | Lodged
ARI_CB_48 | 2027-03-30 07:30 | 2027-04-03 18:30 | Continuous | CLO - Close | Closed for the duration of HAM_T9 | Lodged
ARI_HAM_1 | 2027-03-30 07:30 | 2027-04-03 18:30 | Continuous | OPE - Open Ended | System split with HAM_T9 | Lodged
ARI_HAM_2 | 2027-03-30 07:30 | 2027-04-03 18:30 | Continuous | OPE - Open Ended | System split with HAM_T9 | Lodged
HAM_C_2 | 2027-03-30 07:30 | 2027-04-03 18:30 | Continuous | RS - Removal from Service | Affected equipment HAM_T9 | Lodged
HAM_T9 | 2027-03-30 07:30 | 2027-04-03 18:30 | Continuous | RS - Removal from Service | CT replacement project. HAM-CT-372 | Lodged
KPO_TMU_1 | 2027-03-30 07:30 | 2027-04-03 18:30 | Continuous | OPE - Open Ended | System split with HAM_T9 | Lodged
HAY_TKR_1 | 2027-03-31 07:00 | 2027-04-04 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3B; Bay 80 - Takapu Rd cct 1. No other HAY work on days 1, 4, 5. No other work on associated equipment/lines on day 5 (commissioning). HAY-CT-82. | Lodged
KAW_FDR_72 | 2027-03-31 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | FDR 72 protection replacement project. To align with KAG shutdown. KAW-P-CB-72 | Lodged
KAW_T12_T13_OPS | 2027-03-31 07:30 | 2027-04-02 18:30 | Continuous | RS - Removal from Service | KAW-P-SPS-TF | Lodged
OHB_TWZ_3 | 2027-03-31 07:30 | 2027-04-02 18:30 | Continuous | RS - Removal from Service | OHB-CT-CT1102, OHB-CVT-VT112, OHB-DS-1106, OHB-ES-1109, OHB-P-CB-1102, TWZ-CT-CT2672, TWZ-CVT-CVT9, TWZ-DS-2676, TWZ-ES-2679 | Lodged
OTA_537_597_587 | 2027-03-31 07:30 | 2027-03-31 18:30 | Daily | RS - Removal from Service | OTA-DS-573, HEN-OTA-A0013-20, OTA-CT-572, OTA-CVT-572, OTA-DS-576, OTA-ES-579, OTA-P-CB-572 | Lodged
OTA_CB_538 | 2027-03-31 07:30 | 2027-03-31 18:30 | Daily | RS - Removal from Service | Affected Equipment of OTA_537_597_587 OTA-DS-573, HEN-OTA-A0013-20, OTA-CT-572, OTA-CVT-572, OTA-DS-576, OTA-ES-579, OTA-P-CB-572 | Lodged
OTA_CB_598 | 2027-03-31 07:30 | 2027-03-31 18:30 | Daily | RS - Removal from Service | Affected Equipment of OTA_537_597_587 OTA-DS-573, HEN-OTA-A0013-20, OTA-CT-572, OTA-CVT-572, OTA-DS-576, OTA-ES-579, OTA-P-CB-572 | Lodged
TWZ_2676_2437 | 2027-03-31 07:30 | 2027-04-02 18:30 | Continuous | RS - Removal from Service | TWZ-DS-2534 | Lodged
TWZ_CB_2462 | 2027-03-31 07:30 | 2027-04-02 18:30 | Continuous | RS - Removal from Service | Affected equipment TWZ_2676_2437 & OHB_TWZ_3 & TWZ_T18 | Lodged
TWZ_CB_2532 | 2027-03-31 07:30 | 2027-04-02 18:30 | Continuous | RS - Removal from Service | Affected equipment TWZ_2676_2437 & OHB_TWZ_3 & TWZ_T18 | Lodged
TWZ_T18 | 2027-03-31 07:30 | 2027-04-02 18:30 | Continuous | RS - Removal from Service | TWZ-CBL-2188-2217, TWZ-CBL-LS18-2232, TWZ-CBL-T18-2232, TWZ-CBL-T18-NER18, TWZ-RES-NER-18, TWZ-TF-LS18 | Lodged
HAY_110BZ | 2027-03-31 08:00 | 2027-03-31 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3B; Bay 80 - Takapu Rd cct 1. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-03-31 08:00 | 2027-03-31 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3B; Bay 80 - Takapu Rd cct 1. | Lodged
HEP_FDR_2252 | 2027-04-01 07:30 | 2027-04-01 18:30 | Daily | RS - Removal from Service | HEP-CB-2252, HEP-P-CB-2252 | Lodged
KIN_T8 | 2027-04-01 07:30 | 2027-04-02 18:30 | Continuous | RS - Removal from Service | KIN-M-CT2542, KIN-M-VT2542, KIN-TF-T8 | Lodged
OTA_527_587_597 | 2027-04-01 07:30 | 2027-04-01 18:30 | Daily | RS - Removal from Service | OTA-DS-575, HEN-OTA-A0013-20, OTA-CT-572, OTA-CVT-572, OTA-DS-576, OTA-ES-579, OTA-P-CB-572 | Lodged
OTA_CB_528 | 2027-04-01 07:30 | 2027-04-01 18:30 | Daily | RS - Removal from Service | Affected Equipment of OTA_527_587_597 OTA-DS-575, HEN-OTA-A0013-20, OTA-CT-572, OTA-CVT-572, OTA-DS-576, OTA-ES-579, OTA-P-CB-572 | Lodged
OTA_CB_598 | 2027-04-01 07:30 | 2027-04-01 18:30 | Daily | RS - Removal from Service | Affected Equipment of OTA_527_587_597 OTA-DS-575, HEN-OTA-A0013-20, OTA-CT-572, OTA-CVT-572, OTA-DS-576, OTA-ES-579, OTA-P-CB-572 | Lodged
SBK_WPR_1 | 2027-04-01 07:30 | 2027-04-02 18:30 | Daily | RS - Removal from Service | SBK-WPR-A0006-0007-20, SBK-WPR-A0025-0026-20, SBK-WPR-A0077-0078-20 | Lodged
KAI_11BS_R | 2027-04-02 07:30 | 2027-04-02 18:30 | Daily | RS - Removal from Service | KAI-BS-11-REAR | Lodged
HAM_CB_458 | 2027-04-02 07:30 | 2027-04-03 18:30 | Continuous | RS - Removal from Service | Ref CT for stability checks. CT replacement project. HAM-CT-372 | Lodged
HAM_DIS_447 | 2027-04-02 07:30 | 2027-04-03 18:30 | Continuous | CLO - Close | Closed for the duration of HAM_CB_458. CT replacement project. HAM-CT-372 | Lodged
HAY_110BZ | 2027-04-03 08:00 | 2027-04-03 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3B; Bay 80 - Takapu Rd cct 1. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-04-03 08:00 | 2027-04-03 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3B; Bay 80 - Takapu Rd cct 1. | Lodged
HAY_110BZ | 2027-04-04 08:00 | 2027-04-04 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3B; Bay 80 - Takapu Rd cct 1. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-04-04 08:00 | 2027-04-04 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3B; Bay 80 - Takapu Rd cct 1. | Lodged
HAM_147_VT157 | 2027-04-05 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | CP_HAM_OS_00_00 ES & SA replacement works | Lodged
HAM_C_1 | 2027-04-05 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | Affected Equipment of HAM_147_VT157 CP_HAM_OS_00_00 ES & SA replacement works | Lodged
HAM_STC_3 | 2027-04-05 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | CP_HAM_OS_00_00 ES & SA replacement works | Lodged
HLY_164_397 | 2027-04-05 07:30 | 2027-04-07 18:30 | Continuous | RS - Removal from Service | HLY-DS-384, HLY-ES-379 | Lodged
HLY_CB_262 | 2027-04-05 07:30 | 2027-04-07 18:30 | Continuous | RS - Removal from Service | HLY-P-CB-262 | Lodged
HLY_T21 | 2027-04-05 07:30 | 2027-04-07 18:30 | Continuous | RS - Removal from Service | HLY-P-TF-T21, HLY-TF-T21 | Lodged
HOB_T12 | 2027-04-05 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | HOB-CBL-T12-110, HOB-NCT-12, HOB-TF-T12 | Lodged
ISL_KIK_1 | 2027-04-05 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | ISL-CVT-VT572, ISL-DS-573, ISL-DS-575, ISL-DS-576, ISL-ES-579, ISL-KIK-A0276-10, KIK-CVT-VT362, KIK-DS-366 | Lodged
KIK_220BS_B | 2027-04-05 07:30 | 2027-04-06 18:30 | Daily | RS - Removal from Service | affected equipment KIK_CB_398, KIK_CB_328 | Lodged
KIK_CB_328 | 2027-04-05 07:30 | 2027-04-06 18:30 | Daily | RS - Removal from Service | KIK-P-CB-328 | Lodged
KIK_CB_398 | 2027-04-05 07:30 | 2027-04-06 18:30 | Daily | RS - Removal from Service | Affected equipment KIK_220BS_B & KIK_CB_328 | Lodged
WPR_FDR_82 | 2027-04-05 07:30 | 2027-04-06 18:30 | Daily | RS - Removal from Service | WPR-P-CB-82 | Lodged
GYT_AVR_T3 | 2027-04-05 07:30 | 2027-04-07 18:30 | Continuous | RS - Removal from Service | Affected equipment of MST_GYT_UHT_2. | Lodged
GYT_T3 | 2027-04-05 07:30 | 2027-04-07 18:30 | Continuous | RS - Removal from Service | GYT-TF-T3. GYT-M-CT1362, GYT-M-VT6 (Metering not required should GYT ODID commissioning be completed as planned in February 2026). | Lodged
MST_67_44 | 2027-04-05 07:30 | 2027-04-05 18:30 | Daily | RS - Removal from Service | MST-DCB-82 (GYT-UHT-2) | Lodged
MST_GYT_UHT_2 | 2027-04-05 07:30 | 2027-04-07 18:30 | Continuous | RS - Removal from Service | MST-DCB-82, UHT-CB-62, UHT-CT-62, UHT-DS-66, UHT-ES-69, UHT-P-CB-62 | Lodged
MST_T3 | 2027-04-05 07:30 | 2027-04-05 18:30 | Daily | RS - Removal from Service | Affected equipment of MST_67_44, for MST-DCB-82 (GYT-UHT-2) | Lodged
ISL_220BS_E | 2027-04-05 07:30 | 2027-04-07 18:30 | Continuous | RS - Removal from Service | ISL-DS-575 ISL-DS-575 | Lodged
ISL_CB_658 | 2027-04-05 07:30 | 2027-04-07 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_220BS_E ISL-DS-575 ISL-DS-575 | Lodged
ISL_CB_688 | 2027-04-05 07:30 | 2027-04-07 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_220BS_E ISL-DS-575 ISL-DS-575 | Lodged
KIN_TRK_2 | 2027-04-05 07:30 | 2027-04-10 18:30 | Continuous | RS - Removal from Service | ARI-EDG-B0067A-00, ARI-EDG-B0080-00, ARI-EDG-B0118-00, ARI-EDG-B0145-00, ARI-EDG-B0148-00, ARI-EDG-B0153-00, KIN-CT-352, LCH-KIN-B0604-00, LCH-KIN-B0615-00, LCH-KIN-B0643-00, LCH-KIN-B0657-00, LFD-DS-76, TRK-DEV-B0015-00, TRK-DEV-B0016-00 | Lodged
LFD_DIS_76 | 2027-04-05 07:30 | 2027-04-10 18:30 | Continuous | RS - Removal from Service | Affected equipment TRK_124_157 & KIN_TRK_2 | Lodged
TRK_124_157 | 2027-04-05 07:30 | 2027-04-10 18:30 | Continuous | RS - Removal from Service | TRK-BS-110-124-147 | Lodged
TRK_147_157 | 2027-04-05 07:30 | 2027-04-10 18:30 | Continuous | RS - Removal from Service | TRK-VT-VT227 | Lodged
MTO_T1 | 2027-04-05 08:00 | 2027-04-10 18:30 | Continuous | RS - Removal from Service | Affected Equipment OVR031104 | Lodged
WEL_T2 | 2027-04-05 08:00 | 2027-04-10 18:30 | Continuous | RS - Removal from Service | Affected Equipment OVR031104 | Lodged
BEN_F_6 | 2027-04-06 07:30 | 2027-04-08 18:30 | Continuous | RS - Removal from Service | S1.20DB74-C3A, S1.20DB74-C3B, S1.20DB74-C3C, S1.20DB74-FB6, S1.20DB74-L3A, S1.20DB74-L3B, S1.20DB74-L3C, S1.20DB74-Q01, S1.20DB74-Q02, S1.20DB74-R1A, S1.20DB74-R1B, S1.20DB74-R1C, S1.20DB74-R2A, S1.20DB74-R2B, S1.20DB74-R2C, S1.20DB74-R3A, S1.20DB74-R3B, S1.20DB74-R3C | Lodged
LIV_WTK_1 | 2027-04-06 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | AVI-LIV-A0026-00 | Lodged
OAM_STU_BPD_WTK_2 | 2027-04-06 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WTK_56_447 WTK-DS-394, WTK-DS-414, WTK-DS-424, WTK-DS-437, WTK-ES-430 | Lodged
OAM_T2 | 2027-04-06 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WTK_56_447 WTK-DS-394, WTK-DS-414, WTK-DS-424, WTK-DS-437, WTK-ES-430 | Lodged
WTK_11BS_A | 2027-04-06 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WTK_T21 Affected equipment WTK_56_447 & LIV_WTK_1 & WTK_CB_438 & WTK_T23 & OAM_STU_BPD_WTK_2 & OAM_T2 | Lodged
WTK_56_447 | 2027-04-06 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | WTK-DS-394, WTK-DS-414, WTK-DS-424, WTK-DS-437, WTK-ES-430 | Lodged
WTK_CB_438 | 2027-04-06 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | WTK-P-CB-438 | Lodged
WTK_LST_31 | 2027-04-06 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | Affected Equipment of WTK_T21 Affected equipment WTK_56_447 & LIV_WTK_1 & WTK_CB_438 & WTK_T23 & OAM_STU_BPD_WTK_2 & OAM_T2 | Lodged
WTK_T21 | 2027-04-06 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | Affected equipment WTK_56_447 & LIV_WTK_1 & WTK_CB_438 & WTK_T23 & OAM_STU_BPD_WTK_2 & OAM_T2 | Lodged
WTK_T28 | 2027-04-06 07:30 | 2027-04-09 18:30 | Daily | RS - Removal from Service | WTK-CB-1002, WTK-P-CB-18 | Lodged
HWA_SFD_1 | 2027-04-06 07:31 | 2027-04-08 18:31 | Continuous | RS - Removal from Service | Pole replacement x1 (A499). | Lodged
CUL_T23 | 2027-04-07 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | CUL-P-TF-T23, CUL-TF-T23 | Lodged
HEP_ROS_2 | 2027-04-07 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | HEP-ROS-A0083-0084-00 | Lodged
OTA_STC_15 | 2027-04-07 07:30 | 2027-04-07 18:30 | Daily | RS - Removal from Service | OTA-COOL-STC15, OTA-STC-15 | Lodged
ASB_TIM_TWZ_2 | 2027-04-07 07:30 | 2027-04-13 18:30 | Continuous | RS - Removal from Service | ASB-CT-CT492, ASB-CVT-VT492, ASB-DS-496, ASB-P-CB-492, TIM-CVT-CVT282, TIM-DS-286, TIM-ES-289, TWZ-CT-CT2412, TWZ-CVT-CVT2412, TWZ-DS-2415, TWZ-DS-2416, TWZ-DS-2423, TWZ-ES-2419, TWZ-P-CB-2412 | Lodged
TIM_T8 | 2027-04-07 07:30 | 2027-04-13 18:30 | Continuous | RS - Removal from Service | Affected equipment ASB_TIM_TWZ_2 | Lodged
ASB_417_424_494 | 2027-04-07 07:31 | 2027-04-08 18:31 | Continuous | RS - Removal from Service | ASB-DS-424 | Lodged
ASB_FDR_82 | 2027-04-07 07:31 | 2027-04-08 18:31 | Continuous | RS - Removal from Service | Affected equipment ASB_417_424_494 & ASB_ISL_1 & ASB_T10 | Lodged
ASB_ISL_1 | 2027-04-07 07:31 | 2027-04-08 18:31 | Continuous | RS - Removal from Service | ASB-DS-426, CHH-TWZ-A0308-20, ISL-DS-443, ISL-DS-445 | Lodged
ASB_T10 | 2027-04-07 07:31 | 2027-04-08 18:31 | Continuous | RS - Removal from Service | ASB-M-CT82, ASB-M-VT82 | Lodged
ASB_CB_492 | 2027-04-08 07:30 | 2027-04-13 18:30 | Continuous | RS - Removal from Service | ASB-P-CB-492 Transmission circuit protection Diagnostic inspection and service | Lodged
ISL_SBK_1 | 2027-04-08 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | ISL-CB-342 | Lodged
KAW_CB_2818 | 2027-04-08 07:30 | 2027-04-08 18:30 | Daily | RS - Removal from Service | KAW-CB-2818 | Lodged
ROS_T4 | 2027-04-08 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | ROS-M-CT2312, ROS-M-VT2312 | Lodged
ISL_220BS_F | 2027-04-08 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | ISL-DS-573 ISL-DS-573 | Lodged
ISL_CB_668 | 2027-04-08 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_220BS_F ISL-DS-573 ISL-DS-573 | Lodged
ISL_CB_688 | 2027-04-08 07:30 | 2027-04-09 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_220BS_F ISL-DS-573 ISL-DS-573 | Lodged
BRK_1094_1104_1114 | 2027-04-10 07:31 | 2027-04-11 18:31 | Continuous | RS - Removal from Service | Affected equipment of BRK 33kV site shut (alternate date 18/04/27) | Lodged
BRK_DIS_1101 | 2027-04-10 07:31 | 2027-04-11 18:31 | Continuous | RS - Removal from Service | Affected equipment of BRK 33kV site shut (alternate date 18/04/27) | Lodged
BRK_FDR_1092 | 2027-04-10 07:31 | 2027-04-11 18:31 | Continuous | RS - Removal from Service | Affected equipment of BRK 33kV site shut (alternate date 18/04/27) | Lodged
BRK_FDR_1112 | 2027-04-10 07:31 | 2027-04-11 18:31 | Continuous | RS - Removal from Service | BRK 33kV site shut (alternate date 18/04/27). BRK-CB-1112, BRK-CT-1112, BRK-DS-1116, BRK-ES-1119. | Lodged
BRK_LST_1 | 2027-04-10 07:31 | 2027-04-11 18:31 | Continuous | RS - Removal from Service | Affected equipment of BRK 33kV site shut (alternate date 18/04/27) | Lodged
BRK_T1 | 2027-04-10 07:31 | 2027-04-11 18:31 | Continuous | RS - Removal from Service | BRK 33kV site shut (alternate date 18/04/27). BRK-DS-583, BRK-TF-T1B, BRK-TF-T1R, BRK-TF-T1Y. | Lodged
ASB_337_364_386_407 | 2027-04-12 07:30 | 2027-04-13 18:30 | Daily | RS - Removal from Service | ASB-DS-384 | Lodged
ASB_CB_398 | 2027-04-12 07:30 | 2027-04-13 18:30 | Daily | RS - Removal from Service | Affected equipment ASB_337_364_386_407 & ASB_BRY_1 & ASB_T3 | Lodged
BDE_C_1 | 2027-04-12 07:30 | 2027-04-14 18:30 | Continuous | RS - Removal from Service | BDE-CAPS-C1, BDE-CBL-17 | Lodged
BPE_MHO_1 | 2027-04-12 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | Shelterbelt tree works. Conductor repairs [MP_RA4_03N_0_00]. | Lodged
BRB_T2 | 2027-04-12 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | BRB-CBL-112, BRB-TF-T2 | Lodged
HOB_220BZ_A | 2027-04-12 07:30 | 2027-04-13 18:30 | Daily | RS - Removal from Service | HOB-P-BZ-220 | Lodged
HOB_220CBF | 2027-04-12 07:30 | 2027-04-13 18:30 | Daily | RS - Removal from Service | Affected equipment | Lodged
INV_CB_722 | 2027-04-12 07:30 | 2027-04-14 18:30 | Continuous | RS - Removal from Service | INV-DS-716, INV-P-CB-712/722, INV-TWI-A0002-00, INV-TWI-A0002-10, INV-TWI-A0003-00, INV-TWI-A0005-10, INV-TWI-A0006-00, INV-TWI-A0006-10, INV-TWI-A0007-00, INV-TWI-A0010-00, INV-TWI-A0010-10, INV-TWI-A0011-00, INV-TWI-A0017-00, INV-TWI-A0017-10, INV-TWI-A0019-10, INV-TWI-A0020-10, INV-TWI-A0023-00, INV-TWI-A0023-10, INV-TWI-AINVP1-10, INV-TWI-ATWIB3-10, TWI-P-CB-442, TWI-SA-2, FM3 roller door servicing | Lodged
INV_TWI_1 | 2027-04-12 07:30 | 2027-04-14 18:30 | Continuous | RS - Removal from Service | INV-DS-716, INV-P-CB-712/722, INV-TWI-A0023-10, INV-TWI-A0028-00, INV-TWI-A0031-10, INV-TWI-A0032-00, INV-TWI-A0032-10, INV-TWI-A0033-10, INV-TWI-A0047-0048-10, INV-TWI-A0048-0049-00, INV-TWI-A0048-0049-10, INV-TWI-A0049-0050-00, INV-TWI-A0050-0051-00, INV-TWI-A0050-0051-10, INV-TWI-A0051-0052-00, INV-TWI-AINVP1-10, INV-TWI-ATWIB3-10, TWI-P-CB-442, TWI-SA-2, FM3 roller door servicing | Lodged
MHO_T3 | 2027-04-12 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | Affected equipment of BPE_MHO_1, for shelterbelt tree works and conductor repairs [MP_RA4_03N_0_00]. | Lodged
ROS_FDR_142 | 2027-04-12 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | Protection replacement ROS-P-CB-142 | Lodged
MAN_NMA_1 | 2027-04-12 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
BOB_T5 | 2027-04-12 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | BOB-TF-T5 | Lodged
DRY_BOB_HLY_2 | 2027-04-12 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | HLY-OTA-A0030-20, HLY-OTA-A0070-00, HLY-OTA-A0092-20, HLY-OTA-A0096-00, HLY-OTA-A0099-20, HLY-OTA-A0100-20 | Lodged
ARI_BOB_1 | 2027-04-12 07:31 | 2027-04-17 18:31 | Continuous | RS - Removal from Service | Pole replacement, Reinsulation and CA. CP_RA2_01Q_0_00, CP_RA2_00U_0_00, ARI-HAM-A0017-0018-10, ARI-HAM-A0253-0254-10, BOB-P-CB-232 | Lodged
BOB_214_227_267 | 2027-04-12 07:31 | 2027-04-13 18:31 | Continuous | RS - Removal from Service | BOB-DS-227, BOB-DS-247 | Lodged
BOB_FDR_212 | 2027-04-12 07:31 | 2027-04-13 18:31 | Continuous | RS - Removal from Service | Affected equipment BOB_214_227_267 & ARI_BOB_1 & BOB_T5 | Lodged
BOB_FDR_242 | 2027-04-12 07:31 | 2027-04-13 18:31 | Continuous | RS - Removal from Service | Affected equipment BOB_214_227_267 & ARI_BOB_1 & BOB_T5 | Lodged
BRK_FDR_1112 | 2027-04-12 07:31 | 2027-04-12 18:31 | Daily | RS - Removal from Service | Required for 1x day on its own, following BRK 33kV shut. | Lodged
MPE_CB_252 | 2027-04-12 08:00 | 2027-04-12 22:00 | Daily | OPE - Open Ended | System split for the duration of ALB_HPI_1 | Lodged
MPE_CB_292 | 2027-04-12 08:00 | 2027-04-12 22:00 | Daily | OPE - Open Ended | System split for the duration of ALB_HPI_1 | Lodged
HPI_MDN_1 | 2027-04-12 08:00 | 2027-04-17 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
MPE_CB_252 | 2027-04-13 06:00 | 2027-04-15 22:00 | Continuous | OPE - Open Ended | System split for the duration of ALB_HPI_1 | Lodged
MPE_CB_292 | 2027-04-13 06:00 | 2027-04-15 22:00 | Continuous | OPE - Open Ended | System split for the duration of ALB_HPI_1 | Lodged
BEN_T27 | 2027-04-13 07:30 | 2027-04-15 18:30 | Continuous | RS - Removal from Service | BEN-NCTD-T27 | Lodged
NPK_RTU_1 | 2027-04-13 07:30 | 2027-04-13 18:30 | Daily | RS - Removal from Service | SMS & GPS replacements [CP_RA3_03C_0_00] | Lodged
CUL_104_117_127 | 2027-04-13 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | Affected equipment CUL_T1 | Lodged
CUL_1236_1276_1271 | 2027-04-13 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | Affected equipment CUL_T1 | Lodged
CUL_66BS | 2027-04-13 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | Affected equipment CUL_T1 | Lodged
CUL_CB_102 | 2027-04-13 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | Affected equipment CUL_T1 | Lodged
CUL_CB_142 | 2027-04-13 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | Affected Equipment of CUL_104_117_127 Affected equipment CUL_T1 | Lodged
CUL_T1 | 2027-04-13 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | CUL-CB-102, CUL-CB-1232 | Lodged
CUL_FDR_1242 | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | CUL-CB-1242, CUL-P-CB-1242 | Lodged
EDG_110CBF | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
EDG_110KV_BZ | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | EDG-P-BZ-110-A | Lodged
HAY_110BZ | 2027-04-14 07:30 | 2027-04-14 18:30 | Daily | RS - Removal from Service | HAY-P-BZ-110, HAY-P-BZ-110-A1, HAY-P-BZ-110-A2, HAY-P-BZ-110-B, HAY-P-BZ-110-CK | Lodged
OHK_220CBF | 2027-04-14 07:30 | 2027-04-14 18:30 | Daily | RS - Removal from Service | OHK-P-CB-132 | Lodged
PTS_1872_MAN_NMA | 2027-04-14 07:30 | 2027-04-14 18:30 | Daily | RS - Removal from Service | MAN-C-PTSG-1872, NMA-C-PTSG-1872 | Lodged
OAM_STU_BPD_WTK_2 | 2027-04-14 07:30 | 2027-04-15 18:30 | Daily | RS - Removal from Service | Affected Equipment of WTK_T23 WTK-NCTD-T23 | Lodged
OAM_T2 | 2027-04-14 07:30 | 2027-04-15 18:30 | Daily | RS - Removal from Service | Affected Equipment of WTK_T23 WTK-NCTD-T23 | Lodged
STU_CB_62 | 2027-04-14 07:30 | 2027-04-15 18:30 | Daily | RS - Removal from Service | Affected equipment OAM_STU_BPD_WTK_2 & OAM_T2 & WTK_T23 | Lodged
WTK_T23 | 2027-04-14 07:30 | 2027-04-15 18:30 | Daily | RS - Removal from Service | WTK-NCTD-T23 | Lodged
HLY_224_344_357 | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | HLY-DS-224, HLY-DS-324, HLY-DS-344, HLY-ES-339 | Lodged
HLY_CB_222 | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | Affected equipment HLY_224_344_357 & HLY_T22 | Lodged
HLY_CB_342 | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | Affected equipment HLY_224_344_357 & HLY_T22 | Lodged
HLY_T22 | 2027-04-14 07:30 | 2027-04-16 18:30 | Continuous | RS - Removal from Service | HLY-P-TF-T22, HLY-TF-T22 | Lodged
INV_CB_642 | 2027-04-15 07:30 | 2027-04-17 18:30 | Continuous | RS - Removal from Service | INV-DS-615, INV-P-CB-612/642, INV-TWI-A0002-20, INV-TWI-A0005-20, INV-TWI-A0006-20, INV-TWI-A0010-20, INV-TWI-A0017-20, INV-TWI-A0019-20, INV-TWI-A0020-20, INV-TWI-A0023-20, INV-TWI-A0031-0032-20, INV-TWI-A0031-20, INV-TWI-A0032-20, INV-TWI-A0033-20, INV-TWI-A0047-0048-20, INV-TWI-A0048-0049-20, INV-TWI-A0049-0050-20, INV-TWI-A0050-0051-20, INV-TWI-AINVG16-10, INV-TWI-ATWIB4-10, TWI-P-CB-402, TWI-SA-1, FM3 roller door servicing | Lodged
INV_TWI_2 | 2027-04-15 07:30 | 2027-04-17 18:30 | Continuous | RS - Removal from Service | INV-DS-615, INV-P-CB-612/642, INV-TWI-A0002-20, INV-TWI-A0005-20, INV-TWI-A0006-20, INV-TWI-A0010-20, INV-TWI-A0017-20, INV-TWI-A0019-20, INV-TWI-A0020-20, INV-TWI-A0023-20, INV-TWI-A0031-0032-20, INV-TWI-A0031-20, INV-TWI-A0032-20, INV-TWI-A0033-20, INV-TWI-A0047-0048-20, INV-TWI-A0048-0049-20, INV-TWI-A0049-0050-20, INV-TWI-A0050-0051-20, INV-TWI-AINVG16-10, INV-TWI-ATWIB4-10, TWI-P-CB-402, TWI-SA-1, FM3 roller door servicing | Lodged
ASB_347_296 | 2027-04-15 07:30 | 2027-04-15 18:30 | Daily | RS - Removal from Service | ASB-DS-294 | Lodged
ASB_FDR_42 | 2027-04-15 07:30 | 2027-04-15 18:30 | Daily | RS - Removal from Service | Affected equipment ASB_347_296 & ASB_T1 | Lodged
ASB_T8 | 2027-04-15 07:30 | 2027-04-15 18:30 | Daily | RS - Removal from Service | Affected equipment ASB_347_296 & ASB_T1 | Lodged
MPE_CB_252 | 2027-04-16 06:00 | 2027-04-16 18:30 | Daily | OPE - Open Ended | System split for the duration of ALB_HPI_1 | Lodged
MPE_CB_292 | 2027-04-16 06:00 | 2027-04-16 18:30 | Daily | OPE - Open Ended | System split for the duration of ALB_HPI_1 | Lodged
ARI_KIN_1 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Pole replacement, Under-clearance work | Lodged
ARI_KIN_2 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Pole replacement, Under-clearance work | Lodged
MNG_FDR_262 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | CT replacement PJ. MNG-CT-262 | Lodged
NMA_687_835 | 2027-04-19 07:30 | 2027-04-20 18:30 | Continuous | RS - Removal from Service | pdm maint. | Lodged
NMA_CB_738 | 2027-04-19 07:30 | 2027-04-20 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_687_835 pdm maint. | Lodged
TIM_44_54_87 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | TIM-CSA-78 | Lodged
TIM_CB_2752 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | CLO - Close | Affected Equipment of TIM_44_54_87 TIM-CSA-78 | Lodged
TIM_T4 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Affected Equipment of TIM_44_54_87 TIM-CSA-78 | Lodged
TMK_T1 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Affected Equipment of TIM_44_54_87 TIM-CSA-78 | Lodged
TMK_TIM_1_TMK_T1 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Affected Equipment of TIM_44_54_87 TIM-CSA-78 | Lodged
MAN_NMA_2 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Tower Painting | Lodged
OHK_CB_102 | 2027-04-19 07:30 | 2027-04-21 18:30 | Continuous | RS - Removal from Service | OHK-CT-102. Affected equipment of OHK_WRK_1. | Lodged
OHK_CB_132 | 2027-04-19 07:30 | 2027-04-21 18:30 | Continuous | RS - Removal from Service | OHK-CT-132. Affected equipment of OHK_WRK_1. | Lodged
OHK_WRK_1 | 2027-04-19 07:30 | 2027-04-21 18:30 | Continuous | RS - Removal from Service | OHK-CVT-102, OHK-DS-106, OHK-DS-1326, OHK-ES-109, WRK-WKM-A0062-00 | Lodged
CUL_T23 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_WPR_CUL_KIK_3 CUL-DS-416, CUL-P-CB-412, ISL-KIK-B0021-0022-20, ISL-KIK-B0216-20, ISL-KIK-B0223-20, ISL-KIK-B0231-20, ISL-KIK-B0234-20, ISL-KIK-B0236-20, ISL-KIK-B0240-20, ISL-KIK-B0242-20, ISL-KIK-B0247-20, ISL-KIK-B0270-20, ISL-KIK-B0271-20, ISL-KIK-B0272-20, ISL-KIK-B0328-20, ISL-KIK-BISLG83-10, ISL-P-CB-542, KIK-DS-324, KIK-DS-326, KIK-DS-334, KIK-P-CB-322, WPR-DS-476, WPR-P-CB-472 | Lodged
ISL_WPR_CUL_KIK_3 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | CUL-DS-416, CUL-P-CB-412, ISL-KIK-B0021-0022-20, ISL-KIK-B0216-20, ISL-KIK-B0223-20, ISL-KIK-B0231-20, ISL-KIK-B0234-20, ISL-KIK-B0236-20, ISL-KIK-B0240-20, ISL-KIK-B0242-20, ISL-KIK-B0247-20, ISL-KIK-B0270-20, ISL-KIK-B0271-20, ISL-KIK-B0272-20, ISL-KIK-B0328-20, ISL-KIK-BISLG83-10, ISL-P-CB-542, KIK-DS-324, KIK-DS-326, KIK-DS-334, KIK-P-CB-322, WPR-DS-476, WPR-P-CB-472 | Lodged
KIK_STK_2 | 2027-04-19 07:30 | 2027-04-23 18:30 | Daily | RS - Removal from Service | KIK-DS-324 Disconnector & Earth Switch type Hapam SSB-III = Contact Alignment and Re-greasing (2019086) 500648585 ISL_WPR_CUL_KIK_3, KIK_STK_2 KIK-DS-334 Disconnector & Earth Switch type Hapam SSB-III = Contact Alignment and Re-greasing (2019087) 500648589 ISL_WPR_CUL_KIK_3, KIK_STK_2 | Lodged
WPR_T13 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_WPR_CUL_KIK_3 CUL-DS-416, CUL-P-CB-412, ISL-KIK-B0021-0022-20, ISL-KIK-B0216-20, ISL-KIK-B0223-20, ISL-KIK-B0231-20, ISL-KIK-B0234-20, ISL-KIK-B0236-20, ISL-KIK-B0240-20, ISL-KIK-B0242-20, ISL-KIK-B0247-20, ISL-KIK-B0270-20, ISL-KIK-B0271-20, ISL-KIK-B0272-20, ISL-KIK-B0328-20, ISL-KIK-BISLG83-10, ISL-P-CB-542, KIK-DS-324, KIK-DS-326, KIK-DS-334, KIK-P-CB-322, WPR-DS-476, WPR-P-CB-472 | Lodged
GOR_T11 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_GOR_TMH_1 pdm maint | Lodged
NMA_GOR_TMH_1 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | pdm maint | Lodged
GYT_T2 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Affected equipment of MST_GYT_UHT_1. | Lodged
MST_GYT_UHT_1 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Tower crossarm works x1 (A149). | Lodged
ASB_TIM_TWZ_1 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | ASB-DS-296, CHH-TWZ-A0236-10, CHH-TWZ-A0239-10, CHH-TWZ-A0248-10, CHH-TWZ-A0249-10, CHH-TWZ-A0250-10, CHH-TWZ-A0253-10, CHH-TWZ-A0254-10, CHH-TWZ-A0255-10, CHH-TWZ-A0256-10, CHH-TWZ-A0271-10, CHH-TWZ-A0272-10, CHH-TWZ-A0273-10, CHH-TWZ-A0274-10, CHH-TWZ-A0275-10, CHH-TWZ-A0276-10, CHH-TWZ-A0277-10, CHH-TWZ-A0278-10, CHH-TWZ-A0279-10, CHH-TWZ-A0280-10, CHH-TWZ-A0281-10, TWZ-P-CB-2442 CHH-TWZ-A0236-10, CHH-TWZ-A0239-10, CHH-TWZ-A0248-10, CHH-TWZ-A0249-10 | Lodged
TIM_T5 | 2027-04-19 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | TIM-CBL-T5-ET5, TIM-CBL-T5-NER5, TIM-P-CB-212 | Lodged
KIK_MCH_1 | 2027-04-19 07:31 | 2027-04-22 18:31 | Daily | RS - Removal from Service | CA Lifting Inspections | Lodged
TRK_110BZ_A | 2027-04-19 07:31 | 2027-04-21 18:31 | Continuous | RS - Removal from Service | TRK-P-BZ-110-A | Lodged
TRK_110CBF | 2027-04-19 07:31 | 2027-04-21 18:31 | Continuous | RS - Removal from Service | Affected equipment | Lodged
BPE_MTN_WGN_2 | 2027-04-19 07:31 | 2027-04-20 18:31 | Continuous | RS - Removal from Service | Tower works x3 (B85A, B148-B149). | Lodged
MTN_T2 | 2027-04-19 07:31 | 2027-04-20 18:31 | Continuous | RS - Removal from Service | Affected equipment of BPE_MTN_WGN_2 | Lodged
MTO_T2 | 2027-04-19 08:00 | 2027-04-24 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
WEL_T1 | 2027-04-19 08:00 | 2027-04-24 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
BRB_CB_158 | 2027-04-20 07:30 | 2027-04-21 18:30 | Continuous | RS - Removal from Service | BRB-CB-158 | Lodged
NSY_ROX_1 | 2027-04-21 07:30 | 2027-04-21 18:30 | Daily | RS - Removal from Service | ROX-ISL-A0026-00, ROX-ISL-A0063-00, ROX-ISL-A0090-00 | Lodged
ROT_T2 | 2027-04-21 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | ROT-P-AVR-T2 | Lodged
BPE_MTN_WGN_1 | 2027-04-21 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Tower works x10 (B68, B78, B84-B85, B101, B109, B113, B119, B131, B154). | Lodged
MTN_T1 | 2027-04-21 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Affected equipment of BPE_MTN_WGN_1 | Lodged
NMA_220BS_A3 | 2027-04-21 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | pdm maint | Lodged
NMA_CB_708 | 2027-04-21 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A3 pdm maint | Lodged
NMA_CB_718 | 2027-04-21 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_220BS_A3 pdm maint | Lodged
ATI_OHK_1 | 2027-04-22 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | OHK-CT-92, OHK-CVT-92, OHK-DS-96, OHK-ES-99, OHK-P-CB-92 | Lodged
BRB_CB_148 | 2027-04-22 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | BRB-CB-148 | Lodged
KAI_11BS_F | 2027-04-22 07:30 | 2027-04-23 18:30 | Daily | RS - Removal from Service | KAI-BS-11- FRONT | Lodged
ROT_314_367 | 2027-04-22 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | ROT-BS-110-337-367 | Lodged
ROT_T3 | 2027-04-22 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Affected equipment | Lodged
ROT_TRK_2 | 2027-04-22 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | Affected equipment ROT_314_367 & ROT_T2 & ROT_T3 & ROT_WHE_1 | Lodged
ROT_WHE_1 | 2027-04-22 07:30 | 2027-04-23 18:30 | Continuous | RS - Removal from Service | ROT-M-CT312 | Lodged
DRY_TAK_OTA_2 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | RS - Removal from Service | HLY-OTA-A0150-20, HLY-OTA-A0167-20, HLY-OTA-A0172-20, HLY-OTA-A0177-20, HLY-OTA-A0179-20, HLY-OTA-A0191-20, HLY-OTA-A0196-20, HLY-OTA-A0210-20, HLY-OTA-A0213-20, OTA-CBL-1252-DRY2 | Lodged
GOR_T11 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | RS - Removal from Service | Affected Equipment of NMA_GOR_TMH_1 NMA-TMH-A0303-10 NMA-TMH-A0304-10 NMA-TMH-A0305-10 NMA-TMH-A0310-10 NMA-TMH-A0312-10 NMA-TMH-A0313-10 NMA-TMH-A0314-10 NMA-TMH-A0315-10 NMA-TMH-A0316-10 NMA-TMH-A0317-10 NMA-TMH-A0318-10 NMA-TMH-A0319-10 NMA-TMH-A0320-10 NMA-TMH-A0323-10 | Lodged
HAY_F_6 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | RS - Removal from Service | S4.10DC96-FB6, S4.10DC96.A-L1A, S4.10DC96.A-L1B, S4.10DC96.A-L1C, S4.10DC96.A-L2A, S4.10DC96.A-L2B, S4.10DC96.A-L2C, S4.10DC96.A-Q0, S4.10DC96.A-Q1, S4.10DC96.A-Q8 | Lodged
NMA_GOR_TMH_1 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | RS - Removal from Service | NMA-TMH-A0303-10 NMA-TMH-A0304-10 NMA-TMH-A0305-10 NMA-TMH-A0310-10 NMA-TMH-A0312-10 NMA-TMH-A0313-10 NMA-TMH-A0314-10 NMA-TMH-A0315-10 NMA-TMH-A0316-10 NMA-TMH-A0317-10 NMA-TMH-A0318-10 NMA-TMH-A0319-10 NMA-TMH-A0320-10 NMA-TMH-A0323-10 NMA-TMH-A0324-10 | Lodged
TAK_T8 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | RS - Removal from Service | Mid-life refurbishment project. TAK-P-TF-ET8, TAK-TF-T8 | Lodged
KAI_74_87 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | RS - Removal from Service | KAI-VT-VT1 | Lodged
KAI_SBK_1 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | RS - Removal from Service | KAI-DS-76, KAI-ES-79, KAI-P-CB-72 | Lodged
KAI_T1 | 2027-04-27 07:30 | 2027-04-30 18:30 | Continuous | RS - Removal from Service | KAI-CBL-LS11, KAI-CBL-NER1, KAI-CBL-T1, KAI-RES-NER1, KAI-TF-LS11, KAI-TF-T1, KAI-VT-VT2812 | Lodged
HAY_UHT_2 | 2027-04-28 07:00 | 2027-05-03 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3G; Bay 190 - Upper Hutt cct 2. No other HAY work on days 1, 5, 6. No other work on associated equipment/lines on day 6 (commissioning). HAY-CT-192. Tower works x1 (A4). | Lodged
BEN_CB_428 | 2027-04-28 07:30 | 2027-04-28 18:30 | Daily | RS - Removal from Service | BEN-CT-CT428 | Lodged
INV_CB_712 | 2027-04-28 07:30 | 2027-04-28 18:30 | Daily | RS - Removal from Service | INV-P-CB-712 | Lodged
HAY_110BZ | 2027-04-28 08:00 | 2027-04-28 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3G; Bay 190 - Upper Hutt cct 2. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-04-28 08:00 | 2027-04-28 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3G; Bay 190 - Upper Hutt cct 2. | Lodged
APS_OTI_1 | 2027-04-30 07:30 | 2027-04-30 18:30 | Daily | RS - Removal from Service | COL-OTI-A0467-00, COL-OTI-A0468-00, COL-OTI-A0469-00, COL-OTI-A0470-00, COL-OTI-A0472-00, COL-OTI-A0473-00, COL-OTI-A0474-00, COL-OTI-A0475-00, COL-OTI-A0476-00, COL-OTI-A0477-00, COL-OTI-A0478-00, COL-OTI-A0486-0487-10, COL-OTI-A0505A-0507A-10, COL-OTI-A0524-00 | Lodged
COL_OTI_2 | 2027-04-30 07:30 | 2027-04-30 18:30 | Daily | RS - Removal from Service | Affected equipment APS_OTI_1 | Lodged
KIK_STC_2B | 2027-04-30 07:30 | 2027-04-30 18:30 | Daily | RS - Removal from Service | KIK-CAPS-K12-C1, KIK-CAPS-K12-C2 | Lodged
HAY_110BZ | 2027-05-02 08:00 | 2027-05-02 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3G; Bay 190 - Upper Hutt cct 2. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-05-02 08:00 | 2027-05-02 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3G; Bay 190 - Upper Hutt cct 2. | Lodged
ALB_33BZ_K | 2027-05-03 07:30 | 2027-05-04 18:30 | Daily | RS - Removal from Service | ALB-P-BZ-33 | Lodged
ALB_33CBF | 2027-05-03 07:30 | 2027-05-04 18:30 | Daily | RS - Removal from Service | Affected equipment | Lodged
HWA_SFD_1 | 2027-05-03 07:30 | 2027-05-04 18:30 | Continuous | OPE - Open Ended | OPE for the duration of SFD_T10, for post-contingent overloading prevention | Lodged
HWA_T2 | 2027-05-03 07:30 | 2027-05-04 18:30 | Continuous | OPE - Open Ended | Affected equipment of HWA_SFD_1 OPE | Lodged
SFD_T10 | 2027-05-03 07:30 | 2027-05-04 18:30 | Continuous | RS - Removal from Service | SFD-DS-733 headgear refurbishment [CP_RA3_03F_0_00]. | Lodged
HEN_HEP_1 | 2027-05-03 07:30 | 2027-05-07 18:30 | Continuous | RS - Removal from Service | Affected equipment HEP_247_257_314 & HEP_ROS_1 | Lodged
HEN_HEP_2 | 2027-05-03 07:30 | 2027-05-07 18:30 | Continuous | RS - Removal from Service | Affected equipment HEP_247_257_314 & HEP_ROS_1 | Lodged
HEP_247_257_314 | 2027-05-03 07:30 | 2027-05-07 18:30 | Continuous | RS - Removal from Service | VT replacement project. HEP-VT-VT257 | Lodged
HEP_C_12 | 2027-05-03 07:30 | 2027-05-07 18:30 | Continuous | RS - Removal from Service | Affected equipment HEP_247_257_314 & HEP_ROS_1 | Lodged
HEP_C_13 | 2027-05-03 07:30 | 2027-05-07 18:30 | Continuous | RS - Removal from Service | Affected equipment HEP_247_257_314 & HEP_ROS_1 | Lodged
HEP_CB_248 | 2027-05-03 07:30 | 2027-05-07 18:30 | Continuous | RS - Removal from Service | Affected equipment HEP_247_257_314 & HEP_ROS_1 | Lodged
HEP_ROS_1 | 2027-05-03 07:30 | 2027-05-07 18:30 | Continuous | RS - Removal from Service | HEP-P-CB-252, ROS-P-CB-52 | Lodged
HEP_T3 | 2027-05-03 07:30 | 2027-05-07 18:30 | Continuous | RS - Removal from Service | Affected equipment HEP_247_257_314 & HEP_ROS_1 | Lodged
KAI_11BS_B | 2027-05-03 07:30 | 2027-05-04 18:30 | Daily | RS - Removal from Service | KAI-P-CB-38 | Lodged
KAI_FDR_2822 | 2027-05-03 07:30 | 2027-05-04 18:30 | Daily | RS - Removal from Service | Affected equipment KAI_11BS_B & KAI_T1 | Lodged
KAI_FDR_2832 | 2027-05-03 07:30 | 2027-05-04 18:30 | Daily | RS - Removal from Service | Affected equipment KAI_11BS_B & KAI_T1 | Lodged
KAI_T1 | 2027-05-03 07:30 | 2027-05-04 18:30 | Continuous | RS - Removal from Service | KAI-CBL-LS11, KAI-CBL-NER1, KAI-CBL-T1, KAI-RES-NER1, KAI-TF-LS11, KAI-TF-T1, KAI-VT-VT2812 | Lodged
CUL_T22 | 2027-05-03 07:31 | 2027-05-07 18:31 | Continuous | RS - Removal from Service | Affected Equipment of ISL_WPR_CUL_KIK_2 CUL-DS-406, CUL-P-CB-402, ISL-KIK-B0021-0022-10, ISL-KIK-B0223-10, ISL-KIK-B0266-10, ISL-KIK-B0267-10, ISL-KIK-B0270-10, ISL-KIK-B0271-10, ISL-KIK-B0272-10, ISL-P-CB-562, KIK-CVT-VT342, KIK-DS-344, KIK-DS-354, KIK-P-CB-342, WPR-DS-436, WPR-P-CB-432 | Lodged
ISL_WPR_CUL_KIK_2 | 2027-05-03 07:31 | 2027-05-07 18:31 | Continuous | RS - Removal from Service | CUL-DS-406, CUL-P-CB-402, ISL-KIK-B0021-0022-10, ISL-KIK-B0223-10, ISL-KIK-B0266-10, ISL-KIK-B0267-10, ISL-KIK-B0270-10, ISL-KIK-B0271-10, ISL-KIK-B0272-10, ISL-P-CB-562, KIK-CVT-VT342, KIK-DS-344, KIK-DS-354, KIK-P-CB-342, WPR-DS-436, WPR-P-CB-432 | Lodged
WPR_T12 | 2027-05-03 07:31 | 2027-05-07 18:31 | Continuous | RS - Removal from Service | Affected Equipment of ISL_WPR_CUL_KIK_2 CUL-DS-406, CUL-P-CB-402, ISL-KIK-B0021-0022-10, ISL-KIK-B0223-10, ISL-KIK-B0266-10, ISL-KIK-B0267-10, ISL-KIK-B0270-10, ISL-KIK-B0271-10, ISL-KIK-B0272-10, ISL-P-CB-562, KIK-CVT-VT342, KIK-DS-344, KIK-DS-354, KIK-P-CB-342, WPR-DS-436, WPR-P-CB-432 | Lodged
OAM_BPT_WTK_1 | 2027-05-03 07:31 | 2027-05-07 18:31 | Continuous | RS - Removal from Service | Affected equipment WTK_T24 | Lodged
OAM_T1 | 2027-05-03 07:31 | 2027-05-07 18:31 | Continuous | RS - Removal from Service | Affected Equipment of OAM_BPT_WTK_1 Affected equipment WTK_T24 | Lodged
WTK_T24 | 2027-05-03 07:31 | 2027-05-07 18:31 | Continuous | RS - Removal from Service | WTK-NCTD-T24 | Lodged
HAY_110BZ | 2027-05-03 08:00 | 2027-05-03 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3G; Bay 190 - Upper Hutt cct 2. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-05-03 08:00 | 2027-05-03 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3G; Bay 190 - Upper Hutt cct 2. | Lodged
BPE_797_907 | 2027-05-04 06:30 | 2027-05-04 18:30 | Daily | RS - Removal from Service | BPE-DS-893 (LTN-2) | Lodged
BPE_CB_918 | 2027-05-04 06:30 | 2027-05-04 18:30 | Daily | RS - Removal from Service | Affected equipment of BPE_797_907, for BPE-DS-893 (LTN-2) | Lodged
BPE_LTN_2 | 2027-05-04 06:30 | 2027-05-06 18:30 | Continuous | RS - Removal from Service | BPE-CB-892, BPE-CT-892, BPE-CVT-892, BPE-DS-893, BPE-DS-896, BPE-ES-899, LTN-DS-224, LTN-ES-229. Tower works x7 (A11, A20, A29, A35-A36, A46, A51). | Lodged
BPE_WDV_1 | 2027-05-04 06:30 | 2027-05-11 18:30 | Continuous | RS - Removal from Service | BPE-P-CB-72, WDV-P-CB-112. Re-insulation x13. BPE_WDV_1/2 line protection replacement project [CP_BPE_02C_0_00]. Last day for commissioning (no other work). | Lodged
LTN_T2 | 2027-05-04 06:30 | 2027-05-06 18:30 | Continuous | RS - Removal from Service | LTN-CVT-CVT222. Affected equipment of BPE_LTN_2. | Lodged
WDV_67_147 | 2027-05-04 06:30 | 2027-05-04 18:30 | Daily | RS - Removal from Service | WDV_67_147 | Lodged
WDV_CB_132 | 2027-05-04 06:30 | 2027-05-04 18:30 | Daily | RS - Removal from Service | Affected equipment of WDV_67_147 | Lodged
BLN_AVR_C1C2C3C4 | 2027-05-04 07:30 | 2027-05-04 18:30 | Daily | RS - Removal from Service | BLN-P-REG | Lodged
HAY_CB_982A | 2027-05-04 07:30 | 2027-05-07 18:30 | Continuous | RS - Removal from Service | S4.10DC98.A-C1A, S4.10DC98.A-C1B, S4.10DC98.A-C1C, S4.10DC98.A-C2A, S4.10DC98.A-C2B, S4.10DC98.A-C2C, S4.10DC98.A-C3A, S4.10DC98.A-C3B, S4.10DC98.A-C3C, S4.10DC98.A-L1A, S4.10DC98.A-L1B, S4.10DC98.A-L1C, S4.10DC98.A-L2A, S4.10DC98.A-L2B, S4.10DC98.A-L2C, S4.10DC98.A-L3A, S4.10DC98.A-L3B, S4.10DC98.A-L3C, S4.10DC98.A-Q0, S4.10DC98.A-R2A, S4.10DC98.A-R2B, S4.10DC98.A-R2C, S4.10DC98.A-R3A, S4.10DC98.A-R3B, S4.10DC98.A-R3C | Lodged
SBK_FDR_202 | 2027-05-04 07:30 | 2027-05-04 18:30 | Daily | RS - Removal from Service | SBK-CB-202 | Lodged
ARI_KIN_1 | 2027-05-05 07:30 | 2027-05-06 18:30 | Continuous | RS - Removal from Service | ARI-CB-212, ARI-CT-212, ARI-DS-216, ARI-ES-219 | Lodged
ONG_T1 | 2027-05-05 07:30 | 2027-05-06 18:30 | Continuous | RS - Removal from Service | ONG-M-CT162, ONG-TF-T1B, ONG-TF-T1R, ONG-TF-T1SP, ONG-TF-T1Y | Lodged
SFD_T9 | 2027-05-05 07:30 | 2027-05-07 18:30 | Continuous | RS - Removal from Service | SFD-CBL-T9-232 | Lodged
GLN_220BZ | 2027-05-05 07:30 | 2027-05-06 18:30 | Continuous | RS - Removal from Service | GLN-P-BZ-220 | Lodged
GLN_220CBF | 2027-05-05 07:30 | 2027-05-06 18:30 | Continuous | RS - Removal from Service | GLN-P-BZ-220 | Lodged
HWA_SFD_1 | 2027-05-05 07:31 | 2027-05-07 18:31 | Continuous | OPE - Open Ended | OPE for the duration of SFD_T9, for post-contingent overloading prevention | Lodged
HWA_T2 | 2027-05-05 07:31 | 2027-05-07 18:31 | Continuous | OPE - Open Ended | OPE for the duration of HWA_SFD_1, to prevent recirculating currents through the HWA 33kV. | Lodged
MKE_CB_102 | 2027-05-05 07:31 | 2027-05-07 18:31 | Continuous | RS - Removal from Service | MKE-DCB-102 | Lodged
MNI_MKE_SFD_1 | 2027-05-05 07:31 | 2027-05-07 18:31 | Continuous | RS - Removal from Service | MNI-DEV-A0169-20, MNI-DEV-A0170-20 | Lodged
SFD_177_222_232 | 2027-05-05 07:31 | 2027-05-07 18:31 | Continuous | RS - Removal from Service | SFD-DS-187 | Lodged
SFD_T6 | 2027-05-05 07:31 | 2027-05-07 18:31 | Continuous | RS - Removal from Service | SFD-NCT-6, SFD-P-TF-T6 | Lodged
BPE_523_697 | 2027-05-07 06:30 | 2027-05-07 18:30 | Daily | RS - Removal from Service | BPE-DS-553 (T9) | Lodged
BPE_CB_608 | 2027-05-07 06:30 | 2027-05-07 18:30 | Daily | RS - Removal from Service | Affected equipment of BPE_523_697, for BPE-DS-553 (T9) | Lodged
BPE_T9 | 2027-05-07 06:30 | 2027-05-07 18:30 | Daily | RS - Removal from Service | BPE-DS-553 motorisation [CP_RA4_02M_0_00]. | Lodged
ASY_11BZ_A | 2027-05-07 07:30 | 2027-05-07 18:30 | Daily | RS - Removal from Service | ASY-P-BZ-11 | Lodged
ALB_587_597_637 | 2027-05-10 07:30 | 2027-05-12 18:30 | Continuous | RS - Removal from Service | ALB-DS-594 | Lodged
ALB_C_2 | 2027-05-10 07:30 | 2027-05-12 18:30 | Continuous | RS - Removal from Service | Affected equipment ALB_587_597_637 & ALB_SVL_1 | Lodged
ARG_KIK_1 | 2027-05-10 07:30 | 2027-05-14 18:30 | Continuous | RS - Removal from Service | BLN-KIK-A0378-00, BLN-KIK-A0383-00, BLN-KIK-A0424-00, BLN-KIK-A0426-00, BLN-KIK-A0431-00, BLN-KIK-A0438-00, BLN-KIK-A0443-00, BLN-KIK-A0444-00, BLN-KIK-A0450-00, BLN-KIK-A0451-00, BLN-KIK-A0454-00, BLN-KIK-A0457-00, BLN-KIK-A0472-00, BLN-KIK-A0473-00, BLN-KIK-A0496-00, BLN-KIK-A0507-00, BLN-KIK-A0512-00, BLN-KIK-A0522-00, BLN-KIK-A0526-00, BLN-KIK-A0527-00, BLN-KIK-A0528-00, BLN-KIK-A0556-00 | Lodged
EDG_TRK_1 | 2027-05-10 07:30 | 2027-05-14 18:30 | Continuous | RS - Removal from Service | Reinsulation, Attachment Points, Line Maintenance | Lodged
MTN_T2 | 2027-05-10 07:30 | 2027-05-25 18:30 | Continuous | RS - Removal from Service | MTN-TF-T2 | Lodged
ROT_337_367 | 2027-05-10 07:30 | 2027-05-11 18:30 | Continuous | RS - Removal from Service | ROT-DS-354, ROT-DS-357 | Lodged
ROT_T3 | 2027-05-10 07:30 | 2027-05-11 18:30 | Continuous | RS - Removal from Service | ROT-M-CT2792, ROT-M-VT2792 | Lodged
TGA_T2 | 2027-05-10 07:30 | 2027-05-15 18:30 | Continuous | RS - Removal from Service | CB pole replacement TGA-CB-272, TGA-M-CT37 RM at end of outage after maintenance completed. | Lodged
HWA_CB_2648 | 2027-05-10 07:30 | 2027-05-10 18:30 | Daily | RS - Removal from Service | HWA-CB-2648, HWA-P-CB-2648 | Lodged
HWA_FDR_2632 | 2027-05-10 07:30 | 2027-05-10 18:30 | Daily | RS - Removal from Service | HWA-CB-2632, HWA-P-CB-2632 | Lodged
CUL_T23 | 2027-05-10 07:30 | 2027-05-13 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_WPR_CUL_KIK_3 Affected equipment KIK_220BS_C1 & KIK_CB_328 & KIK_STK_2 | Lodged
ISL_WPR_CUL_KIK_3 | 2027-05-10 07:30 | 2027-05-13 18:30 | Continuous | RS - Removal from Service | Affected equipment KIK_220BS_C1 & KIK_CB_328 & KIK_STK_2 | Lodged
KIK_220BS_C1 | 2027-05-10 07:30 | 2027-05-13 18:30 | Continuous | RS - Removal from Service | KIK-DS-357, KIK-P-CB-358 | Lodged
KIK_CB_328 | 2027-05-10 07:30 | 2027-05-13 18:30 | Continuous | RS - Removal from Service | KIK-P-CB-328 | Lodged
KIK_CB_358 | 2027-05-10 07:30 | 2027-05-13 18:30 | Continuous | RS - Removal from Service | Affected equipment KIK_220BS_C1 & KIK_CB_328 & KIK_STK_2 | Lodged
WPR_T13 | 2027-05-10 07:30 | 2027-05-13 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_WPR_CUL_KIK_3 Affected equipment KIK_220BS_C1 & KIK_CB_328 & KIK_STK_2 | Lodged
OAM_STU_BPD_WTK_2 | 2027-05-10 07:31 | 2027-05-14 18:31 | Continuous | RS - Removal from Service | BPD-P-CB-442, BPD-P-CB-482, GNY-TIM-A0364-00, GNY-TIM-A0385-00, GNY-WTK-A0080-0081-20, OAM-DS-86, OAM-ES-89, STU-DS-66, WTK-DS-56, WTK-ES-59 | Lodged
OAM_T2 | 2027-05-10 07:31 | 2027-05-14 18:31 | Continuous | RS - Removal from Service | OAM-CB-312, OAM-CB-82, OAM-DS-316, OAM-DS-87, OAM-M-CT312, OAM-M-VT2, OAM-P-TF-T2, OAM-TF-LS2, OAM-TF-T2, OAM-VT-VT2, OAM-VT-VT4 | Lodged
STU_CB_62 | 2027-05-10 07:31 | 2027-05-14 18:31 | Continuous | RS - Removal from Service | Affected equipment WTK_56_447 & LIV_WTK_1 & WTK_CB_438 & WTK_T23 & OAM_STU_BPD_WTK_2 & OAM_T2 | Lodged
WTK_T23 | 2027-05-10 07:31 | 2027-05-14 18:31 | Continuous | RS - Removal from Service | WTK-NCTD-T23 | Lodged
SVL_T1 | 2027-05-10 08:00 | 2027-05-15 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
WDV_67_147 | 2027-05-11 06:30 | 2027-05-11 18:30 | Daily | RS - Removal from Service | WDV_67_147 | Lodged
WDV_CB_132 | 2027-05-11 06:30 | 2027-05-11 18:30 | Daily | RS - Removal from Service | Affected equipment of WDV_67_147 | Lodged
HAY_UHT_1 | 2027-05-11 07:00 | 2027-05-16 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3H; Bay 210 - Upper Hutt cct 1. No other HAY work on days 1, 5, 6. No other work on associated equipment/lines on day 6 (commissioning). HAY-CT-212. Tower works x2 (A4-A5). | Lodged
HWA_CB_122 | 2027-05-11 07:30 | 2027-05-11 18:30 | Daily | RS - Removal from Service | HWA-M-CT122, HWA-M-VT122 (Metering not required if decommissioned and replaced with digital substation as planned June 2026). | Lodged
HWA_CB_602 | 2027-05-11 07:30 | 2027-05-11 18:30 | Daily | RS - Removal from Service | HWA-P-DCB-602 | Lodged
HWA_WAA_1 | 2027-05-11 07:30 | 2027-05-11 18:30 | Daily | RS - Removal from Service | Affected equipment of HWA_CB_602, for HWA-P-DCB-602 | Lodged
HAY_110BZ | 2027-05-11 08:00 | 2027-05-11 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3H; Bay 210 - Upper Hutt cct 1. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-05-11 08:00 | 2027-05-11 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3H; Bay 210 - Upper Hutt cct 1. | Lodged
WPR_FDR_1132 | 2027-05-12 07:30 | 2027-05-14 18:30 | Continuous | RS - Removal from Service | WPR-P-CB-1132 | Lodged
ALB_SVC_7 | 2027-05-13 07:30 | 2027-05-14 18:30 | Continuous | RS - Removal from Service | ALB-P-PSUP-SVC7-UPS-1, ALB-P-TF-T7, ALB-SVC7-TCR7, ALB-SVC7-TSC7 | Lodged
HAY_110BZ | 2027-05-15 08:00 | 2027-05-15 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3H; Bay 210 - Upper Hutt cct 1. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-05-15 08:00 | 2027-05-15 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3H; Bay 210 - Upper Hutt cct 1. | Lodged
HAY_110BZ | 2027-05-16 08:00 | 2027-05-16 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3H; Bay 210 - Upper Hutt cct 1. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-05-16 08:00 | 2027-05-16 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3H; Bay 210 - Upper Hutt cct 1. | Lodged
ASY_SBK_1 | 2027-05-17 06:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | Affected equipment ASY_124_137_157, ASY-CB-152 | Lodged
ASY_124_137_157 | 2027-05-17 06:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | ASY-DS-137, ASY-DS-147, ASY-DS-154, ASY-DS-157, ASY-DS-124 | Lodged
ASY_T3 | 2027-05-17 06:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | Affected equipment ASY_124_137_157 & ASY_SBK_1 | Lodged
ASY_CB_2722 | 2027-05-17 06:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | Affected equipment ASY_T3, ASY_124_137_157 & ASY_SBK_1 | Lodged
ASY_CB_2742 | 2027-05-17 06:30 | 2027-05-21 18:30 | Continuous | CLO - Close | CLO for ASY_T3 out with ASY_124_137_157 & ASY_SBK_1 | Lodged
ASY_157_167 | 2027-05-17 06:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | Affected equipment ASY-DS-157 | Lodged
ARG_BLN_1 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | BLN-KIK-A0200-00, BLN-KIK-A0366-00, structure replacements BLN-KIK-A0200-00, BLN-KIK-A0201-00, BLN-KIK-A0199-00, BLN-KIK-A0361 , BLN-KIK-A0366-00 under clearance | Lodged
GOR_597_607_604 | 2027-05-17 07:30 | 2027-05-22 18:30 | Continuous | RS - Removal from Service | GOR-DS-604, GOR-DS-607, GOR-P-CB-612, GOR-VT-VT617 | Lodged
GOR_T11 | 2027-05-17 07:30 | 2027-05-22 18:30 | Continuous | RS - Removal from Service | GOR-CB-752, GOR-CBL-T11-ET11, GOR-CT-CT612, GOR-CT-CT752, GOR-CT-NCT11, GOR-DCB-612, GOR-NCTD-T11, GOR-P-CB-752, GOR-P-TF-T11, GOR-TF-ET11, GOR-TF-T11 | Lodged
GOR_T3 | 2027-05-17 07:30 | 2027-05-22 18:30 | Continuous | RS - Removal from Service | GOR-TF-T3 | Lodged
HEN_467_514_524 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | Head gear refurb HEN-DS-507 | Lodged
HEN_CB_488 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | Affected equipment HEN_467_514_524 & HEN_HPI_1 & HEN_SWN_1 & BRB_HPI_1 | Lodged
HEN_HPI_1 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | HEN-CB-512, HEN-MDN-A0001A-10, HEN-MDN-A0002-0003-10, HEN-MDN-A0007-10, HEN-MDN-A0013-10, HEN-MDN-A0036-00, HEN-MDN-A0036-10 | Lodged
HEN_SWN_1 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | HEN-CB-522, HEN-CVT-522, HEN-DS-526, HEN-ES-529, HEN-OTA-A0027-0028-20, HEN-OTA-A0034-20, HEN-OTA-A0037-20, HEN-OTA-A0052-20, HEN-OTA-A0091-20 | Lodged
HEN_T3 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | Affected equipment HEN_467_514_524 & HEN_HPI_1 & HEN_SWN_1 & BRB_HPI_1 | Lodged
HEN_T5 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | Affected equipment HEN_467_514_524 & HEN_HPI_1 & HEN_SWN_1 & BRB_HPI_1 | Lodged
MPE_CB_252 | 2027-05-17 07:30 | 2027-05-17 22:00 | Daily | OPE - Open Ended | System split for the duration of BRB_HPI_1 | Lodged
MPE_CB_292 | 2027-05-17 07:30 | 2027-05-17 22:00 | Daily | OPE - Open Ended | System split for the duration of BRB_HPI_1 | Lodged
EDG_TRK_1 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | EDG-TRK-A0067-10, EDG-TRK-A0092-10, EDG-TRK-A0100-10, EDG-TRK-A0105-10, EDG-TRK-A0106-10, EDG-TRK-A0108-10, EDG-TRK-A0109-10, EDG-TRK-A0110-10, EDG-TRK-A0112-10, EDG-TRK-A0114-10, EDG-TRK-A0120-10, EDG-TRK-A0124-10, EDG-TRK-A0131-10, EDG-TRK-A0132-10, EDG-TRK-A0133-10, EDG-TRK-A0138-10 | Lodged
KMO_TRK_2 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | KMO-DS-386, KMO-ES-389 | Lodged
TRK_357_627_607 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | TRK-BS-220-357-607, TRK-DS-344 | Lodged
TRK_CB_618 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | TRK-CB-618, TRK-CT-618 | Lodged
TRK_DIS_407 | 2027-05-17 07:30 | 2027-05-21 18:30 | Continuous | CLO - Close | Closed for the duration of KAW_357_627_607 | Lodged
MPE_CB_252 | 2027-05-18 06:00 | 2027-05-20 22:00 | Continuous | OPE - Open Ended | System split for the duration of BRB_HPI_1 | Lodged
MPE_CB_292 | 2027-05-18 06:00 | 2027-05-20 22:00 | Continuous | OPE - Open Ended | System split for the duration of BRB_HPI_1 | Lodged
COL_HOR_3 | 2027-05-18 07:30 | 2027-05-18 18:30 | Daily | RS - Removal from Service | BKD-HOR-A0005-0006-20 | Lodged
HAY_F_5 | 2027-05-18 07:30 | 2027-05-21 18:30 | Continuous | RS - Removal from Service | S4.10DC98-FB5, S4.10DC98.B-Q0 | Lodged
OHB_TWZ_3 | 2027-05-18 07:30 | 2027-05-20 18:30 | Continuous | RS - Removal from Service | OHB-CT-CT1102, OHB-CVT-VT112, OHB-DS-1106, OHB-ES-1109, OHB-P-CB-1102, TWZ-CT-CT2672, TWZ-CVT-CVT9, TWZ-DS-2676, TWZ-ES-2679 | Lodged
PEN_LS1 | 2027-05-18 07:30 | 2027-05-19 18:31 | Continuous | RS - Removal from Service | Affected equipment PEN_STC_1 | Lodged
PEN_STC_1 | 2027-05-18 07:30 | 2027-05-19 18:31 | Continuous | RS - Removal from Service | PEN-CB-2412, PEN-CWU-STC1A, PEN-CWU-STC1B, PEN-P-PSUP-STC1-UPS-1, PEN-STC-1A, PEN-STC-1B | Lodged
HAY_CB_2452 | 2027-05-19 07:30 | 2027-05-19 18:30 | Daily | RS - Removal from Service | HAY-CBL-CB2452-LS3 | Lodged
PTS_1873_INV_MAN | 2027-05-20 07:30 | 2027-05-20 18:30 | Daily | RS - Removal from Service | INV-C-PTSG-1873, MAN-C-PTSG-1873 | Lodged
MPE_CB_252 | 2027-05-21 06:00 | 2027-05-21 18:30 | Daily | OPE - Open Ended | System split for the duration of BRB_HPI_1 | Lodged
MPE_CB_292 | 2027-05-21 06:00 | 2027-05-21 18:30 | Daily | OPE - Open Ended | System split for the duration of BRB_HPI_1 | Lodged
BEN_T34 | 2027-05-24 07:30 | 2027-05-25 18:30 | Daily | RS - Removal from Service | S1.P2-AL.T1 | Lodged
HKK_OTI_2 | 2027-05-24 07:30 | 2027-05-27 18:30 | Continuous | RS - Removal from Service | CA Lifting inspections | Lodged
KIK_STK_3 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | RS - Removal from Service | under clearance req | Lodged
KUM_OTI_1 | 2027-05-24 07:30 | 2027-05-27 18:30 | Continuous | RS - Removal from Service | CA Lifting inspections | Lodged
MGM_T2 | 2027-05-24 07:30 | 2027-05-26 18:30 | Continuous | RS - Removal from Service | MGM-CB-1282, MGM-VT-12. MGM-M-CT1282 - metering days 2 + 3. | Lodged
GOR_T11 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | RS - Removal from Service | GOR-CB-752, GOR-CBL-T11-ET11, GOR-CT-CT612, GOR-CT-CT752, GOR-CT-NCT11, GOR-DCB-612, GOR-NCTD-T11, GOR-P-CB-752, GOR-P-TF-T11, GOR-TF-ET11, GOR-TF-T11 | Lodged
NMA_GOR_TMH_1 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | RS - Removal from Service | GOR-CVT-VT752, GOR-DS-756, GOR-ES-759, NMA-CT-CT832, | Lodged
KIN_367_394 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | RS - Removal from Service | KIN-VT-377 | Lodged
KIN_T5 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | RS - Removal from Service | KIN-CBL-36, KIN-CBL-T5-2232, KIN-CBL-T5-NER5, KIN-CT-392, KIN-DS-36, KIN-RES-NER5, KIN-TF-ET5, KIN-TF-T5, KIN-VT-2047, KIN-VT-2232, KIN-VT-30 | Lodged
KIN_T6 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | RS - Removal from Service | KIN-M-CT2932, KIN-M-VT2932 | Lodged
KIN_TRK_1 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | RS - Removal from Service | LCH-KIN-A0739-0740-10 | Lodged
LFD_DIS_56 | 2027-05-24 07:30 | 2027-05-28 18:30 | Continuous | RS - Removal from Service | Affected equipment KIN_367_394 & KIN_T5 & KIN_T6 & KIN_TRK_1 | Lodged
SVL_T2 | 2027-05-24 08:00 | 2027-05-29 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
HAY_SC_9_T9 | 2027-05-25 07:00 | 2027-05-30 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3P; Bay 140 - Transformer T9. No other HAY work on days 1, 5, 6. No other work on associated equipment/lines on day 6 (commissioning). | Lodged
BEN_F_4 | 2027-05-25 07:30 | 2027-05-26 18:30 | Daily | RS - Removal from Service | S1.WA-Z1.F1.A, S1.WA-Z1.F1.B, S1.WA-Z1.F1.C, S1.WA-Z1.Q1, S1.WA-Z1.Q2, S1.WA-Z1.Z1.F1.A, S1.WA-Z1.Z1.F1.B, S1.WA-Z1.Z1.F1.C, S1.WA-Z1.Z1.R1A, S1.WA-Z1.Z1.R1B, S1.WA-Z1.Z1.R1C, S1.WA-Z1.Z2.F1.A, S1.WA-Z1.Z2.F1.B, S1.WA-Z1.Z2.F1.C, S1.WA-Z1.Z2.L1A, S1.WA-Z1.Z2.L1B, S1.WA-Z1.Z2.R1A, S1.WA-Z1.Z2.R1B, S1.WA-Z1.Z2.R1C | Lodged
BPE_WDV_2 | 2027-05-25 07:30 | 2027-06-01 18:30 | Continuous | RS - Removal from Service | BPE-P-CB-82, WDV-P-CB-62. Re-insulation x12. BPE_WDV_1/2 line protection replacement project [CP_BPE_02C_0_00]. Last day for commissioning (no other work). | Lodged
DVK_T1 | 2027-05-25 07:30 | 2027-05-25 18:30 | Daily | RS - Removal from Service | Affected equipment of WDV_DVK_WPW_2. | Lodged
ROX_T10_573_575_584 | 2027-05-25 07:30 | 2027-05-27 18:30 | Continuous | RS - Removal from Service | ROX-CT-CT572, ROX-NCTD-T10 | Lodged
WDV_57_67_117 | 2027-05-25 07:30 | 2027-05-25 18:30 | Daily | RS - Removal from Service | WDV-P-CB-62 (BPE-2) | Lodged
WDV_DVK_WPW_2 | 2027-05-25 07:30 | 2027-05-25 18:30 | Daily | RS - Removal from Service | Affected equipment of WDV_57_67_117, for WDV-P-CB-62 (BPE-2) | Lodged
WPW_T1 | 2027-05-25 07:30 | 2027-05-25 18:30 | Daily | RS - Removal from Service | Affected equipment of WDV_DVK_WPW_2. | Lodged
HAY_110BZ | 2027-05-25 08:00 | 2027-05-25 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3P; Bay 140 - Transformer T9. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-05-25 08:00 | 2027-05-25 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3P; Bay 140 - Transformer T9. | Lodged
MGM_ACO_SPS | 2027-05-26 07:30 | 2027-05-26 18:30 | Daily | RS - Removal from Service | MGM-P-SPS-OTAS [CP_MGM_AC_00_00]. | Lodged
PTS_2309_LFD_TRK | 2027-05-26 07:30 | 2027-05-26 18:30 | Daily | RS - Removal from Service | LFD-C-PTSG-2309A, TRK-C-PTSG-2309A | Lodged
MGM_WDV_1 | 2027-05-27 07:30 | 2027-05-28 18:30 | Continuous | RS - Removal from Service | MGM-CB-152, MGM-CT-152, MGM-VT-152 | Lodged
BDE_110BZ | 2027-05-27 07:31 | 2027-05-28 18:31 | Daily | RS - Removal from Service | BDE-P-BZ-110 | Lodged
BDE_110CBF | 2027-05-27 07:31 | 2027-05-28 18:31 | Daily | RS - Removal from Service | BDE-P-BZ-110 | Lodged
COL_HOR_2 | 2027-05-28 07:30 | 2027-05-28 18:30 | Daily | RS - Removal from Service | BKD-HOR-A0006-0007-10 | Lodged
HAY_110BZ | 2027-05-29 08:00 | 2027-05-29 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3P; Bay 140 - Transformer T9. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-05-29 08:00 | 2027-05-29 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3P; Bay 140 - Transformer T9. | Lodged
HAY_110BZ | 2027-05-30 08:00 | 2027-05-30 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3P; Bay 140 - Transformer T9. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-05-30 08:00 | 2027-05-30 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3P; Bay 140 - Transformer T9. | Lodged
ALB_CB_658 | 2027-05-31 07:30 | 2027-06-01 18:30 | Continuous | RS - Removal from Service | ALB-CT-658, ALB-P-CB-658 | Lodged
ARI_HAM_1 | 2027-05-31 07:30 | 2027-06-04 18:30 | Continuous | RS - Removal from Service | Reinsulation | Lodged
BDE_C_2 | 2027-05-31 07:30 | 2027-06-02 18:30 | Continuous | RS - Removal from Service | BDE-CAPS-C2, BDE-CBL-18, BDE-REA-C2 | Lodged
HTI_T1 | 2027-05-31 07:30 | 2027-06-04 18:30 | Continuous | RS - Removal from Service | HTI-CBL-T1-2242, HTI-CBL-T1-LS1, HTI-TF-LS1, HTI-TF-T1B, HTI-TF-T1R, HTI-TF-T1Y | Lodged
MGM_MST_1 | 2027-05-31 07:30 | 2027-06-04 18:30 | Continuous | RS - Removal from Service | Pole replacements x6. | Lodged
MGM_T3 | 2027-05-31 07:30 | 2027-06-02 18:30 | Continuous | RS - Removal from Service | MGM-CB-1362, MGM-CBL-1362, MGM-TF-LS33, MGM-TF-T3, MGM-VT-13 | Lodged
BOB_HAM_1 | 2027-06-01 07:30 | 2027-06-02 18:30 | Continuous | RS - Removal from Service | HAM-DCB-172, HAM-MER-B0324-00, HAM-P-CB-172 | Lodged
DVK_T1 | 2027-06-01 07:30 | 2027-06-01 18:30 | Daily | RS - Removal from Service | Affected equipment of WDV_DVK_WPW_2. | Lodged
WDV_57_67_117 | 2027-06-01 07:30 | 2027-06-01 18:30 | Daily | RS - Removal from Service | WDV-P-CB-62 (BPE-2) | Lodged
WDV_DVK_WPW_2 | 2027-06-01 07:30 | 2027-06-01 18:30 | Daily | RS - Removal from Service | Affected equipment of WDV_57_67_117, for WDV-P-CB-62 (BPE-2) | Lodged
WPW_T1 | 2027-06-01 07:30 | 2027-06-01 18:30 | Daily | RS - Removal from Service | Affected equipment of WDV_DVK_WPW_2. | Lodged
BLN_33BS_A | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | RS - Removal from Service | 1 yrs, BLN-VT-VT2067 | Lodged
BLN_C_1 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | RS - Removal from Service | BLN-CAPS-C1, BLN-CB-2082, BLN-CBL-C1, BLN-REA-C1-1, BLN-REA-C1-3, BLN-VT-C1-2 | Lodged
BLN_C_3 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | RS - Removal from Service | BLN-CAPS-C3, BLN-CB-2072, BLN-CBL-C3, BLN-REA-C3-1, BLN-REA-C3-3, BLN-VT-C3-2 | Lodged
BLN_CB_2028_CBL | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | RS - Removal from Service | BLN-CB-2028 | Lodged
BLN_CB_2108 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | RS - Removal from Service | Affected equipment BLN_33BS_A & BLN_C_1 & BLN_C_3 & BLN_CB_2028_CBL & BLN_T2 | Lodged
BLN_FDR_2032 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | RS - Removal from Service | Affected equipment BLN_33BS_A & BLN_C_1 & BLN_C_3 & BLN_CB_2028_CBL & BLN_T2 | Lodged
BLN_FDR_2042 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | RS - Removal from Service | Affected equipment BLN_33BS_A & BLN_C_1 & BLN_C_3 & BLN_CB_2028_CBL & BLN_T2 | Lodged
BLN_FDR_2052 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | RS - Removal from Service | Affected equipment BLN_33BS_A & BLN_C_1 & BLN_C_3 & BLN_CB_2028_CBL & BLN_T2 | Lodged
BLN_T2 | 2027-06-01 07:30 | 2027-06-04 18:30 | Continuous | RS - Removal from Service | BLN-CB-92 | Lodged
BEN_T37 | 2027-06-02 07:30 | 2027-06-03 18:30 | Daily | RS - Removal from Service | S1.20T37-T37 | Lodged
WPW_DIS_36A | 2027-06-02 07:31 | 2027-06-03 18:31 | Continuous | RS - Removal from Service | Affected equipment of WPW_T33, for WPW-TF-T33 (TENTATIVE OW - asset may be divested). | Lodged
WPW_DIS_36B | 2027-06-02 07:31 | 2027-06-03 18:31 | Continuous | RS - Removal from Service | Affected equipment of WPW_T33, for WPW-TF-T33 (TENTATIVE OW - asset may be divested). | Lodged
WPW_T33 | 2027-06-02 07:31 | 2027-06-03 18:31 | Continuous | RS - Removal from Service | WPW-TF-T33 (TENTATIVE OW - asset may be divested). | Lodged
BDE_EDN_1 | 2027-06-03 07:30 | 2027-06-04 18:30 | Daily | RS - Removal from Service | BDE-DEV-A0014-0015-00, GOR-INV-A0085-10, GOR-INV-A0113-00, GOR-INV-A0128-00 | Lodged
INV_CB_642 | 2027-06-04 07:30 | 2027-06-04 18:30 | Daily | RS - Removal from Service | INV-CB-642, INV-CT-CT642, INV-P-CB-642 | Lodged
BDE_T1 | 2027-06-07 07:30 | 2027-06-11 18:30 | Continuous | RS - Removal from Service | BDE-CBL-37, BDE-CT-T1, BDE-TF-LS1, BDE-TF-T1, BDE-VT-VT37 | Lodged
HAY_CB_258 | 2027-06-07 07:30 | 2027-06-07 18:30 | Daily | RS - Removal from Service | HAY-CT-258, HAY-P-CB-258 | Lodged
SVL_T2 | 2027-06-07 08:00 | 2027-06-12 18:30 | Continuous | RS - Removal from Service | Affected Equipment Tower Painting | Lodged
ARI_HAM_1 | 2027-06-08 07:30 | 2027-06-11 18:30 | Continuous | RS - Removal from Service | ARI-HAM-B0005-00,, ARI-HAM-B0093-10, ARI-HAM-B0097-00, ARI-HAM-B0098-00, ARI-HAM-B0101-00, ARI-HAM-B0107-00, ARI-HAM-B0108-10, ARI-HAM-B0116-00, ARI-HAM-B0119-10, ARI-HAM-B0120-10, ARI-HAM-B0124-00, ARI-HAM-B0129-10, ARI-HAM-B0132-10, ARI-HAM-B0135-10, ARI-HAM-B0136-10, ARI-HAM-B0140-10 | Lodged
ATI_TRK_1 | 2027-06-08 07:30 | 2027-06-09 18:30 | Continuous | RS - Removal from Service | ATI-CT-102, ATI-CVT-102, ATI-DS-106, ATI-ES-109, TRK-DS-566, TRK-P-CB-562, TRK-VT-CVT562 | Lodged
BAL_T2 | 2027-06-08 07:30 | 2027-06-09 18:30 | Daily | RS - Removal from Service | BAL-TF-T2 | Lodged
ISL_66BS_A | 2027-06-08 07:30 | 2027-06-09 18:30 | Continuous | RS - Removal from Service | ISL-DS-293 Diagnostic inspection and service (DS0011) - Disconnector and Earth Switch: Canterbury Engineering (2045145) 500648116 HOR_KBY_ISL_1, ISL_66BS_A | Lodged
ISL_CB_708 | 2027-06-08 07:30 | 2027-06-09 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_66BS_A ISL-DS-293 Diagnostic inspection and service (DS0011) - Disconnector and Earth Switch: Canterbury Engineering (2045145) 500648116 HOR_KBY_ISL_1, ISL_66BS_A | Lodged
ISL_CB_768 | 2027-06-08 07:30 | 2027-06-09 18:30 | Continuous | RS - Removal from Service | ISL-P-CB-768 -Affected Equipment of ISL_66BS_A ISL-DS-293 Diagnostic inspection and service (DS0011) - Disconnector and Earth Switch: Canterbury Engineering (2045145) 500648116 HOR_KBY_ISL_1, ISL_66BS_A | Lodged
HOR_KBY_ISL_1 | 2027-06-08 07:31 | 2027-06-11 18:31 | Continuous | RS - Removal from Service | HOR-DS-66, HOR-ES-69, HOR-P-CB-62, ISL-CB-292, ISL-CBL-292, ISL-DS-293, ISL-DS-295, ISL-DS-296, ISL-ES-299, ISL-P-CB-292, ISL-VT-VT20, KBY-DS-4926, KBY-ES-4929, KBY-VT-VT4922 | Lodged
KBY_CB_4922 | 2027-06-08 07:31 | 2027-06-11 18:31 | Continuous | RS - Removal from Service | Affected equipment HOR_KBY_ISL_1 | Lodged
ARI_110BZ_A | 2027-06-08 07:31 | 2027-06-10 18:31 | Continuous | RS - Removal from Service | ARI-P-BZ-110-A | Lodged
ARI_110CBF | 2027-06-08 07:31 | 2027-06-10 18:31 | Continuous | RS - Removal from Service | Affected equipment | Lodged
HAY_SC_10_T10 | 2027-06-09 07:00 | 2027-06-14 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 3Q; Bay 160 - Transformer T10. No other HAY work on days 1, 5, 6. No other work on associated equipment/lines on day 6 (commissioning). | Lodged
ALB_FDR_322 | 2027-06-09 07:30 | 2027-06-10 18:30 | Continuous | RS - Removal from Service | ALB-CB-322, ALB-DS-326, ALB-ES-329 | Lodged
HLY_CB_662 | 2027-06-09 07:30 | 2027-06-11 18:30 | Continuous | RS - Removal from Service | HLY-P-CB-662 | Lodged
BPE_220BS_B | 2027-06-09 07:30 | 2027-06-11 18:30 | Continuous | RS - Removal from Service | BPE-DS-667 (bus) headgear replacement | Lodged
BPE_CB_648 | 2027-06-09 07:30 | 2027-06-11 18:30 | Continuous | RS - Removal from Service | Affected equipment of BPE_220BS_B | Lodged
BPE_CB_918 | 2027-06-09 07:30 | 2027-06-11 18:30 | Continuous | RS - Removal from Service | Affected equipment of BPE_220BS_B | Lodged
WRK_T29 | 2027-06-09 07:31 | 2027-06-11 18:31 | Continuous | RS - Removal from Service | WRK-CB-182, WRK-M-VT2002, WRK-NCT-29, WRK-P-TF-T29, WRK-VT-2002 | Lodged
HAY_110BZ | 2027-06-09 08:00 | 2027-06-09 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3Q; Bay 160 - Transformer T10. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-06-09 08:00 | 2027-06-09 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3Q; Bay 160 - Transformer T10. | Lodged
ISL_66BS_B | 2027-06-10 07:30 | 2027-06-11 18:30 | Continuous | RS - Removal from Service | ISL-P-CB-748 | Lodged
ISL_CB_748 | 2027-06-10 07:30 | 2027-06-11 18:30 | Continuous | RS - Removal from Service | ISL-P-CB-748 | Lodged
ISL_CB_768 | 2027-06-10 07:30 | 2027-06-11 18:30 | Continuous | RS - Removal from Service | Affected Equipment of ISL_66BS_B ISL-P-CB-748 | Lodged
WRK_FDR_2022 | 2027-06-10 07:31 | 2027-06-10 18:31 | Daily | RS - Removal from Service | WRK-CBL-2022-FDR | Lodged
WRK_FDR_2042 | 2027-06-11 07:31 | 2027-06-11 18:31 | Daily | RS - Removal from Service | WRK-CBL-2042-FDR | Lodged
HAY_110BZ | 2027-06-13 08:00 | 2027-06-13 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3Q; Bay 160 - Transformer T10. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-06-13 08:00 | 2027-06-13 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3Q; Bay 160 - Transformer T10. | Lodged
HOR_FDR_52 | 2027-06-14 07:30 | 2027-06-14 18:30 | Daily | RS - Removal from Service | HOR-CB-52, HOR-P-CB-52 | Lodged
MNG_227_VT1 | 2027-06-14 07:30 | 2027-06-14 18:31 | Daily | RS - Removal from Service | MNG-M-VT1, MNG-VT-1 | Lodged
MNG_OTA_1 | 2027-06-14 07:30 | 2027-06-14 18:31 | Daily | RS - Removal from Service | Affected equipment MNG_227_VT1 & MNG_ROS_1 | Lodged
MNG_ROS_1 | 2027-06-14 07:30 | 2027-06-14 18:31 | Daily | RS - Removal from Service | MNG-ROS-A0034-10, MNG-ROS-A0037-10 | Lodged
BDE_GOR_1 | 2027-06-14 07:30 | 2027-06-21 18:30 | Continuous | RS - Removal from Service | GOR-INV-A0014-00, GOR-INV-A0019-00, GOR-INV-A0039-00, GOR-INV-A0062-10 | Lodged
GOR_557_607 | 2027-06-14 07:30 | 2027-06-21 18:30 | Continuous | RS - Removal from Service | GOR-DS-567, GOR-DS-574, GOR-DS-597, GOR-VT-VT597 | Lodged
GOR_T12 | 2027-06-14 07:30 | 2027-06-21 18:30 | Continuous | RS - Removal from Service | GOR-CB-712, GOR-CBL-T12-ET12, GOR-CT-CT592, GOR-CT-CT712, GOR-CT-NCT12, GOR-DCB-592, GOR-DS-716, GOR-NCTD-T12, GOR-P-CB-712, GOR-P-TF-T12, GOR-TF-ET12, GOR-TF-T12 | Lodged
GOR_T2 | 2027-06-14 07:30 | 2027-06-21 18:30 | Continuous | RS - Removal from Service | GOR-P-TF-T2, GOR-TF-T2 | Lodged
OPK_KPI_SFD_2 | 2027-06-14 07:31 | 2027-06-15 18:31 | Continuous | RS - Removal from Service | SFD-P-CB-102. OPK-SFD-A0097-00. Benchmarking [CP_VAR_1B7_0_00]. | Lodged
HAM_PAO_WHU_1 | 2027-06-14 07:31 | 2027-06-18 18:31 | Continuous | RS - Removal from Service | HAM-WHU-A0017A-00, HAM-WHU-A0024-10, HAM-WHU-A0025-10, HAM-WHU-A0027-10, HAM-WHU-A0028-10, HAM-WHU-A0029-10, HAM-WHU-A0030-10, HAM-WHU-A0031-10, HAM-WHU-A0033-10, HAM-WHU-A0036-10, HAM-WHU-A0037-10, HAM-WHU-A0039-10 | Lodged
PAO_CB_212 | 2027-06-14 07:31 | 2027-06-18 18:31 | Continuous | RS - Removal from Service | Affected equipment HAM_PAO_WHU_1 | Lodged
HAY_110BZ | 2027-06-14 08:00 | 2027-06-14 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3Q; Bay 160 - Transformer T10. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-06-14 08:00 | 2027-06-14 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 3Q; Bay 160 - Transformer T10. | Lodged
HEP_C_11 | 2027-06-15 07:30 | 2027-06-15 18:30 | Daily | RS - Removal from Service | HEP-CB-172 | Lodged
HKK_OTI_2 | 2027-06-15 07:30 | 2027-06-16 18:30 | Daily | RS - Removal from Service | AHA-OTI-A0051-00, AHA-OTI-A0096-00, AHA-OTI-A0097-00, AHA-OTI-A0098-00, AHA-OTI-A0099-00, AHA-OTI-A0198-00, AHA-OTI-A0199-00, AHA-OTI-A0200-00, AHA-OTI-A0201-00, AHA-OTI-A0202-00, AHA-OTI-A0203-00, AHA-OTI-A0204-00, AHA-OTI-A0205-00, AHA-OTI-A0206-00, AHA-OTI-A0207-00, AHA-OTI-A0208-00, AHA-OTI-A0209-00, OTI 66 kV CB Repl + Pole Refurb 25/26 | Lodged
HOR_KBY_ISL_2 | 2027-06-15 07:30 | 2027-06-18 18:30 | Continuous | RS - Removal from Service | HOR-ISL-EHORG23-10, ISL-CB-132 | Lodged
KBY_CB_4902 | 2027-06-15 07:30 | 2027-06-18 18:30 | Continuous | RS - Removal from Service | Affected equipment HOR_KBY_ISL_2 | Lodged
OPK_T4 | 2027-06-15 07:31 | 2027-06-16 18:31 | Continuous | RS - Removal from Service | OPK-P-TF-T4, OPK-TF-T4. OPK_T4 LV bushing replacement [CP_OPK_00L_0_00]. Benchmarking [CP_VAR_1B7_0_00]. | Lodged
BPE_220BZ | 2027-06-15 07:31 | 2027-06-15 18:31 | Daily | RS - Removal from Service | BPE-P-BZ-220 | Lodged
BPE_220CBF | 2027-06-15 07:31 | 2027-06-15 18:31 | Daily | RS - Removal from Service | Affected equipment of BPE_220BZ, for BPE-P-BZ-220 | Lodged
HAY_CB_2662 | 2027-06-16 07:30 | 2027-06-16 18:30 | Daily | RS - Removal from Service | HAY-CBL-CB2662-LS4 | Lodged
HEN_110BZ | 2027-06-16 07:30 | 2027-06-17 18:30 | Daily | RS - Removal from Service | HEN-P-BZ-110 | Lodged
HEN_110CBF | 2027-06-16 07:30 | 2027-06-17 18:30 | Daily | RS - Removal from Service | Affected equipment | Lodged
BPE_CB_918 | 2027-06-16 07:30 | 2027-06-16 18:30 | Daily | RS - Removal from Service | BPE-CB-918, BPE-CT-918, BPE-P-CB-918 | Lodged
GLN_220BS_B | 2027-06-17 07:30 | 2027-06-17 18:30 | Daily | RS - Removal from Service | Motor mech installation. GLN-BS-220-605-BUS-B, GLN-BS-220-615-BUS-B, GLN-BS-220-625-BUS-B, GLN-BS-220-635-BUS-B, GLN-BS-220-645-BUS-B, GLN-BS-220-B-CLEAN, GLN-DS-615, GLN-DS-635 | Lodged
GLN_CB_658 | 2027-06-17 07:30 | 2027-06-17 18:30 | Daily | RS - Removal from Service | Affected equipment GLN_220BS_B | Lodged
HAM_CB_118 | 2027-06-17 07:30 | 2027-06-17 18:30 | Daily | RS - Removal from Service | HAM-CB-118 | Lodged
OPK_SFD_1 | 2027-06-17 07:30 | 2027-06-18 18:30 | Continuous | RS - Removal from Service | Affected equipment of OPK_T5, for OPK-P-TF-T5, OPK-TF-T5 | Lodged
OPK_T5 | 2027-06-17 07:30 | 2027-06-18 18:30 | Continuous | RS - Removal from Service | OPK-P-TF-T5, OPK-TF-T5. OPK_T5 LV bushing replacement [CP_OPK_00L_0_00]. Benchmarking [CP_VAR_1B7_0_00]. | Lodged
WHI_R1 | 2027-06-17 07:30 | 2027-06-17 18:30 | Daily | RS - Removal from Service | WHI-CB-2862, WHI-CBL-1204-2862, WHI-P-CB-2862 | Lodged
HKK_KUM_1 | 2027-06-19 07:30 | 2027-06-19 18:30 | Daily | RS - Removal from Service | AHA-OTI-A0365-00, AHA-OTI-A0410-00 | Lodged
EDG_KAW_1 | 2027-06-21 06:30 | 2027-06-24 18:30 | Continuous | RS - Removal from Service | EDG-KAW-A0069-10, EDG-KAW-A0071-10, EDG-KAW-A0075-10, EDG-KAW-A0077-10, EDG-KAW-A0078-10, EDG-KAW-A0088-10 | Lodged
UHT_110BZ | 2027-06-21 07:30 | 2027-06-21 18:30 | Daily | RS - Removal from Service | UHT-P-BZ-110 [CP_UHT_36_00_00]. | Lodged
UHT_110CBF | 2027-06-21 07:30 | 2027-06-21 18:30 | Daily | RS - Removal from Service | Affected equipment of UHT_110BZ, for UHT-P-BZ-110 [CP_UHT_36_00_00]. | Lodged
WHI_FDR_12 | 2027-06-21 07:30 | 2027-06-21 18:30 | Daily | RS - Removal from Service | WHI-CB-12 | Lodged
KPU_WKO_2 | 2027-06-21 07:31 | 2027-06-24 18:30 | Continuous | RS - Removal from Service | Affected equipment WKO_504_514_547 & WHU_WKO_2 | Lodged
WHU_WKO_2 | 2027-06-21 07:31 | 2027-06-24 18:30 | Continuous | RS - Removal from Service | WHU-CT-102, WHU-DS-106, WHU-ES-109, WKO-CT-512, WKO-DS-516, WKO-ES-519 | Lodged
WKO_504_514_547 | 2027-06-21 07:31 | 2027-06-24 18:30 | Continuous | RS - Removal from Service | WKO-DS-504, WKO-DS-514, WKO-DS-524, WKO-DS-537, WKO-VT-2 | Lodged
WKO_T1 | 2027-06-21 07:31 | 2027-06-24 18:30 | Continuous | RS - Removal from Service | Affected equipment WKO_504_514_547 & WHU_WKO_2 | Lodged
DRY_GLN_2 | 2027-06-22 07:30 | 2027-06-22 18:30 | Daily | RS - Removal from Service | GLN-BS-220-DRY-GLN-2 | Lodged
HAY_CB_2612 | 2027-06-22 07:30 | 2027-06-22 18:30 | Daily | RS - Removal from Service | HAY-CBL-CB2612-ST9 | Lodged
WHI_FDR_13 | 2027-06-22 07:30 | 2027-06-22 18:30 | Daily | RS - Removal from Service | WHI-CB-13 | Lodged
EDN_INV_1 | 2027-06-22 07:31 | 2027-06-22 18:31 | Daily | RS - Removal from Service | GOR-INV-A0212-10, GOR-INV-A0217-10, GOR-INV-A0222-10, GOR-INV-A0223-10, GOR-INV-A0246-10, GOR-INV-A0250-10, GOR-INV-A0301-10, GOR-INV-A0324-10 | Lodged
INV_T1 | 2027-06-22 07:31 | 2027-06-22 18:31 | Daily | RS - Removal from Service | Affected equipment EDN_INV_1 | Lodged
BRB_CB_168 | 2027-06-23 07:30 | 2027-06-23 18:30 | Daily | RS - Removal from Service | BRB-CB-168 | Lodged
EDN_110BZ | 2027-06-23 07:30 | 2027-06-24 18:30 | Daily | RS - Removal from Service | EDN-P-BZ-110 | Lodged
EDN_110CBF | 2027-06-23 07:30 | 2027-06-24 18:30 | Daily | RS - Removal from Service | EDN-P-BZ-110 | Lodged
WHI_FDR_14 | 2027-06-23 07:30 | 2027-06-23 18:30 | Daily | RS - Removal from Service | WHI-CB-14 | Lodged
WHI_FDR_15 | 2027-06-24 07:30 | 2027-06-24 18:30 | Daily | RS - Removal from Service | WHI-P-CB-15 | Lodged
GYM_KUM_1 | 2027-06-25 07:30 | 2027-06-25 18:30 | Daily | RS - Removal from Service | Affected equipment DOB_GYM_1 | Lodged
HAY_F_7 | 2027-06-28 07:00 | 2027-07-03 18:00 | Continuous | RS - Removal from Service | HAY_110BZ Stage 4A; Bay 40 - Filter Bank 7. No other HAY work on days 1, 5, 6. No other work on associated equipment/lines on day 6 (commissioning). | Lodged
ARI_KIN_2 | 2027-06-28 07:30 | 2027-06-29 18:30 | Continuous | RS - Removal from Service | ARI-CT-202, ARI-DS-206, ARI-EDG-B0042-00, ARI-EDG-B0047-00, ARI-ES-209 | Lodged
MTM_110BZ | 2027-06-28 07:30 | 2027-06-30 18:31 | Continuous | RS - Removal from Service | MTM-P-BZ-110-A | Lodged
MTM_110CBF | 2027-06-28 07:30 | 2027-06-30 18:31 | Continuous | RS - Removal from Service | Affected equipment | Lodged
WHI_FDR_2822 | 2027-06-28 07:30 | 2027-06-28 18:30 | Daily | RS - Removal from Service | WHI-CB-2822, WHI-P-CB-2822 | Lodged
HAY_110BZ | 2027-06-28 08:00 | 2027-06-28 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 4A; Bay 40 - Filter Bank 7. No work in HAY 110kV yard. | Lodged
HAY_110CBF | 2027-06-28 08:00 | 2027-06-28 17:00 | Daily | RS - Removal from Service | HAY_110BZ Stage 4A; Bay 40 - Filter Bank 7. | Lodged
WHI_FDR_2832 | 2027-06-29 07:30 | 2027-06-29 18:30 | Daily | RS - Removal from Service | WHI-CB-2832, WHI-P-CB-2832 | Lodged

## hiddenSheet (hidden)
ions_outagewindow:Y2zQtNfn0A2mm2OJm/AXL9/ySSBL40mYk7POOlSdZVg+V8zgMNCnlHf5kmiT/98x4ERT+hnBK83wERyFaH4F8Q==:ions_outagewindowid=%28Do%20Not%20Modify%29%20Outage%20Window&checksumLogicalName=%28Do%20Not%20Modify%29%20Row%20Checksum&modifiedon=%28Do%20Not%20Modify%29%20Modified%20On&447d7bb4-a902-4620-b3d6-d5fe3578e4ed.ions_name=Request%20ID%20%28OVR%29%20%28Outage%20Variation%20Request%29&oms_windowplanninggroupid=Window%20Planning%20Group%20ID&ions_outageblockid=Outage%20Block&ions_plannedstartdatetime=Planned%20Start%20Date%2fTime&ions_plannedfinishdatetime=Planned%20Finish%20Date%2fTime&ions_timeframe=Time%20Frame&ions_recalltime=Recall%20Time&ions_nature=Nature&ions_crmdescription=Description%20of%20Work&statuscode=Status&oms_jobmanagerid=Job%20Manager&ownerid=Owner&f324fa4b-cb04-4d4e-9f84-9b21242484b8.oms_goszone=GOS%20Zone%20%28Outage%20Block%29%20%28Outage%20Block%29&f324fa4b-cb04-4d4e-9f84-9b21242484b8.oms_preferred=Preferred%20%28Outage%20Block%29%20%28Outage%20Block%29&f324fa4b-cb04-4d4e-9f84-9b21242484b8.oms_nonpreferred=Non%20Preferred%20%28Outage%20Block%29%20%28Outage%20Block%29&oms_acceptancestatus=Acceptance%20Status&oms_outageplannercomments=Works%20Outage%20Planner%20Comments&ions_name=Window%20ID&oms_windowownerid=Window%20Owner&ions_regionid=Region&modifiedon=Modified%20On&modifiedby=Modified%20By&447d7bb4-a902-4620-b3d6-d5fe3578e4ed.statuscode=Request%20Status%20%28OVR%29%20%28Outage%20Variation%20Request%29&oms_proposedfinishdatetime=Proposed%20Finish%20Date%2fTime&oms_proposedstartdatetime=Proposed%20Start%20Date%2fTime&oms_proposedtimeframe=Proposed%20Time%20Frame&createdon=Created%20On&ions_daysout=Days%20Out&oms_hasorwithcommissioningrequirements=Has%20OR%20with%20Commissioning%20Requirements&oms_leadtime=Lead%20Tme&oms_isplanned=Planned%3f&ions_primaryreasonsid=Primary%20Reasons&ions_secondaryreasonsid=Secondary%20Reasons&oms_outagevariationrequestids=Outage%20Variation%20Request%20IDs&ions_outagewindowid1=OVR
Daily | Continuous
RS - Removal from Service | CLO - Close | OPE - Open Ended | PSO - Power System Operating | OTH - Other Work Nature | RCB - Reclose Block | SCA - SCADA Interrupt Request | CIR - Comms Interrupt Request | RM - Revenue Metering | ROT - Risk of Trip | XEF - Earth Free
Lodged | Declined | Approved | Cancelled | Released | Done | Inactive
GZ1 | GZ2 | GZ3 | GZ4 | GZ5 | GZ6 | GZ7 | GZ8 | GZ9 | GZ10 | GZ11 | GZ12 | GZ13 | GZ14 | NA
AC - Accepted | NA - Not Accepted
Draft | Awaiting Approval | Approved | Declined | Cancelled | Not Required | Inactive | Closed
Daily | Continuous
No | Yes
No | Yes