## Forward Pipeline
Project ID | Parent Project ID | Customer | Project name | Region | Connection location (substation or circuit) | Max MW | Connection voltage | Technology | Transpower stage | Status Flag | Stage % complete | Status | Consented | Estimated connection livening date
00037566 | 0 | Todd Generation Limited | Te Rahui Solar Farm (Stage 1) | Hawkes Bay | WRK_WHI | 200 | 220 | Solar | Delivery | ● | 87% | Construction | Consent Granted | 30/10/2026 | ● Progressing normally
00038476 | 00037566 | Todd Generation Limited | Te Rahui Solar Farm (Stage 2) | Hawkes Bay | WRK_WHI | 200 | 220 | Solar | Delivery | ●C | 87% | Construction | Consent Granted |  | ●C Awaiting customer action
00037564 | 0 | Harmony Energy NZ #10 Limited | Waihou (Tauhei) 33kV Solar Farm | Waikato | Waihou | 100 | 33 | BESS | Delivery | ● | 85% | Construction | Application Submitted | 16/06/2026 | ●T Awaiting Transpower action
00037569 | 0 | Dannevirke Solar Farm Limited | Dannevirke Solar Farm (Esco Pacific) | Central North Island | Dannevirke | 25 | 11 | Solar | Delivery | ● | 85% | Construction | Consent Granted | 30/04/2026 | ● On hold
00037567 | 0 | Edgecumbe Solar Project LP (Genesis Energy) | Edgecumbe Solar Farm (Genesis Energy) | Bay of Plenty | Edgecumbe | 115 | 33 | Solar | Delivery | ●T | 60% | Detailed Design | Consent Granted | 31/08/2026
00037577 | 0 | MainPower New Zealand Limited | Mt Cass Wind Farm | Canterbury | Waipara | 93 | 66 | Wind - Onshore | Delivery | ● | 50% | Detailed Design | Consent Granted | 30/05/2027
00037579 | 0 | Rangiriri Solar Farm Limited | Rangiriri Solar Farm | Waikato | HLY_OTA | 214 | 220 | Solar | Delivery | ● | 44% | Detailed Design | Consent Granted | 31/07/2029
00037578 | 0 | Waerenga Solar Farm Limited | Waerenga Solar Farm | Waikato | OTA_WKM | 314 | 220 | Solar | Delivery | ● | 28% | Detailed Design | Consent Appeal Submitted | 31/10/2029
00037575 | 0 | Far North Solar Farm Limited | Greytown Solar Farm | Wellington | Greytown | 158 | 110 | Solar | Delivery | ● | 10% | Detailed Design | Consent Granted | 1/05/2028
00038453 | 00037575 | Far North Solar Farm Limited | Greytown Solar Farm | Wellington | Greytown | 158 | 110 | BESS | Delivery | ●C | 10% | Detailed Design | Application Expected | 1/05/2028
00037573 | 0 | Far North Solar Farm Limited | The Point Solar Farm | South-Canterbury | BEN_ISL-A | 300 | 220 | Solar | Delivery | ●C | 8% | Detailed Design | Application Submitted | 1/11/2027
00037574 | 0 | Contact Energy Limited | Te Mihi Stage II | Central North Island | Te Mihi | 190 | 220 | Geothermal | Delivery | ● | 8% | Detailed Design | Consent Granted | 30/09/2026
00037589 | 0 | Harmony Energy NZ #2 Limited | Masterton Solar Farm (Harmony) | Wellington | Masterton | 100 | 110 | Solar | Delivery | ● | 8% | Detailed Design | Consent Granted | 1/10/2027
00037590 | 00037589 | Harmony Energy NZ #2 Limited | Masterton Solar Farm (Harmony) (BESS) | Wellington | Masterton | 100 | 110 | BESS | Delivery | ● | 8% | Detailed Design | Consent Granted | 1/10/2027
00037571 | 0 | Masterton Solar and Energy Storage Limited (NZCE) | Masterton Solar Farm (NZCE) | Wellington | Masterton | 91 | 33 | Solar | Delivery | ● | 6% | Detailed Design | Consent Granted | 1/11/2027
00037572 | 00037571 | Masterton Solar and Energy Storage Limited (NZCE) | Masterton Solar Farm (NZCE) (BESS) | Wellington | Masterton | 91 | 33 | BESS | Delivery | ● | 6% | Detailed Design | Consent Granted | 1/11/2027
00037591 | 0 | Harmony Energy NZ #3 Limited | Marton Solar Farm (Harmony) | Central North Island | Marton | 50 | 110 | Solar | Delivery | ● | 2% | Detailed Design | Consent Granted | 31/10/2027
00037592 | 00037591 | Harmony Energy NZ #3 Limited | Marton Solar Farm (Harmony) (BESS) | Central North Island | Marton | 50 | 110 | BESS | Delivery | ● | 2% | Detailed Design | Consent Granted | 31/10/2027
00037603 | 0 | Helios Energy Limited | Waipawa Solar Farm (Helios) | Central North Island | Waipawa (North) | 100 | 110 | Solar | Delivery | ● | 1% | Detailed Design | Consent Granted | 1/05/2028
00037604 | 00037603 | Helios Energy Limited | Waipawa Solar Farm (Helios) (BESS) | Central North Island | Waipawa (North) | 100 | 110 | BESS | Delivery | ● | 1% | Detailed Design | Consent Granted | 1/05/2028
Project ID | Parent Project ID |  |  | Region | Connection location (substation or circuit) | Max MW | Connection voltage | Technology | Transpower stage | Status Flag | Stage % complete | Status | Consented | Estimated TP scope completion date
00037584 | 0 |  |  | Central North Island | Waipawa (South) | 100 | 110 | Solar | Investigation | ● | 97% | Investment Contract Negotiation | Consent Granted | TBA
00037585 | 00037584 |  |  | Central North Island | Waipawa (South) | 100 | 110 | BESS | Investigation | ● | 97% | Investment Contract Negotiation | Consent Granted | TBA
00037580 | 0 |  |  | Northland | HEN_MDN | 200 | 220 | Solar | Investigation | ● | 97% | Investment Contract Negotiation | Consent Granted | TBA
00037581 | 0 |  |  | Central North Island | BPE_LTN | 126 | 220 | Wind - Onshore | Investigation | ●C | 92% | Investment Contract Negotiation | Consent Granted | TBA
00037582 | 0 |  |  | South-Canterbury | Ohau A | 222 | 220 | Solar | Investigation | ● | 92% | Investment Contract Negotiation | Application Expected | TBA
00037601 | 0 |  |  | Central North Island | Tangiwai | 110 | 220 | Solar | Investigation | ● | 90% | Investment Contract Negotiation | Consent Granted | TBA
00037602 | 00037601 |  |  | Central North Island | Tangiwai | 110 | 220 | BESS | Investigation | ● | 90% | Investment Contract Negotiation | Consent Granted | TBA
00037643 | 0 |  |  | Otago-Southland | HWB_ROX | 190 | 110 | Wind - Onshore | Investigation | ● | 85% | Early Stage Design | Consent Granted | TBA
00037597 | 0 |  |  | Taranaki | Huirangi | 75 | 110 | Solar | Investigation | ● | 70% | Early Stage Design | Application Submitted | TBA
00037598 | 00037597 |  |  | Taranaki | Huirangi | 75 | 110 | BESS | Investigation | ● | 70% | Early Stage Design | Application Submitted | TBA
00037615 | 0 |  |  | Waikato | HLY_DEV | 300 | 220 | Solar | Investigation | ● | 63% | Early Stage Design | Application Expected | TBA
00037616 | 0 |  |  | Taranaki | Huirangi | 68 | 33 | BESS | Investigation | ● | 57% | Early Stage Design | Application Expected | TBA
00037583 | 0 |  |  | Central North Island | MGM_MST | 90 | 110 | Wind - Onshore | Investigation | ●C | 50% | Early Stage Design | Consent Granted | TBA
00037593 | 0 |  |  | Taranaki | Opunake | 77 | 110 | Solar | Investigation | ● | 50% | Early Stage Design | Consent Granted | TBA
00037594 | 00037593 |  |  | Taranaki | Opunake | 77 | 110 | BESS | Investigation | ● | 50% | Early Stage Design | Consent Granted | TBA
00037605 | 0 |  |  | Otago-Southland | Naseby | 300 | 220 | Solar | Investigation | ● | 42% | Early Stage Design | Consent Granted | TBA
00037606 | 00037605 |  |  | Otago-Southland | Naseby | 300 | 220 | BESS | Investigation | ● | 42% | Early Stage Design | Consent Granted | TBA
00037612 | 0 |  |  | South-Canterbury | CHH_TWZ | 300 | 220 | Solar | Investigation | ● | 41% | Early Stage Design | Application Expected | TBA
00037586 | 0 |  |  | Canterbury | HOR_ISL | 100 | 66 | Solar | Investigation | ● | 35% | Early Stage Design | Application Expected | TBA
00037587 | 00037586 |  |  | Canterbury | HOR_ISL | 100 | 66 | BESS | Investigation | ● | 35% | Early Stage Design | Application Expected | TBA
00037588 | 0 |  |  | Taranaki | Stratford | 32 | 33 | Solar | Investigation | ●C | 35% | Early Stage Design | Application Submitted | TBA
00037621 | 0 |  |  | South-Canterbury | Waitaki/ LIV_WTK | 130 | 220 | Wind - Onshore | Investigation | ● | 34% | Early Stage Design | Application Expected | TBA
00037595 | 0 |  |  | Central North Island | Bunnythorpe | 300 | 220 | Solar | Investigation | ● | 33% | Early Stage Design | Application Submitted | TBA
00037596 | 00037595 |  |  | Central North Island | Bunnythorpe | 300 | 220 | BESS | Investigation | ● | 33% | Early Stage Design | Application Submitted | TBA
00037617 | 0 |  |  | Waikato | Whakamaru (North) | 300 | 220 | BESS | Investigation | ● | 32% | Early Stage Design | Application Expected | TBA
00037614 | 0 |  |  | Central North Island | Marton | 29 | 33 | Solar | Investigation | ● | 30% | Early Stage Design | Application Expected | TBA
00038383 | 00037614 |  |  | Central North Island | Marton | 25 | 33 | Solar | Investigation | ● | 30% | Early Stage Design | Application Expected | TBA
00037610 | 0 |  |  | Nelson-Marlborough | Argyle | 80 | 110 | Solar | Investigation | ● | 30% | Early Stage Design | Application Expected | TBA
00037611 | 0 |  |  | South-Canterbury | Twizel | 350 | 220 | Solar | Investigation | ●C | 28% | Early Stage Design | Application Expected | TBA
00037622 | 0 |  |  | Central North Island | BPE_HAY | 180 | 220 | Solar | Investigation | ● | 28% | Early Stage Design | Application Submitted | TBA
00037620 | 0 |  |  | Canterbury | ISL_KIK | 200 | 220 | Solar | Investigation | ● | 22% | Early Stage Design | Application Submitted | TBA
00037637 | 0 |  |  | Canterbury | ROX_ISL_A | 450 | 220 | Solar | Investigation | ● | 22% | Early Stage Design | Application Expected | TBA
00037638 | 00037637 |  |  | Canterbury | ROX_ISL_A | 450 | 220 | BESS | Investigation | ● | 22% | Early Stage Design | Application Expected | TBA
00037613 | 0 |  |  | Central North Island | BPE_WRK_1, BPE_TNG_1 | 275 | 220 | Wind - Onshore | Investigation | ● | 22% | Early Stage Design | Application Submitted | TBA
00037691 | 0 |  |  | Central North Island | Bunnythorpe | 150 | 220 | Solar | Investigation | ● | 20% | Early Stage Design | Application Submitted | TBA
00037692 | 00037691 |  |  | Central North Island | Bunnythorpe | 100 | 220 | BESS | Investigation | ● | 20% | Early Stage Design | Consent Granted | TBA
00037609 | 0 |  |  | Waikato | WHU_WKO | 157 | 110 | Wind - Onshore | Investigation | ● | 20% | Early Stage Design | Application Submitted | TBA
00037607 | 0 |  |  | Central North Island | Dannevirke | 72 | 110 | Solar | Investigation | ● | 14% | Early Stage Design | Consent Granted | TBA
00037608 | 00037607 |  |  | Central North Island | Dannevirke | 72 | 110 | BESS | Investigation | ● | 14% | Early Stage Design | Consent Granted | TBA
00037635 | 0 |  |  | Otago-Southland | NMA_TMH_A | 380 | 220 | Wind - Onshore | Investigation | ● | 12% | Early Stage Design | Consent Appeal Submitted | TBA
00037618 | 0 |  |  | Otago-Southland | NMA-TMH-A | 330 | 220 | Wind - Onshore | Investigation | ● | 12% | Early Stage Design | Application Submitted | TBA
00037834 | 0 |  |  | Canterbury | Waipara | 14 | 33 | Other Generation | Investigation | ● | 10% | Early Stage Design | No Consent Required | TBA
00037640 | 0 |  |  | Waikato | Piako | 110 | 33 | Solar | Investigation | ● | 10% | Early Stage Design | Application Submitted | TBA
00037619 | 0 |  |  | Northland | HEN_MDN | 120 | 220 | Solar | Investigation | ● | 9% | Early Stage Design | Application Expected | TBA
00037625 | 0 |  |  | Central North Island | Waipawa (South) | 43 | 33 | Solar | Investigation | ● | 9% | Early Stage Design | Application Expected | TBA
00037599 | 0 |  |  | Waikato | Hinuera | 80 | 33 | Solar | Investigation | ● | 8% | Early Stage Design | Application Submitted | TBA
00037600 | 00037599 |  |  | Waikato | Hinuera | 80 | 33 | BESS | Investigation | ● | 8% | Early Stage Design | Application Submitted | TBA
00037632 | 0 |  |  | Taranaki | BRK_SFD | 450 | 220 | Wind - Onshore | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
00037631 | 00037632 |  |  | Taranaki | BRK-SFD | 300 | 220 | Solar | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
00038341 | 00037632 |  |  | Taranaki | BRK-SFD | 230 | 220 | Solar | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
00037641 | 0 |  |  | Central North Island | BPE_WKM | 500 | 220 | Solar | Investigation | ● | 8% | Early Stage Design | Application Submitted | TBA
00037628 | 0 |  |  | Central North Island | Tangiwai | 120 | 220 | Solar | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
00037629 | 00037628 |  |  | Central North Island | Tangiwai | 120 | 220 | BESS | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
00037645 | 0 |  |  | Central North Island | BPE_BRK | 220 | 220 | Solar | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
00037696 | 00037645 |  |  | Central North Island | BPE_BRK | 200 | 220 | BESS | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
00037624 | 0 |  |  | Central North Island | Mangamaire | 50 | 33 | Wind - Onshore | Investigation | ● | 4% | Early Stage Design | Consent Granted | TBA
00037650 | 00037624 |  |  | Central North Island | Mangamaire | 40 | 33 | Solar | Investigation | ● | 4% | Early Stage Design | Consent Granted | TBA
00038058 | 0 |  |  | Auckland | Glenbrook | 200 | 220 | BESS | Investigation | ● | 2% | Starting | Consent Granted | TBA
00037639 | 0 |  |  | Taranaki | Opunake | 86 | 33 | Solar | Investigation | ● | 2% | Starting | Consent Granted | TBA
00037651 | 0 |  |  | Bay of Plenty | EDG-TRK | 16.4 | 110 | Hydro | Investigation | ● | 2% | Starting | Application Expected | TBA
00037697 | 00037651 |  |  | Bay of Plenty | EDG-TRK | 40 | 110 | Geothermal | Investigation | ● | 2% | Starting | Application Expected | TBA
00037623 | 0 |  |  | Auckland | Glenbrook | 80 | 33 | Wind - Onshore | Investigation | ● | 1% | Starting | Application Expected | TBA
00037627 | 0 |  |  | Canterbury | Waipara | 120 | 66 | Solar | Investigation | ●C | 0% | Starting | Application Expected | TBA
00037633 | 0 |  |  | Northland | MDN_MPE / MSD_HPI | 120 | 110 | Wind - Onshore | Investigation | ● | 0% | Starting | Application Expected | TBA
00037642 | 0 |  |  | Waikato | HLY_TMN / HLY_SFD | 338 | 220 | Wind - Onshore | Investigation | ● | 0% | Starting | Application Expected | TBA
00037646 | 0 |  |  | South-Canterbury | BEN_ISL-A | 180 | 220 | Solar | Investigation | ● | 0% | Starting | Application Submitted | TBA
00037687 | 00037646 |  |  | South-Canterbury | BEN_ISL-A | 180 | 220 | BESS | Investigation | ● | 0% | Starting | Application Submitted | TBA
00037626 | 0 |  |  | Nelson-Marlborough | Kikiwa | 100 | 220 | Solar | Investigation | ●C | 0% | Starting | Application Expected | TBA
00037636 | 0 |  |  | Central North Island | Mangahao | 30 | 33 | Solar | Investigation | ● | 0% | Starting | Consent Granted | TBA
00037644 | 0 |  |  | Waikato | HLY_SFD, HLY_TWH | 400 | 220 | Wind - Onshore | Investigation | ●C | 0% | Starting | Application Submitted | TBA
00037690 | 00037644 |  |  | Waikato | HLY_SFD, HLY_TWH | 400 | 220 | BESS | Investigation | ●C | 0% | Starting | Application Submitted | TBA
00037630 | 0 |  |  | Waikato | Ohinewai | 300 | 220 | Wind - Onshore | Investigation | ● | 0% | Starting | Application Expected | TBA
Project ID | Parent Project ID |  |  | Region | Connection location (substation or circuit) | Max MW | Connection voltage | Technology | Transpower stage | Sequence number | Ready to proceed 7 | Status |  | Estimated date to progress to investigation
00037652 | 0 |  |  | Otago-Southland | NSY_ROX-1 | 220 | 220 | Solar | Application | 1 | Y | Confirmed | Application Expected | 2026-04-01
00037688 | 00037652 |  |  | Otago-Southland | NSY_ROX-1 | 220 | 220 | BESS | Application | 1 | Y | Confirmed | Application Expected
00037653 | 0 |  |  | Otago-Southland | ROX_ISL | 310 | 220 | Solar | Application | 2 | Y | Confirmed | Application Expected | 2026-05-01
00037685 | 00037653 |  |  | Otago-Southland | ROX_ISL | 310 | 220 | BESS | Application | 2 | Y | Confirmed | Application Expected
00037654 | 0 |  |  | South-Canterbury | ROX_TWZ | 400 | 220 | Solar | Application | 3 | Y | Confirmed | Application Expected | 2026-05-01
00037686 | 00037654 |  |  | South-Canterbury | ROX_TWZ | 400 | 220 | BESS | Application | 3 | Y | Confirmed | Application Expected
00037655 | 0 |  |  | Canterbury | ISL_KIK | 600 | 220 | Solar | Application | 4 |  | Confirmed | Application Expected | 2026-06-01
00037693 | 00037655 |  |  | Canterbury | ISL_KIK | 600 | 220 | BESS | Application | 4 |  | Confirmed | Application Expected
00037656 | 0 |  |  | Central North Island | BPE_TKU 1_2 | 400 | 220 | Wind - Onshore | Application | 5 | Y | Confirmed | Application Expected | 2026-06-01
00037657 | 0 |  |  | Central North Island | NAP-OKI-2 | 150 | 220 | Solar | Application | 6 | Y | Confirmed | Application Expected | 2026-06-01
00037684 | 00037657 |  |  | Central North Island | NAP-OKI-2 | 150 | 220 | BESS | Application | 6 | Y | Confirmed | Application Expected
00037658 | 0 |  |  | Auckland | Glenbrook | 280 | 33 | BESS | Application | 7 |  | Confirmed | Application Expected | 2027-07-01
00037659 | 0 |  |  | Otago-Southland | Edendale | 259 | 110 | Wind - Onshore | Application | 8 |  | Confirmed | Application Expected | 2026-07-01
00037660 | 0 |  |  | Canterbury | ISL_KIK | 200 | 220 | Solar | Application | 9 |  | Confirmed | Application Expected | 2026-08-01
00037694 | 00037660 |  |  | Canterbury | ISL_KIK | 200 | 220 | BESS | Application | 9 |  | Confirmed | Application Expected
00037662 | 0 |  |  | Canterbury | ISL_KIK | 310 | 220 | Solar | Application | 10 |  | Confirmed | Application Expected | 2026-08-01
00038056 | 00037662 |  |  | Canterbury | ISL_KIK | 310 | 220 | BESS | Application | 10 |  | Confirmed | Application Expected
00037689 | 0 |  |  | Taranaki | BRK-SFD-A | 200 | 220 | Wind - Onshore | Application | 11 |  | Confirmed | Application Expected | 2026-08-01
00038059 | 0 |  |  | Central North Island | WDW_BPE (220) / MST_MGM (110) | 300 | 220 | Wind - Onshore | Application | 12 | Y | Confirmed | Consent Granted | 2026-09-01
00037776 | 0 |  |  | Waikato | WKM_WRK | 120 | 220 | Geothermal | Application | 13 | Y | Confirmed | Application Expected | 2026-09-01
00038378 | 00037776 |  |  | Waikato | WKM_WRK | 80 | 220 | Solar | Application | 13 | Y | Confirmed | Application Expected
00037708 | 0 |  |  | Waikato | Whakamaru / Atiamuri | 350 | 220 | Wind - Onshore | Application | 14 |  | Confirmed | Application Expected | 2026-10-01
00038372 | 0 |  |  | Canterbury | ISL_KIK_A/B | 500 | 220 | Solar | Application | 15 | Y | Confirmed | Application Expected | 2026-10-01
00038377 | 00038372 |  |  | Canterbury | ISL_KIK_A/B | 200 | 220 | BESS | Application | 15 | Y | Confirmed | Application Expected
00037770 | 0 |  |  | Northland | Maungatapere | 150 | 110 | BESS | Application | 16 | Y | Confirmed | Application Expected | 2026-10-01
00037713 | 0 |  |  | Waikato | Hamilton | 200 | 110 | BESS | Application | 17 | Y | Confirmed | Application Expected | 2026-11-01
00038403 | 00037713 |  |  | Waikato | Hamilton | 200 | 110 | BESS | Application | 17 |  | Confirmed | Application Expected
00037647 | 0 |  |  | South-Canterbury | ISL-TKB-1, TKB | 250 | 220 | Solar | Application | 18 |  | Confirmed | Application Expected | 2025-11-01
00038322 | 0 |  |  | Otago-Southland | Gore Substation | 140 | 110 | Solar | Application | 19 |  | Accepted | Application Expected | 2026-12-01
00037835 | 0 |  |  | Bay of Plenty | Kaitemako-Tarukenga-1/2 | 454 | 220 | Wind - Onshore | Application | 20 |  | Received | Application Expected | 2027-02-01
00037649 | 0 |  |  | Central North Island | Linton | 230 | 220 | Wind - Onshore | Application | 21 |  | Confirmed | Application Submitted | 2027-02-01
00038504 | 0 |  |  | Canterbury | Waitaki GXP | 120 | 220 | Hydro | Application | 22 | Y | Received | No Consent Required | 2027-03-01
00037778 | 0 |  |  | Otago-Southland | INV-ROX-A / INV-ROX-B | 500 | 220 | Wind - Onshore | Application | 23 |  | Received | Application Expected | 2027-03-01
Notes
1. The location is given as the substation where a project will connect, or if a new substation is required, the transmission circuit.
2. This list includes generation projects requiring new or upgraded Transpower assets; generation projects connecting to an electricity distribution network and not requiring new or upgraded Transpower assets are not shown.
3. Sequence numbers (for investigations and applications) will be updated as and when projects move to a new stage or are withdrawn; or if a customer with two or more projects with consecutive sequence numbers prioritises a project with a higher number.
4. An Applications sequence number indicates the order in which Transpower will allocate internal resources to new connection investigations and the order in which Transpower will allocate physical assets (spare Transpower transmission assets and land) at the proposed point of connection. An accepted connection application does not guarantee access to transmission capacity beyond the point of connection and does not guarantee the project will proceed to commissioning. For investigations the sequence number indicates the order in which projects entered the investigation stage. Investigations can move into delivery when the investigation is complete, the sequence number will not apply to this transition.
5. Stage % Complete - Approximate progress of the project through the relevant stage based project milestones completed in the project schedule. Progress in delivery is progress for the Transpower connection only, not for the associated generation. Timeframes for delivery contracting will vary as they are dependent on bilateral negotiation and each customer's investment decision process. Progress is dependent on both Transpower work and customer decisions at key stage gates. Where customers are unable to make timely decisions progress may stall. Stalled projects may be put on hold so resources can be re-allocated to other waiting projects.
6. Where a developer for a project with a single connection, has multiple development stages, or multiple technologies, these are split into separate rows in this pipeline.
7. Applications are deemed ready to proceed to investigation where Transpower has had confirmation the applicant: is ready to sign the associated services agreement, has FID for the residual application fee and the investigation costs, maintains a need date which justifies an investigation in the near term, and plans for securing property rights and consenting remain on track. Developers are required to be 'ready to proceed' 3 months ahead of the 'estimated date to progress to investigation'
! - Max MW value includes existing generation of () MW as part of the new connection
*- Progressed based on no requirement for new Transpower capital assets for this connection, similar to the treatment of embedded generation connections with no requirement for new Transpower capital assets
# - Progressed as will contribute to short term system need in line with Security of Supply Assessment

## Completed
Generation commissioning
Customer | Generator name | Region | Connection location | Net new capacity MW | TP Connection voltage | Technology | Transpower / EDB | Transpower connection practical completion date | First sync date | Generation commissioning date | Comments
Todd Generation | JRD - Junction Road G71 | Taranaki | Junction Rd | 52 | 110 | Gas | Transpower | N/A | 2020-02-01 | 2020-05-15
Todd Generation | JRD - Junction Road G72 | Taranaki | Junction Rd | 52 | 110 | Gas | Transpower | N/A | 2020-02-01 | 2020-05-15
Mercury | WPP - Waipipi Wind Farm | Taranaki | Waverly | 130 | 110 | Wind | Transpower | 2020-04-05 | 2020-11-13 | 2021-03-31
Ngawha | NGB - Ngawha B (New) | Northland | Top Energy - Kaikohe | 32 | 110 | Geothermal | Top Energy | N/A | 2020-12-19 | 2021-01-27
Mercury | TUR - Turitea North | Central North Island | Linton | 118 | 220 | Wind | Transpower | 2020-10-19 | 2021-07-14 | 2021-12-20
Mercury | TUR - Turitea South (New) | Central North Island | Linton | 100 | 220 | Wind | Transpower | N/A | 2023-03-20 | 2023-06-15
Mercury | KWD - Kaiwera Downs (New) | Otago Southland | PowerNet - Gore | 41 | 33 | Solar | PowerNet | 2023-06-23 | 2023-08-21 | 2023-11-15
New Power | RHO - Rotohiko (Final New) | Waikato | WEL Networks - Huntly | 33 | 33 | BESS | WEL Networks | N/A | 2023-11-01 | 2023-12-11
Meridian | HRP - Harapaki Wind Farm | Hawkes Bay | Harapaki | 172.9 | 220 | Wind | Transpower | 2023-06-12 | 2023-11-13 | 2024-07-24
Lodestone Energy | KTS - Kaitaia Solar Farm | Northland | Top Energy - Kaikohe | 23.7 | 110 | Solar | Top Energy | N/A | 2023-11-17 | 2024-02-02
Lodestone Energy | RGT - Rangitaiki Solar Farm (New) | Bay of Plenty | Horizon - Edgecumbe | 23.7 | 33 | Solar | Horizon Networks | N/A | 2024-03-06 | 2024-04-17
Contact Energy | TAB - Tauhara Station | Central North Island | Tauhara | 184 | 220 | Geothermal | Transpower | 2023-10-25 | 2024-04-23 | 2024-05-15
Contact Energy | TAC - Te Huka 3 | Central North Island | Unison - Wairaki / Tauhara | 51.4 | 33 | Geothermal | Unison | N/A | 2024-10-01 | 2024-12-16
Genesis Energy | LAU - Lauriston Solar Farm | South Canterbury | Electricity Ashburton - Ashburton | 52 | 66 | Solar | Electricity Ashburton | N/A | 2024-11-11 | 2025-02-10
Northpower | RWI - Ruawai Solar Farm | Northland | Northpower - Mangaturoto | 14 | 33 | Solar | Northpower | N/A | 2024-12-09 | 2024-12-19
Manawa Energy | COL - Coleridge runback scheme | Canterbury | Coleridge | 0 | 66 | Hydro | Transpower | 2024-10-31 | N/A | N/A | SPS to deconstrain COL generation during certain outage scenarios
Lodestone Energy | HTR - Te Herenga O Te Ra Solar Farm | Bay of Plenty | Waiotahe | 22.8 | 33 | Solar | Transpower | 2024-11-21 | 2025-01-06 | 2025-07-25
Meridian Energy | RUK - Ruakākā BESS | Northland | Bream Bay | 100 | 33 | BESS | Transpower | 2024-12-09 | 2025-01-16 | 2025-05-31
Aquila | PSF - Pukenui Solar Farm | Northland | Top Energy - Kaikohe | 17.16 | 110 | Solar | Top Energy | N/A | 2025-05-22 | 2025-06-16
Eastland Generation | KAW - Te Ahi O Maui Upgrade | Bay of Plenty | Kawerau | 0 | 220 | Geothermal | Transpower | 2025-09-18 | 2025-09-22 | 2025-09-22 | New 220kV point of conenction
New Power | TOH - Taiohi Solar Farm | Waikato | WEL Networks - Huntly | 22.4 | 33 | Solar | WEL Networks | N/A | 2025-10-06 | 2025-12-12
Lodestone Energy | WTA - Whitianga Solar Farm | Waikato | Powerco - Kopu | 23.75 | 33 | Solar | Powerco | N/A | 2025-11-24 | 2025-12-17
Eastland Generation | KAW - TOPP 2 | Bay of Plenty | Kawerau | 55 | 220 | Geothermal | Transpower | 2025-09-18 | 2025-12-03 | 2025-12-23
Mercury | NTM - Ngā Tamariki OEC 5 | Central North Island | Nga Awa Purua | 56.87 | 220 | Geothermal | Transpower | N/A | 2026-01-16 | 2026-01-30
Rānui Generation | TRS - Twin Rivers Solar Farm (Stage 3) | Northland | Top Energy - Kaikohe | 24 | 110 | Solar | Top Energy | N/A | 2026-01-27 | 2026-02-11
Horizon Energy | EDS - Edgecumbe Solar Farm | Bay of Plenty | Horizon - Edgecumbe | 27 | 33 | Solar | Horizon Networks | 2025-03-01 | TBA | TBA
Project Waiotahe LP (Aquila) | Waiotahe Solar Farm | Bay of Plenty | Waiotahe | 33 | 33 | Solar | Transpower | 2025-04-15 | TBA | TBA
Harmony Energy | TAH - Tauhei Solar Farm | Waikato | Waihou | 150 | 110 | Solar | Transpower | 2025-06-17 | TBA | TBA
Genesis Energy Limited | Huntly BESS | Waikato | Huntly | 100 | 220 | BESS | Transpower | 2025-07-31 | TBA | TBA
Mercury | KPO - Karapiro runback scheme | Waikato | Karapiro | 16 | 110 | Hydro | Transpower | 2025-09-01 | N/A | N/A | SPS to deconstrain KPO generation following Karapiro re-commissioned 3 units between June 2023 - September 2025 (~15MW increase)
Top Energy | KOE-MPE 110kV Runback SPS | Northland | Top Energy - Kaikohe | 50 | 110 | Geothermal / Solar | Transpower | 2025-12-19 | N/A | N/A | SPS to deconstrain KOE_MPE circuits to allow additional generation export from Northland
New Power | Rangimarie Solar Farm | Waikato | Huntly | 9.9 | 33 | Solar | WEL Networks | N/A | 2026-02-17 | 2026-04-15
Tatuanui Solar Limited | Tatuanui Solar Farm | Waikato | Waihou | 9.9 | 33 | Solar | Powerco | N/A | 2026-02-27 | 2026-03-13
Lightyear Solar | Waimakariri Solar Farm | Canterbury | Southbrook | 5 | 66 | Solar | Orion New Zealand | N/A | 2026-02-27 | 2026-03-31
Contact Energy Limited | Glenbrook BESS I | Auckland | Glenbrook | 100 | 33 | BESS | Transpower | 2026-03-06 | 2026-03-10 | 2026-03-30
MainPower | Thongcaster Road Solar Farm | Canterbury | Southbrook | 7.3 | 66 | Solar | MainPower | N/A | 2026-03-09 | 2026-04-15
Mercury | KWE - Kaiwera Downs 2 | Otago Southland | Kaiwera | 152 | 220 | Wind | Transpower | 2025-03-31 | 2026-04-01 | TBA
Generation decommissioning
Customer | Generator name | Region | Connection location | Capacity change MW | Connection voltage | Technology | Transpower / EDB | Transpower dissconnection completion date | First de-sync date | Generation decommissioning date | Comments
Contact | TRC - Te Rapa | Waikato | Wel Networks - Hamilton | -42 | 33 | Gas | WEL Networks | N/A | 2023-06-01 | 2023-06-30
Contact | WRK - Wairakei G14 (New) | Central North Island | Wairakei | -4.2 | 220 | Geothermal | Transpower | N/A | 2024-08-15 | 2024-08-15