## To publish
Project ID | Parent Project ID | Customer | Project name | Region | Connection location (substation or circuit) | Max MW | Connection voltage | Technology | Transpower stage | Status Flag | Stage % complete | Status | Consented | Estimated connection livening date
00037576 | 0 | Genesis Energy Limited | Huntly BESS | Waikato | Huntly | 100 | 220 | BESS | Delivery | ● | 100% | TP work complete | Consent Granted | 1/04/2026 | Status flag key
00037564 | 0 | Harmony Energy NZ #10 Limited | Waihou (Tauhei) 33kV Solar Farm | Waikato | Waihou | 100 | 33 | BESS | Delivery | ● | 95% | Construction | Application Submitted | 1/07/2026 | ● Progressing normally
00037566 | 0 | Todd Generation Limited | Te Rahui Solar Farm (formerly Otamatea/Solar Surya) | Hawkes Bay | WRK_WHI | 400 | 220 | Solar | Delivery | ● | 85% | Construction | Consent Granted | 31/03/2026 | ●C Awaiting customer action
00037561 | 0 | Contact Energy Limited | Glenbrook BESS | Auckland | Glenbrook | 100 | 33 | BESS | Delivery | ● | 79% | Construction | Consent Granted | 31/10/2025 | ●T Awaiting Transpower action
00037565 | 0 | Horizon Energy Distribution Limited | Edgecumbe Embedded Solar (FNSF Omeheu) | Bay of Plenty | Edgecumbe | 29 | 33 | Solar | Delivery | ● | 73% | Construction | Consent Granted | 1/11/2025 | ● On hold
00037567 | 0 | Helios BOP Op LP (Genesis Energy) | Edgecumbe Solar Farm (Helios Genesis) | Bay of Plenty | Edgecumbe | 115 | 33 | Solar | Delivery | ●T | 63% | Detailed Design | Consent Granted | 30/06/2026
00037579 | 0 | Rangiriri Solar Farm Limited | Rangiriri Solar Farm | Waikato | OTA_WKM | 214 | 220 | Solar | Delivery | ●C | 54% | Detailed Design | Consent Granted | 31/07/2029
00037569 | 0 | Dannevirke Solar Farm Limited | Dannevirke Solar Farm (Esco Pacific) | Central North Island | Dannevirke | 25 | 11 | Solar | Delivery | ● | 50% | Detailed Design | Application Submitted | 31/03/2026
00037574 | 0 | Contact Energy Limited | Te Mihi Stage II | Central North Island | Te Mihi | 190!(132) | 220 | Geothermal | Delivery | ● | 50% | Detailed Design | Consent Granted | 1/09/2026
00037568 | 0 | Tararua Wind Power Limited | Kaiwera Downs Stage 2 | Otago-Southland | NMA_TMH_A | 155 | 220 | Wind - Onshore | Delivery | ● | 49% | Construction | Consent Granted | 31/03/2026
00037573 | 0 | Far North Solar Farm Limited | The Point Solar Farm | South-Canterbury | BEN_ISL-A | 300 | 220 | Solar | Delivery | ●C | 40% | Detailed Design | Application Submitted | 1/06/2027
00037571 | 0 | Masterton Solar and Energy Storage Limited (NZCE) | Masterton Solar Farm (NZCE) | Wellington | Masterton | 91 | 33 | Solar | Delivery | ● | 30% | Detailed Design | Consent Granted | 1/11/2027
00037572 | 00037571 | Masterton Solar and Energy Storage Limited (NZCE) | Masterton Solar Farm (NZCE) (BESS) | Wellington | Masterton | 91 | 33 | BESS | Delivery | ● | 30% | Detailed Design | Consent Granted | 1/11/2027
00037578 | 0 | Waikato Solar Farms Limited | Waerenga Solar Farm | Waikato | HLY_OTA | 314 | 220 | Solar | Delivery | ● | 28% | Detailed Design | Consent Appeal Submitted | 31/07/2028
00037648 | 0 | Top Energy Limited | KOE-MPE 110kV Runback SPS | Northland | Kaikohe | 50 # | 110 | Solar | Delivery | ● | 10% | Detailed Design | No Consent Required | 10/12/2025
00037575 | 0 | Far North Solar Farm Limited | Greytown Solar Farm | Wellington | Greytown | 158 | 110 | Solar | Delivery | ● | 8% | Detailed Design | Consent Granted | 1/05/2028
00037577 | 0 | MainPower New Zealand Limited | Mt Cass Wind Farm | Canterbury | Waipara | 93 | 66 | Wind - Onshore | Delivery | ● | 5% | Detailed Design | Consent Granted | 30/09/2027
00037589 | 0 | Harmony Energy NZ #2 Limited | Masterton Solar Farm (Harmony) | Wellington | Masterton | 100 | 110 | Solar | Delivery | ● | 3% | Detailed Design | Consent Granted | 1/10/2027
00037590 | 00037589 | Harmony Energy NZ #2 Limited | Masterton Solar Farm (Harmony) (BESS) | Wellington | Masterton | 100 | 110 | BESS | Delivery | ● | 3% | Detailed Design | Consent Granted | 1/10/2027
Project ID | Parent Project ID |  |  | Region | Connection location (substation or circuit) | Max MW | Connection voltage | Technology | Transpower stage | Status Flag | Stage % complete | Status | Consented | Estimated TP scope completion date
00037580 | 0 |  |  | Northland | HEN_MDN | 200 | 220 | Solar | Investigation | ● | 98% | Investment Contract Negotiation | Consent Appeal Submitted | TBA
00037591 | 0 |  |  | Central North Island | Marton | 50 | 110 | Solar | Investigation | ● | 98% | Investment Contract Negotiation | Consent Granted | TBA
00037592 | 00037591 |  |  | Central North Island | Marton | 50 | 110 | BESS | Investigation | ● | 98% | Investment Contract Negotiation | Consent Granted | TBA
00037581 | 0 |  |  | Central North Island | BPE_LTN | 126 | 220 | Wind - Onshore | Investigation | ●C | 95% | Investment Contract Negotiation | Consent Granted | TBA
00037603 | 0 |  |  | Central North Island | Waipawa (North) | 100 | 110 | Solar | Investigation | ● | 77% | Early Stage Design | Consent Granted | TBA
00037604 | 00037603 |  |  | Central North Island | Waipawa (North) | 100 | 110 | BESS | Investigation | ● | 77% | Early Stage Design | Consent Granted | TBA
00037584 | 0 |  |  | Central North Island | Waipawa (South) | 100 | 110 | Solar | Investigation | ●T | 75% | Early Stage Design | Consent Granted | TBA
00037585 | 00037584 |  |  | Central North Island | Waipawa (South) | 100 | 110 | BESS | Investigation | ●T | 75% | Early Stage Design | Consent Granted | TBA
00037601 | 0 |  |  | Central North Island | Tangiwai | 110 | 220 | Solar | Investigation | ● | 70% | Early Stage Design | Consent Granted | TBA
00037602 | 00037601 |  |  | Central North Island | Tangiwai | 110 | 220 | BESS | Investigation | ● | 70% | Early Stage Design | Consent Granted | TBA
00037582 | 0 |  |  | South-Canterbury | Ohau A | 222 | 220 | Solar | Investigation | ● | 55% | Early Stage Design | Application Expected | TBA
00037583 | 0 |  |  | Central North Island | MGM_MST | 90 | 110 | Wind - Onshore | Investigation | ●C | 50% | Early Stage Design | Consent Granted | TBA
00037593 | 0 |  |  | Taranaki | Opunake | 77 | 110 | Solar | Investigation | ● | 50% | Early Stage Design | Consent Granted | TBA
00037594 | 00037593 |  |  | Taranaki | Opunake | 77 | 110 | BESS | Investigation | ● | 50% | Early Stage Design | Consent Granted | TBA
00037698 | 00037648 |  |  | Northland | Kaikohe | 50 | 110 | Geothermal | Investigation | ● | 50% | Early Stage Design | Application Expected | TBA
00037586 | 0 |  |  | Canterbury | HOR_ISL | 100 | 66 | Solar | Investigation | ● | 35% | Early Stage Design | Application Expected | TBA
00037587 | 00037586 |  |  | Canterbury | HOR_ISL | 100 | 66 | BESS | Investigation | ● | 35% | Early Stage Design | Application Expected | TBA
00037588 | 0 |  |  | Taranaki | Stratford | 32 | 33 | Solar | Investigation | ●C | 35% | Early Stage Design | Application Submitted | TBA
00037597 | 0 |  |  | Taranaki | Huirangi | 75 | 110 | Solar | Investigation | ● | 35% | Early Stage Design | Application Submitted | TBA
00037598 | 00037597 |  |  | Taranaki | Huirangi | 75 | 110 | BESS | Investigation | ● | 35% | Early Stage Design | Application Submitted | TBA
00037595 | 0 |  |  | Central North Island | Bunnythorpe | 300 | 220 | Solar | Investigation | ● | 33% | Early Stage Design | Application Submitted | TBA
00037596 | 00037595 |  |  | Central North Island | Bunnythorpe | 300 | 220 | BESS | Investigation | ● | 33% | Early Stage Design | Application Submitted | TBA
00037610 | 0 |  |  | Nelson-Marlborough | Argyle | 80 | 110 | Solar | Investigation | ● | 28% | Early Stage Design | Application Expected | TBA
00037611 | 0 |  |  | South-Canterbury | Twizel | 350 | 220 | Solar | Investigation | ● | 28% | Early Stage Design | Application Expected | TBA
00037613 | 0 |  |  | Central North Island | BPE_WRK_1, BPE_TNG_1 | 275 | 220 | Wind - Onshore | Investigation | ● | 22% | Early Stage Design | Application Submitted | TBA
00037605 | 0 |  |  | Otago-Southland | Naseby | 300 | 220 | Solar | Investigation | ● | 20% | Early Stage Design | Consent Granted | TBA
00037606 | 00037605 |  |  | Otago-Southland | Naseby | 300 | 220 | BESS | Investigation | ● | 20% | Early Stage Design | Consent Granted | TBA
00037609 | 0 |  |  | Waikato | WHU_WKO | 157 | 110 | Wind - Onshore | Investigation | ● | 20% | Early Stage Design | Application Submitted | TBA
00037614 | 0 |  |  | Central North Island | Marton | 29 | 33 | Solar | Investigation | ● | 20% | Early Stage Design | Application Expected | TBA
00038383 | 00037614 |  |  | Central North Island | Marton | 25 | 33 | Solar | Investigation | ● | 20% | Early Stage Design | Application Expected | TBA
00037617 | 0 |  |  | Waikato | Whakamaru (North) | 300 | 220 | BESS | Investigation | ● | 18% | Early Stage Design | Application Expected | TBA
00037620 | 0 |  |  | Canterbury | ISL_KIK | 200 | 220 | Solar | Investigation | ● | 18% | Early Stage Design | Application Submitted | TBA
00037691 | 0 |  |  | Central North Island | Bunnythorpe | 525 | 220 | Solar | Investigation | ● | 18% | Early Stage Design | Application Submitted | TBA
00037692 | 00037691 |  |  | Central North Island | Bunnythorpe | 525 | 220 | BESS | Investigation | ● | 18% | Early Stage Design | Consent Granted | TBA
00037607 | 0 |  |  | Central North Island | Dannevirke | 72 | 110 | Solar | Investigation | ● | 14% | Early Stage Design | Application Expected | TBA
00037608 | 00037607 |  |  | Central North Island | Dannevirke | 72 | 110 | BESS | Investigation | ● | 14% | Early Stage Design | Application Expected | TBA
00037612 | 0 |  |  | South-Canterbury | CHH_TWZ | 300 | 220 | Solar | Investigation | ●C | 12% | Early Stage Design | Application Expected | TBA
00037618 | 0 |  |  | Otago-Southland | NMA_TMH_A | 330 | 220 | Wind - Onshore | Investigation | ● | 12% | Early Stage Design | Application Submitted | TBA
00037621 | 0 |  |  | South-Canterbury | Waitaki/ LIV_WTK | 130 | 220 | Wind - Onshore | Investigation | ● | 12% | Early Stage Design | Application Expected | TBA
00037619 | 0 |  |  | Northland | HEN_MDN | 120 | 220 | Solar | Investigation | ● | 10% | Early Stage Design | Application Expected | TBA
00037643 | 0 |  |  | Otago-Southland | HWB_ROX | 190 | 110 | Wind - Onshore | Investigation | ● | 10% | Early Stage Design | Consent Granted | TBA
00037599 | 0 |  |  | Waikato | Hinuera | 80 | 33 | Solar | Investigation | ● | 8% | Early Stage Design | Application Submitted | TBA
00037600 | 00037599 |  |  | Waikato | Hinuera | 80 | 33 | BESS | Investigation | ● | 8% | Early Stage Design | Application Submitted | TBA
00037615 | 0 |  |  | Waikato | HLY_DEV | 300 | 220 | Solar | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
00037616 | 0 |  |  | Taranaki | Huirangi | 68 | 33 | BESS | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
00037622 | 0 |  |  | Central North Island | BPE_HAY | 180 | 220 | Solar | Investigation | ● | 8% | Early Stage Design | Application Submitted | TBA
00037623 | 0 |  |  | Auckland | Glenbrook | 80 | 33 | Wind - Onshore | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
00037624 | 0 |  |  | Central North Island | Mangamaire | 50 | 33 | Wind - Onshore | Investigation | ● | 8% | Early Stage Design | Consent Granted | TBA
00037650 | 00037624 |  |  | Central North Island | Mangamaire | 40 | 33 | Solar | Investigation | ● | 8% | Early Stage Design | Consent Granted | TBA
00037625 | 0 |  |  | Central North Island | Waipawa (South) | 43 | 33 | Solar | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
00037626 | 0 |  |  | Nelson-Marlborough | Kikiwa | 100 | 220 | Solar | Investigation | ●C | 8% | Early Stage Design | Application Expected | TBA
00037632 | 0 |  |  | Taranaki | BRK_SFD | 320 | 220 | Wind - Onshore | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
00037631 | 00037632 |  |  | Taranaki | BRK-SFD | 200 | 220 | Solar | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
00038341 | 00037632 |  |  | Taranaki | BRK-SFD | 230 | 220 | Solar | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
00037640 | 0 |  |  | Waikato | Piako | 110 | 33 | Solar | Investigation | ● | 8% | Early Stage Design | Application Submitted | TBA
00037628 | 0 |  |  | Central North Island | Tangiwai | 120 | 220 | Solar | Investigation | ● | 5% | Early Stage Design | Application Expected | TBA
00037629 | 00037628 |  |  | Central North Island | Tangiwai | 120 | 220 | BESS | Investigation | ● | 5% | Early Stage Design | Application Expected | TBA
00037641 | 0 |  |  | Central North Island | BPE_WKM | 500 | 220 | Solar | Investigation | ● | 5% | Starting | Application Submitted | TBA
00037644 | 0 |  |  | Waikato | HLY_SFD, HLY_TWH | 400 | 220 | Wind - Onshore | Investigation | ● | 5% | Starting | Application Submitted | TBA
00037690 | 00037644 |  |  | Waikato | HLY_SFD, HLY_TWH | 400 | 220 | BESS | Investigation | ● | 5% | Starting | Application Submitted | TBA
00037630 | 0 |  |  | Waikato | Ohinewai | 300 | 220 | Wind - Onshore | Investigation | ● | 3% | Starting | Application Expected | TBA
00037639 | 0 |  |  | Taranaki | Opunake | 86 | 33 | Solar | Investigation | ● | 3% | Starting | Consent Granted | TBA
00037627 | 0 |  |  | Canterbury | Waipara | 120 | 66 | Solar | Investigation | ●C | 3% | Starting | Application Expected | TBA
00037635 | 0 |  |  | Otago-Southland | NMA_TMH_A | 300 | 220 | Wind - Onshore | Investigation | ● | 2% | Early Stage Design | Consent Appeal Submitted | TBA
00037633 | 0 |  |  | Northland | MDN_MPE / MSD_HPI | 120 | 110 | Wind - Onshore | Investigation | ● | 0% | Starting | Application Expected | TBA
00037636 | 0 |  |  | Central North Island | Mangahao | 30 | 33 | Solar | Investigation | ● | 0% | Starting | Consent Granted | TBA
00037637 | 0 |  |  | Canterbury | ROX_ISL_A | 450 | 220 | Solar | Investigation | ● | 0% | Starting | Application Expected | TBA
00037638 | 00037637 |  |  | Canterbury | ROX_ISL_A | 450 | 220 | BESS | Investigation | ● | 0% | Starting | Application Expected | TBA
00037642 | 0 |  |  | Waikato | HLY_TMN / HLY_SFD | 338 | 220 | Wind - Onshore | Investigation | ● | 0% | Starting | Application Expected | TBA
Project ID | Parent Project ID |  |  | Region | Connection location (substation or circuit) | Max MW | Connection voltage | Technology | Transpower stage | Sequence number |  | Status |  | Estimated date to progress to investigation
00037645 | 0 |  |  | Central North Island | BPE_BRK | 200 | 220 | Solar | Application | 1 |  | Confirmed | Application Expected | 2026-01-01
00037696 | 00037645 |  |  | Central North Island | BPE_BRK | 200 | 220 | BESS | Application | 1 |  | Confirmed | Application Expected | 2026-01-01
00037646 | 0 |  |  | South-Canterbury | BEN_ISL-A | 180 | 220 | Solar | Application | 2 |  | Confirmed | Application Submitted | 2026-01-01
00037687 | 00037646 |  |  | South-Canterbury | BEN_ISL-A | 180 | 220 | BESS | Application | 2 |  | Confirmed | Application Submitted | 2026-01-01
00037647 | 0 |  |  | South-Canterbury | ISL-TKB-1, TKB | 250 | 220 | Solar | Application | 3 |  | Confirmed | Application Expected | 2026-02-01
00037651 | 0 |  |  | Bay of Plenty | EDG-TRK | 16.4 | 110 | Hydro | Application | 4 |  | Confirmed | Application Expected | 2026-02-01
00037697 | 00037651 |  |  | Bay of Plenty | EDG-TRK | 40 | 110 | Geothermal | Application | 4 |  | Confirmed | Application Expected | 2026-02-01
00037649 | 0 |  |  | Central North Island | Linton | 230 | 220 | Wind - Onshore | Application | 5 |  | Confirmed | Application Submitted | 2026-02-01
00037652 | 0 |  |  | Otago-Southland | NSY_ROX-1 | 220 | 220 | Solar | Application | 6 |  | Confirmed | Application Expected | 2026-03-01
00037688 | 00037652 |  |  | Otago-Southland | NSY_ROX-1 | 220 | 220 | BESS | Application | 6 |  | Confirmed | Application Expected | 2026-03-01
00037653 | 0 |  |  | Otago-Southland | ROX_ISL | 310 | 220 | Solar | Application | 7 |  | Confirmed | Application Expected | 2026-03-01
00037685 | 00037653 |  |  | Otago-Southland | ROX_ISL | 310 | 220 | BESS | Application | 7 |  | Confirmed | Application Expected | 2026-03-01
00037654 | 0 |  |  | South-Canterbury | ROX_TWZ | 400 | 220 | Solar | Application | 8 |  | Confirmed | Application Expected | 2026-04-01
00037686 | 00037654 |  |  | South-Canterbury | ROX_TWZ | 400 | 220 | BESS | Application | 8 |  | Confirmed | Application Expected | 2026-04-01
00037655 | 0 |  |  | Canterbury | ISL_KIK | 600 | 220 | Solar | Application | 9 |  | Confirmed | Application Expected | 2026-04-01
00037693 | 00037655 |  |  | Canterbury | ISL_KIK | 600 | 220 | BESS | Application | 9 |  | Confirmed | Application Expected | 2026-04-01
00037656 | 0 |  |  | Central North Island | BPE_TKU 1_2 | 400 | 220 | Wind - Onshore | Application | 10 |  | Confirmed | Application Expected | 2026-04-01
00037657 | 0 |  |  | Central North Island | NAP-OKI-2 | 150 | 220 | Solar | Application | 11 |  | Confirmed | Application Expected | 2026-05-01
00037684 | 00037657 |  |  | Central North Island | NAP-OKI-2 | 150 | 220 | BESS | Application | 11 |  | Confirmed | Application Expected | 2026-05-01
00037658 | 0 |  |  | Auckland | Glenbrook | 280 | 33 | BESS | Application | 12 |  | Confirmed | Application Expected | 2026-05-01
00037659 | 0 |  |  | Otago-Southland | Edendale | 259 | 110 | Wind - Onshore | Application | 13 |  | Confirmed | Application Expected | 2026-06-01
00037660 | 0 |  |  | Canterbury | ISL_KIK | 200 | 220 | Solar | Application | 14 |  | Confirmed | Application Expected | 2026-06-01
00037694 | 00037660 |  |  | Canterbury | ISL_KIK | 200 | 220 | BESS | Application | 14 |  | Confirmed | Application Expected | 2026-06-01
00037661 | 0 |  |  | Auckland | Glenbrook | 150 | 220 | BESS | Application | 15 |  | Confirmed | Application Expected | 2026-06-01
00037662 | 0 |  |  | Canterbury | ISL_KIK | 310 | 220 | Solar | Application | 16 |  | Confirmed | Application Expected | 2026-07-01
00038056 | 00037662 |  |  | Canterbury | ISL_KIK | 310 | 220 | BESS | Application | 16 |  | Confirmed | Application Expected | 2026-07-01
00037689 | 0 |  |  | Taranaki | BRK-SFD-A | 200 | 220 | Wind - Onshore | Application | 17 |  | Confirmed | Application Expected | 2026-07-01
00038058 | 0 |  |  | Auckland | Glenbrook | 50 | 33 | BESS | Application | 18 |  | Confirmed | Application Expected | 2026-08-01
00038059 | 0 |  |  | Central North Island | WDW_BPE (220) / MST_MGM (110) | 300 | 220 | Wind - Onshore | Application | 19 |  | Confirmed | Consent Granted | 2026-08-01
00037834 | 0 |  |  | Canterbury | Waipara | 4 | 66 | Other Generation | Application | 20 |  | Confirmed | No Consent Required | 2026-08-01
00037776 | 0 |  |  | Waikato | WKM_WRK | !120(120) | 220 | Geothermal | Application | 21 |  | Confirmed | Application Expected | 2026-09-01
00038378 | 00037776 |  |  | Waikato | WKM_WRK | 80 | 220 | Solar | Application | 21 |  | Confirmed | Application Expected | 2026-09-01
00037708 | 0 |  |  | Waikato | Whakamaru / Atiamuri | 350 | 220 | Wind - Onshore | Application | 22 |  | Confirmed | Application Expected | 2026-09-01
00038372 | 0 |  |  | Canterbury | ISL_KIK_A/B | 200 | 220 | Solar | Application | 23 |  | Confirmed | Application Expected | 2026-10-01
00038377 | 00038372 |  |  | Canterbury | ISL_KIK_A/B | 200 | 220 | BESS | Application | 23 |  | Confirmed | Application Expected | 2026-10-01
00037770 | 0 |  |  | Northland | Maungatapere | 150 | 110 | BESS | Application | 24 |  | Received | Application Expected | 2026-10-01
00037713 | 0 |  |  | Auckland | Hamilton | 200 | 110 | BESS | Application | 25 |  | Received | Application Expected | 2026-10-01
00038403 | 00037713 |  |  | Auckland | HAM-MER | 200 | 110 | BESS | Application | 25 |  | Received | Application Expected | 2026-10-01
Notes
1. The location is given as the substation where a project will connect, or if a new substation is required, the transmission circuit.
2. This list includes generation projects requiring new or upgraded Transpower assets; generation projects connecting to an electricity distribution network and not requiring new or upgraded Transpower assets are not shown.
3. Sequence numbers (for investigations and applications) will be updated as and when projects move to a new stage or are withdrawn; or if a customer with two or more projects with consecutive sequence numbers prioritises a project with a higher number.
4. An Applications sequence number indicates the order in which Transpower will allocate internal resources to new connection investigations and the order in which Transpower will allocate physical assets (spare Transpower transmission assets and land) at the proposed point of connection. An accepted connection application does not guarantee access to transmission capacity beyond the point of connection and does not guarantee the project will proceed to commissioning. For investigations the sequence number indicates the order in which projects entered the investigation stage. Investigations can move into delivery when the investigation is complete, the sequence number will not apply to this transition.
5. Stage % Complete - Approximate progress of the project through the relevant stage based project milestones completed in the project schedule. Progress in delivery is progress for the Transpower connection only, not for the associated generation. Timeframes for delivery contracting will vary as they are dependent on bilateral negotiation and each customer's investment decision process. Progress is dependent on both Transpower work and customer decisions at key stage gates. Where customers are unable to make timely decisions progress may stall. Stalled projects may be put on hold so resources can be re-allocated to other waiting projects.
6. Where a developer for a project with a single connection, has multiple development stages, or multiple technologies, these are split into separate rows in this pipeline.
! - Max MW value includes existing generation of () MW as part of the new connection
* - Progressed based on no requirement for new Transpower capital assets for this connection, similar to the treatment of embedded generation connections with no requirement for new Transpower capital assets
# - Progressed as will contribute to short term system need in line with Security of Supply Assessment