## Forward Pipeline
Project ID | Parent Project ID | Customer | Project name | Region | Connection location (substation or circuit) | Max MW | Connection voltage | Technology | Transpower stage | Status Flag | Stage % complete | Status | Consented | Estimated connection livening date
37576 | 0 | Genesis Energy Limited | Huntly BESS | Waikato | Huntly | 100 | 220 | BESS | Delivery | ● | 100% | Transpower scope complete | Consent Granted | 2026-04-01 | Status flag key
37566 | 0 | Todd Generation Limited | Te Rahui Solar Farm (Stage 1) | Hawkes Bay | WRK_WHI | 200 | 220 | Solar | Delivery | ● | 85% | Construction | Consent Granted | 2026-10-30 | ● Progressing normally
38476 | 37566 | Todd Generation Limited | Te Rahui Solar Farm (Stage 2) | Hawkes Bay | WRK_WHI | 200 | 220 | Solar | Delivery | ●C | 85% | Construction | Consent Granted | 2026-10-30 | ●C Awaiting customer action
37564 | 0 | Harmony Energy NZ #10 Limited | Waihou (Tauhei) 33kV Solar Farm | Waikato | Waihou | 100 | 33 | BESS | Delivery | ● | 80% | Construction | Application Submitted | 2026-06-16 | ●T Awaiting Transpower action
37569 | 0 | Dannevirke Solar Farm Limited | Dannevirke Solar Farm (Esco Pacific) | Central North Island | Dannevirke | 25 | 11 | Solar | Delivery | ● | 65% | Construction | Consent Granted | 2026-03-31 | ● On hold
37565 | 0 | Horizon Energy Distribution Limited | Edgecumbe Embedded Solar (Aquila Omeheu) | Bay of Plenty | Edgecumbe | 29 | 33 | Solar | Delivery | ● | 60% | Construction | Consent Granted | 2026-06-30
37567 | 0 | Edgecumbe Solar Project LP (Genesis Energy) | Edgecumbe Solar Farm (Genesis Energy) | Bay of Plenty | Edgecumbe | 115 | 33 | Solar | Delivery | ●T | 60% | Detailed Design | Consent Granted | 2026-08-31
37568 | 0 | Tararua Wind Power Limited | Kaiwera Downs Stage 2 | Otago-Southland | NMA_TMH_A | 155 | 220 | Wind - Onshore | Delivery | ● | 60% | Construction | Consent Granted | 2026-03-31
37577 | 0 | MainPower New Zealand Limited | Mt Cass Wind Farm | Canterbury | Waipara | 93 | 66 | Wind - Onshore | Delivery | ● | 48% | Detailed Design | Consent Granted | 2027-05-30
37579 | 0 | Rangiriri Solar Farm Limited | Rangiriri Solar Farm | Waikato | OTA_WKM | 214 | 220 | Solar | Delivery | ● | 44% | Detailed Design | Consent Granted | 2029-07-31
37578 | 0 | Waerenga Solar Farm Limited | Waerenga Solar Farm | Waikato | HLY_OTA | 314 | 220 | Solar | Delivery | ● | 28% | Detailed Design | Consent Appeal Submitted | 2029-10-31
37575 | 0 | Far North Solar Farm Limited | Greytown Solar Farm | Wellington | Greytown | 158 | 110 | Solar | Delivery | ● | 10% | Detailed Design | Consent Granted | 2028-05-01
38453 | 37575 | Far North Solar Farm Limited | Greytown Solar Farm | Wellington | Greytown | 158 | 110 | BESS | Delivery | ●C | 10% | Detailed Design | Application Expected | 2028-05-01
37589 | 0 | Harmony Energy NZ #2 Limited | Masterton Solar Farm (Harmony) | Wellington | Masterton | 100 | 110 | Solar | Delivery | ● | 10% | Detailed Design | Consent Granted | 2027-10-01
37590 | 37589 | Harmony Energy NZ #2 Limited | Masterton Solar Farm (Harmony) (BESS) | Wellington | Masterton | 100 | 110 | BESS | Delivery | ● | 10% | Detailed Design | Consent Granted | 2027-10-01
37573 | 0 | Far North Solar Farm Limited | The Point Solar Farm | South-Canterbury | BEN_ISL-A | 300 | 220 | Solar | Delivery | ●C | 8% | Detailed Design | Application Submitted | 2027-11-01
37571 | 0 | Masterton Solar and Energy Storage Limited (NZCE) | Masterton Solar Farm (NZCE) | Wellington | Masterton | 91 | 33 | Solar | Delivery | ● | 6% | Detailed Design | Consent Granted | 2027-11-01
37572 | 37571 | Masterton Solar and Energy Storage Limited (NZCE) | Masterton Solar Farm (NZCE) (BESS) | Wellington | Masterton | 91 | 33 | BESS | Delivery | ● | 6% | Detailed Design | Consent Granted | 2027-11-01
37574 | 0 | Contact Energy Limited | Te Mihi Stage II | Central North Island | Te Mihi | 190!(132) | 220 | Geothermal | Delivery | ● | 2% | Detailed Design | Consent Granted | 2026-09-30
37591 | 0 | Harmony Energy NZ #3 Limited | Marton Solar Farm (Harmony) | Central North Island | Marton | 50 | 110 | Solar | Delivery | ● | 1% | Detailed Design | Consent Granted | 2027-10-31
37592 | 37591 | Harmony Energy NZ #3 Limited | Marton Solar Farm (Harmony) (BESS) | Central North Island | Marton | 50 | 110 | BESS | Delivery | ● | 1% | Detailed Design | Consent Granted | 2027-10-31
37603 | 0 | Helios Energy Limited | Waipawa Solar Farm (Helios) | Central North Island | Waipawa (North) | 100 | 110 | Solar | Delivery | ● | 0% | Detailed Design | Consent Granted | 2028-05-01
37604 | 37603 | Helios Energy Limited | Waipawa Solar Farm (Helios) (BESS) | Central North Island | Waipawa (North) | 100 | 110 | BESS | Delivery | ● | 0% | Detailed Design | Consent Granted | 2028-05-01
Project ID | Parent Project ID |  |  | Region | Connection location (substation or circuit) | Max MW | Connection voltage | Technology | Transpower stage | Status Flag | Stage % complete | Status | Consented | Estimated TP scope completion date
37584 | 0 |  |  | Central North Island | Waipawa (South) | 100 | 110 | Solar | Investigation | ● | 97% | Investment Contract Negotiation | Consent Granted | TBA
37585 | 37584 |  |  | Central North Island | Waipawa (South) | 100 | 110 | BESS | Investigation | ● | 97% | Investment Contract Negotiation | Consent Granted | TBA
37580 | 0 |  |  | Northland | HEN_MDN | 200 | 220 | Solar | Investigation | ● | 95% | Investment Contract Negotiation | Consent Granted | TBA
37581 | 0 |  |  | Central North Island | BPE_LTN | 126 | 220 | Wind - Onshore | Investigation | ●C | 94% | Investment Contract Negotiation | Consent Granted | TBA
37643 | 0 |  |  | Otago-Southland | HWB_ROX | 190 | 110 | Wind - Onshore | Investigation | ● | 85% | Early Stage Design | Consent Granted | TBA
37601 | 0 |  |  | Central North Island | Tangiwai | 110 | 220 | Solar | Investigation | ● | 77% | Early Stage Design | Consent Granted | TBA
37602 | 37601 |  |  | Central North Island | Tangiwai | 110 | 220 | BESS | Investigation | ● | 77% | Early Stage Design | Consent Granted | TBA
37582 | 0 |  |  | South-Canterbury | Ohau A | 222 | 220 | Solar | Investigation | ● | 77% | Early Stage Design | Application Expected | TBA
37615 | 0 |  |  | Waikato | HLY_DEV | 300 | 220 | Solar | Investigation | ● | 63% | Early Stage Design | Application Expected | TBA
37616 | 0 |  |  | Taranaki | Huirangi | 68 | 33 | BESS | Investigation | ● | 57% | Early Stage Design | Application Expected | TBA
37583 | 0 |  |  | Central North Island | MGM_MST | 90 | 110 | Wind - Onshore | Investigation | ●C | 50% | Early Stage Design | Consent Granted | TBA
37593 | 0 |  |  | Taranaki | Opunake | 77 | 110 | Solar | Investigation | ● | 50% | Early Stage Design | Consent Granted | TBA
37594 | 37593 |  |  | Taranaki | Opunake | 77 | 110 | BESS | Investigation | ● | 50% | Early Stage Design | Consent Granted | TBA
37605 | 0 |  |  | Otago-Southland | Naseby | 300 | 220 | Solar | Investigation | ● | 42% | Early Stage Design | Consent Granted | TBA
37606 | 37605 |  |  | Otago-Southland | Naseby | 300 | 220 | BESS | Investigation | ● | 42% | Early Stage Design | Consent Granted | TBA
37612 | 0 |  |  | South-Canterbury | CHH_TWZ | 300 | 220 | Solar | Investigation | ● | 41% | Early Stage Design | Application Expected | TBA
37586 | 0 |  |  | Canterbury | HOR_ISL | 100 | 66 | Solar | Investigation | ● | 35% | Early Stage Design | Application Expected | TBA
37587 | 37586 |  |  | Canterbury | HOR_ISL | 100 | 66 | BESS | Investigation | ● | 35% | Early Stage Design | Application Expected | TBA
37597 | 0 |  |  | Taranaki | Huirangi | 75 | 110 | Solar | Investigation | ● | 35% | Early Stage Design | Application Submitted | TBA
37598 | 37597 |  |  | Taranaki | Huirangi | 75 | 110 | BESS | Investigation | ● | 35% | Early Stage Design | Application Submitted | TBA
37588 | 0 |  |  | Taranaki | Stratford | 32 | 33 | Solar | Investigation | ●C | 35% | Early Stage Design | Application Submitted | TBA
37621 | 0 |  |  | South-Canterbury | Waitaki/ LIV_WTK | 130 | 220 | Wind - Onshore | Investigation | ● | 34% | Early Stage Design | Application Expected | TBA
37595 | 0 |  |  | Central North Island | Bunnythorpe | 300 | 220 | Solar | Investigation | ● | 33% | Early Stage Design | Application Submitted | TBA
37596 | 37595 |  |  | Central North Island | Bunnythorpe | 300 | 220 | BESS | Investigation | ● | 33% | Early Stage Design | Application Submitted | TBA
37617 | 0 |  |  | Waikato | Whakamaru (North) | 300 | 220 | BESS | Investigation | ● | 32% | Early Stage Design | Application Expected | TBA
37610 | 0 |  |  | Nelson-Marlborough | Argyle | 80 | 110 | Solar | Investigation | ● | 30% | Early Stage Design | Application Expected | TBA
37611 | 0 |  |  | South-Canterbury | Twizel | 350 | 220 | Solar | Investigation | ● | 28% | Early Stage Design | Application Expected | TBA
37622 | 0 |  |  | Central North Island | BPE_HAY | 180 | 220 | Solar | Investigation | ● | 28% | Early Stage Design | Application Submitted | TBA
37614 | 0 |  |  | Central North Island | Marton | 29 | 33 | Solar | Investigation | ● | 26% | Early Stage Design | Application Expected | TBA
38383 | 37614 |  |  | Central North Island | Marton | 25 | 33 | Solar | Investigation | ● | 26% | Early Stage Design | Application Expected | TBA
37620 | 0 |  |  | Canterbury | ISL_KIK | 200 | 220 | Solar | Investigation | ● | 22% | Early Stage Design | Application Submitted | TBA
37637 | 0 |  |  | Canterbury | ROX_ISL_A | 450 | 220 | Solar | Investigation | ● | 22% | Early Stage Design | Application Expected | TBA
37638 | 37637 |  |  | Canterbury | ROX_ISL_A | 450 | 220 | BESS | Investigation | ● | 22% | Early Stage Design | Application Expected | TBA
37613 | 0 |  |  | Central North Island | BPE_WRK_1, BPE_TNG_1 | 275 | 220 | Wind - Onshore | Investigation | ● | 22% | Early Stage Design | Application Submitted | TBA
37609 | 0 |  |  | Waikato | WHU_WKO | 157 | 110 | Wind - Onshore | Investigation | ● | 20% | Early Stage Design | Application Submitted | TBA
37691 | 0 |  |  | Central North Island | Bunnythorpe | 525 | 220 | Solar | Investigation | ● | 18% | Early Stage Design | Application Submitted | TBA
37692 | 37691 |  |  | Central North Island | Bunnythorpe | 525 | 220 | BESS | Investigation | ● | 18% | Early Stage Design | Consent Granted | TBA
37607 | 0 |  |  | Central North Island | Dannevirke | 72 | 110 | Solar | Investigation | ● | 14% | Early Stage Design | Consent Granted | TBA
37608 | 37607 |  |  | Central North Island | Dannevirke | 72 | 110 | BESS | Investigation | ● | 14% | Early Stage Design | Consent Granted | TBA
37618 | 0 |  |  | Otago-Southland | NMA_TMH_A | 330 | 220 | Wind - Onshore | Investigation | ● | 12% | Early Stage Design | Application Submitted | TBA
37640 | 0 |  |  | Waikato | Piako | 110 | 33 | Solar | Investigation | ● | 10% | Early Stage Design | Application Submitted | TBA
37619 | 0 |  |  | Northland | HEN_MDN | 120 | 220 | Solar | Investigation | ● | 9% | Early Stage Design | Application Expected | TBA
37625 | 0 |  |  | Central North Island | Waipawa (South) | 43 | 33 | Solar | Investigation | ● | 9% | Early Stage Design | Application Expected | TBA
37599 | 0 |  |  | Waikato | Hinuera | 80 | 33 | Solar | Investigation | ● | 8% | Early Stage Design | Application Submitted | TBA
37600 | 37599 |  |  | Waikato | Hinuera | 80 | 33 | BESS | Investigation | ● | 8% | Early Stage Design | Application Submitted | TBA
37635 | 0 |  |  | Otago-Southland | NMA_TMH_A | 300 | 220 | Wind - Onshore | Investigation | ● | 8% | Early Stage Design | Consent Appeal Submitted | TBA
37628 | 0 |  |  | Central North Island | Tangiwai | 120 | 220 | Solar | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
37629 | 37628 |  |  | Central North Island | Tangiwai | 120 | 220 | BESS | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
37642 | 0 |  |  | Waikato | HLY_TMN / HLY_SFD | 338 | 220 | Wind - Onshore | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
37632 | 0 |  |  | Taranaki | BRK_SFD | 320 | 220 | Wind - Onshore | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
37631 | 37632 |  |  | Taranaki | BRK-SFD | 200 | 220 | Solar | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
38341 | 37632 |  |  | Taranaki | BRK-SFD | 230 | 220 | Solar | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
37641 | 0 |  |  | Central North Island | BPE_WKM | 500 | 220 | Solar | Investigation | ● | 8% | Early Stage Design | Application Submitted | TBA
37645 | 0 |  |  | Central North Island | BPE_BRK | 200 | 220 | Solar | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
37696 | 37645 |  |  | Central North Island | BPE_BRK | 200 | 220 | BESS | Investigation | ● | 8% | Early Stage Design | Application Expected | TBA
37624 | 0 |  |  | Central North Island | Mangamaire | 50 | 33 | Wind - Onshore | Investigation | ● | 4% | Starting | Consent Granted | TBA
37650 | 37624 |  |  | Central North Island | Mangamaire | 40 | 33 | Solar | Investigation | ● | 4% | Starting | Consent Granted | TBA
37639 | 0 |  |  | Taranaki | Opunake | 86 | 33 | Solar | Investigation | ● | 2% | Starting | Consent Granted | TBA
37651 | 0 |  |  | Bay of Plenty | EDG-TRK | 16.4 | 110 | Hydro | Investigation | ● | 2% | Starting | Application Expected | TBA
37697 | 37651 |  |  | Bay of Plenty | EDG-TRK | 40 | 110 | Geothermal | Investigation | ● | 2% | Starting | Application Expected | TBA
37623 | 0 |  |  | Auckland | Glenbrook | 80 | 33 | Wind - Onshore | Investigation | ● | 1% | Starting | Application Expected | TBA
37834 | 0 |  |  | Canterbury | Waipara* | 4 | 33 | Other Generation* | Investigation | ● | 0% | Starting | No Consent Required | TBA
38058 | 0 |  |  | Auckland | Glenbrook# | 200 | 220 | BESS# | Investigation | ● | 0% | Starting | Consent Granted | TBA
37627 | 0 |  |  | Canterbury | Waipara | 120 | 66 | Solar | Investigation | ●C | 0% | Starting | Application Expected | TBA
37633 | 0 |  |  | Northland | MDN_MPE / MSD_HPI | 120 | 110 | Wind - Onshore | Investigation | ● | 0% | Starting | Application Expected | TBA
37646 | 0 |  |  | South-Canterbury | BEN_ISL-A | 180 | 220 | Solar | Investigation | ●C | 0% | Starting | Application Submitted | TBA
37687 | 37646 |  |  | South-Canterbury | BEN_ISL-A | 180 | 220 | BESS | Investigation | ●C | 0% | Starting | Application Submitted | TBA
37626 | 0 |  |  | Nelson-Marlborough | Kikiwa | 100 | 220 | Solar | Investigation | ●C | 0% | Starting | Application Expected | TBA
37636 | 0 |  |  | Central North Island | Mangahao | 30 | 33 | Solar | Investigation | ● | 0% | Starting | Consent Granted | TBA
37644 | 0 |  |  | Waikato | HLY_SFD, HLY_TWH | 400 | 220 | Wind - Onshore | Investigation | ●C | 0% | Starting | Application Submitted | TBA
37690 | 37644 |  |  | Waikato | HLY_SFD, HLY_TWH | 400 | 220 | BESS | Investigation | ●C | 0% | Starting | Application Submitted | TBA
37630 | 0 |  |  | Waikato | Ohinewai | 300 | 220 | Wind - Onshore | Investigation | ● | 0% | Starting | Application Expected | TBA
Project ID | Parent Project ID |  |  | Region | Connection location (substation or circuit) | Max MW | Connection voltage | Technology | Transpower stage | Sequence number | Ready to proceed 7 | Status |  | Estimated date to progress to investigation
37652 | 0 |  |  | Otago-Southland | NSY_ROX-1 | 220 | 220 | Solar | Application | 1 | Y | Confirmed | Application Expected | 2026-04-01
37688 | 37652 |  |  | Otago-Southland | NSY_ROX-1 | 220 | 220 | BESS | Application | 1 | Y | Confirmed | Application Expected
37653 | 0 |  |  | Otago-Southland | ROX_ISL | 310 | 220 | Solar | Application | 2 | Y | Confirmed | Application Expected | 2026-04-01
37685 | 37653 |  |  | Otago-Southland | ROX_ISL | 310 | 220 | BESS | Application | 2 | Y | Confirmed | Application Expected
37654 | 0 |  |  | South-Canterbury | ROX_TWZ | 400 | 220 | Solar | Application | 3 | Y | Confirmed | Application Expected | 2026-05-01
37686 | 37654 |  |  | South-Canterbury | ROX_TWZ | 400 | 220 | BESS | Application | 3 | Y | Confirmed | Application Expected
37655 | 0 |  |  | Canterbury | ISL_KIK | 600 | 220 | Solar | Application | 4 |  | Confirmed | Application Expected | 2026-05-01
37693 | 37655 |  |  | Canterbury | ISL_KIK | 600 | 220 | BESS | Application | 4 |  | Confirmed | Application Expected
37656 | 0 |  |  | Central North Island | BPE_TKU 1_2 | 400 | 220 | Wind - Onshore | Application | 5 | Y | Confirmed | Application Expected | 2026-06-01
37657 | 0 |  |  | Central North Island | NAP-OKI-2 | 150 | 220 | Solar | Application | 6 | Y | Confirmed | Application Expected | 2026-06-01
37684 | 37657 |  |  | Central North Island | NAP-OKI-2 | 150 | 220 | BESS | Application | 6 | Y | Confirmed | Application Expected
37658 | 0 |  |  | Auckland | Glenbrook | 280 | 33 | BESS | Application | 7 |  | Confirmed | Application Expected | 2027-07-01
37659 | 0 |  |  | Otago-Southland | Edendale | 259 | 110 | Wind - Onshore | Application | 8 |  | Confirmed | Application Expected | 2026-07-01
37660 | 0 |  |  | Canterbury | ISL_KIK | 200 | 220 | Solar | Application | 9 |  | Confirmed | Application Expected | 2026-07-01
37694 | 37660 |  |  | Canterbury | ISL_KIK | 200 | 220 | BESS | Application | 9 |  | Confirmed | Application Expected
37662 | 0 |  |  | Canterbury | ISL_KIK | 310 | 220 | Solar | Application | 10 |  | Confirmed | Application Expected | 2026-08-01
38056 | 37662 |  |  | Canterbury | ISL_KIK | 310 | 220 | BESS | Application | 10 |  | Confirmed | Application Expected
37689 | 0 |  |  | Taranaki | BRK-SFD-A | 200 | 220 | Wind - Onshore | Application | 11 |  | Confirmed | Application Expected | 2026-08-01
38059 | 0 |  |  | Central North Island | WDW_BPE (220) / MST_MGM (110) | 300 | 220 | Wind - Onshore | Application | 12 | Y | Confirmed | Consent Granted | 2026-09-01
37776 | 0 |  |  | Waikato | WKM_WRK | 120 | 220 | Geothermal | Application | 13 | Y | Confirmed | Application Expected | 2026-09-01
38378 | 37776 |  |  | Waikato | WKM_WRK | 80 | 220 | Solar | Application | 13 | Y | Confirmed | Application Expected
37708 | 0 |  |  | Waikato | Whakamaru / Atiamuri | 350 | 220 | Wind - Onshore | Application | 14 |  | Confirmed | Application Expected | 2026-09-01
38372 | 0 |  |  | Canterbury | ISL_KIK_A/B | 500 | 220 | Solar | Application | 15 | Y | Confirmed | Application Expected | 2026-10-01
38377 | 38372 |  |  | Canterbury | ISL_KIK_A/B | 200 | 220 | BESS | Application | 15 | Y | Confirmed | Application Expected
37770 | 0 |  |  | Northland | Maungatapere | 150 | 110 | BESS | Application | 16 | Y | Confirmed | Application Expected | 2026-10-01
37713 | 0 |  |  | Waikato | Hamilton | 200 | 110 | BESS | Application | 17 | Y | Confirmed | Application Expected | 2026-11-01
38403 | 37713 |  |  | Waikato | Hamilton | 200 | 110 | BESS | Application | 17 |  | Confirmed | Application Expected
37647 | 0 |  |  | South-Canterbury | ISL-TKB-1, TKB | 250 | 220 | Solar | Application | 18 |  | Confirmed | Application Expected | 2025-11-01
38322 | 0 |  |  | Otago-Southland | Gore Substation | 140 | 110 | Solar | Application | 19 |  | Accepted | Application Expected | 2026-12-01
37835 | 0 |  |  | Bay of Plenty | Kaitemako-Tarukenga-1/2 | 454 | 220 | Wind - Onshore | Application | 20 |  | Received | Application Expected | 2027-02-01
37649 | 0 |  |  | Central North Island | Linton | 230 | 220 | Wind - Onshore | Application | 21 |  | Confirmed | Application Submitted | 2027-02-01
Notes
1. The location is given as the substation where a project will connect, or if a new substation is required, the transmission circuit.
2. This list includes generation projects requiring new or upgraded Transpower assets; generation projects connecting to an electricity distribution network and not requiring new or upgraded Transpower assets are not shown.
3. Sequence numbers (for investigations and applications) will be updated as and when projects move to a new stage or are withdrawn; or if a customer with two or more projects with consecutive sequence numbers prioritises a project with a higher number.
4. An Applications sequence number indicates the order in which Transpower will allocate internal resources to new connection investigations and the order in which Transpower will allocate physical assets (spare Transpower transmission assets and land) at the proposed point of connection. An accepted connection application does not guarantee access to transmission capacity beyond the point of connection and does not guarantee the project will proceed to commissioning. For investigations the sequence number indicates the order in which projects entered the investigation stage. Investigations can move into delivery when the investigation is complete, the sequence number will not apply to this transition.
5. Stage % Complete - Approximate progress of the project through the relevant stage based project milestones completed in the project schedule. Progress in delivery is progress for the Transpower connection only, not for the associated generation. Timeframes for delivery contracting will vary as they are dependent on bilateral negotiation and each customer's investment decision process. Progress is dependent on both Transpower work and customer decisions at key stage gates. Where customers are unable to make timely decisions progress may stall. Stalled projects may be put on hold so resources can be re-allocated to other waiting projects.
6. Where a developer for a project with a single connection, has multiple development stages, or multiple technologies, these are split into separate rows in this pipeline.
7. Applications are deemed ready to proceed to investigation where Transpower has had confirmation the applicant: is ready to sign the associated services agreement, has FID for the residual application fee and the investigation costs, maintains a need date which justifies an investigation in the near term, and plans for securing property rights and consenting remain on track. Developers are required to be 'ready to proceed' 3 months ahead of the 'estimated date to progress to investigation'
! - Max MW value includes existing generation of () MW as part of the new connection
*- Progressed based on no requirement for new Transpower capital assets for this connection, similar to the treatment of embedded generation connections with no requirement for new Transpower capital assets
# - Progressed as will contribute to short term system need in line with Security of Supply Assessment

## Completed
Generation commissioning
Customer | Generator name | Region | Connection location | Net new capacity MW | TP Connection voltage | Technology | Transpower / EDB | Transpower connection practical completion date | First sync date | Generation commissioning date | Comments
Todd Generation | JRD - Junction Road G71 | Taranaki | Junction Rd | 52 | 110 | Gas | Transpower | N/A | 2020-02-01 | 2020-05-15
Todd Generation | JRD - Junction Road G72 | Taranaki | Junction Rd | 52 | 110 | Gas | Transpower | N/A | 2020-02-01 | 2020-05-15
Mercury | WPP - Waipipi Wind Farm | Taranaki | Waverly | 130 | 110 | Wind | Transpower | 2020-04-05 | 2020-11-13 | 2021-03-31
Ngawha | NGB - Ngawha B (New) | Northland | Top Energy - Kaikohe | 32 | 110 | Geothermal | Top Energy | N/A | 2020-12-19 | 2021-01-27
Mercury | TUR - Turitea North | Central North Island | Linton | 118 | 220 | Wind | Transpower | 2020-10-19 | 2021-07-14 | 2021-12-20
Mercury | TUR - Turitea South (New) | Central North Island | Linton | 100 | 220 | Wind | Transpower | N/A | 2023-03-20 | 2023-06-15
Mercury | KWD - Kaiwera Downs (New) | Otago Southland | PowerNet - Gore | 41 | 33 | Solar | PowerNet | 2023-06-23 | 2023-08-21 | 2023-11-15
New Power | RHO - Rotohiko (Final New) | Waikato | WEL Networks - Huntly | 33 | 33 | BESS | WEL Networks | N/A | 2023-11-01 | 2023-12-11
Meridian | HRP - Harapaki Wind Farm | Hawkes Bay | Harapaki | 172.9 | 220 | Wind | Transpower | 2023-06-12 | 2023-11-13 | 2024-07-24
Lodestone Energy | KTS - Kaitaia Solar Farm | Northland | Top Energy - Kaikohe | 23.7 | 110 | Solar | Top Energy | N/A | 2023-11-17 | 2024-02-02
Lodestone Energy | RGT - Rangitaiki Solar Farm (New) | Bay of Plenty | Horizon - Edgecumbe | 23.7 | 33 | Solar | Horizon Networks | N/A | 2024-03-06 | 2024-04-17
Contact Energy | TAB - Tauhara Station | Central North Island | Tauhara | 184 | 220 | Geothermal | Transpower | 2023-10-25 | 2024-04-23 | 2024-05-15
Contact Energy | TAC - Te Huka 3 | Central North Island | Unison - Wairaki / Tauhara | 51.4 | 33 | Geothermal | Unison | N/A | 2024-10-01 | 2024-12-16
Genesis Energy | LAU - Lauriston Solar Farm | South Canterbury | Electricity Ashburton - Ashburton | 52 | 66 | Solar | Electricity Ashburton | N/A | 2024-11-11 | 2025-02-10
Northpower | RWI - Ruawai Solar Farm | Northland | Northpower - Mangaturoto | 14 | 33 | Solar | Northpower | N/A | 2024-12-09 | 2024-12-19
Manawa Energy | COL - Coleridge runback scheme | Canterbury | Coleridge | 0 | 66 | Hydro | Transpower | 2024-10-31 | N/A | N/A | SPS to deconstrain COL generation during certain outage scenarios
Lodestone Energy | HTR - Te Herenga O Te Ra Solar Farm | Bay of Plenty | Waiotahe | 22.8 | 33 | Solar | Transpower | 2024-11-21 | 2025-01-06 | 2025-07-25
Meridian Energy | RUK - Ruakākā BESS | Northland | Bream Bay | 100 | 33 | BESS | Transpower | 2024-12-09 | 2025-01-16 | 2025-05-31
Aquila | PSF - Pukenui Solar Farm | Northland | Top Energy - Kaikohe | 17.16 | 110 | Solar | Top Energy | N/A | 2025-05-22 | 2025-06-16
Eastland Generation | KAW - Te Ahi O Maui Upgrade | Bay of Plenty | Kawerau | 0 | 220 | Geothermal | Transpower | 2025-09-18 | 2025-09-22 | 2025-09-22 | New 220kV point of conenction
New Power | TOH - Taiohi Solar Farm | Waikato | WEL Networks - Huntly | 22.4 | 33 | Solar | WEL Networks | N/A | 2025-10-06 | 2025-12-12
Lodestone Energy | WTA - Whitianga Solar Farm | Waikato | Powerco - Kopu | 23.75 | 33 | Solar | Powerco | N/A | 2025-11-24 | 2025-12-17
Eastland Generation | KAW - TOPP 2 | Bay of Plenty | Kawerau | 55 | 220 | Geothermal | Transpower | 2025-09-18 | 2025-12-03 | 2025-12-23
Mercury | NTM - Ngā Tamariki OEC 5 | Central North Island | Nga Awa Purua | 56.87 | 220 | Geothermal | Transpower | N/A | 2026-01-16 | 2026-01-30
Rānui Generation | TRS - Twin Rivers Solar Farm (Stage 3) | Northland | Top Energy - Kaikohe | 24 | 110 | Solar | Top Energy | N/A | 2026-01-27 | 2026-02-11
Horizon Energy | EDS - Edgecumbe Solar Farm | Bay of Plenty | Horizon - Edgecumbe | 27 | 33 | Solar | Horizon Networks | 2025-03-01 | TBA | TBA
Project Waiotahe LP (Aquila) | Waiotahe Solar Farm | Bay of Plenty | Waiotahe | 33 | 33 | Solar | Transpower | 2025-04-15 | TBA | TBA
Harmony Energy | TAH - Tauhei Solar Farm | Waikato | Waihou | 150 | 110 | Solar | Transpower | 2025-06-17 | TBA | TBA
Genesis Energy Limited | Huntly BESS | Waikato | Huntly | 100 | 220 | BESS | Transpower | 2025-07-31 | TBA | TBA
Mercury | KPO - Karapiro runback scheme | Waikato | Karapiro | 16 | 110 | Hydro | Transpower | 2025-09-01 | N/A | N/A | SPS to deconstrain KPO generation following Karapiro re-commissioned 3 units between June 2023 - September 2025 (~15MW increase)
Top Energy | KOE-MPE 110kV Runback SPS | Northland | Top Energy - Kaikohe | 50 | 110 | Geothermal / Solar | Transpower | 2025-12-19 | N/A | N/A | SPS to deconstrain KOE_MPE circuits to allow additional generation export from Northland
Contact Energy Limited | Glenbrook BESS I | Auckland | Glenbrook | 100 | 33 | BESS | Transpower | 2026-03-06 | 2026-03-09 | TBA
Generation decommissioning
Customer | Generator name | Region | Connection location | Capacity change MW | Connection voltage | Technology | Transpower / EDB | Transpower dissconnection completion date | First de-sync date | Generation decommissioning date | Comments
Contact | TRC - Te Rapa | Waikato | Wel Networks - Hamilton | -42 | 33 | Gas | WEL Networks | N/A | 2023-06-01 | 2023-06-30
Contact | WRK - Wairakei G14 (New) | Central North Island | Wairakei | -4.2 | 220 | Geothermal | Transpower | N/A | 2024-08-15 | 2024-08-15