## List (hidden)
AD
KT
Not started | LW
In progress | RT
In first review | HM
In second review | DF
Complete | ADT
HP
LS
MSR
MS
DLS
JC
LB
TR
JW
AF
RK
KP
SJ
JM
IM
GC
Pending audit sign off
Pending reconfirmation

## CoverSheet
Transpower Information Disclosure Schedules F1-7a, TP1-6, G1-8, SO1
| Disclosure Year (year ended) | 2026-06-30
Prepared and Published on 23 October 2026

## Directors' certificate
Directors' Certificate - October 2026

## Table of Contents
TRANSPOWER INFORMATION DISCLOSURE
Table of Contents
Compliance
| Directors' Certificate | Transpower generated
| Assurance Report | Transpower generated
Financial Information
F1 | Value of the Regulatory Asset Base (RAB Roll Forward)
F2 | Operating Expenditure (Opex): Actual
F3 | Base Capital Expenditure (Base Capex): Actual Commissioned
F4 | Comparison of Forecasts for Opex and base Capex Commissioning
F5 | Major Capital Expenditure (Major Capex)
F6 | Regulated Revenue
F7 | Cost Allocation
F7a | Asset Allocation
TP1 | ROI and profit calculations (required by ID Determination Clause 8.7 to 8.14) | Transpower generated
TP2 | Major project costs (required by ID Determination Clause 8.18 and 8.19) | Transpower generated
TP3 | Major project timing (required by ID Determination Clause 8.18 and 8.19) | Transpower generated
TP4 | Fully commissioned project details (required by ID Determination Clause 8.20) | None in 2026
TP5 | Related party transactions (required by ID Determination Clause 8.21) | Transpower generated
TP6 | Investment contracts (required by ID Determination Clause 10) | Transpower generated
Grid Management Information
G1 | Transmission System Statistics
G2 | Grid Demand and Injection
G3 | Grid Exit Point (GXP) Connection Capacity and Demand (Actual and Forecast)
G4 | Quality of Supply: Grid Outputs and Performance Measures
G5 | Quality of Supply: Interconnection Assets
G6 | Asset Health and Age (2nd Year of RCP and in RCP Proposal)
G7 | Asset Management Maturity Assessment Tool (AMMAT)
G8 | AMMAT Results Summary
System Operator
SO1 | System Operator

## Assurance report
Assurance Report - October 2026
.

## F1. RAB
[11 empty] | Transpower |  | Disclosure Date |  | 2026-10-23
SCHEDULE F1: VALUE OF THE REGULATORY ASSET BASE (RAB ROLL FORWARD) | [12 empty] | Disclosure Year (year ended) |  | 2026-06-30
Disclosure of line items required from disclosure year 2026 onward are specified in column U. The opening balance of the RAB has been adjusted to bring it in line with the RAB balance in the Annual Compliance Statements. The Commission's decision to allow IDC cap revenue reductions to be subtracted off depreciation means that the ID and ACS RAB's will be aligned going forward. https://comcom.govt.nz/__data/assets/pdf_file/0020/363152/Information-Disclosure-Transpower-Amendment-Determination-2024-Final-Decision-Reasons-Paper-13-November-2024.pdf Clause 2.83 align IPP RAB with ID RAB
ref
5 |  | F1(i): Value of Regulatory Asset Base (RAB Roll Forward)
6 | [8 empty] | RAB | RAB | RAB | RAB | RAB
7 | [8 empty] | CY-4 | CY-3 | CY-2 | CY-1 | CY
8 | [8 empty] | ($M) | ($M) | ($M) | ($M) | ($M)
9 |  |  |  | Opening RAB value (excl ACA) |  |  |  |  | 4864216474.6736 | 4882848062.6986 | 4956466525.2144 | 5050212277.4996 | 5224500000
10 |  |  | plus | Value of found assets |  |  |  |  | 0 | 0 | 0 | 0 | 0
11 |  |  | less | Value of disposed assets |  |  |  |  | 8994642.09 | 7467082.173 | 3060788.84 | 3678767.98 | 6400000
12 |  |  | less | Value of lost assets |  |  |  |  | 0 | 0 | 0 | 0 | 0
13 |  |  | less | Total depreciation |  |  |  |  | 247604830.2337 | 250836346.7763 | 255632095.5696 | 267558469.3695 | 281600000
|  |  | plus | Total revaluations |  |  |  |  | 0 | 0 | 0 | 0 | 204100000
15 |  |  | plus | Total Value of commissioned assets (including acquired assets and costs incurred after an asset is first commissioned) |  |  |  |  | 275231060.3487 | 331921891.4651 | 331508408.0299 | 445510163.2116 | 482500000
16 |  |  | plus | Adjustment to opening RAB resulting from change in cost allocation |  |  |  |  | 0 | 0 | 0 | 0 | -300000
17 |  |  |  | Closing RAB value |  |  |  |  | 4882848062.6986 | 4956466525.2144 | 5029282048.8347 | 5224485203.3617 | 5622800000
18
19 |  |  | plus | Opening RAB of Anticipatory Connection Assets (ACA)
20 |  |  |  | Opening RAB value including Anticipatory Connection Assets (ACA) | [8 empty] | 5224500000
21 |  |  |  | Value of commissioned ACA |  |  |  |  | 0 | 0 | 0 | 0 | 0
22
23 |  | F1(ii): Unallocated Regulatory Asset Base
24 | [8 empty] | Unallocated RAB | Unallocated RAB | Unallocated RAB | Unallocated RAB | Unallocated RAB
25 | [8 empty] | CY-4 | CY-3 | CY-2 | CY-1 | CY
26 | [8 empty] | ($M) | ($M) | ($M) | ($M) | ($M)
27 |  |  |  | Unallocated opening RAB value |  |  |  |  | 4910918248.5235 | 4933005584.1313 | 5009056431.4634 | 5094097471.8646 | 5261400000
28 |  |  | plus | Found assets |  |  |  |  | 0 | 0 | 0 | 0 | 0
29 |  |  | less | Asset disposals |  |  |  |  | 8994642.09 | 7467082.173 | 3060788.84 | 3678767.98 | 6400000
30 |  |  | less | Lost Assets |  |  |  |  | 0 | 0 | 0 | 0 | 0
31 |  |  | less | Total depreciation |  |  |  |  | 259858758.6909 | 264897147.1428 | 270196924.7519 | 280485409.888 | 295900000
|  |  | plus | Total revaluations |  |  |  |  | 0 | 0 | 0 | 0 | 205200000
33 |  |  | plus | Assets commissioned |  |  |  |  | 290940736.3887 | 348415076.648 | 337425029.1699 | 451496639.6366 | 497800000
34 |  |  |  | Unallocated closing RAB value |  |  |  |  | 4933005584.1313 | 5009056431.4634 | 5073223747.0415 | 5261429933.6332 | 5662100000
35
36 |  |  |  | Result of cost allocation ratio (opening values) |  |  |  |  | 99.05% | 98.98% | 98.95% | 99.14% | 99.3%
37
38 |  | F1(iii): Calculation of Revaluation Rate and Revaluation of Assets
39
40 |  |  |  | CPI4 | [8 empty] | 1359
41 |  |  |  | CPI4-4 | [8 empty] | 1306
42 |  |  |  | Revaluation rate (%) | [8 empty] | 4.1%
43
44 | [9 empty] | Unallocated RAB ($000) |  | RAB ($000)
45 |  |  |  |  | Total opening RAB value |  |  |  |  | 5261400000 |  | 5224500000
|  |  | less |  | Adjustments to opening RAB - see footnote |  |  |  |  | 36384714.8465 |  | 32439772.1878
47 |  |  | less |  | Opening value of assets with nil physical life, and disposed and lost assets |  |  |  |  | 6400000 |  | 6400000
|  |  | less |  | Depreciation on opening RAB |  |  |  |  | 286506666.066 |  | 272490991.7
49
50 |  |  |  |  | Total opening RAB value adjusted for depreciation, and fully depreciated, disposed and lost assets |  |  |  |  | 5004878048.7805 |  | 4978048780.4878
51
52 |  |  |  | Total revaluations | [5 empty] | 205200000 |  | 204100000
53
54
55 |  | F1(iv): Disclosure by Asset Category
56 | [5 empty] | HVAC Substations | HVAC Lines and Transmission cables | HVDC Substations and Submarine cables | HVDC Lines | Easements | Intangibles | IST | Business Support | Pseudo Assets | Total
57 | [5 empty] | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
58 |  |  |  | Opening RAB value (CY) |  | 1878800000 | 2111900000 | 421500000 | 100000000 | 302600000 | 48600000 | 153600000 | 165600000 | 41900000 | 5224500000
59 |  | plus |  | Found assets |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 |  | less |  | Asset disposals |  | 3100000 | 1600000 | 400000 | 0 | 0 | 300000 | 900000 | 100000 | 0 | 6400000
61 |  | less |  | Lost Assets |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 |  | less |  | Total depreciation |  | 81800000 | 94400000 | 27100000 | 4900000 | 600000 | 20600000 | 26200000 | 24000000 | 2000000 | 281600000
|  |  | plus | Total revaluations |  | 72800000 | 84500000 | 16100000 | 4000000 | 12600000 | 1300000 | 5200000 | 6000000 | 1600000 | 204100000
64 |  | plus |  | Total Assets commissioned |  | 142500000 | 224900000 | 12600000 | 1500000 | 5100000 | 31700000 | 18500000 | 45700000 | 0 | 482500000
65 |  | less |  | Adjustment to opening RAB resulting from change in cost allocation | [8 empty] | -300000 |  | -300000
66 |  |  |  | Closing RAB value (CY) |  | 2009200000 | 2325300000 | 422700000 | 100600000 | 319700000 | 60700000 | 150200000 | 192900000 | 41500000 | 5622800000
67
68 |  | plus |  | Opening RAB value of Anticipatory Connection Assets (ACA)
69 |  |  |  | Opening RAB value including Anticipatory Connection Assets (ACA) |  | 1878800000 | 2111900000 | 421500000 | 100000000 | 302600000 | 48600000 | 153600000 | 165600000 | 41900000 | 5224500000
70 |  |  |  | Commissioned ACA |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71
72
73 |  | F1(v): Found Assets
74 | [5 empty] | HVAC Substations | HVAC Lines and Transmission cables | HVDC Substations and Submarine cables | HVDC Lines | Easements | Intangibles | IST | Business Support | Pseudo Assets | Total
75 | [5 empty] | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
76 |  |  |  |  | RAB value (CY) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 |  |  |  |  | Unallocated RAB value (CY) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78
79 |  | F1(vi): Asset Disposals
80 | [5 empty] | HVAC Substations | HVAC Lines and Transmission cables | HVDC Substations and Submarine cables | HVDC Lines | Easements | Intangibles | IST | Business Support | Pseudo Assets | Total
81 | [5 empty] | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
82 |  |  |  |  | RAB Asset Sales - Related Party (CY) | [9 empty] | 0
83 |  |  |  |  | RAB Asset Sales - Regulated Supplier (CY) | [9 empty] | 0
84 |  |  |  |  | RAB Asset Sales - Other (CY) | [9 empty] | 0
85 |  |  |  |  | RAB Asset Disposals (CY) | 3100000 | 1600000 | 400000 | 0 | 0 | 300000 | 900000 | 100000 | 0 | 6400000
86 |  |  |  |  | Unallocated RAB Asset Sales - Related party (CY) | [9 empty] | 0
87 |  |  |  |  | Unallocated RAB Asset Sales - Regulated Supplier (CY) | [9 empty] | 0
88 |  |  |  |  | Unallocated RAB Asset Sales - Other (CY) | [9 empty] | 0
89 |  |  |  |  | Unallocated RAB Asset Disposals (CY) | 3100000 | 1600000 | 400000 | 0 | 0 | 300000 | 900000 | 100000 | 0 | 6400000
90
91 |  | F1(vii): Lost Assets
92 | [5 empty] | HVAC Substations | HVAC Lines and Transmission cables | HVDC Substations and Submarine cables | HVDC Lines | Easements | Intangibles | IST | Business Support | Pseudo Assets | Total
93 | [5 empty] | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
94 |  |  |  |  | RAB value (CY) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 |  |  |  |  | Unallocated RAB value (CY) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96
97 |  | F1(viii): Depreciation
98 | [5 empty] | HVAC Substations | HVAC Lines and Transmission cables | HVDC Substations and Submarine cables | HVDC Lines | Easements | Intangibles | IST | Business Support | Pseudo Assets | Total
99 | [5 empty] | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
100 |  |  |  |  | Depreciation and impairment on the RAB (CY) | 81800000 | 94400000 | 27100000 | 4900000 | 600000 | 20600000 | 26200000 | 24000000 | 2000000 | 281600000
101 |  |  |  |  | Depreciation and impairment on the unallocated RAB (CY) | 81800000 | 94400000 | 27100000 | 4900000 | 600000 | 31300000 | 26400000 | 27400000 | 2000000 | 295900000
102
103
104 |  | F1(ix): Value of Commissioned Assets
105 | [5 empty] | HVAC Substations | HVAC Lines and Transmission cables | HVDC Substations and Submarine cables | HVDC Lines | Easements | Intangibles | IST | Business Support | Pseudo Assets | Total
106 | [5 empty] | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
107 |  |  |  |  | RAB value (CY) | 142500000 | 224900000 | 12600000 | 1500000 | 5100000 | 31700000 | 18500000 | 45700000 | 0 | 482500000
108 |  |  |  |  | Unallocated RAB value (CY) | 142500000 | 224900000 | 12600000 | 1500000 | 5100000 | 47100000 | 17500000 | 46600000 | 0 | 497800000
109
110
F1(x):Revaluations
[6 empty] | HVAC Substations | HVAC Lines and Transmission cables | HVDC Substations and Submarine cables | HVDC Lines | Easements | Intangibles | IST | Business Support | Pseudo Assets | Total
[6 empty] | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
[5 empty] | RAB value (CY) | 72800000 | 84500000 | 16100000 | 4000000 | 12600000 | 1300000 | 5200000 | 6000000 | 1600000 | 204100000
[5 empty] | Unallocated RAB value (CY) | 72800000 | 84500000 | 16100000 | 4000000 | 12600000 | 1700000 | 5300000 | 6600000 | 1600000 | 205200000
118
119 |  | F1(xi): Anticipatory Connection Assets (ACA)
120 | [6 empty] | New investment contracts | Unit
121 |  |  | New investment contract - total capacity |  |  |  | 0 | (MW)
122 |  |  | New investment contract - ACA capacity |  |  |  | 0 | (MW)
123 |  |  | Percentage of anticipatory capacity |  |  |  |  | (%)
124
125 |  |  | New investment contract costs |  |  |  | 0 | ($M)
126 |  |  | New investment contract cost allocated to ACA |  |  |  | 0 | ($M)
127 |  |  | Percentage of cost allocated to ACA |  |  |  |  | (%)
128
129
RAB Reconciliation Note:
A $32.4 million difference exists between the top down and the bottom up revaluable opening RAB. The difference is due to the difference between commissioned assets accrued into the reported opening RAB and the actual assets added to the Fixed Asset Register (i.e. an under-accrual of asset commissioning). The difference results in approximately $1.3 million additional revaluation. A minor adjustment has been made to the reported revaluation amount to align the Information Disclosure RAB with the indexed RAB used for IPP revenue-setting purposes.

## F2.Opex
[5 empty] | Transpower |  | Disclosure Date |  | 2026-10-23
SCHEDULE F2: OPERATING EXPENDITURE (OPEX): ACTUAL | [6 empty] | Disclosure Year (year ended) |  | 2026-06-30
Disclosure of line items required and not required from disclosure year 2026 onward are specified in column N.
ref
5 | F2(i): Operating Expenditure (Actual Totals)
6 |  |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
7 |  |  |  |  | ($M) | ($M) | ($M) | ($M) | ($M)
8 |  | Grid - maintenance projects |  |  | 0 | 0 | 0 | 0 | 0
9 |  | Grid - routine maintenance |  |  | 0 | 0 | 0 | 0 | 0
10 |  | IST - grid |  |  | 0 | 0 | 0 | 0 | 0
11 |  | IST - business support |  |  | 0 | 0 | 0 | 0 | 0
12 |  | Corporate |  |  | 0 | 0 | 0 | 0 | 0
13
14 |  | Grid maintenance |  |  | 107816842.63 | 133531615.7329 | 131116662.604 | 140066409.58 | 148310707.95
15 |  | ICT |  |  | 38168116.0929 | 40962389.4729 | 45893699.5484 | 50768700.1301 | 62294449.9231
16 |  | Asset Management & Operations |  |  | 65398707.9534 | 72474796.2246 | 77986279.4156 | 87587487.2681 | 94079841.3551
17 |  | Business Support |  |  | 45441541.1037 | 55085948.0555 | 59628018.5463 | 63787820.2521 | 66450660.9305
18 |  | Insurance |  |  | 22154277.9 | 26547466.96 | 30086222.1 | 32216912.76 | 30995060.52
19 |  | Total operating expenditure * |  |  | 278979485.68 | 328602216.4458 | 344710882.2143 | 374427329.9902 | 402130720.6787
20
21 |  | Comprising:
22 |  | HVAC operating expenditure |  |  | 249948011.3196 | 294711672.393 | 306477315.2979 | 331954464.7181 |  | Not required from disclosure year 2026
23 |  | HVDC operating expenditure |  |  | 29031438.0637 | 33858476.9728 | 38233566.6864 | 42467646.1422 |  | Not required from disclosure year 2026
24 |  | * Excluding the cost of capitalised operating leases (CY-1 $11.8 million, CY $12.7 million).
25 | F2(ii): Operating Expenditure (Actual Details)
26 |  |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
27 |  |  |  |  | ($M) | ($M) | ($M) | ($M) | ($M)
28 |  | Grid | Maintenance Projects - Transmission | TL Tower | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
29 |  | Grid | Maintenance Projects - Transmission | TL Conductor | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
30 |  | Grid | Maintenance Projects - Transmission | TL Foundation | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
31 |  | Grid | Maintenance Projects - Transmission | TL Insulators | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
32 |  | Grid | Maintenance Projects - Transmission | TL Pole | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
33 |  | Grid | Maintenance Projects - Transmission | TL Access | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
34 |  | Grid | Maintenance Projects - AC Stations | ACS Buildings & Grounds | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
35 |  | Grid | Maintenance Projects - AC Stations | ACS Power Transformers | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
36 |  | Grid | Maintenance Projects - AC Stations | ACS Outdoor Circuit Breakers | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
37 |  | Grid | Maintenance Projects - AC Stations | ACS Indoor Switchgear | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
38 |  | Grid | Maintenance Projects - HVDC Stations | HVDC | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
39 |  | Grid | Maintenance Projects - Other | MP Other | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
40 |  | Total grid - maintenance projects |  |  | 0 | 0 | 0 | 0 | 0
41
42 |  | Grid | Routine Maintenance | RM Stations | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
43 |  | Grid | Routine Maintenance | RM Transmission Lines | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
44 |  | Grid | Routine Maintenance | RM HVDC | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
45 |  | Grid | Routine Maintenance | RM Operating | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
46 |  | Grid | Routine Maintenance | RM Training | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
47 |  | Grid | Routine Maintenance | RM Contractor Transition | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
48 |  | Total grid - routine maintenance |  |  | 0 | 0 | 0 | 0 | 0
49
50 |  | IST ICT Grid | IST ICT Grid | IT Asset Management | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
51 |  | IST ICT Grid | IST ICT Grid | IT Transmission System Plan | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
52 |  | IST ICT Grid | IST ICT Grid | IT Telecommunications Services | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
53 |  | IST ICT Grid | IST ICT Grid | IT Network Services | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
54 |  | Total IST - grid |  |  | 0 | 0 | 0 | 0 | 0
55
56 |  | IST Business Support | IST Business Support | IT Corporate services | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
57 |  | IST Business Support | IST Business Support | IT ICT Shared Services | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
58 |  | IST Business Support | IST Business Support | IT Security Services | 0 | 0 | 0 | 0 | 0 |  | Old format - RT (explained to CC we will hide these rows)
59 |  | Total IST - business support |  |  | 0 | 0 | 0 | 0 | 0
60
61 |  | Corporate | Corporate | CS Departmental Corporate | [6 empty] | Old format - RT (explained to CC we will hide these rows)
62 |  | Corporate | Corporate | CS Departmental Grid | [6 empty] | Old format - RT (explained to CC we will hide these rows)
63 |  | Corporate | Corporate | Grid Operating Services Costs (GOS) | [6 empty] | Old format - RT (explained to CC we will hide these rows)
64 |  | Corporate | Corporate | Reseach and Development (R&D) | [6 empty] | Old format - RT (explained to CC we will hide these rows)
65 |  | Corporate | Corporate | Investigations | [6 empty] | Old format - RT (explained to CC we will hide these rows)
66 |  | Corporate | Corporate | Insurance | [6 empty] | Old format - RT (explained to CC we will hide these rows)
67 |  | Corporate | Corporate | Ancillary Services | [6 empty] | Old format - RT (explained to CC we will hide these rows)
68 |  | Total Corporate |  |  | 0 | 0 | 0 | 0 | 0
69
70
71 |  | Grid maintenance | Grid maintenance | Preventive Maintenance | 38780206.2535 | 44322559.6173 | 51363958.8087 | 49747927.3945 | 52017003.8399
72 |  | Grid maintenance | Grid maintenance | Predictive Maintenance | 63667881.8965 | 83568838.3356 | 71875776.3353 | 82766497.0755 | 86120023.9301
73 |  | Grid maintenance | Grid maintenance | Corrective Maintenance | 4756041.55 | 4870033.59 | 6838899.04 | 6505954.67 | 7077966.46
74 |  | Grid maintenance | Grid maintenance | Proactive Maintenance | 612712.93 | 770184.19 | 1038028.42 | 1046030.44 | 859207.72
75 |  | Grid maintenance | Grid maintenance | Resilience |  |  |  |  | 2236506 | Required from disclosure year 2026
76 |  | Total - Grid maintenance |  |  | 107816842.63 | 133531615.7329 | 131116662.604 | 140066409.58 | 148310707.95
77
78 |  | ICT | ICT | ICT Opex | 38168116.0929 | 40962389.4729 | 45893699.5484 | 50768700.1301 | 47330317.6131 | Required from disclosure year 2026
79 |  | ICT | ICT | ICT Software as a Service |  |  |  |  | 14964132.31 | Required from disclosure year 2026
80 |  | Total - ICT |  |  | 38168116.0929 | 40962389.4729 | 45893699.5484 | 50768700.1301 | 62294449.9231
81
82 |  | Asset Management & Operations | Asset Management & Operations | Asset Management & Operations | 65398707.9534 | 72474796.2246 | 77986279.4156 | 87587487.2681 | 93493083.2251 | Required from disclosure year 2026
83 |  | Asset Management & Operations | Asset Management & Operations | Sustainability |  |  |  | 0 | 586758.13 | Required from disclosure year 2026
84 |  | Total - Asset Management & Operations |  |  | 65398707.9534 | 72474796.2246 | 77986279.4156 | 87587487.2681 | 94079841.3551
85
86 |  | Business Support | Business Support | Business Support | 45441541.1037 | 55085948.0555 | 59628018.5463 | 63787820.2521 | 66450660.9305
87
88 |  | Insurance | Insurance | Insurance | 22154277.9 | 26547466.96 | 30086222.1 | 32216912.76 | 30995060.52
89
90
91 | F2(iii): Network Divestiture Expenditure
92 |  |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
93 |  |  |  |  | ($M) | ($M) | ($M) | ($M) | ($M)
94 |  | Network divestiture expenses |  |  | 0 | 0 | 0 | 0 | 0
95
96 | F2(iv): Other Disclosures
97 |  |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
98 |  |  |  |  | ($M) | ($M) | ($M) | ($M) | ($M)
99 |  | Third party insurance allowance |  |  | 0 | 0 | 0 | 0 | 0
100 |  | Self-insurance allowance |  |  | 17800223.6949 | 19610840.8584 | 21135822.2023 | 22324331.0621 | 36777978.0406
101
102

## F3. Base Capex
[5 empty] | Transpower |  | Disclosure Date |  | 2026-10-23
SCHEDULE F3: BASE CAPITAL EXPENDITURE (BASE CAPEX): ACTUAL Spend | [6 empty] | Disclosure Year (year ended) |  | 2026-06-30
Line items not required from disclosure year 2026 onward are specified in column M. Schedule F3 was reported as Commissioned Assets up until 2024. This schedule reports Capex values from 2025 onwards which is consistent with the 2024 Information Disclosure Review Final Decision on F4(ii)
ref
5 | F3(i): Base Capex (Actual Commissioned Totals up to 2024 and 2025 Capex) |  |  |  | Commissioned | Commissioned | Commissioned | SPEND basis | SPEND basis
6 |  |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
7 |  |  |  |  | ($M) | ($M) | ($M) | ($M) | ($M)
8 |  | Grid - refurbishment and replacement |  |  | 176025394.64 | 210824205.44 | 241832966.76 | 348936574.68 | 331348186
9 |  | Grid - enhancement and development |  |  | 7115716 | 21873281 | 47076178.02 | 47822321 | 45795538
10 |  | IST |  |  | 28253820.82 | 21841730.74 | 22392572.08 | 47587019.13 | 67198026.831
11 |  | Business support |  |  | 17324445 | 3860306.837 | 9741593.5442 | 9582106 | 6423577.3371
12 |  | Total base capex commissioned/ Spend basis |  |  | 228719376.46 | 258399524.017 | 321043310.4042 | 453928020.81 | 450765328.1681
13
14 |  | Comprising:
15 |  | HVAC base capex commissioned / Spend basis |  |  | 221738914.595 | 245085445.687 | 295000000 | 407310699.31 |  | Not required from disclosure year 2026
16 |  | HVDC base capex commissioned / Spend basis |  |  | 6980461.865 | 13314078.33 | 26080469 | 46617321.5 |  | Not required from disclosure year 2026
17
18 | F3(ii): Base Capex (Actual Commissioned Totals up to 2024 and 2025 Capex) |  |  |  | Commissioned | Commissioned | Commissioned | SPEND basis | SPEND basis
19 |  |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
20 |  |  |  |  | ($M) | ($M) | ($M) | ($M) | ($M)
21 |  | Grid refurbishment and replacement | AC Stations | ACS Power Transformers | 10568565 | 25083339 | 6854812 | 33191462 | 18412478
22 |  | Grid refurbishment and replacement | AC Stations | ACS Outdoor to Indoor Conv | 33445865 | 4386357 | 3014162 | 1795688 | 4294966
23 |  | Grid refurbishment and replacement | AC Stations | ACS Buildings & Grounds-Seismic | 0 | 0 | 0 | 0 | 0
24 |  | Grid refurbishment and replacement | AC Stations | ACS Buildings & Grounds | 5125842.64 | 9860131.44 | 14096915.76 | 48463912.68 | 17063017
25 |  | Grid refurbishment and replacement | AC Stations | ACS Outdoor Circuit Breakers | 1257850 | 469458 | 203297 | 1440364 | 2432701
26 |  | Grid refurbishment and replacement | AC Stations | ACS Indoor Switchgear | 7932259 | 11571151 | 6945099 | 16513010 | 7063731
27 |  | Grid refurbishment and replacement | AC Stations | ACS Capacitors and Reactors | 0 | 3555159 | 757795 | 718668 | 272428
28 |  | Grid refurbishment and replacement | AC Stations | ACS Structures & Buswork | 13476 | 192990 | 219566 | 4031968 | 2594234
29 |  | Grid refurbishment and replacement | AC Stations | ACS Instrument Transformers | 2948897 | 1888745 | 1852274 | 2904788 | 7466464
30 |  | Grid refurbishment and replacement | AC Stations | ACS Disconnectors & E/S | 926142 | 3497 | 0 | 2558001 | 4053061
31 |  | Grid refurbishment and replacement | AC Stations | ACS Other Station Equipment | 799253 | 14238209 | 8882619 | 6254533 | 14283036
32 |  | Grid refurbishment and replacement | AC Stations | ACS Power Cables | 12209 | 5890693 | 4109811 | 30671176 | 31000435
33 |  | Grid refurbishment and replacement | AC Stations | ACS Dynamic Reactive | 1772238 | 3563655 | 6087002 | 5684479 | 5224145
34 |  | Grid refurbishment and replacement | Protection and Metering | SA Metering | 227160 | 67455 | 4648758 | 1868163 | 32932
35 |  | Grid refurbishment and replacement | Protection and Metering | SA BZ Protection | 4286435 | 4992306 | 6153707 | 10697535 | 13859738
36 |  | Grid refurbishment and replacement | Protection and Metering | SA Line Protection | 11222622 | 2965856 | 6269628 | 7089970 | 12306918
37 |  | Grid refurbishment and replacement | Protection and Metering | SA Transformer Protection | 814121 | 1505527 | 3949958 | 3700653 | 7685208
38 |  | Grid refurbishment and replacement | Protection and Metering | SA Batteries & DC Systems | 1898869 | 4660068 | 2615864 | 3583167 | 2130549
39 |  | Grid refurbishment and replacement | Protection and Metering | SA Feeder Protection | 3421893 | 1839267 | 4369033 | 2196741 | 908731
40 |  | Grid refurbishment and replacement | Protection and Metering | SA Substation Mgmt Systems | 12484480 | 12765257 | 16330294 | 8673551 | 5026926
41 |  | Grid refurbishment and replacement | Protection and Metering | SA Special Protection Schemes | -21742 | 634976 | 841541 | 700396 | 403386
| New | Grid refurbishment and replacement | Protection and Metering | SA ODJB |  |  |  |  | 2271262
| New | Grid refurbishment and replacement | Protection and Metering | SA Reactive Asset Protection |  |  |  |  | 1008691
44 |  | Grid refurbishment and replacement | HVDC Stations | HVDC | 2259803 | 8151077 | 21453047 | 24601589 | 24415933
45 |  | Grid refurbishment and replacement | Transmission Lines | TL Paint | 38879163 | 43566111 | 56277714 | 55702469 | 64683855
46 |  | Grid refurbishment and replacement | Transmission Lines | TL Tower | 15329 | 4050412 | 9248928 | 16813227 | 12215756
47 |  | Grid refurbishment and replacement | Transmission Lines | TL Foundation | 4282499 | 3526657 | 7191313 | 17639445 | 12066346
48 |  | Grid refurbishment and replacement | Transmission Lines | TL Grillage | 6815811 | 5693106 | 10688687 | 9074071 | 9111820
49 |  | Grid refurbishment and replacement | Transmission Lines | TL Conductor | 11242023 | 24764385 | 15756868 | 10475871 | 21155083
50 |  | Grid refurbishment and replacement | Transmission Lines | TL Pole | 9614996 | 7869126 | 8745147 | 13564950 | 15766771
51 |  | Grid refurbishment and replacement | Transmission Lines | TL Insulators | 2635922 | 2425272 | 6115445 | 6651104 | 8447468
52 |  | Grid refurbishment and replacement | Transmission Lines | TL Access | 1143414 | 643963 | 8153682 | 1675623 | 3690117
53 |  | Total grid refurbishment and replacement |  |  | 176025394.64 | 210824205.44 | 241832966.76 | 348936574.68 | 331348186
54
55 |  | Grid enhancment and development | Corridor Management program |  | 200036 | 610858 | 0 | 1372219 | 1088217
56 |  | Grid enhancment and development | CP_SNI_AC_00_00 BPE CPK WIL Fire Protection |  | 5460 | 0 | -8450 | 0 | 0
57 |  | Grid enhancment and development | CP_CST_94_00_00 CST 33kV Outdoor to Indoor Conversion |  | 111891 | 19436 | 0 | 0 | 0
58 |  | Grid enhancment and development | CP_NPL_51_00_00 SFD 2nd Interconnector Bld |  | 50763 | 1956 | 0 | 0 | 0
59 |  | Grid enhancment and development | CP_VSA_08_00_00 Waikato and UNI Voltage Management - Shunt Capacitors Stage 1 - HAM & OHW Capacitors |  | 227127 | 298517 | 0 | 0 | 0
60 |  | Grid enhancment and development | CP_VSI_62_00_00 USI Reliability Solution - Stage 2 - Investigation |  | 488266 | 0 | 0 | 0 | 0
61 |  | Grid enhancment and development | CP_HTI_87_00_00 HTI Voltage Constraints - Build TMU Cap Banks |  | 5130581 | 149237 | 512837 | 54084 | 0
62 |  | Grid enhancment and development | CP_RDF_FB_00_00 RDF T3 & T4 Protection Limit SPS pre-contingency loading increased to 160 MVA |  | 413619 | 13787 | 0 | 0 | 0
63 |  | Grid enhancment and development | CP_AVI_66_00_00 AVI-BEN A SPS North Flow |  | 389509 | 0 | 0 | 0 | 0
64 |  | Grid enhancment and development | CP_VTN_13_00_00 BOB 220/110kV Interconnection Transformer - Capex Investigation |  |  | 2172712 | 0 | 0 | 0
65 |  | Grid enhancment and development | CP_VTL_85_00_00 Wairakei Ring transmission capacity - Build - Reactor |  |  | 5401828 | 167160 | 133073 | 0
66 |  | Grid enhancment and development | CP_VTL_95_00_00 NPL-SFD A & CST-NPL A lines junction capex investigation |  |  | 826853 | 0 | 0 | 0
67 |  | Grid enhancment and development | CP_VTL_96_00_00 CST-SFD A Permanent Junction |  |  | 2946938 | 183926 | 0 | 0
68 |  | Grid enhancment and development | CP_TPR_00J_0_00 Digital Substation PAC Inception - initial capital investigation |  |  | 4194928 | 0 | 0 | 0
69 |  | Grid enhancment and development | CP_ISL_01K_0_00 USI High voltage management, ISL Reactor- Install |  |  | 123726 | 606709 | 0 | 0
70 |  | Grid enhancment and development | CP_ISL_001_0_00 USI High voltage management, ISL Reactor - Cap Inv |  |  | 2906416 | 0 | 0 | 0
71 |  | Grid enhancment and development | CP_ISL_002_0_00 USI High voltage management, ISL Reactor- Build |  |  | 1789552 | 0 | 0 | 0
72 |  | Grid enhancment and development | CP_RA1_026_0_00 HEN-MPE A 0160 Slip Deviation Cyclone Gabrielle |  |  | 416537 | 543617 | 0 | 0
73 |  | Grid enhancment and development | CP_VNN_27_00_00 UNI High Voltage Management - Build |  | 0 | 0 | 14444930 | 602270 | 372682
74 |  | Grid enhancment and development | CP_TIM_00U_0_00 TIM Voltage Stability ICT Pre-purchase & Build |  | 0 | 0 | 10058247 | 2017627 | 0
75 |  | Grid enhancment and development | CP_OHW_00F_0_00 OHW Deviation Build |  | 0 | 0 | 7679343 | 0 | 0
76 |  | Grid enhancment and development | CP_627_13_00_00 OTA PEN C Line Deviation and Protection (CAPEX) |  | 0 | 0 | 2093225 | 0 | 3141
77 |  | Grid enhancment and development | CP_SWN_007_0_00 SWN Generator exit - Build |  | 0 | 0 | 2195508 | 0 | 0
78 |  | Grid enhancment and development | CP_VLT_00_00_00 Lichfield-Kinleith A reconductoring - Build |  | 0 | 0 | 1585859 | 157344 | 0
79 |  | Grid enhancment and development | CP_TIM_DB_00_00 TIM voltage support - Capex Investigation |  | 0 | 0 | 482740 | 0 | 0
80 |  | Grid enhancment and development | CP_810_22_00_00 Connection of WMG-WPT A at ORO tee due to WPT substation decommissioning |  | 0 | 0 | 320765 | 0 | 0
81 |  | Grid enhancment and development | CP_811_29_00_00 IGH-WPT B Connection at ORO tee due to WPT Substation decommissioning |  | 0 | 0 | 464137 | 0 | 0
82 |  | Grid enhancment and development | CP_VTL_BD_00_00 WPT ORO lines junctn capex inv |  | 0 | 0 | 250393 | 0 | 0
83 |  | Grid enhancment and development | CP_VAR_1A3_0_00 22/23 U/C Capex Design Project |  | 0 | 0 | 917127 | 0 | 0
84 |  | Grid enhancment and development | CP_VAR_1FZ_0_00 Ohinewai Diversion Inv |  | 0 | 0 | 711761 | 0 | 0
85 |  | Grid enhancment and development | CP_VTL_DK_00_00 National Vegetation |  | 0 | 0 | 394317 | 0 | 0
86 |  | Grid enhancment and development | CP_KAW_FS_00_00 Kawerau interconnection capacity- Build |  | 0 | 0 | 0 | 895268 | 730106
87 |  | Grid enhancment and development | CP_KAW_006_0_00 Kawerau interconnection capacity- Cap Inv |  | 0 | 0 | 0 | 2577 | 0
88 |  | Grid enhancment and development | CP_VNI_35_00_00 AOVCS UNI RPC changes Cap Inv |  | 0 | 0 | 0 | -5420 | 0
89 |  | Grid enhancment and development | CP_651_001_0_00 BHL-OTA Cable Route Designation Extension |  | 0 | 0 | 0 | 114340 | 8501
90 |  | Grid enhancment and development | CP_VTL_79_00_00 Arapuni-Kinleith-Tarukenga transmission capacity - Capex Investigation |  | 0 | 0 | 0 | 3711 | 0
91 |  | Grid enhancment and development | CP_HAM_OR_00_00 Bussing ARI-BOB at Hamilton - Capex Investigation |  | 0 | 0 | 0 | 261820 | 13351
92 |  | Grid enhancment and development | CP_VSI_AQ_00_00 USI Transmission Capacity - Capex Investigation |  | 0 | 0 | 0 | 1245609 | 154586
93 |  | Grid enhancment and development | CP_RDF_EV_00_00 RDF interconnecting capacity - build |  | 0 | 0 | 0 | 11030255 | 2840039
94 |  | Grid enhancment and development | CP_TPR_00G_0_00 Substation Digital PAC - Inception 2, Development 1 and 2 |  | 0 | 0 | 0 | 1143997 | 0
95 |  | Grid enhancment and development | CP_SFD_00U_0_00 Whareroa Electrification (Ohangai GXP) Transpower Build |  | 0 | 0 | 0 | 97430 | 10398606
96 |  | Grid enhancment and development | CP_792_006_0_00 BEN-HAY-A Cross-arm Design and Replacements |  | 0 | 0 | 0 | 140711 | 0
97 |  | Grid enhancment and development | CP_EDG_00Y_0_00 EDG 220/110 kV interconnecting transformer - Cap Inv |  | 0 | 0 | 0 | 273024 | 17434
98 |  | Grid enhancment and development | CP_RDF_00Q_0_00 RDF 220kV Yard Capex Inv |  | 0 | 0 | 0 | 1303875 | 0
99 |  | Grid enhancment and development | CP_RDF_00P_0_00 RDF Interim Resilience |  | 0 | 0 | 0 | 378942 | 559966
100 |  | Grid enhancment and development | CP_HPI_00G_0_00 HPI Advancing Designation Alteration |  | 0 | 0 | 0 | 258006 | 216848
101 |  | Grid enhancment and development | CP_VAR_1T6_0_00 ENC Southland Capex Investigation |  | 0 | 0 | 0 | 433320 | 71665
102 |  | Grid enhancment and development | CP_HAY_SJ_00_00 HVDC cable replacement and capacity increase - capex investigation |  | 0 | 0 | 0 | 5436329 | 0
103 |  | Grid enhancment and development | CP_HAM_OS_00_00 Bussing ARI-BOB at Hamilton - Build |  | 0 | 0 | 0 | 0 | 2291055
104 |  | Grid enhancment and development | CP_EDG_010_0_00 EDG T5 interconnector replacement (new T6) - Build |  | 0 | 0 | 0 | 0 | 4978769
105 |  | Grid enhancment and development | CP_896_00B_0_00 INV-NMA TTU Build |  | 0 | 0 | 0 | 0 | 185099
106 |  | Grid enhancment and development | CP_INV_00W_0_00 INV-NMA TTU Build Substation |  | 0 | 0 | 0 | 0 | 32679
107 |  | Grid enhancment and development | CP_VAR_23Q_0_00 HVDC Control System Upgrade Investigation |  | 0 | 0 | 0 | 0 | 0
|  | Grid enhancment and development | CP_SWN_00G_0_00 SWN Land Purchase Transpower | [5 empty] | 17001706
109 |  | Grid enhancment and development | CP_VAR_1S3_0_00 North Canterbury 66 kV SPS Build |  | 0 | 0 | 0 | 0 | 175727
110 | New | Grid enhancment and development | Resilience program |  | 0 | 0 | 0 | 1514197 | 4389207
111 |  | Grid enhancment and development | Other |  | 98464 | 0 | 2451 | 382016 | 266154
112 |  | Grid enhancment and development | Operating leases (transmisson line) |  | 0 | 0 | 3469576.02 |  | 0
113 | New | Grid enhancment and development | Unapproved MCP: HVDC Cable Replacement and new cable - CRA Cable deposit |  | 0 | 0 | 0 | 18575697 | 0
114 |  | Total grid enhancement and development |  |  | 7115716 | 21873281 | 47076178.02 | 47822321 | 45795538 | Leases are included in Opex as a separate line item on F4(i) from 2025. Leases are captialised with Commissioned Assets.
115 |  | *Insert additional rows and update calculation of totals as needed
116
117 |  | IST | Transmission Systems | IT Transmission Systems | 13446005.82 | 6212577.44 | 9853103.08 | 17102446.26 | 12891148.97
118 |  | IST | Transmission Systems | IT Meter Data Management | 0 | 0 | 0 | 0 | 0
119 |  | IST | Asset Management Systems | IT Asset Management Systems | 371279 | 126246 | 1196150 | 2899047 | 2164357.85
120 |  | IST | Asset Management Systems | IT Outage Management | 7589 | 0 | 0 | 0 | 0
121 |  | IST | Telecommunications | IT Shared Comms Infrastructure | -13987 | 0 | 0 | 0 | 0
122 |  | IST | Telecommunications | IT Subst Comms Infrastructure | 0 | 0 | 0 | 0 | 0
123 |  | IST | Telecommunications | IT Telecommunications Networks | 315 | 0 | 5490879.65 | 20329757.87 | 48587103.031
124 |  | IST | Corporate Systems | IT Stakeholder Management | 0 | 7419277.9 | 0 | 0 | 0
125 |  | IST | Corporate Systems | IT Corporate Systems | 2573515 | 0 | 1789889 | 4143034 | 1064864.635
126 |  | IST | IST Shared Services | IT Enabling Infrastructure | 0 | 2595752 | 0 | 0 | 0
127 |  | IST | IST Shared Services | IT Shared Services | 2909836 | 0 | 2872678 | 3112734 | 1969137.345
128 |  | IST | Security Services | IT Security Infrastructure | 0 | 2624771 | 0 | 0 | 0
129 |  | IST | Security Services | IT Telecoms Network Security | 6328038 | 0 | 0 | 0 | 0
130 |  | IST | Security Services | Transmission Pricing Methodology | 2032566 | 1939856 | 1003838 | 0 | 521415
131 |  | IST | Security Services | Operating leases | 598664 | 923250.4 | 186034.35 |  | 0
132 |  | Total IST |  |  | 28253820.82 | 21841730.74 | 22392572.08 | 47587019.13 | 67198026.831 | Leases are included in Opex as a separate line item on F4(i) from 2025. Leases are captialised with Commissioned Assets.
133
134 |  | Business support | Office buildings and facilities | BS Office buildings and facilities | 21311 | 829670.76 | 686866 | 370784 | 368048.414
135 |  | Business support | Minor Fixed Assets | BS Vehicles | 773459 | 651262 | 1197992 | 2164485 | 2286434
136 |  | Business support | Minor Fixed Assets | BS Office Equipment | 1689250 | 2084513 | 3061363 | 3839823 | 3769094.9231
137 |  | Business support | Spares and inventory | BS Mobile Substation | 0 | 0 | 0 | 0 | 0
138 |  | Business support | Properties | BS Strategic Properties | 0 | 0 | 0 | 3207014 | 0
139 |  | Business support | Other | BS Other | 72152 | 246826 | 0 | 0 | 0
140 |  | Business support | Operating leases | Operating leases | 14768273 | 48035.077 | 4795372.5442
141 |  | Total business support |  |  | 17324445 | 3860306.837 | 9741593.5442 | 9582106 | 6423577.3371 | Leases are included in Opex as a separate line item on F4(i) from 2025. Leases are captialised with Commissioned Assets.
142

## F4. Actuals vs Forecasts
[6 empty] | Transpower |  | Disclosure Date |  | 2026-10-23
SCHEDULE F4: COMPARISON OF FORECASTS FOR OPEX AND BASE CAPEX | [7 empty] | Disclosure Year (year ended) |  | 2026-06-30
Disclosure of line items required from disclosure year 2026 onward are specified in column O.
ref
5
6 | F4(i): Opex
7 |  |  | CY | CY | CY
8 |  |  | Actual | Forecast* | Variance
9 |  |  | ($M) | ($M) | %
10 |  | Grid maintenance | 148310707.95 | 154579933.3472 | -4.056%
11 |  | ICT | 62294449.9231 | 63606822.9204 | -2.063%
12 |  | Asset Management & Operations | 94079841.3551 | 101579287.8699 | -7.383%
13 |  | Business Support | 66450660.9305 | 69655804.2138 | -4.601%
14 |  | Insurance | 30995060.52 | 36777978.0406 | -15.72% | Note 1
15 |  | Total operating expenditure | 402130720.6787 | 426199826.3919 | -5.647%
16
17 |  | Leases expenditure | 12728786 | 11454702.164 | 11.12% |  | Note this has been added as a seperate category as we are now reporting capex on spend basis (not commissioned which included lease additions).
18
19 | F4(ii): Base Capex |  | SPEND BASIS | SPEND BASIS
20 |  |  | CY | CY | CY
21 |  |  | Actual | Forecast* | Variance
22 |  |  | ($M) | ($M) | %
23 |  | Grid - replacement and refurbishment | 331348186 | 377562955.3387 | -12.24% | Note 4
24 |  | Grid - enhancement and development - ACA capacity | 0 | 0 | 0% | [5 empty] | Required from disclosure year 2026
25 |  | Grid - enhancement and development - other | 45795538 | 46033382.1808 | -0.5167% | [5 empty] | Required from disclosure year 2026
26 |  | IST | 67198026.831 | 60038938.2877 | 11.92% | Note 5
27 |  | Business support | 6423577.3371 | 8294518.7892 | -22.56% | Note 6
28 |  | Total base capex expenditure | 450765328.1681 | 491929794.5964 | -8.368%
29 |  |  | *Prior year disclosure of CY forecast nominal value
30
31
32
33 | F4(iii): Opex comparison by expenditure categories
34 |  |  | CY | CY | CY
35 |  |  | Actual | Forecast in RCP Proposal | Variance
36 |  |  | ($M) | ($M) | %
37 |  | Preventive Maintenance | 52017003.8399 | 51246988.7293 | 1.503% | [5 empty] | Required from disclosure year 2026
38 |  | Predictive Maintenance | 86120023.9301 | 95286268.8184 | -9.62% | [5 empty] | Required from disclosure year 2026
39 |  | Corrective Maintenance | 7077966.46 | 5344139.0923 | 32.44% | [5 empty] | Required from disclosure year 2026
40 |  | Proactive Maintenance | 859207.72 | 1199320.2748 | -28.36% | [5 empty] | Required from disclosure year 2026
41 |  | Resilience | 2236506 | 1503216.4325 | 48.78% | [5 empty] | Required from disclosure year 2026
42 |  | Total - Grid maintenance | 148310707.95 | 154579933.3472 | -4.056% | [5 empty] | Required from disclosure year 2026
43
44 |  | ICT Opex | 47330317.6131 | 46830984.7647 | 1.066% | [5 empty] | Required from disclosure year 2026
45 |  | ICT Software as a Service | 14964132.31 | 16775838.1557 | -10.8% | [5 empty] | Required from disclosure year 2026
46 |  | Total - ICT | 62294449.9231 | 63606822.9204 | -2.063% | [5 empty] | Required from disclosure year 2026
47
48 |  | Asset Management & Operations | 93493083.2251 | 101052674.7067 | -7.481% | [5 empty] | Required from disclosure year 2026
49 |  | Sustainability | 586758.13 | 526613.1632 | 11.42% | [5 empty] | Required from disclosure year 2026
50 |  | Total - Asset Management & Operations | 94079841.3551 | 101579287.8699 | -7.383% | [5 empty] | Required from disclosure year 2026
51
52 |  | Business support | 66450660.9305 | 69655804.2138 | -4.601% | [5 empty] | Required from disclosure year 2026
53
54 |  | Insurance | 30995060.52 | 36777978.0406 | -15.72% | [5 empty] | Required from disclosure year 2026
55
56
57 | F4(iv): Base capex comparison by expenditure categories
58 |  |  | CY | CY | CY | CY | CY | CY | CY
59 |  |  | Actual | Forecast in RCP Proposal | Variance | Actual percentage of assets with an AHI between 8 and 10 Actual change in percentage of assets with AHI between 8 and 10. | Forecast percentage of assets with an AHI between 8 and 10 Forecast change in percentage of assets with AHI between 8 and 10. | Variance | CY new asset ratio (including renewals and growth) CY change in percentage of Asset health index = 0.5
60 |  |  | ($M) | ($M) | % |  |  | %
61
62 |  | ACS Power Transformers | 18412478 | 28352223.708 | -35.06% | 3.95% | 5.86% | -1.91% | 2.43% |  | Required from disclosure year 2026
63 |  | ACS Outdoor to Indoor Conv | 4294966 | 19917246.3358 | -78.44% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
64 |  | ACS Buildings & Grounds-Seismic | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
65 |  | ACS Buildings & Grounds | 17063017 | 21717583.0031 | -21.43% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
66 |  | ACS Outdoor Circuit Breakers | 2432701 | 8438800.7449 | -71.17% | 0.3% | 0.37% | -0.07% | 1.7% |  | Required from disclosure year 2026
67 |  | ACS Indoor Switchgear | 7063731 | 11688967.8834 | -39.57% | 0.28% | 0.09% | 0.19% | 2.99% |  | Required from disclosure year 2026
68 |  | ACS Capacitors and Reactors | 272428 | 1303541.7582 | -79.1% | 4.2% | 4.34% | -0.14% | 0.29% |  | Required from disclosure year 2026
69 |  | ACS Structures & Buswork | 2594234 | 11944.183 | 21620% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
70 |  | ACS Instrument Transformers | 7466464 | 13531729.4585 | -44.82% | 0.58% | 1.04% | -0.46% | 2.8% |  | Required from disclosure year 2026
71 |  | ACS Disconnectors & E/S | 4053061 | 9326379.1765 | -56.54% | 15.51% | 20.23% | -4.72% | 0.97% |  | Required from disclosure year 2026
72 |  | ACS Other Station Equipment | 14283036 | 10272146.0791 | 39.05% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
73 |  | ACS Power Cables | 31000435 | 29178248.6557 | 6.245% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
74 |  | ACS Dynamic Reactive | 5224145 | 8574911.0631 | -39.08% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
75 |  | SA Metering | 32932 | 169277.2222 | -80.55% | 0.16% | 0.33% | -0.17% | 6.92% |  | Required from disclosure year 2026
76 |  | SA BZ Protection | 13859738 | 20386768.6737 | -32.02% | 5.97% | 5.72% | 0.25% | 0.54% |  | Required from disclosure year 2026
77 |  | SA Line Protection | 12306918 | 12550116.0694 | -1.938% | 6.56% | 6.17% | 0.39% | 1.88% |  | Required from disclosure year 2026
78 |  | SA Transformer Protection | 7685208 | 5549251.648 | 38.49% | 13.04% | 13.98% | -0.94% | 0.62% |  | Required from disclosure year 2026
79 |  | SA Batteries & DC Systems | 2130549 | 1435858.985 | 48.38% | 6.37% | 4.92% | 1.45% | 7.48% |  | Required from disclosure year 2026
80 |  | SA Feeder Protection | 908731 | 3857352.465 | -76.44% | 10.44% | 12.6% | -2.16% | 4.46% |  | Required from disclosure year 2026
81 |  | SA Special Protection Schemes | 403386 | 994437.1487 | -59.44% | 12.2% | 11.11% | 1.09% | 9.76% |  | Required from disclosure year 2026
82 | New | SA Reactive Asset Protection | 1008691 | 295645.1063 | 241.2% | 4.26% | 10% | -5.74% | 2.13%
83 | New | SA ODJB | 2271262 | 7069056.9597 | -67.87% | 26.22% | 26.07% | 0.15% | 3.63%
84 |  | SA Substation Mgmt Systems | 5026926 | 5396569.2898 | -6.85% | 3.84% | 1.74% | 2.1% | 0.91% |  | Required from disclosure year 2026
85 |  | HVDC | 24415933 | 15328134.7724 | 59.29% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
86 |  | TL Paint | 64683855 | 69162511.7772 | -6.476% | 9.11% | 11.19% | -2.08% | 0.03% | Many repaints, but "new assets" is only counting first paint | Required from disclosure year 2026
87 |  | TL Tower | 12215756 | 14568677.4682 | -16.15% | 0.61% | 0.65% | -0.04% | 0.03% |  | Required from disclosure year 2026
88 |  | TL Foundation | 12066346 | 3121352.0768 | 286.6% | 0.09% | 0.23% | -0.14% | 2.38% |  | Required from disclosure year 2026
89 |  | TL Grillage | 9111820 | 9782071.1145 | -6.852% | 5.84% | 6.98% | -1.14% | 0.42% | Not adding new grillages, all replace with other foundation types. Some "renewed" grillages. | Required from disclosure year 2026
90 |  | TL Conductor | 21155083 | 23485556.0687 | -9.923% | 0.56% | 0.68% | -0.12% | 0.6% |  | Required from disclosure year 2026
91 |  | TL Pole | 15766771 | 13300542.0799 | 18.54% | 0.77% | 1.28% | -0.51% | 2.22% |  | Required from disclosure year 2026
92 |  | TL Insulators | 8447468 | 6565793.074 | 28.66% | 2.36% | 2.77% | -0.41% | 2.46% |  | Required from disclosure year 2026
93 |  | TL Access | 3690117 | 2230261.2897 | 65.46% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
94 |  | Total grid refurbishment and replacement | 331348186 | 377562955.3387 | -12.24% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
95
96 |  | IT SCADA/RTS | 0 | 0 | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
97 |  | IT Time Series | 0 | 0 | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
98 |  | IT Transmission Systems | 12891148.97 | 11969560.4112 | 7.699% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
99 |  | IT Meter Data Management | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
100 |  | IT Asset Management Systems | 2164357.85 | 3256401.6199 | -33.54% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
101 |  | IT Spatial & Drawings | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
102 |  | IT Outage Management | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
103 |  | IT Communication Services | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
104 |  | IT Shared Comms Infrastructure | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
105 |  | IT Subst Comms Infrastructure | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
106 |  | IT Telecommunications Networks | 48587103.031 | 40656968.5676 | 19.5% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
107 |  | IT Stakeholder Management | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
108 |  | IT Corp Info & Doc Mgmt | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
109 |  | IT Safety | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
110 |  | IT Risk/Audit Management | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
111 |  | IT Finance | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
112 |  | IT Human Resources | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
113 |  | IT Corporate Systems | 1064864.635 | 997265.646 | 6.778% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
114 |  | IT Enabling Infrastructure | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
115 |  | IT Service Management | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
116 |  | IT Workforce Mobility | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
117 |  | IT Data Centre | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
|  | IT Shared Services | 1969137.345 | 3158791.8928 | -37.66% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2027
|  | IT Security Infrastructure | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2028
|  | IT Telecoms Network Security | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2029
|  | Transmission Pricing Methodology | 521415 |  | #VALUE! | N/A | N/A | 0% | N/A |  | Required from disclosure year 2030
122 |  | Total IST (excl Lease expenses) | 67198026.831 | 60038988.1375 | 11.92% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
123
124 |  | BS Office buildings and facilities | 368048.414 | 4720882.5992 | -92.2% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
125 |  | BS Vehicles | 2286434 | 896572.4702 | 155% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
126 |  | BS Office Equipment | 3769094.9231 | 2677063.7198 | 40.79% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
127 |  | BS Mobile Substation | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
128 |  | BS Strategic Properties | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
129 |  | BS Other | 0 |  | 0% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
130 |  | Total business support | 6423577.3371 | 8294518.7892 | -22.56% | N/A | N/A | 0% | N/A |  | Required from disclosure year 2026
131
132
133
134 | Opex variance explanations (required for variances greater than 10% or $10 million between actual and forecast opex expenditure)
135
136 | Note 1 | Lower increase in insurance premiums than assumed in the Submission
137
138 | Note 2 | Planned increase in fibre leases (TransGO project) have started earlier than assumed in the Submission
139
140 | Note 3
141
142
143 | Base capex expenditure variance explanations (required for variances greater than 10% or $10 million between actual and forecast base capex expenditure)
144
145 | Note 4 | The 12% lower expenditure in FY2026 compared to forecast, primarily within primary and secondary substation portfolios, is driven by: - Outdoor to Indoor conversions $16 million: Postponement of Maungaturoto ODID due to possible divestment to connected customer; Long lead-times for equipment and Geotech resource has lead to rephasing of Tokaanu ODID, Waipawa ODID being undertaken by connected customer (Centralines); Wellsford ODID deferred until more certainty around customer (Vector) scope, which once decided, the ODID would need to align with other work at the site ( e.g. transformer replacement and protection benchmark work). The Transpower ODID was replaced with managing the existing outdoor yard, due to low feeder numbers and limited safety concerns as a more economic solution. The customer is investigating upgrades to the outdoor yard which may lead to an ODID. - Power transformers $10 million: - Gracefield was replaced in RCP3 due to failure; - Alignment of replacement at Central Park substation with connected customer's (Wellington Electricity) new substation delayed the replacement and T4 was prioritised over T3 for replacement, - cancelling Whanganui T2 replacement and and doing a mid-life refurbishment of Brunswick transformer instead of replacement due to regional planning and consultation with Powerco and the availability of an operational spare phase as redundancy. -Remaining $20 million is primarily within other primary and secondary substation portfolios: Replacements have been rescheduled to later in RCP4 to align with other primary and secondary asset work at similar sites for delivery and outage efficiency, and allow for increased equipment and material lead times as well as complexity from incorporating benchmark agreement criteria. This has impacted Outdoor circuit breakers, instrument transformers and protection work in particular.
146 | Note 5 | 12% Higher expenditure of ICT work is primarily due to the rephasing of the TransGo project with sections of the work program being undertaken earlier than originally anticipated.
147 | Note 6 | 23% Lower expenditure on Business Support capex due to the upgrade to our Grid Skills facility being undertaken in FY27 ($4.4 million), offset by higher than anticipated costs to replace IST equipment $1.1 million and earlier procurement of motor vehicles $1.4 million.
148
149 | Base capex variance interpretations (adjusted interpretation of asset health metrics added in 2026)
150
151 | Note 8 | Actual change in percentage of assets with AHI between 8 and 10 interpreted as Actual percentage of assets with AHI between 8 and 10 This adjustment simplifies interpretation, while still allowing the change to be worked out by comparing the numbers from this schedule between years
152 | Note 9 | Forecast change in percentage of assets with AHI between 8 and 10 interpreted as Forecast percentage of assets with AHI between 8 and 10 This adjustment simplifies interpretation, while still allowing the change to be worked out by comparing the numbers from this schedule between years. Forecast is as at end of previous FY forecasting end of reporting FY
153 | Note 10 | CY change in percentage of Asset health index = 0.5 interpreted as New asset ratio (including renewals and growth) Agreed with Commerce Commission as a good metric of volume of work being done on the fleet.
154
155
156
157

## F5. Major Capex Projects
[15 empty] | Transpower |  | Disclosure Date |  | 2026-10-23
SCHEDULE F5: MAJOR CAPITAL EXPENDITURE (MAJOR CAPEX) | [16 empty] | Disclosure Year (year ended) |  | 2026-06-30
ref
5 | F5(i): Major Capex Projects (Summary): Approved But Not Yet Commissioned
6
7 |  |  |  | Initial Project Approvals | [8 empty] | Amendments to Approved Projects
8 |  |  |  | Approved MCP Outputs | Major Capex Allowance | Max. Recoverable costs | Recovery Scheme |  | Commissioning Date(s) | P50 | Approval Expiry Date | Completion date Assumption | Major Capex Allowance | Max. Recoverable costs | Recovery Scheme | P50 | Approval Expiry Date | Completion Date Assumption | Approved MCP Outputs
9 |  |  | Project Name |  | ($M) | ($M) |  |  |  | ($M) |  |  | ($M) | ($M) |  | ($M)
10 |  |  | Stage 1 - Waikato and Upper North Island Voltage Management | 1) one dynamic reactive device in the Upper North Island capable of delivering (within 10%) 150 Mvar capacitive to 150 Mvar inductive at nominal voltage 2) one dynamic reactive device in the Waikato capable of delivering (within 10%) 150 Mvar capacitive to 150 Mvar inductive at nominal voltage 3) a post-fault demand management scheme for the Waikato Upper North Island region 4) preparatory works for Stage 2, including additional investigation, consultation, obtaining property rights and environmental approvals, design work and non-binding tendering for future series capacitors and installation works on the BrownhillWhakamaru 1&2 transmission lines (BHL-WKM lines) | 143000000 | n/a | Capex |  | Dec 2022 (except for Stage 2 preparatory works) | 143000000 | 2029-12-01 | Dec 2022 (except for Stage 2 preparatory works)
11 |  |  | Net Zero Grid Pathways stage 1 | HVDC upgrade – increasing transfer capacity from 1071 MW to closer to 1200 MW by installing: 1) reactive plant; 2) filter banks; and 3) associated equipment to upgrade the HVDC. Central North Island upgrade - increasing transfer capacity north from Bunnythorpe by between 60% and 90% by: 1)installing variable line rating and tactical thermal upgrade of the Tokaanu-Whakamaru and the Bunnythorpe-Tokaanu circuits; 2) duplexing the Tokaanu-Whakamaru circuits with Goat conductor; 3) splitting the Bunnythorpe-Ongarue circuit; 4) upgrading protection on the Huntly-Stratford circuit; and 5) replacing special protection scheme at Tokaanu. Wairakei ring upgrade - increasing transmission capacity by 25% (300 MW) under typical operating conditions by: 1) tactical thermal upgrade of both circuits of the WairakeiWhakamaru C line; 2) a tactical thermal upgrade of the Edgecumbe-Kawerau 3 circuit on the Ohakuri-Edgecumbe A and Kawerau-Deviation lines; and 3) splitting the Edgecumbe-Kawerau circuit. NZGP1 stage two preparatory work to: - carry out a detailed design of duplex Bunnythorpe-Tokaanu A and B lines; - carry out a detailed design for tactical thermal upgrade of Bunnythorpe-Wairakei A line; - investigate options for reconductoring one of the two 200 kV Brunswick-Stratford lines; - develop quantifying resilience methodology; - carry out a study on diversification of Bunnythorpe substation; - carry out a study on lower North Island voltage stability; and - carry out a study on lower North Island system stability. | 392900000 | n/a | Capex |  | Various | 392900000 | 2035-12-31 | 2028-06-30 | 0 | 0
12 |  |  | Western Bay of Plenty | $83.2m for the enhancement of the WBOP transmission grid, namely: Western corridor - Kaitemako: - install a new 220kV/110kV interconnecting transformer at Kaitemako; Western corridor - Reconductoring: - reconductor the interconnection section of the Kaitemako-Tauranga 110kV line to a rating of 200MVA; Eastern corridor - reconductor the Okere-Te Matai, Okere-Tarukenga, and Kaitemako-Te Matai 110kV lines to a rating of 195 MVA; and Potential non-transmission solution (NTS) - $2.9m to fund NTS. Refer to Final Decision WBOP MCP 11 June 2025 "treat the capital cost contingency risk component of the MCA, and the development NTS recoverable cost component, as exempt major capex, equal to $12.5 million ($ nominal)" | 86100000 | n/a | Capex |  | Various | 86100000 | 2037-12-31 | 2032-12-31
13 |  |  | Redclyffe 220kV Switchyard Resilience | - Raising the height of critical HV plant - Installing new 220 kV electrical equipment including circuit breakers, disconnectors, busbars rigid and strung, current transformers (CTs), capacitive voltage transformers (CVTs) and outdoor junction boxes. - Building a digital substation control building | 47000000 | n/a | Capex |  | 2027-12-01 | 47000000 | 2032-12-31 | 2027-12-01
14 |  |  | HVDC Link Upgrade Programme Stage 1 | - procure, install, and commission four new HVDC submarine cables, increasing the HVDC link’s transfer capacity north from 1200 MW to around 1400 MW; - construct and commission new cable termination stations and associated equipment located at Oteranga Bay (North Island) and Ōraumoa Fighting Bay (South Island), along with necessary modifications to the existing overhead line connections; - procure, construct, and commission an additional filter bank at Benmore substation to facilitate continuous operation at the increased capacity of around 1400 MW; - works to increase the Pole 2 overload capacity at Haywards and Benmore; - construct and commission a new submarine cable storage facility and associated infrastructure and equipment to house spare cable lengths for future maintenance and repairs; and - preparatory work for a potential Stage 2, including early engagement with vendors and suppliers to refine scope and confirm cost estimates for anticipated future stage projects. | 1138600000 | n/a | Capex |  | 2031-12-01 | 1138600000 | 2036-12-31 | 2031-12-01
15 |  |  | [insert project]
16 |  |  | [insert project]
17
18 | F5(ii): Major Capex Projects (Detail): Approved But Not Yet Commissioned*
19 |  | *Insert additional tables as required for projects
20 |  |  |  |  | CY-4 + previous | CY-3 | CY-2 | CY-1 | CY | CY+1 | CY+2 | CY+3 | CY+4 | CY+5 | CY+6 | CY+7 | CY+8 | Total
21 |  |  |  |  | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
22 |  | Project name | Stage 1 - Waikato and Upper North Island Voltage Management | Forecast Expenditure | 120139439.4665 | 22892086.324 | 95919.4824 | 0 | 0 | [8 empty] | 143127445.2729
23 |  |  |  | Actual Expenditure | 29044549 | 16658094 | 25468587 | 25253307 | 7660072 | [8 empty] | 104084609
24 |  |  |  | Variance | 91094890.4665 | 6233992.324 | -25372667.5176 | -25253307 | -7660072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39042836.2729
25
26 |  |  |  |  | CY-4 + previous | CY-3 | CY-2 | CY-1 | CY | CY+1 | CY+2 | CY+3 | CY+4 | CY+5 | CY+6 | CY+7 | CY+8 | Total
27 |  |  |  |  | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
28 |  | Project name | Net Zero Grid Pathways stage 1 | Forecast Expenditure | 11550 | 1663743 | 11558970 | 30586642 | 62336009 | 74376298 | 81114742 | 109771515 | 21480531 | 0 | 0 |  |  | 392900000
29 |  |  |  | Actual Expenditure | 0 | 0 | 11563060 | 28769904 | 68737726 | [8 empty] | 109070690
30 |  |  |  | Variance | 11550 | 1663743 | -4090 | 1816738 | -6401717 | 74376298 | 81114742 | 109771515 | 21480531 | 0 | 0 | 0 | 0 | 283829310
31
32 |  |  |  |  | CY-4 + previous | CY-3 | CY-2 | CY-1 | CY | CY+1 | CY+2 | CY+3 | CY+4 | CY+5 | CY+6 | CY+7 | CY+8 | Total
33 |  |  |  |  | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
34 |  | Project name | Western Bay of Plenty - (Excluding approved NTS recoverable cost of $2.9m) | Forecast Expenditure |  |  |  | 315000 | 315000 | 3943000 | 10489000 | 12616000 | 22669000 | 21683000 | 9787000 | 1662000 |  | 83479000
35 |  |  |  | Actual Expenditure |  |  |  | 1538687 | 1449169 | [8 empty] | 2987856
36 |  |  |  | Variance | 0 | 0 | 0 | -1223687 | -1134169 | 3943000 | 10489000 | 12616000 | 22669000 | 21683000 | 9787000 | 1662000 | 0 | 80491144
37
38 |  |  |  |  | CY-4 + previous | CY-3 | CY-2 | CY-1 | CY | CY+1 | CY+2 | CY+3 | CY+4 | CY+5 | CY+6 | CY+7 | CY+8 | Total
39 |  |  |  |  | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
40 |  |  |  |  | CY-4 + previous | CY-3 | CY-2 | CY-1 | CY | CY+1 | CY+2 | CY+3 | CY+4 | CY+5 | CY+6 | CY+7 | CY+8 | Total
41 |  |  |  |  | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
42 |  | Project name | Redclyffe 220kV Switchyard Resilience | Forecast Expenditure |  |  |  | 700000 | 17200000 | 29100000 | [7 empty] | 47000000
43 |  |  |  | Actual Expenditure |  |  |  |  | 3495941 | [8 empty] | 3495941
44 |  |  |  | Variance | 0 | 0 | 0 | 700000 | 13704059 | 29100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43504059
45
46 |  |  |  |  | CY-4 + previous | CY-3 | CY-2 | CY-1 | CY | CY+1 | CY+2 | CY+3 | CY+4 | CY+5 | CY+6 | CY+7 | CY+8 | Total
47 |  |  |  |  | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
48 |  | Project name | HVDC Link Upgrade Programme Stage 1 | Forecast Expenditure |  |  |  | 27300000 | 69300000 | 45600000 | 73000000 | 210000000 | 227400000 | 485950000 |  |  |  | 1138550000
49 |  |  |  | Actual Expenditure |  |  |  | 24012026 | 16076288 | [8 empty] | 40088314
50 |  |  |  | Variance | 0 | 0 | 0 | 3287974 | 53223712 | 45600000 | 73000000 | 210000000 | 227400000 | 485950000 | 0 | 0 | 0 | 1098461686
51
52 |  |  |  |  | CY-4 + previous | CY-3 | CY-2 | CY-1 | CY | CY+1 | CY+2 | CY+3 | CY+4 | CY+5 | CY+6 | CY+7 | CY+8 | Total
53 |  |  |  |  | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
54 |  | Project name | [insert project] | Forecast Expenditure | [13 empty] | 0
55 |  |  |  | Actual Expenditure | [13 empty] | 0
56 |  |  |  | Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57
58 |  |  |  |  | CY-4 + previous | CY-3 | CY-2 | CY-1 | CY | CY+1 | CY+2 | CY+3 | CY+4 | CY+5 | CY+6 | CY+7 | CY+8 | Total
59 |  |  |  |  | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M) | ($M)
60 |  | Project name | [insert project] | Forecast Expenditure | [13 empty] | 0
61 |  |  |  | Actual Expenditure | [13 empty] | 0
62 |  |  |  | Variance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63
64 | F5(iii): Future Major Capex Projects Under Consideration: Not Yet Approved
65
66 |  |  | Project Name | Project Description |  |  | Estimated cost ($M) | Estimated Start Date | Estimated Commissioning Date | Purpose/Benefits of Project
67 |  |  | USI Stage 1 MCP | Upper South Island Grid Upgrade stage 1 |  |  | 193000000 | TBC (Pending NTS, consulting, etc) | 2030-12-31 | To maintain reliable electricity supply to the Upper South Island by addressing forecast transmission capacity and voltage stability constraints as electricity demand grows
68 |  |  | [insert project] | There were no other MCPs that were submitted to the Commission (under consideration) for approval as at 30 June 2026
69 |  |  | [insert project]
70
71
72 | F5(iv): Commissioned Major Capex Projects | [15 empty] | Required from disclosure year 2026
73 |  |  |  |  | Value of Commissioned Assets | [5 empty] | Commissiong Dates |  |  |  | Project Outputs |  | Major Capex Adjustments
74 |  |  | Project Name | Project Description | Expected (P50) ($M) | MCA ($M) | Adjusted MCA ($M) | Actual Cost ($M) | Variance v adjusted MCA ($M) | Material Change in Value? (y/n) | Approved Date | Actual Date | Variance (months) | Material Change in Date? (y/n) | Variance to approved outputs? (y/n) | Material Variance? (y/n) | Incentive rate % | Exempt major capex ($M) | Major capex expenditure adjustment
75 |  |  | Project Outputs
76 |  |  | See schedule TP4 | [7 empty] | See schedule TP4 | See schedule TP4 | See schedule TP4 | See schedule TP4 | See schedule TP4 | See schedule TP4
77
78 |  |  |  |  | Value of Commissioned Assets | [5 empty] | Commissiong Dates |  |  |  | Project Outputs |  | Major Capex Adjustments
79 |  |  | Project Name | Project Description | Expected (P50) ($M) | MCA ($M) | Adjusted MCA ($M) | Actual Cost ($M) | Variance v adjusted MCA ($M) | Material Change in Value? (y/n) | Approved Date | Actual Date | Variance (months) | Material Change in Date? (y/n) | Variance to approved outputs? (y/n) | Material Variance? (y/n) | Incentive rate % | Exempt major capex ($M) | Major capex expenditure adjustment
80 |  |  | Project Outputs
81 |  |  | See schedule TP4 | [7 empty] | See schedule TP4 | See schedule TP4 | See schedule TP4 | See schedule TP4 | See schedule TP4 | See schedule TP4
82

## F6. Revenues
[8 empty] | Transpower |  | Disclosure Date |  | 2026-10-23
SCHEDULE F6: REGULATED REVENUE | [9 empty] | Disclosure Year (year ended) |  | 2026-06-30
Regulated revenue is received in Pricing Years, ending on 31 March each year. For example, the pricing year corresponding to the 30 June 2024 disclosure year is the pricing year ended 31 March 2024. All revenue numbers here are stated in pricing years, except where indicated.
ref
5 | F6(i): Regulated Electricity Transmission Revenue
6 |  |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
7 |  |  |  |  | ($M) | ($M) | ($M) | ($M) | ($M)
8 |  |  | HVAC - Interconnection (excl. EV) |  | 604814791.8 | 613546718.02 | [19 empty] | Not required from disclosure year 2029
9 |  |  | HVAC - NEA and PDA income |  | 2555722.3106 | 2555722 | [19 empty] | Not required from disclosure year 2029
10 |  |  | HVAC - Connection (excl.EV) |  | 112834125.69 | 123570620.82 | [19 empty] | Not required from disclosure year 2029
11 |  |  | HVAC - EV adjustment |  | -21429212.64 | -24219180.24 | [19 empty] | Not required from disclosure year 2029
12 |  |  | HVDC - NEA and PDA income |  | 491017.6894 | 491017.6894
13 |  |  | HVDC (excl. EV) |  | 93503907.12 | 92684583.76 | [19 empty] | Not required from disclosure year 2029
14 |  |  | HVDC - EV adjustment |  | -1413568.8 | -632608.96 | [19 empty] | Not required from disclosure year 2029
15 |  |  | Connection charge |  |  |  | 117347730.42 | 125579318.13 | 150770315.68
16 |  |  | Benefits-based charge |  |  |  | 256192595.84 | 266721155.27 | 304579826.71
17 |  |  | Residual charge |  |  |  | 468224196.22 | 476566592.19 | 474950056.08
18 |  |  | Transitional cap (charge) |  |  |  | 1420055.04 | -625.18 | -1468.56
19 |  |  | EV Adjustment |  |  |  | -24668816.76 | -24932460 | 44696844
20 |  |  | Other regulated transmission revenue |  | 9752516.03 | 22133254.72 | 8590990.0455 | 10951283.2296 | 6799314.042
21 |  |  | Total regulated electricity transmission revenue |  | 801109299.2 | 830130127.8094 | 827106750.8055 | 854885263.6396 | 981794887.952
22
23
24 | F6(ii): Regulated Revenue
25
26
27 |  | Total Revenue (CY)
28 |  |  |  |  | Connection charge ($M) | Benefits-based charge ($M) | Residual charge ($M) | Transitional cap (charge) ($M) | Other regulated transmission revenue ($M) | Total Revenue ($M) | EV adjustment ($M) | TOTAL ($M) | Offtake quantities (MWH) | Injection quantities (MWH)
29 |  |  |  | Distributor | 10322413.93 | 20018363.58 | 57401886.12 | -371400.12 |  | 87371263.51 | 0 | 87371263.51 | 31528961.2 | 1466837.8
30 |  |  |  | Direct Connect | 99967310.02 | 169554665.49 | 455292636.24 | 320708.28 |  | 725135320.03 | 0 | 725135320.03 | 6444333 | 283090.4
31 |  |  |  | Generator | 40480591.73 | 115006797.64 | 6952377.72 | 49223.28 |  | 162488990.37 | 0 | 162488990.37 | 103493.5 | 37797604.8
32 |  |  |  | Other |  |  | -44696844 |  | 6799314.042 | -37897529.958 | 44696844 | 6799314.042
33 |  |  |  | Grand Total | 150770315.68 | 304579826.71 | 474950056.08 | -1468.56 | 6799314.042 | 937098043.952 | 44696844 | 981794887.952 | 38076787.7 | 39547533
34
35
36
37
38 | F6(iii): Customer Charges
39 |  |  | The customer charges shown must include all charges irrespective of the form of the contract
40 | [7 empty] | Current Year Charges (CY) | [8 empty] | Current Year +1 (CY+1) Charges
41 | [8 empty] | Required from disclosure year 2026 |  | Required from disclosure year 2026 |  |  |  | Required from disclosure year 2026 |  |  | Required from disclosure year 2026 |  | Required from disclosure year 2026 |  |  |  | Required from disclosure year 2026
42 |  |  |  | Customer Code | Customer Name | Location Code | Location Name | Connection Charge ($M) | ACA portion of Connection charge ($M) | Benefits-based charge ($M) | ACA portion of Benefits-based charge ($M) | Residual charge ($M) | Transitional cap (charge) ($M) | Investment Contract Charge ($M) | ACA portion of Investment Contract Charge ($M) | Total Charges ($M) | Connection Charge ($M) | ACA portion of Connection charge ($M) | Benefits-based charge ($M) | ACA portion of Benefits-based charge ($M) | Residual charge ($M) | Transitional cap (charge) ($M) | Investment Contract Charges ($M) | ACA portion of Investment Contract Charges ($M) | Total Charges ($M)
43 |  |  |  | ALPE | Alpine Energy Ltd | ABY011S1 | Albury | 527527.44 |  | 13817.89 |  | 290477.64 |  |  |  | 831822.97 | 504374.79 |  | 32482.07 |  | 352984.71 | 0 |  |  | 889841.57 |  | 352984710000 | 0 | 889841570000.0001
44 |  |  |  | ALPE | Alpine Energy Ltd | BPD110S1 | Bells Pond | 12331.08 |  | 126085.25 |  | 621791.88 |  | 89193.27 |  | 849401.48 | 21752.91 |  | 136882.51 |  | 773562.23 | 0 | 89193.27 |  | 1021390.92
45 |  |  |  | ALPE | Alpine Energy Ltd | STU011S1 | Studholme | 227586.84 |  | 181931.71 |  | 798883.8 |  |  |  | 1208402.35 | 245088.02 |  | 196233.14 |  | 985102.71 | 0 |  |  | 1426423.87
46 |  |  |  | ALPE | Alpine Energy Ltd | TKA033S1 | Tekapo A | 322332.63 |  | 66237.81 |  | 249566.4 |  | 102268.2 |  | 740405.04 | 357148.38 |  | 86623.44 |  | 297909.08 | 0 | 102268.2 |  | 843949.1
47 |  |  |  | ALPE | Alpine Energy Ltd | TMK033S1 | Temuka | 1265350.56 |  | 642034.06 |  | 3548619.36 |  | 46776.6 |  | 5502780.58 | 1368454.78 |  | 930591.46 |  | 4382267.58 | 0 | 46776.6 |  | 6728090.42
48 |  |  |  | ALPE | Alpine Energy Ltd | TIM011S1 | Timaru | 590713.68 |  | 1104840.32 |  | 4466750.64 |  | 1240566.24 |  | 7402870.88 | 638099.14 |  | 1470642.68 |  | 5488787.02 | 0 | 1240566.24 |  | 8838095.08
49 |  |  |  | ALPE | Alpine Energy Ltd | TWZ033S1/TWZ033S3 | Twizel | 243549.96 |  | 40672.82 |  | 189430.2 |  |  |  | 473652.98 | 298008.15 |  | 42290.62 |  | 236574.86 | 0 |  |  | 576873.63
50 |  |  |  | ALPE | Alpine Energy Ltd | N/A | All Locations |  |  | 0 |  |  | 6655.92 | 1277.52 |  | 7933.44 | [6 empty] | 1277.52 |  | 1277.52
51 |  |  |  | BUEL | Buller Electricity Ltd | ORO110S1 | Orowaiti Tee | 1722597.48 |  | 225821.88 |  | 659747.16 |  |  |  | 2608166.52 | 1865395.5 |  | 271429.13 |  | 809968.04 | 0 |  |  | 2946792.67
52 |  |  |  | BUEL | Buller Electricity Ltd | N/A | All Locations |  |  | 0 |  |  | 443.76 |  |  | 443.76 | [8 empty] | 0
53 |  |  |  | CHBP | Centralines Limited | WPW011S1/WPW033S1 | Waipawa | 561072.84 |  | 689212.87 |  | 1309907.28 |  |  |  | 2560192.99 | 607360.49 |  | 767578.71 |  | 1634258.78 | 0 | 130211.3743 |  | 3139409.3543
54 |  |  |  | CHBP | Centralines Limited | N/A | All Locations |  |  | 0 |  |  | 901.68 |  |  | 901.68 | [8 empty] | 0
55 |  |  |  | CHHE | Oji Fibre Solutions (NZ) Ltd | KAW011S1/SA/S2 | Kawerau | 830415.97 |  | 256206.22 |  |  |  | 254370.69 |  | 1340992.88 | 892676.58 |  | 316119 |  | 0 | 0 | 254370.69 |  | 1463166.27
56 |  |  |  | CHHE | Oji Fibre Solutions (NZ) Ltd | N/A | All Locations | 0 |  |  |  |  | 75.12 |  |  | 75.12 | [8 empty] | 0
57 |  |  |  | COUP | Counties Energy Ltd | BOB033S1/BOB110S1 | Bombay | 185794.44 |  | 3806935.52 |  | 6285329.04 |  | 224242.92 |  | 10502301.92 | 259128.47 |  | 4062546.17 |  | 8047280.33 | 0 | 224242.92 |  | 12593197.89
58 |  |  |  | COUP | Counties Energy Ltd | GLN033SA/GLN033S3 | Glenbrook | 820908.24 |  | 855841.19 |  | 2176402.68 |  |  |  | 3853152.11 | 921576.73 |  | 959425.92 |  | 2735622.43 | 0 |  |  | 4616625.08
59 |  |  |  | COUP | Counties Energy Ltd | N/A | All Locations |  |  | 0 |  |  | 6704.52 |  |  | 6704.52 | [8 empty] | 0
60 |  |  |  | CTCT | Contact Energy Limited | CYD033S1 | Clyde | 512053.2 |  | 9963251.51 |  | 377649.36 |  |  |  | 10852954.07 | 554027.7 |  | 10443484.24 |  | 435538.11 | 0 |  |  | 11433050.05
61 |  |  |  | CTCT | Contact Energy Limited | N/A | Ohaaki | 1911238.68 |  | 757489.64 |  | 112120.32 |  |  |  | 2780848.64 | 2044606.77 |  | 846902.75 |  | 145236.73 | 0 |  |  | 3036746.25
62 |  |  |  | CTCT | Contact Energy Limited | OTA022S1 | Otahuhu A | [8 empty] | 0 | [8 empty] | 0
63 |  |  |  | CTCT | Contact Energy Limited | N/A | Poihipi | 304759.8 |  | 930179.55 |  | 16251.48 |  |  |  | 1251190.83 | 325363.71 |  | 1034532.82 |  | 21854.34 | 0 |  |  | 1381750.87
64 |  |  |  | CTCT | Contact Energy Limited | N/A | Roxburgh | 285442.92 |  | 7057193.24 |  | 5.4 |  |  |  | 7342641.56 | 308502.49 |  | 7185075.1 |  | 0 | 0 |  |  | 7493577.59
65 |  |  |  | CTCT | Contact Energy Limited | SFD033S1 | Stratford | 174106.2 |  | 2914906.86 |  | 560983.8 |  |  |  | 3649996.86 | 187879.08 |  | 3355516.16 |  | 765418.22 | 0 |  |  | 4308813.46
66 |  |  |  | CTCT | Contact Energy Limited | TAB033S1 | Tauhara B | 135913.43 |  | 1282613.4 |  |  |  | 2802874.56 |  | 4221401.39 | 157218.57 |  | 1266933.56 |  | 0 | 0 | 2802874.56 |  | 4227026.69
67 |  |  |  | CTCT | Contact Energy Limited | TWH033S1 | Te Kowhai |  |  | 37090.92 | [5 empty] | 37090.92 | 0 |  | 48333.69 |  | 0 | 0 |  |  | 48333.69
68 |  |  |  | CTCT | Contact Energy Limited | N/A | Te Mihi | 220282.44 |  | 3151297.07 |  | 16138.56 |  | 1925726.76 |  | 5313444.83 | 240988.35 |  | 3525007.97 |  | 14110.68 | 0 | 1925726.76 |  | 5705833.76
69 |  |  |  | CTCT | Contact Energy Limited | WRK033S1 | Wairakei | 75589.2 |  | 2555199.36 |  | 7606.68 |  |  |  | 2638395.24 | 81702.18 |  | 2853110.31 |  | 9464.48 | 0 |  |  | 2944276.97
70 |  |  |  | CTCT | Contact Energy Limited | WHI011SA | Whirinaki | 72914.28 |  | 44333.69 |  | 268841.28 |  |  |  | 386089.25 | 78646.16 |  | 44310.9 |  | 329191.78 | 0 |  |  | 452148.84
71 |  |  |  | CTCT | Contact Energy Limited | N/A | All Locations |  |  | 0 |  |  | 12481.92 | 85213.89 |  | 97695.81 | [6 empty] | 85213.89 |  | 85213.89
72 |  |  |  | DUNE | Aurora Energy Limited | CYD033S1 | Clyde | 990436.32 |  | 49597.39 |  | 1351988.16 |  |  |  | 2392021.87 | 1067778.23 |  | 61119.59 |  | 1683194.04 | 0 |  |  | 2812091.86
73 |  |  |  | DUNE | Aurora Energy Limited | CML033S1 | Cromwell | 435589.56 |  | 411541.84 |  | 2925429.12 |  | 375435.48 |  | 4147996 | 480187.46 |  | 430078.23 |  | 3684433.47 | 0 | 375435.48 |  | 4970134.64
74 |  |  |  | DUNE | Aurora Energy Limited | FKN033S1/S2 | Frankton | 2005942.08 |  | 810373.67 |  | 3709387.92 |  | 321991.08 |  | 6847694.75 | 1941218.11 |  | 836375.88 |  | 4511351.47 | 0 | 321991.08 |  | 7610936.54
75 |  |  |  | DUNE | Aurora Energy Limited | HWB033S1/S2 | Halfway Bush | 968550.84 |  | 842468.94 |  | 7397840.04 |  |  |  | 9208859.82 | 1042587.79 |  | 888962.36 |  | 8917503.32 | 0 |  |  | 10849053.47
76 |  |  |  | DUNE | Aurora Energy Limited | SDN033S1 | South Dunedin | 2232889.44 |  | 818229.39 |  | 4554330.72 |  | 45446.16 |  | 7650895.71 | 2406674.71 |  | 858849.33 |  | 5668547.38 | 0 | 45446.16 |  | 8979517.58
77 |  |  |  | DUNE | Aurora Energy Limited | N/A | All Locations |  |  | 0 |  |  | 12783.48 |  |  | 12783.48 | [8 empty] | 0
78 |  |  |  | EASH | EA Networks | ASB066SA | Ashburton | 358601.04 |  | 1662178.11 |  | 10554011.76 |  | 57524.04 |  | 12632314.95 | 384901.16 |  | 1836634.63 |  | 12894068.74 | 0 | 57524.04 |  | 15173128.57
79 |  |  |  | EASH | EA Networks | N/A | All Locations |  |  | 0 |  |  | 6558.48 | 4241.39 |  | 10799.87 | [6 empty] | 4241.39 |  | 4241.39
80 |  |  |  | EAST | Firstlight Network Limited | TUI110S2 | Tuai | 402519.48 |  | 1008157.81 |  | 3818249.76 |  | 85358.52 |  | 5314285.57 | 451629.56 |  | 1103187.95 |  | 4751729.92 | 0 | 85358.52 |  | 6391905.95
81 |  |  |  | EAST | Firstlight Network Limited | N/A | All Locations |  |  | 0 |  |  | 2428.44 |  |  | 2428.44 | [8 empty] | 0
82 |  |  |  | GENE | Genesis Energy Ltd | HLY033SA | Huntly | 183312.36 |  | 5069011.96 |  | 3263.16 |  |  |  | 5255587.48 | 198179.8 |  | 6494767.81 |  | 80283.93 | 0 |  |  | 6773231.54
83 |  |  |  | GENE | Genesis Energy Ltd | RPO220I1 | Rangipo | 1226577.48 |  | 1490992.78 | [5 empty] | 2717570.26 | 1322978.35 |  | 1652989.13 |  | 0 | 0 |  |  | 2975967.48
84 |  |  |  | GENE | Genesis Energy Ltd | TKA033S1 | Tekapo A | 916367.3 |  | 468889.68 |  | 18525 |  |  |  | 1403781.98 | 1199228.17 |  | 536283.41 |  | 23059.28 | 0 |  |  | 1758570.86
85 |  |  |  | GENE | Genesis Energy Ltd | TKA033S2 | Tekapo B | 768952.68 |  | 3763646.01 |  | 13.44 |  |  |  | 4532612.13 | 828663.77 |  | 4093735.05 |  | 0 | 0 |  |  | 4922398.82
86 |  |  |  | GENE | Genesis Energy Ltd | TKU033S1 | Tokaanu | 1638951.6 |  | 2011941.5 |  | 798838.92 |  |  |  | 4449732.02 | 1801590.09 |  | 2243565.41 |  | 837663.5 | 0 |  |  | 4882819
87 |  |  |  | GENE | Genesis Energy Ltd | TUI110S2 | Tuai | 167960.4 |  | 1218562.49 |  | 142.8 |  |  |  | 1386665.69 | 181428.54 |  | 1179886.54 |  | 188.24 | 0 |  |  | 1361503.32
88 |  |  |  | GENE | Genesis Energy Ltd | N/A | All Locations | 0 |  | 0 |  |  | 4443.84 | 25853.46 |  | 30297.3 | [6 empty] | 25853.46 |  | 25853.46
89 |  |  |  | HORO | Electra Limited | MHO033S1 | Mangahao | 1632752.64 |  | 356545.05 |  | 2908359.48 |  | 108864.24 |  | 5006521.41 | 1769899.41 |  | 408083.43 |  | 3631659.93 | 0 | 108864.24 |  | 5918507.01
90 |  |  |  | HORO | Electra Limited | PRM033S1 | Paraparaumu | 471545.4 |  | 1179579.54 |  | 4190454.6 |  | 658579.68 |  | 6500159.22 | 507463.36 |  | 1321262.61 |  | 5187329.69 | 0 | 658579.68 |  | 7674635.34
91 |  |  |  | HORO | Electra Limited | N/A | All Locations |  |  | 0 |  |  | 4552.8 |  |  | 4552.8 | [8 empty] | 0
92 |  |  |  | HRZE | Horizon Energy Distribution Ltd | EDG033S1 | Edgecumbe | 518916.72 |  | 745976.46 |  | 3946899.48 |  |  |  | 5211792.66 | 559205.01 |  | 927714.14 |  | 4913754.59 | 0 |  |  | 6400673.74
93 |  |  |  | HRZE | Horizon Energy Distribution Ltd | KAW011S1/SA/S2 | Kawerau | 565676.34 |  | 54805.62 |  | 1336035.36 |  |  |  | 1956517.32 | 611705.08 |  | 91608.92 |  | 1678630.32 | 0 |  |  | 2381944.32
94 |  |  |  | HRZE | Horizon Energy Distribution Ltd | N/A | All Locations | 0 |  | 0 |  |  | 3598.44 | 18488.73 |  | 22087.17 | [6 empty] | 274509.9802 |  | 274509.9802
95 |  |  |  | HRZE | Horizon Energy Distribution Ltd | WAI011S1/WAI005S1 | Waiotahe | 237118.76 |  | 160409.36 |  | 667509.36 |  |  |  | 1065037.48 | 428925.51 |  | 187814.23 |  | 854954.57 |  |  |  | 1471694.31
96 |  |  |  | KIWI | Whareroa Cogeneration Limited | HWA033S1/HWA033S2 | Hawera | 160679.52 |  | 270590.24 |  | 1648772.64 |  |  |  | 2080042.4 | [8 empty] | 0
97 |  |  |  | KIWI | Whareroa Cogeneration Limited | N/A | All Locations | 0 |  | 0 |  |  | 969.12 |  |  | 969.12 | [8 empty] | 0
98 |  |  |  | KUPE | Beach Energy Resources NZ (Holdings) Ltd | HWA033S1/HWA033S2 | Hawera | 141466.44 |  | 334190.73 |  | 620898 |  |  |  | 1096555.17 | 36551.06 |  | 375931.96 |  | 937091.68 | 0 |  |  | 1349574.7
99 |  |  |  | KUPE | Beach Energy Resources NZ (Holdings) Ltd | N/A | All Locations |  |  | 0 |  |  | 417.84 |  |  | 417.84 | [8 empty] | 0
100 |  |  |  | KWGL | Kawerau Geothermal Limited | KAW011S1/SA/S2 | Kawerau | 26122.6 |  | 543057.35 |  | 77385.12 |  |  |  | 646565.07 | 28366.63 |  | 680245.69 |  | 191149.98 | 0 |  |  | 899762.3
101 |  |  |  | KWGL | Kawerau Geothermal Limited | N/A | All Locations |  |  | 0 |  |  | 171.84 |  |  | 171.84 | [8 empty] | 0
102 |  |  |  | MARL | Marlborough Lines Limited | BLN033S1 | Blenheim | 506338.2 |  | 1886017.34 |  | 4711656 |  | 383334.72 |  | 7487346.26 | 549132.29 |  | 2335262.72 |  | 5867661.8 | 0 | 383334.72 |  | 9135391.53
103 |  |  |  | MARL | Marlborough Lines Limited | N/A | All Locations |  |  | 0 |  |  | 3159 |  |  | 3159 | [8 empty] | 0
104 |  |  |  | MELT | MEL (Te Apiti) Limited | WDV011S1 | Woodville | 36503.52 |  | 415158.53 |  | 65166.36 |  |  |  | 516828.41 | 39611.35 |  | 464700.06 |  | 72465.12 | 0 |  |  | 576776.53
105 |  |  |  | MELT | MEL (Te Apiti) Limited | N/A | All Locations |  |  | 0 |  |  | 84.6 |  |  | 84.6 | [8 empty] | 0
106 |  |  |  | MELW | MEL (West Wind) Limited | WWD110I1 | West Wind | 43173.12 |  | 650241.31 |  | 75818.64 |  | 685159.44 |  | 1454392.51 | 47519.73 |  | 737950.24 |  | 84465.22 | 0 | 685159.44 |  | 1555094.63
107 |  |  |  | MELW | MEL (West Wind) Limited | N/A | All Locations |  |  | 0 |  |  | 176.16 |  |  | 176.16 | [8 empty] | 0
108 |  |  |  | MERI | Meridian Energy Limited | AVI220I1 | Aviemore | 108216 |  | 3679640.83 |  | 29499.84 |  |  |  | 3817356.67 | 116840.89 |  | 4042093 |  | 20487.56 | 0 |  |  | 4179421.45
109 |  |  |  | MERI | Meridian Energy Limited | BEN220I1 | Benmore | 140364.48 |  | 12687460.08 |  | 110465.4 |  |  |  | 12938289.96 | 151547.61 |  | 13581882.22 |  | 86360.76 | 0 |  |  | 13819790.59
110 |  |  |  | MERI | Meridian Energy Limited | BRB033S1 | Bream Bay | 2626107.48 |  | 206102.2 |  |  |  | 2894977.56 |  | 5727187.24 | 2824981.91 |  | 307800.15 |  | 0 | 0 | 2894977.56 |  | 6027759.62
111 |  |  |  | MERI | Meridian Energy Limited | MAN220I1 | Manapouri | 17909417.76 |  | 20002496.05 | [5 empty] | 37911913.81 | 19269192.82 |  | 21155737.63 |  | 0 | 0 |  |  | 40424930.45
112 |  |  |  | MERI | Meridian Energy Limited | OHA220I1 | Ohau A | 1533067.08 |  | 4252728.24 |  | 105302.64 |  |  |  | 5891097.96 | 1651700.74 |  | 4695844.81 |  | 59186.29 | 0 |  |  | 6406731.84
113 |  |  |  | MERI | Meridian Energy Limited | OHB220I1 | Ohau B | 745253.28 |  | 3717691.28 |  | 76672.44 |  |  |  | 4539617 | 803712.74 |  | 4091039.69 |  | 41117.4 | 0 |  |  | 4935869.83
114 |  |  |  | MERI | Meridian Energy Limited | OHC220I1 | Ohau C | 787451.64 |  | 3691586.19 |  | 74044.2 |  |  |  | 4553082.03 | 849126.59 |  | 4062648.73 |  | 40406.02 | 0 |  |  | 4952181.34
115 |  |  |  | MERI | Meridian Energy Limited | TWZ033S1/TWZ033S3 | Twizel | 100430.76 |  | 16020.46 |  | 962609.52 |  |  |  | 1079060.74 | 125636.64 |  | 16588.63 |  | 1175189.3 | 0 |  |  | 1317414.57
116 |  |  |  | MERI | Meridian Energy Limited | WTK011S2 | Waitaki | 695644.08 |  | 1991196.62 | [5 empty] | 2686840.7 | 738696.84 |  | 2183981.06 |  | 0 | 0 |  |  | 2922677.9
117 |  |  |  | MERI | Meridian Energy Limited | N/A | All Locations |  |  | 0 |  |  | 23795.52 | 55250.72 |  | 79046.24 | [6 empty] | 55250.72 |  | 55250.72
118 |  |  |  | MERI | Meridian Energy Limited | HRP220I1 | Harapaki | 249212.76 |  | 521099.28 |  |  |  | 1766661.96 |  | 2536974 | 268410.32 |  | 477710.77 |  | 0 | 0 | 1766661.96 |  | 2512783.05
119 |  |  |  | METH | Methanex New Zealand Ltd | MNI011SA | Motunui | 486642 |  | 269962.35 |  | 554854.32 |  |  |  | 1311458.67 | 502521.57 |  | 301551.3 |  | 695076.76 | 0 |  |  | 1499149.63
120 |  |  |  | METH | Methanex New Zealand Ltd | N/A | All Locations |  |  | 0 |  |  | 371.88 |  |  | 371.88 | [8 empty] | 0
121 |  |  |  | MPOW | Mainpower New Zealand Limited | ASY011S1 | Ashley | 801385.32 |  | 326864.8 |  | 1182087.12 |  | 345781.68 |  | 2656118.92 | 871537.68 |  | 364726.76 |  | 1493498.94 | 0 | 345781.68 |  | 3075545.06
122 |  |  |  | MPOW | Mainpower New Zealand Limited | CUL033S1 | Culverden | 1134154.08 |  | 298160.5 |  | 1315558.32 |  |  |  | 2747872.9 | 1223879.62 |  | 324416.75 |  | 1614421.44 | 0 |  |  | 3162717.81
123 |  |  |  | MPOW | Mainpower New Zealand Limited | KAI011S1 | Kaiapoi | 943694.88 |  | 537822.41 |  | 1862876.16 |  | 425691 |  | 3770084.45 | 1018902.21 |  | 597696.01 |  | 2329349.2 | 0 | 425691 |  | 4371638.42
124 |  |  |  | MPOW | Mainpower New Zealand Limited | SBK066S1 | Southbrook | 302869.08 |  | 898169.48 |  | 3193518.72 |  | 443871.6 |  | 4838428.88 | 335282.59 |  | 1000233.47 |  | 3957560.04 | 0 | 443871.6 |  | 5736947.7
125 |  |  |  | MPOW | Mainpower New Zealand Limited | WPR033S1 | Waipara | 284478 |  | 204951.16 |  | 976617.48 |  | 54213.48 |  | 1520260.12 | 307874.16 |  | 229629.28 |  | 1212407.16 | 0 | 54213.48 |  | 1804124.08
126 |  |  |  | MPOW | Mainpower New Zealand Limited | N/A | All Locations |  |  | 0 |  |  | 5708.4 | 8672.73 |  | 14381.13 | [6 empty] | 149800.227 |  | 149800.227
127 |  |  |  | MRPL | Mercury NZ Limited | ARI110S2 | Arapuni | 225779.4 |  | 1302834.23 |  | 29210.28 |  |  |  | 1557823.91 | 243822.45 |  | 1437547.88 |  | 44142.82 | 0 |  |  | 1725513.15
128 |  |  |  | MRPL | Mercury NZ Limited | ARA220I1 | Aratiatia | 787934.16 |  | 1144945.06 |  | 3 |  |  |  | 1932882.22 | 848709.35 |  | 1235173.5 |  | 0 | 0 |  |  | 2083882.85
129 |  |  |  | MRPL | Mercury NZ Limited | ATI220S1 | Atiamuri | 95417.88 |  | 844143.1 |  | 270766.8 |  |  |  | 1210327.78 | 103071.45 |  | 928148.55 |  | 322268.14 | 0 |  |  | 1353488.14
130 |  |  |  | MRPL | Mercury NZ Limited | KPO110I1 | Karapiro | 71013.36 |  | 770447.53 | [5 empty] | 841460.89 | 76711.88 |  | 848485.14 |  | 0 | 0 |  |  | 925197.02
131 |  |  |  | MRPL | Mercury NZ Limited | MTI220I1 | Maraetai | 1725140.76 |  | 2339371.47 |  | 6322.8 |  |  |  | 4070835.03 | 1873261.05 |  | 2619668.91 |  | 9951.27 | 0 |  |  | 4502881.23
132 |  |  |  | MRPL | Mercury NZ Limited | OHK220I1 | Ohakuri | 109083.96 |  | 1520397.09 |  | 6372.72 |  |  |  | 1635853.77 | 117801.72 |  | 1625282.14 |  | 8675.47 | 0 |  |  | 1751759.33
133 |  |  |  | MRPL | Mercury NZ Limited | SWN025S1 | Southdown |  |  | 3466.92 | [5 empty] | 3466.92 | 0 |  | 4682.35 |  | 0 | 0 |  |  | 4682.35
134 |  |  |  | MRPL | Mercury NZ Limited | WPA220I1 | Waipapa | 979239.48 |  | 561662.22 |  | 1426.08 |  |  |  | 1542327.78 | 1039446.74 |  | 636796.88 |  | 2041.29 | 0 |  |  | 1678284.91
135 |  |  |  | MRPL | Mercury NZ Limited | WKM220I1 | Whakamaru | 178743.48 |  | 1751842.88 |  | 1797477.6 |  |  |  | 3728063.96 | 193132.92 |  | 1904266.77 |  | 2164529.37 | 0 |  |  | 4261929.06
136 |  |  |  | MRPL | Mercury NZ Limited | N/A | All Locations | 0 |  | 0 |  |  | 4821.96 | 15247.26 |  | 20069.22 | [6 empty] | 15247.26 |  | 15247.26
137 |  |  |  | MSVP | Mercury SPV Limited | LTN033S1 | Linton | 57445.68 |  | 855342.87 |  | 44049.96 |  |  |  | 956838.51 | 61901.41 |  | 1053955.65 |  | 108929.94 | 0 |  |  | 1224787
138 |  |  |  | MSVP | Mercury SPV Limited | N/A | All Locations | 0 |  | 0 |  |  | 157.8 |  |  | 157.8 | [8 empty] | 0
139 |  |  |  | NAPA | Nga Awa Purua Joint Venture | NAP220I1 | Nga Awa Purua | 561126.84 |  | 2816771.67 |  | 270816.48 |  | 408353.04 |  | 4057068.03 | 614842.13 |  | 3147328.85 |  | 406842.1 | 0 | 408353.04 |  | 4577366.12
140 |  |  |  | NAPA | Nga Awa Purua Joint Venture | N/A | All Locations |  |  | 0 |  |  | 1057.44 |  |  | 1057.44 | [8 empty] | 0
141 |  |  |  | NELS | Nelson Electricity Ltd | STK033S1 | Stoke | [8 empty] | 0 | 110468.83 |  | 167685.37 |  | 1053221.68 | 0 |  |  | 1331375.88
142 |  |  |  | NELS | Nelson Electricity Ltd | N/A | All Locations | [8 empty] | 0 | [8 empty] | 0
143 |  |  |  | NELS | Network Tasman Ltd | STK033S1 | Stoke | 87037.56 |  | 154310.19 |  | 872540.52 |  |  |  | 1113888.27 | [5 empty] | 0 |  |  | 0
144 |  |  |  | NELS | Network Tasman Ltd | N/A | All Locations |  |  | 0 |  |  | 562.44 |  |  | 562.44 | [8 empty] | 0
145 |  |  |  | NPOW | Northpower Limited | BRB033S1 | Bream Bay | 484950.24 |  | 2175764.65 |  | 3094778.04 |  |  |  | 5755492.93 | 532568.37 |  | 2537554.68 |  | 1211116.87 | 0 |  |  | 4281239.92
146 |  |  |  | NPOW | Northpower Limited | MPE110S1 | Maungatapere | 396451.56 |  | 6649082.69 |  | 4931616.84 |  |  |  | 11977151.09 | 453203.21 |  | 7343547.13 |  | 8059040.77 | 0 |  |  | 15855791.11
147 |  |  |  | NPOW | Northpower Limited | MTO033S1 | Maungaturoto | 490775.04 |  | 925498.43 |  | 845697.24 |  |  |  | 2261970.71 | 529738.23 |  | 1054966.15 |  | 1495325.62 | 0 |  |  | 3080030
148 |  |  |  | NPOW | Northpower Limited | N/A | All Locations |  |  | 0 |  |  | 7749.48 |  |  | 7749.48 | [8 empty] | 0
149 |  |  |  | NTRG | Ngatamariki Geothermal Ltd | NAP220I1 | Nga Awa Purua | 334604.52 |  | 1721115.82 |  | 107148.6 |  | 483120.36 |  | 2645989.3 | 364674.41 |  | 1925717.59 |  | 70219.94 | 0 | 483120.36 |  | 2843732.3
150 |  |  |  | NTRG | Ngatamariki Geothermal Ltd | N/A | All Locations | 0 |  | 0 |  |  | 608.4 |  |  | 608.4 | [8 empty] | 0
151 |  |  |  | NZAS | NZ Aluminium Smelters Limited | TWI220S1 | Tiwai | 1690423.32 |  | 13134592.72 |  | 36971091.84 |  |  |  | 51796107.88 | 1823041.03 |  | 13769139.71 |  | 46004434.98 | 0 |  |  | 61596615.72
152 |  |  |  | NZAS | NZ Aluminium Smelters Limited | N/A | All Locations |  |  | 0 |  |  | 27526.92 |  |  | 27526.92 | [8 empty] | 0
153 |  |  |  | NZST | New Zealand Steel Limited | GLN033SA/GLN033S3 | Glenbrook | 3045290.04 |  | 3436041.91 |  | 9906608.64 |  | 83772 |  | 16471712.59 | 3244030.41 |  | 3716400.82 |  | 12203792.02 | 0 | 83772 |  | 19247995.25
154 |  |  |  | NZST | New Zealand Steel Limited | N/A | All Locations |  |  | 0 |  |  | 7128.84 |  |  | 7128.84 | [8 empty] | 0
155 |  |  |  | OMVP | OMV New Zealand Limited | MNI011SA | Motunui | 374847.96 |  | 336069.16 |  | 323513.64 |  |  |  | 1034430.76 | 432108.15 |  | 368303.3 |  | 599617.9 | 0 |  |  | 1400029.35
156 |  |  |  | OMVP | OMV New Zealand Limited | N/A | All Locations |  |  | 0 |  |  | 271.8 |  |  | 271.8 | [8 empty] | 0
157 |  |  |  | ORON | Orion New Zealand Limited | APS011S1 | Arthurs Pass | 120693.84 |  | 4121.34 |  | 15251.52 |  |  |  | 140066.7 | 130311.45 |  | 4579.52 |  | 17914.91 | 0 |  |  | 152805.88
158 |  |  |  | ORON | Orion New Zealand Limited | BRY066SA | Bromley | 2645567.28 |  | 1880270.27 |  | 9604269.84 |  | 740925.84 |  | 14871033.23 | 2849297.09 |  | 2052843.31 |  | 11883557.35 | 0 | 740925.84 |  | 17526623.59
159 |  |  |  | ORON | Orion New Zealand Limited | CLH011S1 | Castle Hill | 150058.08 |  | 7030.2 |  | 23551.56 |  |  |  | 180639.84 | 161904.31 |  | 7723.66 |  | 29858.18 | 0 |  |  | 199486.15
160 |  |  |  | ORON | Orion New Zealand Limited | COL011S1 | Coleridge | 138878.28 |  | 4397.12 |  | 16746.72 |  |  |  | 160022.12 | 149761.5 |  | 4894.69 |  | 17914.91 | 0 |  |  | 172571.1
161 |  |  |  | ORON | Orion New Zealand Limited | HOR033S1 | Hororata | 390151.44 |  | 544104.35 |  | 2202137.76 |  |  |  | 3136393.55 | 424900.26 |  | 609543.67 |  | 2340881.65 | 0 |  |  | 3375325.58
162 |  |  |  | ORON | Orion New Zealand Limited | ISL033S1 | Islington | 2211056.28 |  | 9301787.77 |  | 35202381.48 |  |  |  | 46715225.53 | 2415114.23 |  | 10275154.58 |  | 44082623.3 | 0 |  |  | 56772892.11
163 |  |  |  | ORON | Orion New Zealand Limited | KBY066SA | Kimberley | 24459.12 |  | 184894.49 |  | 1047951.6 |  |  |  | 1257305.21 | 34624.54 |  | 214950.13 |  | 1343618.29 | 0 |  |  | 1593192.96
164 |  |  |  | ORON | Orion New Zealand Limited | NWD066S1 | Norwood | 240377.16 | [5 empty] | 3437500.08 |  | 3677877.24 | 258471.07 |  | 0 |  | 0 | 0 | 3437500.08 |  | 3695971.15
165 |  |  |  | ORON | Orion New Zealand Limited | N/A | All Locations |  |  | 0 |  |  | 32030.4 | 8192.73 |  | 40223.13 | [6 empty] | 8192.73 |  | 8192.73
166 |  |  |  | PANP | Pan Pac Forest Product Limited | WHI011SA | Whirinaki | 1441656.12 |  | 1383756.62 |  | 4320970.92 |  |  |  | 7146383.66 | 1567170.19 |  | 1595878.47 |  | 4970518.84 | 0 |  |  | 8133567.5
167 |  |  |  | PANP | Pan Pac Forest Product Limited | N/A | All Locations |  |  | 0 |  |  | 2823.72 |  |  | 2823.72 | [8 empty] | 0
168 |  |  |  | POCO | Powerco Limited | ARI110S2 | Arapuni | 33268.8 | [5 empty] | 180795 |  | 214063.8 | 36123.51 |  | 0 |  | 0 | 0 | 180795 |  | 216918.51
169 |  |  |  | POCO | Powerco Limited | BRK033S1 | Brunswick | 235085.16 |  | 456594.24 |  | 1598391.24 |  |  |  | 2290070.64 | 254071.03 |  | 522257.46 |  | 1981650.49 | 0 |  |  | 2757978.98
170 |  |  |  | POCO | Powerco Limited | BPE033S1 | Bunnythorpe | 936484.32 |  | 1398006.02 |  | 6061789.32 |  | 46573.92 |  | 8442853.58 | 1009674.24 |  | 1588432.83 |  | 7457476.53 | 0 | 46573.92 |  | 10102157.52
171 |  |  |  | POCO | Powerco Limited | CST033S1 | Carrington St | 533332.56 |  | 1778950.51 |  | 3279485.28 |  | 441268.32 |  | 6033036.67 | 574841.88 |  | 1966879.71 |  | 4383896.18 | 0 | 441268.32 |  | 7366886.09
172 |  |  |  | POCO | Powerco Limited | GYT033S1 | Greytown | 568293.12 |  | 276697.6 |  | 979797.84 |  |  |  | 1824788.56 | 613940.7 |  | 313592.27 |  | 1237520.51 | 0 | 21962.0769 |  | 2187015.5569
173 |  |  |  | POCO | Powerco Limited | HWA033S1/HWA033S2 | Hawera | 540334.56 |  | 583746 |  | 1259973 |  |  |  | 2384053.56 | 408756.88 |  | 689023.97 |  | 1504436.7 | 0 |  |  | 2602217.55
174 |  |  |  | POCO | Powerco Limited | HIN033S1 | Hinuera | 856761.12 |  | 1110113.08 |  | 2707883.16 |  | 241425.6 |  | 4916182.96 | 925790.19 |  | 1247395.67 |  | 3348584.91 | 0 | 241425.6 |  | 5763196.37
175 |  |  |  | POCO | Powerco Limited | HUI033S1 | Huirangi | 486196.44 |  | 829838.88 |  | 2355581.16 |  | 808958.16 |  | 4480574.64 | 526250.34 |  | 927351.67 |  | 2871371.11 | 0 | 808958.16 |  | 5133931.28
176 |  |  |  | POCO | Powerco Limited | KMO033S1 | Kaitimako | 134915.76 |  | 194721.58 |  | 990894 |  | 396876.48 |  | 1717407.82 | 145414.33 |  | 230551.46 |  | 1261785.62 | 0 | 396876.48 |  | 2034627.89
177 |  |  |  | POCO | Powerco Limited | KIN011SA | Kinleith | 1568657.88 |  | 979776.03 |  | 8241506.04 |  |  |  | 10789939.95 | 1701765.33 |  | 1167541.13 |  | 9989136.13 | 0 |  |  | 12858442.59
178 |  |  |  | POCO | Powerco Limited | KPU066S1 | Kopu | 3755200.8 |  | 1179214.68 |  | 2824520.04 |  | 146479.32 |  | 7905414.84 | 4037335.6 |  | 1303952.09 |  | 3526529.03 | 0 | 146479.32 |  | 9014296.04
179 |  |  |  | POCO | Powerco Limited | LTN033S1 | Linton | 1056485.64 |  | 569062.95 |  | 3353270.4 |  | 230763.48 |  | 5209582.47 | 1143240.41 |  | 647349.25 |  | 4230217.16 | 0 | 230763.48 |  | 6251570.3
180 |  |  |  | POCO | Powerco Limited | MGM033S1 | Mangamaire | 654014.88 |  | 460997.69 |  | 1025973.48 |  |  |  | 2140986.05 | 706599.86 |  | 513652.97 |  | 1294139.09 | 0 |  |  | 2514391.92
181 |  |  |  | POCO | Powerco Limited | MTN033S1 | Marton | 384087.72 |  | 510767.49 |  | 1150810.44 |  |  |  | 2045665.65 | 415593.49 |  | 569747.76 |  | 1431641.37 | 0 |  |  | 2416982.62
182 |  |  |  | POCO | Powerco Limited | MST033S1 | Masterton | 429097.56 |  | 1143221.77 |  | 2882411.4 |  | 518515.56 |  | 4973246.29 | 462493.13 |  | 1295290.34 |  | 3583147.62 | 0 | 518515.56 |  | 5859446.65
183 |  |  |  | POCO | Powerco Limited | MTR033S1 | Mataroa | 329140.8 |  | 197684.72 |  | 424285.32 |  |  |  | 951110.84 | 355837.15 |  | 220119.16 |  | 525744.01 | 0 |  |  | 1101700.32
184 |  |  |  | POCO | Powerco Limited | MTM033S1 | Mt Maunganui | 850656.48 |  | 767169.34 |  | 3568130.88 |  |  |  | 5185956.7 | 924000.69 |  | 896738.96 |  | 4400072.92 | 0 |  |  | 6220812.57
185 |  |  |  | POCO | Powerco Limited | No POS Code | New Plymouth |  |  |  |  | 623194.32 |  |  |  | 623194.32 | 0 |  | 0 |  | 436771.94 | 0 |  |  | 436771.94
186 |  |  |  | POCO | Powerco Limited | OKN011S2 | Ohakune | 102294.24 |  | 51372.45 |  | 127467.24 |  |  |  | 281133.93 | 99601.51 |  | 56875.5 |  | 161767.39 | 0 |  |  | 318244.4
187 |  |  |  | POCO | Powerco Limited | OPK033S1 | Opunake | 1454620.8 |  | 273492.8 |  | 620441.64 |  | 154399.2 |  | 2502954.44 | 1614828.48 |  | 305129.56 |  | 768395.09 | 0 | 154399.2 |  | 2842752.33
188 |  |  |  | POCO | Powerco Limited | PAO110S1 | Piako | 361977.84 |  | 923560.63 |  | 2472350.76 |  | 1191933.6 |  | 4949822.83 | 405678.02 |  | 1049625.06 |  | 3130198.93 | 0 | 1191933.6 |  | 5777435.61
189 |  |  |  | POCO | Powerco Limited | SFD033S1 | Stratford | 506920.2 |  | 729236.21 |  | 1900892.52 |  |  |  | 3137048.93 | 546879.87 |  | 812742.91 |  | 2264743.41 | 0 |  |  | 3624366.19
190 |  |  |  | POCO | Powerco Limited | TGA011S1 | Tauranga | 1249016.52 |  | 961847.67 |  | 7159814.28 |  | 819001.72 |  | 10189680.19 | 1348830.32 |  | 1146204.8 |  | 9091327.14 | 0 | 819001.72 |  | 12405363.98
191 |  |  |  | POCO | Powerco Limited | TMI033S1 | Te Matai | 316122.72 |  | 444040.03 |  | 2841489.36 |  | 255243.84 |  | 3856895.95 | 345547.47 |  | 542744.16 |  | 3720649.9 | 0 | 466935.0809 |  | 5075876.6109
192 |  |  |  | POCO | Powerco Limited | WHU033S1 | Waihou | 1435853.28 |  | 889192.72 |  | 2109319.56 |  |  |  | 4434365.56 | 1540130.18 |  | 995977.25 |  | 2604454.93 | 0 |  |  | 5140562.36
193 |  |  |  | POCO | Powerco Limited | WKO033S1 | Waikino | 1627288.08 |  | 921218.29 |  | 2331860.76 |  |  |  | 4880367.13 | 1765523.67 |  | 1037503.27 |  | 2919901.33 | 0 |  |  | 5722928.27
194 |  |  |  | POCO | Powerco Limited | WGN033S1 | Wanganui | 481903.56 |  | 842133.26 |  | 1907389.2 |  | 69163.56 |  | 3300589.58 | 519831.07 |  | 940227.88 |  | 2402245.69 | 0 | 69163.56 |  | 3931468.2
195 |  |  |  | POCO | Powerco Limited | WVY011S1 | Waverley | 311747.76 |  | 136925.08 |  | 295355.76 |  |  |  | 744028.6 | 336780.81 |  | 152237.89 |  | 355888.25 | 0 | 107767.2963 |  | 952674.2463
196 |  |  |  | POCO | Powerco Limited | N/A | All Locations |  |  | 0 |  |  | 42311.88 | 22139.34 |  | 64451.22 | [6 empty] | 22139.34 |  | 22139.34
197 |  |  |  | POWN | Powernet Ltd | BAL033S1 | Balclutha | 1253355.36 |  | 562056.38 |  | 2012587.56 |  |  |  | 3827999.3 | 1351734.62 |  | 600160.88 |  | 2512079.38 | 0 |  |  | 4463974.88
198 |  |  |  | POWN | Powernet Ltd | CML033S1 | Cromwell | [6 empty] | 44045.52 |  | 44045.52 | [6 empty] | 44045.52 |  | 44045.52
199 |  |  |  | POWN | Powernet Ltd | EDN033S1 | Edendale | 210415.68 |  | 805162.8 |  | 1709348.76 |  | 42745.56 |  | 2767672.8 | 226717.02 |  | 909704.45 |  | 2172914.75 | 0 |  |  | 3309336.22
200 |  |  |  | POWN | Powernet Ltd | FKN033S1/S2 | Frankton | 406426.08 |  | 64750.68 |  | 357017.76 |  | 59047.44 |  | 887241.96 | 444872.23 |  | 67795.68 |  | 490658.17 | 0 | 59047.44 |  | 1062373.52
201 |  |  |  | POWN | Powernet Ltd | GOR033S1 | Gore | 653907.96 |  | 1550292.89 |  | 2015402.16 |  | 152476.44 |  | 4372079.45 | 705097.25 |  | 1607208.07 |  | 2507557.19 | 0 | 152476.44 |  | 4972338.95
202 |  |  |  | POWN | Powernet Ltd | HWB033S1/S2 | Halfway Bush | 80255.28 |  | 83121.14 |  | 383497.44 |  |  |  | 546873.86 | 89921.7 |  | 87175.06 |  | 483874.88 | 0 |  |  | 660971.64
203 |  |  |  | POWN | Powernet Ltd | INV033S1 | Invercargill | 541694.76 |  | 1128644.2 |  | 5513644.08 |  | 622782.24 |  | 7806765.28 | 583667.84 |  | 1183949.2 |  | 6968702.66 | 0 | 622782.24 |  | 9359101.94
204 |  |  |  | POWN | Powernet Ltd | NSY033S1 | Naseby | 878505.72 |  | 427308.26 |  | 2678806.56 |  |  |  | 3984620.54 | 946093.73 |  | 443759.15 |  | 3341902.18 | 0 |  |  | 4731755.06
205 |  |  |  | POWN | Powernet Ltd | NMA033S1 | North Makarewa | 745591.32 |  | 215289.14 |  | 3332352.36 |  |  |  | 4293232.82 | 804129.51 |  | 236940.95 |  | 4133286.33 | 0 |  |  | 5174356.79
206 |  |  |  | POWN | Powernet Ltd | N/A | All Locations |  |  | 0 |  |  | 12172.8 | 29115.62 |  | 41288.42 | [6 empty] | 29115.62 |  | 29115.62
207 |  |  |  | RAYN | Daiken Southland Limited | BDE011S1 | Brydone | 188861.28 |  | 270629.26 |  | 584743.08 |  |  |  | 1044233.62 | 210809.56 |  | 285295.86 |  | 716754.36 | 0 |  |  | 1212859.78
208 |  |  |  | RAYN | Daiken Southland Limited | N/A | All Locations |  |  | 0 |  |  | 434.88 |  |  | 434.88 | [8 empty] | 0
209 |  |  |  | SCAN | Scanpower Limited | DVK011S1 | Dannevirke | 321809.04 |  | 415792.37 |  | 800076 |  | 170850.45 |  | 1708527.86 | 347570.4 |  | 461850.15 |  | 993071.18 | 0 | 170850.45 |  | 1973342.18
210 |  |  |  | SCAN | Scanpower Limited | WDV011S1 | Woodville | 353232.24 |  | 77075.42 |  | 149035.08 |  | 98376.15 |  | 677718.89 | 380868.53 |  | 85680.34 |  | 185648.32 | 0 | 98376.15 |  | 750573.34
211 |  |  |  | SCAN | Scanpower Limited | N/A | All Locations |  |  | 0 |  |  | 655.56 |  |  | 655.56 | [8 empty] | 0
212 |  |  |  | SCGL | Mercury NZ Limited | SWN025S1 | Southdown |  |  | -12.76 | [5 empty] | -12.76 | [8 empty] | 0
213 |  |  |  | SCGL | Mercury NZ Limited | N/A | All Locations |  |  | 0 | [5 empty] | 0 | [8 empty] | 0
214 |  |  |  | SHPK | Southpark Utilities Limited | PEN022S1 | Penrose | 31200.72 |  | 836.29 |  | 10840.2 |  | 22442.49 |  | 65319.7 | 33798.16 |  | 1144.47 |  | 13083.98 | 0 | 22442.49 |  | 70469.1
215 |  |  |  | SHPK | Southpark Utilities Limited | N/A | All Locations |  |  | 0 |  |  | 6.24 |  |  | 6.24 | [8 empty] | 0
216 |  |  |  | SKOG | Norske Skog Tasman Limited | N/A | All Locations |  |  | 0 | [5 empty] | 0 | [8 empty] | 0
217 |  |  |  | SOLE | Resolution Development Ltd | BDE011S1 | Brydone | [8 empty] | 0 | [8 empty] | 0
218 |  |  |  | SOLE | Resolution Development Ltd | N/A | All Locations | [8 empty] | 0 | [8 empty] | 0
219 |  |  |  | SOLE | Southern Biomass Limited | BDE011S1 | Brydone | 3597 |  | 2085.49 |  | 9399 |  |  |  | 15081.49 | 6491.48 |  | 2129.94 |  | 7122.64 | 0 |  |  | 15744.06
220 |  |  |  | SOLE | Southern Biomass Limited | N/A | All Locations |  |  | 0 |  |  | -5604.72 |  |  | -5604.72 | 271562.6 |  | 54741.6 | [5 empty] | 326304.2
221 |  |  |  | TARW | Tararua Wind Power | TWC220S1 | Tararua | 26499.24 |  | 597804.09 |  | 66795.6 |  | 340988.1 |  | 1032087.03 | 29423.54 |  | 742076.26 |  | 83149.08 | 0 | 340988.1 |  | 1195636.98
222 |  |  |  | TARW | Tararua Wind Power | N/A | All Locations | 0 |  | 0 |  |  | 121.44 |  |  | 121.44 | [8 empty] | 0
223 |  |  |  | TASM | Network Tasman Limited | KIK011S1 | Kikiwa | 53088.12 |  | 38475.59 |  | 169526.4 |  |  |  | 261090.11 | 56384.37 |  | 41987.49 |  | 213390.02 | 0 |  |  | 311761.88
224 |  |  |  | TASM | Network Tasman Limited | MCH011S1 | Murchison | 292093.2 |  | 53688.96 |  | 147634.56 |  |  |  | 493416.72 | 314824.25 |  | 67220.07 |  | 179757.9 | 0 |  |  | 561802.22
225 |  |  |  | TASM | Network Tasman Limited | STK033S1 | Stoke | 1501765.32 |  | 1802492.51 |  | 8971808.16 |  |  |  | 12276065.99 | 1610826.29 |  | 2021478.02 |  | 11204135.82 | 0 |  |  | 14836440.13
226 |  |  |  | TASM | Network Tasman Limited | N/A | All Locations |  |  | 0 |  |  | 6011.64 |  |  | 6011.64 | [8 empty] | 0
227 |  |  |  | TBOP | Nova Energy Limited | JRD110I1 | Junction Road | 10815.36 |  | 773187.18 |  | 2053.08 |  |  |  | 786055.62 | 12096.43 |  | 835614.51 |  | 4558.89 | 0 |  |  | 852269.83
228 |  |  |  | TBOP | Nova Energy Limited | KPA110S1 | Kaponga | 465080.16 |  | 203326.26 |  | 535144.44 |  |  |  | 1203550.86 | 460043.95 |  | 227910.43 |  | 677133.64 | 0 |  |  | 1365088.02
229 |  |  |  | TBOP | Nova Energy Limited | MKE110I1 | McKee | 14346.48 |  | 770261.54 |  | 6565.92 |  | 185677.2 |  | 976851.14 | 15821.67 |  | 832736.04 |  | 9048.71 | 0 | 185677.2 |  | 1043283.62
230 |  |  |  | TBOP | Nova Energy Limited | N/A | All Locations |  |  | 0 |  |  | 676.8 |  |  | 676.8 | [8 empty] | 0
231 |  |  |  | TOD3 | Nova Energy Limited | N/A | All Locations | [6 empty] | 7910.01 |  | 7910.01 | [6 empty] | 7910.01 |  | 7910.01
232 |  |  |  | TOPE | Top Energy Ltd | KOE110S1 | Kaikohe | 1960653.12 |  | 1968272.4 |  | 4393781.88 |  |  |  | 8322707.4 | 2121654.61 |  | 2161236.23 |  | 5451374.46 | 0 |  |  | 9734265.3
233 |  |  |  | TOPE | Top Energy Ltd | N/A | All Locations |  |  | 0 |  |  | 3163.2 | 12851.85 |  | 16015.05 | [6 empty] | 12851.85 |  | 12851.85
234 |  |  |  | TRNZ | KiwiRail Holdings Limited | BPE033S1 | Bunnythorpe | 375926.76 |  | 14237.87 |  | 132100.68 |  |  |  | 522265.31 | 405469.46 |  | 15610.54 |  | 140022.82 | 0 |  |  | 561102.82
235 |  |  |  | TRNZ | KiwiRail Holdings Limited | HAM011S1 | Hamilton | 369593.4 |  | 15429.23 |  | 116065.56 |  |  |  | 501088.19 | 398572.06 |  | 16592.64 |  | 121902.22 | 0 |  |  | 537066.92
236 |  |  |  | TRNZ | KiwiRail Holdings Limited | PEN022S1 | Penrose | 149062.92 |  | 131651.74 |  | 953805.72 |  |  |  | 1234520.38 | 160105.67 |  | 141786.31 |  | 1105905.71 | 0 |  |  | 1407797.69
237 |  |  |  | TRNZ | KiwiRail Holdings Limited | SWN025S1 | Southdown | 113366.04 |  | 128385.58 |  | 946335.12 |  | 493494.48 |  | 1681581.22 | 125949.32 |  | 138450.43 |  | 1059780.55 | 0 | 493494.48 |  | 1817674.78
238 |  |  |  | TRNZ | KiwiRail Holdings Limited | TNG011S1 | Tangiwai | 482051.04 |  | 15344.37 |  | 151092.48 |  |  |  | 648487.89 | 1377052.07 |  | 17009 |  | 158967.08 | 0 |  |  | 1553028.15
239 |  |  |  | TRNZ | KiwiRail Holdings Limited | TMN055SA | Taumarunui | 437333.4 |  | 18650.99 |  | 150794.28 |  |  |  | 606778.67 | 471538.9 |  | 20262.36 |  | 158967.08 | 0 |  |  | 650768.34
240 |  |  |  | TRNZ | KiwiRail Holdings Limited | N/A | All Locations | 0 |  | 0 |  |  | -405821.76 |  |  | -405821.76 | [8 empty] | 0
241 |  |  |  | TRUG | Manawa Energy Ltd | ARG110I1 | Argyle | 56904.48 |  | 239958.05 |  | 33734.28 |  |  |  | 330596.81 | 61337.93 |  | 269032.43 |  | 40289.79 | 0 |  |  | 370660.15
242 |  |  |  | TRUG | Manawa Energy Ltd | BWK110I1 | Berwick | 120967.68 |  | 52139.02 |  | 1693.32 |  |  |  | 174800.02 | 130621.07 |  | 62611.92 |  | 5059.9 | 0 |  |  | 198292.89
243 |  |  |  | TRUG | Manawa Energy Ltd | COL011S1 | Coleridge | 43121.28 |  | 687074.98 |  | 3380.76 |  |  |  | 733577.02 | 46579.39 |  | 728198.33 |  | 5974.47 | 0 |  |  | 780752.19
244 |  |  |  | TRUG | Manawa Energy Ltd | HWA033S1/HWA033S2 | Hawera | 91397.52 |  | 158847.15 |  | 1858.08 |  |  |  | 252102.75 | 101022.49 |  | 182331.3 |  | 2792.42 | 0 |  |  | 286146.21
245 |  |  |  | TRUG | Manawa Energy Ltd | MAT110S1 | Matahina | 617689.68 |  | 251110.55 | [5 empty] | 868800.23 | 684580.18 |  | 293554.06 |  | 0 | 0 |  |  | 978134.24
246 |  |  |  | TRUG | Manawa Energy Ltd | N/A | All Locations |  |  | 0 |  |  | 540.24 | 9863.25 |  | 10403.49 | [6 empty] | 9863.25 |  | 9863.25
247 |  |  |  | UNET | Wellington Electricity Lines Limited | CPK011S1 | Central Park | 1475033.88 |  | 4155419.31 |  | 11322271.56 |  |  |  | 16952724.75 | 1590281.33 |  | 4682292.8 |  | 13692397.95 | 0 |  |  | 19964972.08
248 |  |  |  | UNET | Wellington Electricity Lines Limited | GFD033S1 | Gracefield | 2327393.52 |  | 1453751.24 |  | 4034443.32 |  |  |  | 7815588.08 | 2508824.86 |  | 1642656.29 |  | 4990041.62 | 0 |  |  | 9141522.77
249 |  |  |  | UNET | Wellington Electricity Lines Limited | HAY011S1 | Haywards | 769567.44 |  | 687810.35 |  | 2134994.16 |  |  |  | 3592371.95 | 866437.01 |  | 779057.46 |  | 2676319.9 | 0 |  |  | 4321814.37
250 |  |  |  | UNET | Wellington Electricity Lines Limited | KWA011S1 | Kaiwharawhara | 581617.08 |  | 792345.21 |  | 2097718.56 |  | 641143.44 |  | 4112824.29 | 626890.8 |  | 891382.03 |  | 2520920.68 | 0 | 641143.44 |  | 4680336.95
251 |  |  |  | UNET | Wellington Electricity Lines Limited | MLG011S1 | Melling | 1892605.68 |  | 1333396.97 |  | 3637142.64 |  |  |  | 6863145.29 | 2041116.39 |  | 1503778.63 |  | 4489310.8 | 0 |  |  | 8034205.82
252 |  |  |  | UNET | Wellington Electricity Lines Limited | PNI033S1 | Pauatahanui | 1473764.64 |  | 364887.34 |  | 1003038.48 |  |  |  | 2841690.46 | 1589763.1 |  | 412024.39 |  | 1256143.7 | 0 |  |  | 3257931.19
253 |  |  |  | UNET | Wellington Electricity Lines Limited | TKR033S1 | Takapu Road | 866983.56 |  | 2057113.23 |  | 5914968.24 |  |  |  | 8839065.03 | 516934.29 |  | 2334478.27 |  | 7403046.18 | 0 |  |  | 10254458.74
254 |  |  |  | UNET | Wellington Electricity Lines Limited | UHT033S1 | Upper Hutt | 277592.28 |  | 673245.27 |  | 1914345.72 |  |  |  | 2865183.27 | 299400.75 |  | 762699.2 |  | 2413004.56 | 0 |  |  | 3475104.51
255 |  |  |  | UNET | Wellington Electricity Lines Limited | WIL033S1 | Wilton | 1618480.68 |  | 238142.59 |  | 3031429.32 |  | 99064.32 |  | 4987116.91 | 1743940.75 |  | 309507.18 |  | 3725264.64 | 0 | 99064.32 |  | 5877776.89
256 |  |  |  | UNET | Wellington Electricity Lines Limited | N/A | All Locations |  |  | 0 |  |  | 23550.96 |  |  | 23550.96 | [6 empty] | 63960.2847 |  | 63960.2847
257 |  |  |  | UNIS | Unison Networks Limited | FHL033S1 | Fernhill | 704040.96 |  | 954891.58 |  | 3833621.28 |  | 348972.6 |  | 5841526.42 | 759132.32 |  | 1046340.59 |  | 4812595.17 | 0 | 348972.6 |  | 6967040.68
258 |  |  |  | UNIS | Unison Networks Limited | OWH011S1 | Owhata | 1331771.28 |  | 57752.45 |  | 757424.4 |  | 26156.16 |  | 2173104.29 | 1436280.27 |  | 83817.74 |  | 944715.88 | 0 | 26156.16 |  | 2490970.05
259 |  |  |  | UNIS | Unison Networks Limited | RDF033S1 | Redclyffe | 411216.84 |  | 987142.44 |  | 4075442.04 |  |  |  | 5473801.32 | 443301.89 |  | 1078133.82 |  | 5016470.03 | 0 |  |  | 6537905.74
260 |  |  |  | UNIS | Unison Networks Limited | ROT011S1 | Rotorua | 2114300.52 |  | 342584.87 |  | 4687095 |  | 35679.84 |  | 7179660.23 | 2280940.9 |  | 447653.24 |  | 5731467.76 |  | 35679.84 |  | 8495741.74
261 |  |  |  | UNIS | Unison Networks Limited | TRK011S1 | Tarukenga | 145274.88 |  | 92376.13 |  | 484374.6 |  |  |  | 722025.61 | 159999.86 |  | 108971.97 |  | 605881.61 | 0 |  |  | 874853.44
262 |  |  |  | UNIS | Unison Networks Limited | TAB033S1 | Tauhara B | 91820.91 |  | 871809.96 |  |  |  | 1419889.8 |  | 2383520.67 | 77160.96 |  | 692519.35 |  | 0 | 0 | 1419889.8 |  | 2189570.11
263 |  |  |  | UNIS | Unison Networks Limited | WRK033S1 | Wairakei | 420659.16 |  | 244362.12 |  | 3383570.04 |  |  |  | 4048591.32 | 453925.52 |  | 316731.2 |  | 4255528.67 | 0 |  |  | 5026185.39
264 |  |  |  | UNIS | Unison Networks Limited | WTU033S1 | Whakatu | 2011272.6 |  | 1372555.44 |  | 5880650.76 |  | 36041.04 |  | 9300519.84 | 2173706.79 |  | 1588087.1 |  | 7348109.21 | 0 | 36041.04 |  | 11145944.14
265 |  |  |  | UNIS | Unison Networks Limited | N/A | All Locations |  |  | -622.21 |  |  | 14137.2 | 9106.65 |  | 22621.64 | [6 empty] | 9106.65 |  | 9106.65
266 |  |  |  | VEC8 | Vector Limited | N/A | All Locations | [6 empty] | 41799.38 |  | 41799.38 | [6 empty] | 41799.38 |  | 41799.38
267 |  |  |  | VECT | Vector Limited | ALB033S1 | Albany | 1842538.2 |  | 7976615.87 |  | 13397042.52 |  | 279440.76 |  | 23495637.35 | 1986927.5 |  | 8703051.84 |  | 16756807.78 | 0 | 1248911.76 |  | 28695698.88
268 |  |  |  | VECT | Vector Limited | HEN033S1 | Henderson | 502600.68 |  | 4063950.87 |  | 6804233.64 |  | 315729.6 |  | 11686514.79 | 541725.78 |  | 4392127.03 |  | 8409094.01 | 0 | 315729.6 |  | 13658676.42
269 |  |  |  | VECT | Vector Limited | HEP033S1 | Hepburn Road | 949846.92 |  | 5976068.2 |  | 8982488.88 |  | 284148.48 |  | 16192552.48 | 1024383.79 |  | 6811698.54 |  | 10987064.44 | 0 | 284148.48 |  | 19107295.25
270 |  |  |  | VECT | Vector Limited | HOB110S1 | Hobson St | 249332.28 |  | 2224489.42 |  | 3722794.44 |  | 3916703.16 |  | 10113319.3 | 266721.13 |  | 2535944.35 |  | 4680243.93 | 0 | 3916703.16 |  | 11399612.57
271 |  |  |  | VECT | Vector Limited | LFD110S1 | Lichfield | 37681.68 |  | 142429.56 |  | 955071.48 |  |  |  | 1135182.72 | 40770.36 |  | 173403.3 |  | 1181569.78 | 0 |  |  | 1395743.44
272 |  |  |  | VECT | Vector Limited | MNG033S1 | Mangere | 636398.64 |  | 5726063.42 |  | 9013869.84 |  | 135949.56 |  | 15512281.46 | 686658.9 |  | 6489735.88 |  | 11186550.25 | 0 | 135949.56 |  | 18498894.59
273 |  |  |  | VECT | Vector Limited | MTM033S1 | Mt Roskill | 983100.12 |  | 6567444.98 |  | 9823961.4 |  |  |  | 17374506.5 | 1064541.08 |  | 7400007.41 |  | 12076563.85 | 0 |  |  | 20541112.34
274 |  |  |  | VECT | Vector Limited | OTA022S1 | Otahuhu A | 719307.36 |  | 2278433.96 |  | 4429145.64 |  |  |  | 7426886.96 | 741992.79 |  | 2462707.18 |  | 5401461.85 | 0 |  |  | 8606161.82
275 |  |  |  | VECT | Vector Limited | PAK033S1 | Pakuranga | 1351447.8 |  | 5502307.12 |  | 8942671.32 |  | 479494.32 |  | 16275920.56 | 1456890 |  | 5868496.54 |  | 11171205.19 | 0 | 479494.32 |  | 18976086.05
276 |  |  |  | VECT | Vector Limited | PEN022S1 | Penrose | 2348569.44 |  | 18240836.55 |  | 31326736.68 |  | 114939.84 |  | 52031082.51 | 2532141.21 |  | 19545168.05 |  | 37702817.5 | 0 | 114939.84 |  | 59895066.6
277 |  |  |  | VECT | Vector Limited | SVL033S1 | Silverdale | 1077442.68 |  | 2861963.46 |  | 6071373.48 |  | 512843.16 |  | 10523622.78 | 1158608.27 |  | 3081014.91 |  | 7626495.85 | 0 | 512843.16 |  | 12378962.19
278 |  |  |  | VECT | Vector Limited | TAK033S1 | Takanini | 1559185.68 |  | 3635139.01 |  | 7655120.88 |  | 27461.28 |  | 12876906.85 | 1680569.73 |  | 3964777.55 |  | 9682734.16 | 0 | 27461.28 |  | 15355542.72
279 |  |  |  | VECT | Vector Limited | WRD033S1 | Wairau Road | 324979.44 |  | 2310113.84 |  | 4146543.72 |  | 2941620.96 |  | 9723257.96 | 351756.63 |  | 2482702.4 |  | 5140595.79 | 0 | 2941620.96 |  | 10916675.78
280 |  |  |  | VECT | Vector Limited | WEL033S1 | Wellsford | 350971.56 |  | 1555541.49 |  | 2391440.52 |  |  |  | 4297953.57 | 381922.15 |  | 1757030.7 |  | 3007632.17 | 0 |  |  | 5146585.02
281 |  |  |  | VECT | Vector Limited | WIR033S1 | Wiri | 1672798.32 |  | 5271040.42 |  | 6752131.32 |  | 64068.24 |  | 13760038.3 | 1790234.27 |  | 5842885.22 |  | 8439784.14 | 0 | 64068.24 |  | 16136971.87
282 |  |  |  | VECT | Vector Limited | N/A | All Locations |  |  | 0 |  |  | 101618.4 |  |  | 101618.4 | [8 empty] | 0
283 |  |  |  | WAIP | Waipa Networks Limited | CBG011S1 | Cambridge | 760523.04 |  | 1119934.74 |  | 2626116.24 |  | 120919.2 |  | 4627493.22 | 820604.35 |  | 1265034.9 |  | 3342718.78 | 0 | 120919.2 |  | 5549277.23
284 |  |  |  | WAIP | Waipa Networks Limited | TMI033S1 | Te Awamutu | 772326.24 |  | 972281.99 |  | 2243505.6 |  | 581978.4 |  | 4570092.23 | 834084.24 |  | 1096125.02 |  | 2825797.14 | 0 | 581978.4 |  | 5337984.8
285 |  |  |  | WAIP | Waipa Networks Limited | N/A | All Locations |  |  | 0 |  |  | 3367.32 | 2566400 |  | 2569767.32 | [6 empty] | 2566400 |  | 2566400
286 |  |  |  | WAIP | Waipa Networks Limited | HTU | Hautapu | 113300.46 | [5 empty] | 1256862.12 |  | 1370162.58 | 155126.31 |  | 0 |  | 0 | 0 | 1256862.12 |  | 1411988.43
287 |  |  |  | WATA | Network Waitaki Limited | BPT110S1 | Blackpoint | 16975.8 |  | 100417.35 |  | 407778.96 |  | 158270.04 |  | 683442.15 | 23023.81 |  | 105809.14 |  | 465430.69 | 0 | 158270.04 |  | 752533.68
288 |  |  |  | WATA | Network Waitaki Limited | OAM033S1 | Oamaru | 689046.72 |  | 647918.66 |  | 3093179.16 |  | 53075.16 |  | 4483219.7 | 748135.5 |  | 692992.47 |  | 3772762.69 | 0 | 53075.16 |  | 5266965.82
289 |  |  |  | WATA | Network Waitaki Limited | TWZ033S1/TWZ033S3 | Twizel | 291596.4 |  | 34540.4 |  | 177453.24 |  |  |  | 503590.04 | 261736.25 |  | 35779.56 |  | 244017.19 | 0 |  |  | 541533
290 |  |  |  | WATA | Network Waitaki Limited | WTK011S2 | Waitaki | 208369.44 |  | 85618.67 |  | 555650.16 |  | 41405.11 |  | 891043.38 | 237601.18 |  | 89305.47 |  | 654993.52 | 0 | 41405.11 |  | 1023305.28
291 |  |  |  | WATA | Network Waitaki Limited | N/A | All Locations |  |  | 0 |  |  | 2783.28 |  |  | 2783.28 | [8 empty] | 0
292 |  |  |  | WAV1 | Waverley Windfarm Limited | WVY011S1 | Waverley | 44373.6 |  | 512435.17 |  | 10213.56 |  |  |  | 567022.33 | 48070.94 |  | 631423.9 |  | 25161.5 | 0 |  |  | 704656.34
293 |  |  |  | WAV1 | Waverley Windfarm Limited | N/A | All Locations |  |  | 0 |  |  | 85.32 |  |  | 85.32 | [8 empty] | 0
294 |  |  |  | WELE | WEL Networks Limited | HAM011S1 | Hamilton | 1172826.48 |  | 2937998.57 |  | 10033848.96 |  | 117405.96 |  | 14262079.97 | 1265271.88 |  | 3344033.8 |  | 12452858.33 | 0 | 117405.96 |  | 17179569.97
295 |  |  |  | WELE | WEL Networks Limited | HLY033SA | Huntly | 200715.36 |  | 843413.76 |  | 1678872.48 |  | 697197.6 |  | 3420199.2 | 218505.96 |  | 895508.42 |  | 2138912.1 | 0 | 697197.6 |  | 3950124.08
296 |  |  |  | WELE | WEL Networks Limited | Training Centre | Meremere |  |  |  |  | 102 |  |  |  | 102 | [8 empty] | 0
297 |  |  |  | WELE | WEL Networks Limited | TWH033S1 | Te Kowhai | 346980.48 |  | 211710.08 |  | 7035675.12 |  | 479295.94 |  | 8073661.62 | 372868.9 |  | 289187.75 |  | 8758798.35 | 0 | 479295.94 |  | 9900150.94
298 |  |  |  | WELE | WEL Networks Limited | N/A | All Locations |  |  | 0 |  |  | 12068.88 |  |  | 12068.88 | [8 empty] | 0
299 |  |  |  | WNST | Winstone Pulp International | TNG011S1 | Tangiwai |  |  | -297.19 | [5 empty] | -297.19 | 0 |  | 3828.23 |  | 0 | 0 |  |  | 3828.23
300 |  |  |  | WNST | Winstone Pulp International | N/A | All Locations |  |  | 0 | [5 empty] | 0 | [8 empty] | 0
301 |  |  |  | WPOW | Westpower Limited | NA | Atarau |  |  | 13327.21 |  | 50850.48 |  |  |  | 64177.69 | 0 |  | 17369.81 |  | 62096.57 | 0 |  |  | 79466.38
302 |  |  |  | WPOW | Westpower Limited | DOB033S1 | Dobson | 330398.04 |  | 27226.79 |  | 579566.28 |  |  |  | 937191.11 | 356388.57 |  | 32740.87 |  | 706945.56 | 0 |  |  | 1096075
303 |  |  |  | WPOW | Westpower Limited | GYM066S1 | Greymouth | 6332.28 |  | 135139.48 |  | 749311.2 |  |  |  | 890782.96 | 6812.9 |  | 159254.85 |  | 918312.72 | 0 |  |  | 1084380.47
304 |  |  |  | WPOW | Westpower Limited | HKK066S1 | Hokitika | 146637.48 |  | 95006.4 |  | 1488185.28 |  |  |  | 1729829.16 | 167511 |  | 109306.39 |  | 1804383 | 0 |  |  | 2081200.39
305 |  |  |  | WPOW | Westpower Limited | KUM066S1 | Kumara | 3166.2 |  | 16526.39 |  | 106503.24 |  |  |  | 126195.83 | 3406.45 |  | 22716.28 |  | 134144.51 | 0 |  |  | 160267.24
306 |  |  |  | WPOW | Westpower Limited | OTI011S1 | Otira | 152629.68 |  | 4793.55 |  | 18825.84 |  |  |  | 176249.07 | 164670.98 |  | 5384.87 |  | 21893.02 | 0 |  |  | 191948.87
307 |  |  |  | WPOW | Westpower Limited | RFN110SA | Reefton | 4531.2 |  | 101898.45 |  | 268085.4 |  |  |  | 374515.05 | 13211.28 |  | 125149.24 |  | 332773.92 | 0 |  |  | 471134.44
308 |  |  |  | WPOW | Westpower Limited | N/A | All Locations |  |  | 0 |  |  | 1958.4 | 0 |  | 1958.4 | [6 empty] | 0 |  | 0
309 |  |  |  | WTOM | The Lines Company Ltd | HTI033S1 | Hangatiki | 415439.76 |  | 863225.04 |  | 3024979.56 |  | 0 |  | 4303644.36 | 452676.62 |  | 973135.44 |  | 3683995.08 | 0 | 0 |  | 5109807.14
310 |  |  |  | WTOM | The Lines Company Ltd | NPK033S1 | National Park | 427622.76 |  | 100235.48 |  | 258873.36 |  | 0 |  | 786731.6 | 462070.49 |  | 111826.6 |  | 307145.85 | 0 | 0 |  | 881042.94
311 |  |  |  | WTOM | The Lines Company Ltd | OKN011S2 | Ohakune | 246976.56 |  | 110604.48 |  | 282784.56 |  | 0 |  | 640365.6 | 261230.19 |  | 123206.93 |  | 346343.51 | 0 | 0 |  | 730780.63
312 |  |  |  | WTOM | The Lines Company Ltd | ONG033S1 | Ongarue | 297834.6 |  | 81428.16 |  | 686430.72 |  | 0 |  | 1065693.48 | 322841.87 |  | 92472.83 |  | 847137.51 | 0 | 0 |  | 1262452.21
313 |  |  |  | WTOM | The Lines Company Ltd | TNG011S1 | Tangiwai |  |  |  |  | 289.08 |  | 0 |  | 289.08 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0
314 |  |  |  | WTOM | The Lines Company Ltd | TKU033S1 | Tokaanu | 154357.32 |  | 112320.67 |  | 533177.52 |  | 0 |  | 799855.51 | 133856.22 |  | 130620.3 |  | 665775.19 | 0 | 0 |  | 930251.71
315 |  |  |  | WTOM | The Lines Company Ltd | N/A | All Locations |  |  | -94.88 |  |  | 3071.52 | 0 |  | 2976.64 | [6 empty] | 0 |  | 0
316 |  |  |  | EASG | Eastland Generation Ltd | KAW011S1/SA/S2 | Kawerau | 113597.16 |  | 220186.01 |  |  |  | 0 |  | 333783.17 | [6 empty] | 0 |  | 0
317 |  |  |  | EASG | Eastland Generation Ltd | N/A | All Locations | [6 empty] | 0 |  | 0 | [6 empty] | 0 |  | 0
318 |  |  |  | LODS | Lodestone Solar Ltd | N/A | All Locations | -17354.21 | [5 empty] | 0 |  | -17354.21 | [6 empty] | 0 |  | 0
319 |  |  |  | LODS | Lodestone Solar Ltd | WAI011S1/WAI005S1 | Waiotahe | 886653.01 |  | 69059.43 |  |  |  | 0 |  | 955712.44 | 795771.5 |  | 76678.44 |  |  |  | 0 |  | 872449.94
320 |  |  |  | SOU2 | Pioneer Energy Renewables LP | MAT110S1 | Matahina | 268480.2 |  | 37247.47 |  |  |  | 0 |  | 305727.67 |  |  |  |  | 0 | 0 | 0 |  | 0
321 |  |  |  | SOU2 | Pioneer Energy Renewables LP | N/A | All Locations |  |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 |  | 0
322 |  |  |  | N/A | Fonterra Todd Cogeneration | N/A | Hawera | [8 empty] | 0 | 177679.15 |  | 304093.78 |  | 2004016.7 |  |  |  | 2485789.63
323 |  |  |  | UNET | Wellington Electricity Lines Limited | N/A | Ngauranga | [8 empty] | 0 | 417384.31 | [7 empty] | 417384.31
324 | [15 empty] | 0 | [8 empty] | 0
325 | [15 empty] | 0 | [8 empty] | 0
326 |  |  |  |  | EV Account Adjustment | [6 empty] | -44696844 |  |  |  | -44696844 | [8 empty] | 0
327 | [15 empty] | 0 | [8 empty] | 0
328 |  |  |  | TOTALS |  |  |  | 150770315.68 | 0 | 304579826.71 | 0 | 474950056.08 | -1468.56 | 46334285.65 | 0 | 976633015.56 | 163304378.1 | 0 | 335053107.93 | 0 | 642993229.22 | 0 | 48193752.1103 | 0 | 1189544467.3603
329 |  |  |  | *Insert additional rows and update calculation of totals as needed
330
331 | F6(iv): Other Regulated Income (excl Asset Disposals)
332
333 |  |  |  |  | Total Income | Distributors | Direct Connects | Generators | Other
334 |  |  |  | Type of Income | ($M) | ($M) | ($M) | ($M) | ($M)
335 |  |  |  | Insurance Proceeds | 88985 |  |  |  | 88985 | (Claims Paid in DY = $47k Lower North Island Conductor Drop 09/06/26, $41k for Haywards Circuit Breaker replacement 09/06/26)
336 |  |  |  | Scrap Metal proceeds (120 items avg $10k each) | 1185229 |  |  |  | 1185229
337 |  |  |  | Meridian Transformer Lease | 108000 |  |  | 108000
338 |  |  |  | Micellaneous items | 70819 |  |  |  | 70819
339 |  |  |  | Car park lease | 65265 |  |  |  | 65265
340 |  |  |  | TOTAL | 1518298 | 0 | 0 | 108000 | 1410298
341 |  |  |  | *Insert additional rows and update calculation of totals as needed
342
343 | F6(v): Asset Disposals
344
345 |  |  |  |  | Total Income/(Loss) | Disposal Value
346 |  |  |  |  | ($M) | ($M)
347 |  |  |  | TOTAL (Minor Assets) | -5660999.5652 | 6398067.1352
348
349
350 | F6(vi): Asset Divestments
351
352 |  |  |  | Party Asset Divested to | Description of Assets Divested | Disposal Value
353 | [5 empty] | ($M)
354 |  |  |  | Metservice | Lightning Detection Network | 1
355
356
357 |  |  |  | TOTAL | 0 | 1
358 |  |  |  | *Insert additional rows and update calculation of totals as needed
359

## F7. Cost Allocation
SCHEDULE 7: Cost allocation
7(i): Operating Cost Allocations
Section | Row | Category1 | Category2 | Arm's length deduction¦Value allocated ($M) | Transmission lines services¦Value allocated ($M) | Other services (includes unregulated services, system operator and investment contracts)¦Value allocated ($M) | Total¦Value allocated ($M) | ABAA allocation increase¦Value allocated ($M)
7(i): Operating Cost Allocations | 5 | Grid maintenance | Directly attributable |  | 148310707.95
7(i): Operating Cost Allocations | 6 | Grid maintenance | Not directly attributable |  |  |  | 0
7(i): Operating Cost Allocations | 7 | Total attributable to regulated service |  |  | 148310707.95
7(i): Operating Cost Allocations | 8 | ICT | Directly attributable |  | 37804207.3378
7(i): Operating Cost Allocations | 9 | ICT | Not directly attributable | 44796.2208 | 24490242.5853 | 4183569.4939 | 28718608.3 | -63335.5529
7(i): Operating Cost Allocations | 10 | Total attributable to regulated service |  |  | 62294449.9231
7(i): Operating Cost Allocations | 11 | Asset Management & Operations | Directly attributable |  | 94079841.3551
7(i): Operating Cost Allocations | 12 | Asset Management & Operations | Not directly attributable |  | 0 |  | 0
7(i): Operating Cost Allocations | 13 | Total attributable to regulated service |  |  | 94079841.3551
7(i): Operating Cost Allocations | 14 | Business support | Directly attributable |  | 44906414.046
7(i): Operating Cost Allocations | 15 | Business support | Not directly attributable | 73809.0454 | 21544246.8845 | 1545916.5601 | 23163972.49 | -75174.8741
7(i): Operating Cost Allocations | 16 | Total attributable to regulated service |  |  | 66450660.9305
7(i): Operating Cost Allocations | 17 | Insurance | Directly attributable |  | 30995060.52
7(i): Operating Cost Allocations | 18 | Insurance | Not directly attributable |  | 0 |  | 0
7(i): Operating Cost Allocations | 19 | Total attributable to regulated service |  |  | 30995060.52
7(i): Operating Cost Allocations | 20 | Operating costs directly attributable |  |  | 356096231.2089
7(i): Operating Cost Allocations | 21 | Operating costs not directly attributable |  | 118605.2662 | 46034489.4698 | 5729486.054 | 51882580.79 | -138510.4271
7(i): Operating Cost Allocations | 22 | Operating expenditure |  |  | 402130720.6787
a

## F7a. Asset Allocation
SCHEDULE 7a: Asset allocation
7a(i): Regulated Service Asset Allocations
Section | Row | Category1 | Category2 | Transmission lines services¦Value allocated ($M)
7a(i): Regulated Service Asset Allocations | 5 | HVAC Substations | Directly attributable | 2009200000
7a(i): Regulated Service Asset Allocations | 6 | HVAC Substations | Not directly attributable | 0
7a(i): Regulated Service Asset Allocations | 7 | Total attributable to regulated service |  | 2009200000
7a(i): Regulated Service Asset Allocations | 8 | HVAC Lines and Transmission cables | Directly attributable | 2325300000
7a(i): Regulated Service Asset Allocations | 9 | HVAC Lines and Transmission cables | Not directly attributable | 0
7a(i): Regulated Service Asset Allocations | 10 | Total attributable to regulated service |  | 2325300000
7a(i): Regulated Service Asset Allocations | 11 | HVDC Substations and Submarine cables | Directly attributable | 422700000
7a(i): Regulated Service Asset Allocations | 12 | HVDC Substations and Submarine cables | Not directly attributable | 0
7a(i): Regulated Service Asset Allocations | 13 | Total attributable to regulated service |  | 422700000
7a(i): Regulated Service Asset Allocations | 14 | HVDC Lines | Directly attributable | 100600000
7a(i): Regulated Service Asset Allocations | 15 | HVDC Lines | Not directly attributable | 0
7a(i): Regulated Service Asset Allocations | 16 | Total attributable to regulated service |  | 100600000
7a(i): Regulated Service Asset Allocations | 17 | Easements | Directly attributable | 319700000
7a(i): Regulated Service Asset Allocations | 18 | Easements | Not directly attributable | 0
7a(i): Regulated Service Asset Allocations | 19 | Total attributable to regulated service |  | 319700000
7a(i): Regulated Service Asset Allocations | 20 | Intangibles | Directly attributable | 58512825.7215
7a(i): Regulated Service Asset Allocations | 21 | Intangibles | Not directly attributable | 2187174.2786
7a(i): Regulated Service Asset Allocations | 22 | Total attributable to regulated service |  | 60700000
7a(i): Regulated Service Asset Allocations | 23 | IST | Directly attributable | 147060185.3632
7a(i): Regulated Service Asset Allocations | 24 | IST | Not directly attributable | 3139814.6368
7a(i): Regulated Service Asset Allocations | 25 | Total attributable to regulated service |  | 150200000
7a(i): Regulated Service Asset Allocations | 26 | Business Support | Directly attributable | 144696959.1642
7a(i): Regulated Service Asset Allocations | 27 | Business Support | Not directly attributable | 48203040.8358
7a(i): Regulated Service Asset Allocations | 28 | Total attributable to regulated service |  | 192900000
7a(i): Regulated Service Asset Allocations | 29 | Pseudo Assets | Directly attributable | 41500000
7a(i): Regulated Service Asset Allocations | 30 | Pseudo Assets | Not directly attributable | 0
7a(i): Regulated Service Asset Allocations | 31 | Total attributable to regulated service |  | 41500000
7a(i): Regulated Service Asset Allocations | 32 | Regulated service asset value directly attributed |  | 5569269970.2488
7a(i): Regulated Service Asset Allocations | 33 | Regulated service asset value not directly attributed |  | 53530029.7512
7a(i): Regulated Service Asset Allocations | 34 | Total closing RAB value |  | 5622800000
7a(ii): Changes in Asset Allocations*† | [13 empty] | Required from disclosure year 2026
Section | Row | Category1 | Category2 | Asset category | Original allocator or line items | New allocator or line items | Rationale for change | Original allocation¦ CY-1¦ ($M) | Original allocation¦ Current Year (CY)¦ ($M) | New allocation¦ CY-1¦ ($M) | New allocation¦ Current Year (CY)¦ ($M) | Difference¦ CY-1¦ ($M) | Difference¦ Current Year (CY)¦ ($M)
7a(ii): Changes in Asset Allocations*† | 40 | Change in asset value allocation 1 | [9 empty] | 0 | 0
7a(ii): Changes in Asset Allocations*† | 41 | Change in asset value allocation 2 | [9 empty] | 0 | 0
7a(ii): Changes in Asset Allocations*† | 42 | Change in asset value allocation 3 | [9 empty] | 0 | 0
* a change in asset allocation must be completed for each allocator or component change that has occurred in the disclosure year.
† include additional rows if needed

## TP1. ROI and profit
|  |  | Transpower | Disclosure Date | 2026-10-23
Return on Investment (ROI) and Profit calculations |  |  |  | Disclosure Year (year ended) | 2026-06-30
Refer to paragraphs 8.7 to 8.14 of the Transpower Information Disclosure Determination 2014
Reconciliation from the regulatory WACC to our ROI (clause 8.10.2)
65th percentile vanilla WACC (IPP version) | 7.096%
Inflation adjustment (through the revaluation building block) | 1.179%
Effect of permanent voluntary revenue reductions | 0%
Contribution from incentives | 0.7694%
Transpower's actual ROI | 9.045%
Adjust for exclusion of interest on EV account from ROI calculation | -0.05652%
Double-count TCSD in tax allowance | 0.04208%
Adjust to include IRIS as cashflow in regulatory profit calculation | 0.07481%
Apply incorrect cashflow timing factor adjustment to revenue | 0.6078%
Vanilla ROI calculated under clause 8.7 | 9.713%
Transpower's ROI (clauses 8.7 and 8.8)
ROI (vanilla) | 9.713% | Vanilla ROI calculated as required by Clause 8.7
Cost of debt (ID) | 5.44%
ROI (post-tax) | 9.088% | Post-tax ROI calculated as required by Clause 8.8
A comparison of our ROI to the WACC used to calculate our revenue (clause 8.9.4)
ROI (vanilla) | 9.713% | per clause 8.7
65th percentile vanilla WACC (IPP version) | 7.096% | this is the WACC used for the purposes of calculating revenue for the disclosure year
Difference | 2.616%
Comparison required by Clause 8.9.2
ROI (vanilla) | 9.713% | per clause 8.7
75th percentile vanilla WACC (ID version) | 7.16%
Difference | 2.553%
Comparison required by Clause 8.10.3
ROI (post-tax) | 9.088% | per clause 8.8
75th percentile post-tax WACC (ID version) | 6.53%
Difference | 2.558%
Clause 8.11.1 and clause 8.11.3
This difference has the same components as those described under Clause 8.11.2 above, but with the added difference that the ID vanilla WACC rate is different from the IPP vanilla WACC rate and
the 65th and 75th percentile WACCs are different.
65th percentile vanilla WACC (IPP version) | 7.096%
75th percentile vanilla WACC (ID version) | 7.16%
Difference | -0.0637%
as above | 2.616%
as above (8.8.3) | 2.553%
Comparison required by Clause 8.9.2
ROI (vanilla) | 9.713% | per clause 8.7
Mid-point vanilla WACC (ID version) | 6.43%
Difference | 3.283% | this difference (also see below) is the same as those calculated above but updated for the difference between the mid-point and 75th percentile WACCs
Comparison required by Clause 8.10.2
ROI (post-tax) | 9.088% | per clause 8.8
Mid-point post-tax WACC (ID version) | 5.8%
Difference | 3.288% | see above
Regulatory profit/(loss) before tax
Revenue | 981794887.952
Operating expenditure (incl. operating lease costs capitalised under GAAP) | -414859506.6787
Pass-through costs | -19213789.25
Recoverable costs | -4640834.2401
Depreciation (tax depreciation and write-offs) | -364796764.4016
TCSD | -2162872.9131 | double counted in Notional Interest until the rules are corrected
Regulatory profit/(loss) before tax | 176121120.4686 | Disclosure required by Clause 8.12
Notional interest (IM clause 2.3.1(3)(a)) | -114362110.0912
61759010.3774
Tax | 17292522.9057
Regulatory profit/(loss) before tax including EV account movement | 222966527.961 | Disclosure required by Clause 8.13
Regulatory profit/(loss) after tax including EV account movement | 192557290.9574 | Disclosure required by Clause 8.14

## TP2. Major project costs
|  |  |  | Transpower |  | Disclosure Date |  | 2026-10-23
SCHEDULE TP2: PARTIALLY COMPLETED MAJOR PROJECTS: COSTS | [5 empty] | Disclosure Year (year ended) |  | 2026-06-30
ref
5 | Updated cost forecasts for partially completed major projects
6
7 |  |  | Major capex allowance | Current forecast expected cost | Original forecast expected costs | Variance in the expected cost | Variance in the expected cost | Material (1)
8 |  |  | ($M) | ($M) | ($M) | ($M) | (%) | (Y or N)
9 |  | Stage 1 - Waikato and Upper North Island Voltage Management | 143000000 | 106834560 | 143000000 | -36165440 | -25.29% | Y
10 |  | Net Zero Grid Pathways Stage 1 | 392900000 | 295130645 | 392900000 | -97769355 | -24.88% | Y
11 |  | Western Bay of Plenty | 86100000 | 86100000 | 86100000 | 0 | 0% | N
12 |  | Redclyffe 220kV Switchyard Resilience | 47000000 | 46710196 | 47000000 | -289804 | -0.6166% | N
13 |  | HVDC Link Upgrade Programme Stage 1 | 1138600000 | 1138600000 | 1138600000 | 0 | 0% | N
14 |  |  | 1807600000 | 1673375401 | 1807600000 | -134224599
15
16 |  | (1) 'Material' has been specified in our Information Disclosure Determination as being greater than 10% or $10m.
17
19 |  | Stage 1 - Waikato and Upper North Island Voltage Management
20 |  | The reduction in cost is driven by three primary factors: a Special Protection Scheme that will no longer be constructed, a land purchase at Hangawera for a new site to host series capacitors that is not required, and thirdly a reduction in forecast due to cost savings realised through the construction phases of the Hamilton and Otahuhu STATCOMs.
Net Zero Grid Pathways Stage 1
22 |  | The lower forecast reflects the exclusion of the $32 million risk allowance and savings achieved through optimisation of thermal upgrade scopes in the Central North Island and Wairakei Ring areas. Haywards STATCOM tenders are currently under review and are expected to increase the NZGP forecast.
23
23 |  | Western Bay of Plenty
23 |  | The project is currently in the early detailed design phase, and pricing and detailed scope for major works has not yet been confirmed. The lower forecast vs the MAC reflects the exclusion of risk allowances from the forecast.
23

## TP3. Major project timing
|  |  | Transpower | Disclosure Date | 2026-10-23
SCHEDULE TP3: PARTIALLY COMPLETED MAJOR PROJECTS: TIMING |  |  |  | Disclosure Year (year ended) | 2026-06-30
ref
5 | Updated timing forecasts for partially completed major projects
6
7 |  |  | Forecast commissioning at approval | Current forecast commissioning | Material (1)
8 |  |  | (date or date range) | (date or date range) | (Y or N)
9 |  | Waikato and Upper North Island Voltage Management Stage 1 | Dec 2022 (except for Stage 2 preparatory works) | 2023 to October 2025 for final commission of assets in Stage 1 - except for ongoing investigation costs and preparatory works | Y
|  | Net Zero Grid Pathways Stage 1 | Various with final commissioning June 2028 | Various with final commissioning for build work June 2029. Stage 2 preparatory work cannot be commissioned until Stage 2 is built | Y
|  | Western Bay of Plenty | Various with final commissioning in Dec 2032 | Various with final commissioning in Dec 2032 | N
|  | Redclyffe 220kV Switchyard Resilience | 2027-12-01 | 2027-12-01 | N
|  | HVDC Link Upgrade Programme Stage 1 | Various with final commissioning December 2031 | Various with final commissioning December 2031 | N
14
15 |  | (1) 'Material' has been specified in our Information Disclosure Determination as being greater than 3 months
16
17
18 |  | Stage 1 - Waikato and Upper North Island Voltage Management (WUNIVM):
19 |  | The WUNIVM investment challenge was complex when considering both prospective generation changes from the Huntly Power Station, and demand growth in the region. Given these uncertainties, the potential for a significant reduction in generation at short notice, and the lead times for investment, Transpower initially decided to proceed with the first phase of the WUNIVM stage 1 proposal in November 2020: one grid stability device at Hamilton with a target commissioning date of winter 2023. This plan reduced risk by addressing voltage stability needs should regional thermal generation reduce, and demand increase as forecast. Transpower needed 30 months to install the equipment. By undertaking construction of the first of two phases of stage one of the project, we could adequately manage risk to electricity supply by winter 2023 and the following one to two years. Prior to committing to the device at Hamilton, we investigated possible non-transmission alternatives to the transmission investment. Given the technical performance requirements of the voltage stability need at Hamilton we were unable to secure a lower-cost option. We then undertook an RFP process for the installation of a non-transmission investment that could potentially defer or replace the need for transmission investment of the second STATCOM at Otahuhu. This evaluation concluded that neither Battery Energy Storage Systems options were economic when compared with the second STATCOM. As a result, the Ōtāhuhu STATCOM remained the preferred solution and was subsequently delivered and commissioned, with the final milestone payment made in FY26. The approved WUNI Stage 1 delivery outputs have now been completed, with both STATCOM installations commissioned and operational. The only remaining activity under the WUNI Stage 1 approval relates to the Stage 2 investigation programme, including preparatory work and development of the WUNI Stage 2 Major Capex Proposal. The WUNI Stage 2 submission is currently expected to be lodged with the Commerce Commission in October 2026. |  |  |  | Commentary consistent with prior year - all build has been commissioned
20
21 |  | Net Zero Grid Pathways Stage 1
22 |  | Commissioning dates of a number for works have been extended due to long lead times from suppliers for Statcoms, as well as the requirement of lines work to be extended over an additional summer to accommodate outages and lines service provider resource. |  |  |  | Commentary consistent with prior year - all build has been commissioned
23

## TP5. Related party transactions
|  |  | Transpower | Disclosure Date | 2026-10-23
SCHEDULE TP5: RELATED PARTY TRANSACTIONS |  |  |  | Disclosure Year (year ended) | 2026-06-30
ref
5
6 | Transactions with key management personnel
7 | The Group did not conduct any business with key management personnel aside from the compensation payments below.
8
9 | Key management personnel compensation
10 | Key management personnel received the following compensation for their services to the Group.
11
12 |  | $m
13 | Directors' fees | 1
14 | Other key management personnel | 7
15 | Defined contribution schemes | 0
16
17 | There were no termination payments to key management personnel in 2026.
18 | There was no long-term compensation paid to key management personnel in 2026.
19
20 | Transactions with other parts of Transpower | $m
21 | Risk Reinsurance Limited - claims received | -2.4
| Risk Reinsurance Limited - interest received | -0.6
23 | Risk Reinsurance Limited - intercompany facility fee received | 0.5
24 | Risk Reinsurance Limited - premiums paid | -29.7
25 | Risk Reinsurance Limited - insurance expenses paid | 0.6
26
27 | Transpower procures insurance services from a captive insurance company, Risk Reinsurance Limited.
28 | Note that transactions with Risk Reinsurance Limited (RRL) are valued consistent with IFRS17, following RRL’s adoption of the standard from disclosure year 2024.
29
30 | Some directors of the company may be directors or officers of other companies or organisations with
31 | which Transpower may transact.
32
33 | All transactions are carried out at on an "arm's length" basis.
34

## TP6. Investment contracts
Investment Contracts (new contracts in the disclosure year) |  | Transpower |  | Disclosure Date |  |  | 2026-10-23
under paragraph 10 of the Transpower Information Disclosure Determination 2014 |  |  |  | Disclosure Year (year ended) |  |  | 2026-06-30
Transmission Works Agreements (TWA) - Investment Contracts signed between 1 July to 30 June |  |  |  |  | Required from 2026 |  | Required from 2026
Customer Name | Contract Title | Brief Description | Contract Signed Date | New Investment Contract - Total Capacity (kV) | Anticipatory Connection Asset - ACA Capacity | New Investment Contract Costs (Budget / estimated build costs) | New Investment Contract Costs allocated to ACA | New Investment Contract - Total Capacity (MW)
Tararua Wind Power Limited | Kaiwera Downs Stage 2 Windfarm TDA | Customer-led development of a Grid Injection Point (GIP) substation, approximately 15 km south-east of Gore, in Southland. The location is geographically close to the 220 kV double circuit North Makarewa-Three Mile Hill (NMA-TMH-A) line, that carries the North Makarewa-Gore - Three Mile Hill 1&2 (NMA-GOR-TMH 1&2) circuits. | 2025-07-09 | 220 | 0 | 3627861 | 0 | 155
Glorit Solar P LP | Glorit Solar Farm GIP TDA | 150MWac solar farm and Grid Injection Point (GIP) into 220 kV Line HEN-MDN-A, circuit HPI-MDN-1 at Tower A132 with a loop in out configuration at existing tower (A132) by coming off the existing tower with slack spans onto substation gantries. | 2026-05-29 | 220 | 0 | 14208389.78 | 0 | 200
Fonterra Co-operative Group Limited | Whareroa Electrification (Ohangai Sub) TWA | Transpower will construct an interconnecting switching station near Stratford tentatively known as Ohangai, enabling the Customer to connect their Whareroa plant via 110kV connection from the new substation. This will support forecasted electrification projects at the Whareroa site. Part of the intent of the construction of the Works is to provide an additional 80 MVA supply to the Whareroa manufacturing plant via Transpower’s Hawera 110 kV bus. | 2025-07-10 | 110 | 0 | 15689464.05 | 0 | 80
Meridian Energy Limited | Aviemore Outdoor Junction Box TWA | Transpower is undertaking Policy Replacement of the 220 kV Bus Zone at Aviemore Power Station (AVI) which has reached end of life and Outdoor Junction Box (ODJB) based on their age and condition. Meridian has asked Transpower to replace four ODJBs. | 23/07/2025 | N/A | 0 | 415693 | 0 | 0
Genesis Energy Limited | Huntly BESS TWA | Facilitate the connection of Genesis Energy’s 100MW BESS system, though the reinstatement of bus selector disconnector DS444 and transverse bus connections onto the 220kV ‘B’ bus. | 31/07/2025 | 220 | 0 | 548000 | 0 | 100
Contact Energy Limited | Te Mihi Stage II TWA | Enabling the connection of Contact Energy’s new 100MWgeothermal generator, through the construction of a new 220kV line bay at the existing Te Mihi site. | 31/07/2025 | 220 | 0 | 2582805 | 0 | 190
Network Tasman Limited | Brightwater GXP TWA | Network Tasman has engaged Transpower to deliver a new 220/33 kV GXP on the STK-KIK-A line, utilising Transpower’s standard design for 220/33 kV substations and a loop-in-loop-out arrangement. This GXP will support future load demand within Network Tasman’s network and increase resilience of supply within the area. | 26/09/2025 | 220 | 0 | 41951013 | 0 | 60
Harmony Energy NZ #2 Limited | Masterton Solar Farm (Harmony) TWA | The Customer is developing a 100 MW solar farm and Battery Energy Storage System (BESS) on land adjacent to the MST substation. The Customer has approached Transpower to connect their solar farm to the grid at 110 kV. | 14/10/2025 | 110 | 0 | 6256452 | 0 | 100
Top Energy Limited | KOE-MPE 110kV Runback SPS TWA | The customer has requested the expedited implementation of a Circuit Overload Protection Scheme (COPS) until the end of 2025. This runback scheme will enable increased generationdispatch capability for generation in the Far North. | 23/10/2025 | 110 | 0 | 204000 | 0 | 50
Vector Limited | Takanini 1x 33kV Feeder TWA | Vector have requested one new indoor 33 kV feeder at Transpower’s Takanini (TAK) Grid Exit Point (GXP) substation. This feeder is for Vector to further supply their zone substation. | 4/11/2025 | 33 | 0 | 550237.87 | 0 | 0
Horizon Energy Distribution Limited | Edgecumbe Capacity Increase TWA | The scope of the Transpower project is to install a new Transformer Overload Protection Scheme (TOPS) to manage loading on the existing Edgecumbe 220/33 kV transformers (T4 and T7) supplying the new Customer 33/11 kV dairy factory substation. | 3/12/2025 | 33 | 0 | 533058 | 0 | 30
Waka Kotahi New Zealand Transport Agency | C2P Project Stage 1 (Online) HIN-KPO-A TWA | Line relocation to accommodate Waka Kotahi's Cambridge to Piarere (C2P) roading project. Stage One intersects HIN-KPO-A, ARI-HAM-A, HAM-KPO-A line spans. This TWA covers the mitigation work on HIN-KPO-A line only. | 17/12/2025 | N/A | 0 | 3137000 | 0 | 0
Vector Limited | Henderson 1x 33kV Feeder (Microsoft) TWA | Design and install one new 33 kV feeder at Transpower’s Henderson (HEN) Grid Exit Point (GXP) substation for Vector. This feeder will supply a new Microsoft data centre. | 22/12/2025 | 33 | 0 | 753900 | 0 | 20
Helios Energy Limited | Waipawa Solar Farm TWA | Building connection assets to enable the connection of Helios’s Ongaonga Solar Farm onto the the WPW 110kV bus. | 22/12/2025 | 110 | 0 | 4367704.72 | 0 | 100
Vector Limited | Takanini 2x 33kV Feeders (TenPeaks/Spark) TWA | Vector have requested two new indoor 33 kV feeders at Transpower’s Takanini (TAK) Grid Exit Point (GXP) substation for Vector. These feeders are for Vector to supply their new Data Centre Customer Spark. | 22/12/2025 | 33 | 0 | 956900 | 0 | 30
Harmony Energy NZ #3 Limited | Marton Solar Farm (Harmony) TWA | The Customer is developing a 50 MW solar farm and Battery Energy Storage System (BESS) on land adjacent to the MTN substation. The Customer has approached Transpower to connect their solar farm to the grid at 110 kV. | 23/12/2025 | 110 | 0 | 7775518 | 0 | 50
MainPower New Zealand Limited | ASY 66kV Coldstream Feeder TWA | MainPower wish to radially connect a new zone substation at Coldstream to the Ashley 66kV bus. | 23/12/2025 | 66 | 0 | 3154631 | 0 | 0
Vector Limited | Silverdale 2x 33kV Feeders (CDC) TWA | Building two new 33kV feeders at Transpower’s Silverdale (SVL), including switchroom upgrades to supply Vector’s data centre customers. | 19/03/2026 | 33 | 0 | 2583000 | 0 | 30
Alpine Energy Limited | TIM 33kV GXP Upgrade TWA | Installation of two new 120 MVA 220/33 kV supply transformers at TIM substation to address load growth in Washdyke.Installation of two new 120 MVA 220/33 kV supply transformers and supporting power electronics/switchgear at TIM substation to address load growth in the Washdyke area. | 30/03/2026 | 110 | 0 | 44116600 | 0 | 40
Helios Energy Limited | Karioi Solar Farm (Tangiwai Solar + BESS) TWA | Building connection assets to the enable the connection of Helios’ 110MW solar farm onto the TNG 220kV ‘B’ bus. | 23/04/2026 | 220 | 0 | 4007451.29 | 0 | 110
Waka Kotahi New Zealand Transport Agency | Mill Road TWA | The existing Transpower Tower 195 on the Huntly-Otahuhu A (HLY-OTA-A) 220 kV transmission line is located within the proposed road designation of the NZTA Mill Road upgrade and must be removed and a new tower (Tower 195A) built outside the road reserve to enable the roading works to proceed. | 12/05/2026 | N/A | 0 | 2690058 | 0 | 0
Waka Kotahi New Zealand Transport Agency | C2P Project Stage 1 (Online) ARI-HAM-A & HAM-KPO-A TWA | Line relocation to accommodate Waka Kotahi's Cambridge to Piarere (C2P) roading project. Stage One intersects HIN-KPO-A, ARI-HAM-A, HAM-KPO-A line spans. This TWA covers the mitigation work on ARI-HAM-A and HAM-KPO-A lines. | 12/06/2026 | N/A | 0 | 2809534 | 0 | 0
Kahahakuri Limited | Waipawa Solar Farm TWA | The customer plans to develop a 100 MW solar farm adjacent to the Transpower, Waipawa substation. There will be a 110/33 kV substation within the solar farm site and a single-circuit 110 kV line connecting it to the Waipawa substation. | 30/06/2026 | 110 | 0 | 6441000 | 0 | 100
NOTE: PPAs are not included in investment contracts as these agreements are for materials and not the provision of electricity transmission services |  |  |  |  | 0 | 162919270.71 | 0 | 1345
NOTE: The kilovolt (kV) figures in column E are not cumulative and refers to the maximum voltage that a transmission line can carry. For new/added capacity in megawatts (MW), please see column I.

## G1. System Statistics
|  |  | Transpower |  | Disclosure Date | 2026-10-23
SCHEDULE G1: TRANSMISSION SYSTEM STATISTICS |  |  |  |  | Disclosure Year (year ended) | 2026-06-30
ref
5 | G1(i): Circuit Information | Transmission System Statistics
6
7 |  | System length by operating voltage (kV) | CY-1 (km) | CY (km)
8 |  | Total | 16525.93 | 16538.25
9 |  | 350kV (HVDC) | 1262.97 | 1262.97
10 |  | 0 kV (HVDC earth electrode) | 12.05 | 12.05
11 |  | 220kV (HVAC) | 9114.65 | 9122.44
12 |  | 110kV (HVAC) | 5490.35 | 5494.88
13 |  | 66/50kV (HVAC) (Includes leased assets) | 645.91 | 645.91
14
15 |  | Circuit length of overhead electric lines by operating voltage (kV)
16 |  | Total | 16316.09 | 16328.93
17 |  | 350kV (HVDC) | 1142.34 | 1142.34
18 |  | 0 kV (HVDC earth electrode) | 12.05 | 12.05
19 |  | 220kV (HVAC) | 9049.56 | 9057.87
20 |  | 110kV (HVAC) | 5469.04 | 5473.57
21 |  | 66/50kV (HVAC) (includes leased assets) | 643.1 | 643.1
23 |  | Route length of overhead electric lines by operating voltage (kV)
24 |  | Total | 10906.17 | 10917.18
25 |  | 350kV (HVDC) | 571.17 | 571.17
26 |  | 0 kV (HVDC earth electrode) | 12.05 | 12.05
27 |  | 220kV (HVAC) | 5919.25 | 5924.3
28 |  | 110kV (HVAC) | 4075.07 | 4081.03
29 |  | 66/50kV (HVAC) (includes leased assets) | 328.63 | 328.63
31 |  | Circuit length of HVAC underground transmission cable by operating voltage (kV)
32 |  | Total | 89.21 | 88.69
33 |  | 350kV (HVDC) | 0 | 0
34 |  | 220kV (HVAC) | 65.09 | 64.57
35 |  | 110kV (HVAC) | 21.31 | 21.31
36 |  | 66kV (HVAC) | 2.81 | 2.81
38 |  | Total length of HVDC submarine cable by operating voltage (kV)
39 |  | Total | 120.63 | 120.63
40 |  | 350kV (HVDC) | 120.63 | 120.63
41
42 |  |  | CY-1 (Quantity) | CY (Quantity)
43 |  | HVAC Substation/Switching Station | 173 | 174
44 |  | HVDC Convertor stations | 2 | 2
45 |  | HVDC Electrode stations | 2 | 2
46 |  | HVDC Cable transition stations | 2 | 2
47 |  | HVAC Cable transition stations | 15 | 15
48 |  | Interconnecting Transformer Banks ( 66 kV and above) | 56 | 56
49 |  | Supply Transformer Banks ( 66 kV and above) | 246 | 247
50 |  | Dynamic Reactive power Static (SVCs and STATCOMs) | 11 | 11
51 |  | Dynamic Reactive power Synchronous Condensers | 8 | 8
52 |  | Capacitor Banks (HVAC System) | 61 | 61
53 |  | AC filter Banks (HVDC) | 14 | 14
54 |  | Series and Shunt reactors | 134 | 134
55 |  | Outdoor Circuit Breakers ( 66 kV and above) | 1198 | 1208
56 |  | Outdoor Circuit Breakers (33,22,11kV) | 158 | 134
57 |  | Indoor Circuit Breakers ( 66 kV and above) | 73 | 73
58 |  | Indoor Circuit Breakers (33,22,11kV) | 1083 | 1100
59

## G2. Grid Demand and Injection
[6 empty] | Transpower |  | Disclosure Date | 2026-10-23
SCHEDULE G2: GRID DEMAND AND INJECTION | [7 empty] | Disclosure Year (year ended) | 2026-06-30
ref
5 | G2(i): Demand and Injection
6 |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
7 |  | Energy Volume (GWh) |  | (GWh) | (GWh) | (GWh) | (GWh) | (GWh)
8 |  |  | Generators (Injection) | 37621.2635 | 37945.8546 | 38372.6401 | 37143.1 | 38080.6952
9 |  |  | GXP-EDBs (offtake) | 30875.8585 | 31115.5327 | 32002.8752 | 31521.74 | 31528.9612
10 |  |  | GXP-direct connects (Offtake) | 6698.3162 | 6541.4076 | 6342.2661 | 5563.82 | 6547.8265
11 |  |  | HVDC flows north | 3206.1183 | 3445.7202 | 2324.3044 | 2017.41 | 2655.9161
12 |  |  | HVDC flows south | 171.2783 | 208.4649 | 380.4834 | 745.26 | 311.4383
13 |  |  | HVDC Losses | 122.2175 | 136.8536 | 90.3007 | 95.94 | 104.1895
14 |  |  | AC System Losses | 1314.0607 | 1361.8535 | 1240.9011 | 1311.68 | 1366.5558
15
|  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
17 |  | Maximum peak demand (MW) |  | (MW) | (MW) | (MW) | (MW) | (MW)
18 |  |  | Generators (Injection) | 6741.6326 | 6674.0215 | 6864.13 | 6632.69 | 6888.3
19 |  |  | GXP-EDBs (offtake) | 5924.438 | 5764.7683 | 5965.03 | 5834.4 | 6014.48
20 |  |  | GXP-direct connects (Offtake) | 833.344 | 821.0555 | 788.65 | 742.99 | 918.51
21 |  |  | HVDC flows north | 1025.16 | 1108.9106 | 932.38 | 999.78 | 943.39
22 |  |  | HVDC flows south | 542.0445 | 687.3949 | 578.5 | 765.93 | 620.01
23 |  |  | HVDC Losses | 57.4255 | 66.096 | 46.84 | 55.16 | 48.84
24 |  |  | AC System Losses | 286.0115 | 281.1247 | 264.12 | 268 | 277.06
25
26

## G3. GXP Capacity and Demand
[11 empty] | Transpower |  | Disclosure Date |  | 2026-10-23
SCHEDULE G3: GRID EXIT POINT (GXP) CONNECTION CAPACITY AND DEMAND (ACTUAL AND FORECAST) | [12 empty] | Disclosure Year (year ended) |  | 2026-06-30
Disclosure of line items required and not required from disclosure year 2026 onward are specified in column U.
ref
5 | G3(i): Current Connection Capacity vs Actual and Forecast Demand
6
7 |  |  | Firm Capacity | Actual Demand (MW) | Forecast Net Demand (MW)
8 |  | GXP Name / Region Name | CY | CY | CY+1 | CY+2 | CY+3 | CY+4 | CY+5 | CY+6 | CY+7 | CY+8 | CY+9 | CY+10 | Comments on Capacity
9 |  | Bream Bay | Yes | 35.9693 | 23 | 24 | 25 | 26 | 26 | 26 | 27 | 27 | 27 | 27 | No issues.
10 |  | Kaikohe | Yes | 72.0057 | 60.1856 | 62.3304 | 64.073 | 65.944 | 68.153 | 70.1038 | 72.1802 | 74.2018 | 76.1331 | 77.7566 | The TPR reports the gross demand forecast instead of net, excluding contribution from embedded generation. Ngawha has multiple generating units and without the largest of these (Ngawha B), forecast peak load is above the n 1 limit from 2033.
11 |  | Maungatapere | N/A | 112.7913 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 128 | 129 | 129 | Northpower owns the supply transformers at Maungatapere.
12 |  | Maungaturoto | Yes | 24.819 | 25 | 26 | 27 | 27 | 28 | 29 | 30 | 30 | 31 | 31 | Peak load at Maungaturoto exceeds the n 1 capacity of the supply transformers from 2033
13 |  | Wellsford | No | 39.0619 | 45 | 46 | 47 | 50 | 52 | 54 | 55 | 58 | 60 | 62 | Peak load at Wellsford already exceeds the n-1 capacity of the supply transformers.
14 |  | Albany 33 kV | Yes | 131.7353 | 178 | 184 | 189 | 196 | 204 | 211 | 218 | 226 | 235 | 241 | Peak load at Albany is forecast to exceed the n 1 capacity of the supply transformers from winter 2034. Significant new load increases are forecast across the Auckland grid exit points of Henderson, Silverdale, Albany 33 kV, Takanini and Auckland CBD (including Hobson Street and Liverpool Street), with a large share from data centres.
15 |  | Bombay 33 kV | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Counties Energy has constructed a new zone substation supplied from Bombay 110 kV bus and has relinquished Bombay 33 kV Grid Exit Point.
16 |  | Bombay 110 kV | Yes | 98.941 | 115 | 120 | 125 | 129 | 134 | 139 | 143 | 148 | 153 | 156 | No issues.
17 |  | Glenbrook 33 kV (clean bus) | No | 60.1 | 30 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 38 | 39 | No capacity issues. The Glenbrook clean bus is supplied by a single 220/33 kV, 140 MVA transformer. The TPR reports the gross demand forecast instead of net, excluding contribution from embedded generation.
18 |  | Glenbrook - NZ Steel (dirty bus) | No | 131.68 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | 133 | Peak load at the Glenbrook dirty bus already exceeds the n-1 capacity of the supply transformers. Capacity is limited by equipment other than the supply transformer(s) NZ Steel has advised 12 MW load increase from addition of an electric arc furnace in 2026.
19 |  | Henderson | Yes | 139.15 | 169 | 181 | 193 | 207 | 222 | 236 | 250 | 265 | 280 | 295 | Peak load at Henderson is forecast to exceed the n 1 capacity of the supply transformers from winter 2026 and the n capacity from winter 2033. Capacity is limited by equipment other than the supply transformer(s) Significant new load increases are forecast across the Auckland grid exit points of Henderson, Silverdale, Albany 33 kV, Takanini and Auckland CBD (including Hobson Street and Liverpool Street), with a large share from data centres.
20 |  | Hepburn Rd | Yes | 144.9 | 167 | 174 | 180 | 185 | 189 | 194 | 198 | 202 | 207 | 212 | No issues. Vector has advised significant new load increase at Hepburn Road, with a large share from EV uptake.
21 |  | Hobson Street | Yes | 97.2462 | 102 | 113 | 122 | 130 | 137 | 145 | 152 | 160 | 168 | 175 | No issues. The load split between Hobson Street and Liverpool Street–Penrose is an estimate only. The Vector and Transpower networks between these grid exit points are operated in parallel. Significant new load increases are forecast across the Auckland grid exit points of Henderson, Silverdale, Albany 33 kV, Takanini and Auckland CBD (including Hobson Street and Liverpool Street), with a large share from data centres.
22 |  | Mangere 33 kV | Yes | 117.625 | 135 | 142 | 149 | 153 | 158 | 163 | 167 | 172 | 177 | 181 | Peak load at Mangere 33 kV is forecast to exceed the n-1 capacity of the supply transformers from winter 2027 . Capacity is limited by equipment other than the supply transformer(s)
23 |  | Mangere 110 kV | N/A | 21.3 | 20 | 20 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | Vector owns the 110 kV feeders at Mangere.
24 |  | Mt Roskill 22 kV | Yes | 112.7625 | 125 | 128 | 131 | 135 | 139 | 143 | 147 | 151 | 156 | 160 | Peak load at Mount Roskill 22 kV is forecast to exceed the n-1 capacity of the supply transformers from winter 2037
25 |  | Mt Roskill 110 kV - Kingsland feeder | N/A | 56.4 | 77 | 79 | 81 | 83 | 86 | 88 | 91 | 94 | 97 | 100 | Vector owns the 110 kV feeders at Mount Roskill. This includes the Kingsland feeders only.
26 |  | Otahuhu | Yes | 62.6 | 73 | 75 | 76 | 78 | 80 | 81 | 83 | 85 | 88 | 90 | Peak load at Otahuhu is forecast to exceed the n-1 capacity of the supply transformers from winter 2036 . Capacity is limited by equipment other than the supply transformer(s)
27 |  | Pakuranga | Yes | 135.8846 | 167 | 174 | 179 | 183 | 187 | 191 | 195 | 198 | 203 | 207 | No issues.
28 |  | Penrose 22 kV | Yes | 39.7385 | 46 | 48 | 50 | 52 | 53 | 55 | 56 | 57 | 59 | 60 | Peak load at Penrose 22 kV exceeds the n-1 capacity of the supply transformers from 2033. Capacity is limited by equipment other than the supply transformer(s). The Penrose 22 kV load is split between three 33/22 kV transformers that are not directly connected on the 22 kV side. Only the aggregate 22 kV load is forecast, not separate load forecasts for the three 33/22 kV transformers.
29 |  | Penrose 25 kV | Yes | 16.3 | 15 | 15 | 15 | 15 | 15 | 17 | 18 | 20 | 22 | 25 | No issues. A single 220/25 kV traction transformer at Penrose supplies the Auckland passenger rail system. This transformer, along with the single traction transformer at Southdown, provides switched n-1 security. The average transformer loading is low, with high levels of peak load occurring for only a few minutes at a time. Therefore, we do not assess the capacity of traction transformers in the TPR.
30 |  | Penrose 33 kV | Yes | 257.525 | 307 | 316 | 324 | 335 | 346 | 356 | 366 | 376 | 388 | 400 | Peak load at Penrose 33 kV is forecast to exceed the n-1 capacity of the supply transformers from winter 2030.
31 |  | Penrose 110 kV - Liverpool Street | Yes | 159.8 | 102 | 113 | 122 | 130 | 137 | 145 | 152 | 160 | 168 | 175 | No issues. The load split between Hobson Street and Liverpool Street–Penrose is an estimate only. The Vector and Transpower networks between these grid exit points are operated in parallel. Significant new load increases are forecast across the Auckland grid exit points of Henderson, Silverdale, Albany 33 kV, Takanini and Auckland CBD (including Hobson Street and Liverpool Street), with a large share from data centres.
32 |  | Silverdale | Yes | 99.8 | 119 | 126 | 133 | 140 | 148 | 156 | 164 | 171 | 179 | 186 | Peak load at Silverdale is forecast to exceed the n-1 capacity of the transformers from winter 2029. Significant new load increases are forecast across the Auckland grid exit points of Henderson, Silverdale, Albany 33 kV, Takanini and Auckland CBD (including Hobson Street and Liverpool Street), with a large share from data centres.
33 |  | Southdown 25 kV | Yes | 21.9 | 15 | 15 | 15 | 15 | 15 | 17 | 19 | 20 | 23 | 25 | No issues. A single 220/25 kV traction transformer at Southdown supplies the Auckland passenger rail system. This transformer, along with the single traction transformer at Penrose, provides switched n 1 security. The average transformer loading is low, with high levels of peak load occurring for only a few minutes at a time. Therefore, we do not assess the capacity of traction transformers in the TPR.
34 |  | Takanini | Yes | 128.7286 | 206 | 230 | 257 | 262 | 267 | 272 | 277 | 281 | 286 | 291 | Peak load at Takanini is forecast to exceed the n-1 capacity of the supply transformers from winter 2026 and n capacity from 2035. Significant new load increases are forecast across the Auckland grid exit points of Henderson, Silverdale, Albany 33 kV, Takanini and Auckland CBD (including Hobson Street and Liverpool Street), with a large share from data centres.
35 |  | Wairau Road | Yes | 154.45 | 160 | 164 | 167 | 172 | 178 | 183 | 189 | 194 | 200 | 205 | Considering capacity of the two Transpower-owned transformers at Wairau Road, peak load at Wairau Road is forecast to exceed the n-1 capacity of the transformers from winter 2026.
36 |  | Wiri | Yes | 91.998 | 113 | 120 | 126 | 129 | 132 | 134 | 137 | 139 | 143 | 145 | Peak load at Wiri is forecast to exceed the n-1 capacity of the supply transformers from winter 2027
37 |  | Arapuni North | N/A | 28.789 | 23 | 24 | 24 | 25 | 26 | 27 | 27 | 27 | 27 | 27 | Powerco owns the 110 kV feeders at Arapuni North.
38 |  | Cambridge | Yes | 42.0684 | 44 | 46 | 47 | 49 | 50 | 51 | 53 | 54 | 55 | 56 | Peak load at Cambridge is forecast to exceed the n-1 capacity of the supply transformers from 2029. Capacity is limited by equipment other than the supply transformer(s).
39 |  | Hamilton 11 kV | Yes | 31.1625 | 33 | 35 | 33 | 35 | 37 | 38 | 39 | 40 | 41 | 42 | Peak load at Hamilton 11 kV is forecast to exceed the n-1 capacity of the transformers from 2039. Load shifting of 3.5 MW from Hamilton 11 kV to Hamilton 33 kV in 2029
40 |  | Hamilton 33 kV | No | 148.4 | 164 | 170 | 184 | 166 | 174 | 182 | 189 | 194 | 199 | 203 | Peak load at Hamilton 33 kV already exceeds the n-1 capacity of the 220/33 kV transformers and is forecast to exceed the n capacity from 2029. Load transfer to Te Kowhai in 2030 reduces the load below the n limit until 2032, after which peak load is again forecast to exceed the transformer n capacity. Load shifting of 3.5 MW from Hamilton 11 kV to Hamilton 33 kV in 2029. Includes contribution from Ruakura Energy. WEL Networks advised 10 MW dairy load increase in 2030 at Hamilton 33 kV. Load shifting of 25 MW from Hamilton 33 kV to Te Kowhai in 2030.
41 |  | Hamilton NZR | Yes | 8.8 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | No issues. Two 220/55 kV traction transformers at Hamilton supply the KiwiRail North Island Main Trunk railway line. The two transformers are normally operated split, each providing n security to a portion of the railway line. The average transformer loading is low, with high levels of peak load occurring for only a few minutes at a time. Therefore, we do not assess the capacity of traction transformers in the TPR
42 |  | Hangatiki 33 kV | No | 23.6368 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | Peak load at the Hangatiki 33 kV grid exit point already exceeds the n-1 capacity of the supply transformers and is forecast to exceed the n capacity from 2029.
43 |  | Hangatiki 110 kV | N/A | 15.4 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | The 110 kV grid exit point is on n security and its capacity is not reported in the TPR as the supply transformer is owned by The Lines Company.
44 |  | Hautapu | Yes | 13.435 | 13 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 16 | 16 | No issues.
45 |  | Hinuera | Yes | 27.4158 | 29 | 30 | 31 | 32 | 32 | 32 | 33 | 33 | 33 | 34 | No issues.
46 |  | Huntly | Yes | 36.94 | 38 | 38 | 87 | 88 | 102 | 104 | 105 | 107 | 108 | 109 | Peak load at Huntly is forecast to exceed the winter n-1 capacity of the supply transformers from 2029. Capacity is limited by equipment other than the supply transformer(s). Load shifting of 10 MW from Te Kowhai to Huntly in 2031. WEL Networks advised 45 MW load growth from heavy industry in Huntly in 2029.
47 |  | Kopu | Yes | 45.6429 | 50 | 51 | 52 | 54 | 55 | 56 | 57 | 57 | 58 | 59 | Peak load at Kopu is forecast to exceed the n-1 capacity of the supply transformers from winter 2036 . Capacity is limited by equipment other than the supply transformer(s).
48 |  | Piako | N/A | 41.8 | 51 | 52 | 52 | 53 | 54 | 55 | 56 | 56 | 57 | 57 | Powerco owns the supply transformers at Piako. Peak load at Piako is forecast to remain within the n-1 capacity of the two Piako–Morrinsville Tee line sections.
49 |  | Te Awamutu | Yes | 49.9875 | 52 | 53 | 54 | 73 | 74 | 75 | 76 | 77 | 77 | 78 | Peak load at Te Awamutu is forecast to exceed the n-1 transformer capacity from 2027. Waipa Networks advised 19 MW industrial growth in 2030 at Te Awamutu.
50 |  | Te Kowhai | Yes | 108.6 | 109 | 113 | 143 | 177 | 171 | 176 | 180 | 184 | 188 | 191 | Peak load at Te Kowhai (excluding contribution from Te Uku generation) is forecast to exceed the n-1 capacity of the 220/33 kV transformers from 2029. Capacity is limited by equipment other than the supply transformer(s). Load shifting of 25 MW from Hamilton 33 kV to Te Kowhai in 2030. Load shifting of 10 MW from Te Kowhai to Huntly in 2031. WEL Networks advised 24 MW load increase from electrification in 2029 at Te Kowhai.
51 |  | Waihou | Yes | 42.3176 | 43 | 44 | 44 | 44 | 45 | 45 | 46 | 46 | 46 | 46 | No issues.
52 |  | Waikino | Yes | 38.5625 | 41 | 42 | 45 | 49 | 54 | 55 | 52 | 53 | 54 | 54 | Peak load at Waikino is forecast to exceed the n-1 capacity of the T1 transformer from 2029. Powerco advised some industrial load decrease from 2033 at Waikino.
53 |  | Whakamaru | Yes | 12.0457 | -36.2532 | -36.2492 | -36.246 | -36.2433 | -36.2411 | -36.2394 | -36.2379 | -36.2367 | -36.2357 | -36.2349 | No issues. The TPR reports the gross demand forecast instead of net, excluding contribution from embedded generation.
54 |  | Edgecumbe | Yes | 59.9615 | 84 | 86 | 87 | 89 | 91 | 92 | 93 | 95 | 96 | 97 | The peak load is forecast to exceed the n-1 capacity of T4 and T7 in 2026 following the planned electrification of Fonterra’s dairy plant at Edgecumbe. Horizon advised a 34 MW step load increase at Edgecumbe in 2026, caused by the electrification of the Fonterra dairy plant.
55 |  | Kaitemako | No | 38.9 | 40 | 42 | 43 | 25 | 26 | 26 | 27 | 29 | 30 | 30 | No capacity issues. A single 110/33 kV, 75 MVA transformer supplies load at Kaitemako, resulting in n security. Powerco advised an 18 MW load shift from Kaitemako to Tauranga 33 kV in 2030. Several major commercial, industrial and residential load increases are expected in the Tauriko area, which will be supplied from Tauranga 33 kV.
56 |  | Kawerau Horizon | Yes | 21.641 | 21.1238 | 21.7513 | 22.1846 | 22.6348 | 23.186 | 23.6288 | 24.0543 | 24.4283 | 24.7416 | 24.9339 | Peak load is forecast to exceed the n-1 capacity of the supply transformers from 2027. The TPR reports the gross demand forecast instead of net, excluding contribution from embedded generation. Horizon Energy has advised about 12 MW load increase from heavy industry in 2027 at Kawerau. The Te Ahi O Maui geothermal generator, previously connected within Horizon’s 11 kV distribution network, is now shifted to a new grid injection point on the Kawerau 220 kV bus as part of Eastland Generation’s TOPP2 geothermal project. As a result, the Te Ahi O Maui generator no longer offsets the 11 kV load, reducing the supply capacity. The generator was shifted in mid-late 2025, and the embedded generation contribution for net demand forecast is included in the disclosure year.
57 |  | Kawerau T6 - T9 | Yes | 25.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | No issues. The TPR reports the gross demand forecast instead of net, excluding contribution from embedded generation
58 |  | Kinleith 11 kV | Yes | 45.4 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | No issues. . Oji has rationalised its 11 kV supply arrangement following the closure of paper production at Kinleith
59 |  | Kinleith 33 kV | No | 20.7 | 23 | 23 | 24 | 24 | 24 | 26 | 27 | 28 | 29 | 30 | The winter peak 33 kV load at Kinleith already exceeds the continuous capacity of T5 but is within the continuous capacity of T9
60 |  | Lichfield | N/A | 16.6337 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | The supply transformers at Lichfield are owned by Vector and are not reported in the TPR.
61 |  | Matahina | Yes | 13.965 | -2.7586 | -2.6575 | -2.5752 | -2.4866 | -2.3942 | -2.3101 | -2.2448 | -2.1828 | -2.126 | -2.0765 | No issues. This load is supplied by transformers owned by Pioneer Energy and located at Aniwhenua. The TPR reports the gross demand forecast instead of net, excluding contribution from embedded generation
62 |  | Mt Maunganui 33 kV | Yes | 64.2 | 66 | 68 | 73 | 77 | 78 | 80 | 82 | 66 | 67 | 72 | No issues. Powerco advised the following load shifts from Mount Maunganui 33 kV to Te Matai: 2.3 MW in 2027 and 15 MW in 2034.
63 |  | Owhata | Yes | 13.8118 | 16 | 16 | 16 | 16 | 17 | 17 | 17 | 17 | 17 | 17 | No issues.
64 |  | Rotorua 11 kV | Yes | 27.475 | 30 | 30 | 30 | 31 | 31 | 31 | 32 | 32 | 32 | 32 | No issues.
65 |  | Rotorua 33 kV | Yes | 48.8545 | 53 | 54 | 55 | 56 | 57 | 57 | 58 | 58 | 58 | 59 | No issues.
66 |  | Tarukenga 11 kV | No | 8.6789 | 10 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | No capacity issues. A single 110/11 kV, 20 MVA supply transformer supplies the Tarukenga grid exit point resulting in n security.
67 |  | Tauranga 11 kV | Yes | 23.92 | 27 | 28 | 28 | 31 | 32 | 33 | 33 | 34 | 35 | 36 | Peak load at Tauranga 11 kV is forecast to exceed the n-1 capacity of the supply transformers from 2039 .
68 |  | Tauranga 33 kV | Yes | 86.5 | 74 | 79 | 82 | 116 | 120 | 124 | 127 | 132 | 135 | 138 | Peak load at Tauranga 33 kV is forecast to exceed the n-1 capacity of the supply transformers from winter 2030 if Kaimai generation is low (14 MW) and from 2032 if Kaimai generation is medium (33 MW) . Powerco advised an 18 MW load shift from Kaitemako to Tauranga 33 kV in 2030. Several major commercial, industrial and residential load increases are expected in the Tauriko area, which will be supplied from Tauranga 33 kV.
69 |  | Te Matai | Yes | 53.5 | 66 | 71 | 74 | 84 | 90 | 103 | 105 | 125 | 130 | 132 | The Te Matai load is forecast to exceed the n-1 capacity of T2 from winter 2026, n-1 capacity of T1 from winter 2031 and the n capacity of T1 from winter 2033. Powerco advised the following load shifts from Mount Maunganui 33 kV to Te Matai: 2.3 MW in 2027 and 15 MW in 2034.
70 |  | Waiotahe | Yes | 18.0292 | 14 | 14 | 14 | 15 | 15 | 15 | 16 | 16 | 16 | 17 | No issues. Waiotahe currently comprises of 11 kV, and 33 kV load supplied through two 110/33/11 kV transformers. There is a project underway to transfer the Waiotahe 11 kV load supply to 33 kV, scheduled for completion in early 2027.
71 |  | Waiotahe 50 kV | No | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Horizon has recently upgraded their network (late 2025) and consilidated their 50 kV load to 33 kV, at "Waiotahe". The 50 kV load was previously supplied by a single 11/50 kV, 3 MVA transformer, resulting in n security.
72 |  | Bunnythorpe 33 kV | Yes | 84.7433 | 82 | 85 | 85 | 87 | 88 | 94 | 95 | 95 | 97 | 97 | No issues. Powerco has advised a 1 MW load shift from Bunnythorpe to Linton in 2027.
73 |  | Bunnythorpe - NZR | Yes | 9.65 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | No issues. Two 220/55 kV traction transformers at Bunnythorpe supply the KiwiRail North Island Main Trunk railway line. The two transformers are operated normally split, each providing n security to a portion of the railway line. The average transformer loading is low, with high levels of peak load occurring for only a few minutes at a time. Therefore, we do not assess the capacity of traction transformers in the TPR.
74 |  | Dannevirke | Yes | 13.9 | 17 | 21 | 22 | 22 | 23 | 23 | 24 | 24 | 24 | 25 | Peak load at Dannevirke is forecast to exceed the n-1 capacity of the supply transformers from winter 2031. Capacity is limited by equipment other than the supply transformer(s).
75 |  | Linton | Yes | 73.9308 | 86 | 92 | 95 | 103 | 105 | 107 | 108 | 109 | 111 | 111 | Peak load at Linton is forecast to exceed the n-1 capacity of the supply transformers from winter 2030. Capacity is limited by equipment other than the supply transformer(s). Powerco has advised a 1 MW load shift from Bunnythorpe to Linton in 2027.
76 |  | Mangahao | No | 47.9456 | 46 | 48 | 49 | 51 | 52 | 53 | 54 | 55 | 57 | 57 | Peak load at Mangahao already exceeds the n-1 capacity of the supply transformers when Mangahao power station is not generating.
77 |  | Mangamaire | Yes | 14.6 | 15 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 17 | No issues.
78 |  | Mataroa | No | 6.6 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | No capacity issues. The load at Mataroa is supplied by a single 110/33 kV, 26 MVA supply transformer comprising three single-phase units, resulting in n security.
79 |  | National Park | No | 5.6111 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | No capacity issues. The load at National Park is supplied through a single Ohakune–National Park–Ongarue 110 kV circuit and a single 110/33 kV, 15 MVA supply transformer, resulting in n security.
80 |  | Ohakune | No | 8.2 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 12 | 12 | No capacity issues. The load at Ohakune is supplied by a single 110/11 kV, 20 MVA supply transformer, resulting in n security.
81 |  | Ongarue | No | 9.7583 | 10 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | No capacity issues. The load at Ongarue is supplied by a single 110/33 kV, 20 MVA supply transformer comprising three single-phase units, resulting in n security.
82 |  | Tangiwai 11 kV | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Following Winstone Pulp International’s decision to indefinitely close its Tangiwai Sawmill and Karioi Pulpmill in 2024, no load is supplied by the Tangiwai 220/11 kV transformers
83 |  | Tangiwai NZR | Yes | 11.15 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | No issues. Two 220/55 kV traction transformers at Tangiwai supply the KiwiRail North Island Main Trunk railway line. The two transformers are operated normally split, each providing n security to a portion of the railway line. The average transformer loading is low, with high levels of peak load occurring for only a few minutes at a time. Therefore, we do not assess the capacity of traction transformers in the TPR.
84 |  | Tokaanu | No | 10 | 8 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 11 | No capacity issues. The load at Tokaanu is supplied by a single 220/33 kV, 20 MVA supply transformer, with a second transformer that can be manually switched into service when required.
85 |  | Waipawa | Yes | 23.5682 | 27 | 28 | 29 | 29 | 30 | 31 | 31 | 32 | 33 | 33 | Peak load at Waipawa is forecast to exceed the n-1 capacity of the supply transformers from shoulder season 2026. Capacity is limited by equipment other than the supply transformer(s).
86 |  | Wairakei | Yes | 54.3529 | 17.0665 | 16.4119 | 18.0263 | 19.0939 | 20.2489 | 21.2534 | 22.1912 | 23.1645 | 24.0113 | 24.7552 | No issues. The TPR reports the gross demand forecast instead of net, excluding contribution from embedded generation. Unison has advised 6 MW load shift in 2026, from Wairakei to Tauhara (Hawke’s Bay region).
87 |  | Woodville | Yes | 2.6 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | Peak load at Woodville is forecast to exceed the n-1 capacity of the supply transformers from winter 2032. Capacity is limited by equipment other than the supply transformer(s).
88 |  | Brunswick | No | 31.2 | 35 | 37 | 38 | 38 | 39 | 52 | 53 | 53 | 54 | 54 | Peak load at Brunswick is forecast to exceed the supply capacity of the single supply transformer by 2032 . The Brunswick load is currently supplied by a single 220/33 kV, 50 MVA transformer, resulting in n security. Powerco has advised 10.7 MW load shift from Whanganui to Brunswick in 2032.
89 |  | Carrington Street | Yes | 65.0867 | 73 | 74 | 75 | 79 | 80 | 81 | 82 | 86 | 86 | 87 | No issues.
90 |  | Huirangi | Yes | 28.286 | 31 | 36 | 36 | 37 | 37 | 37 | 37 | 38 | 38 | 38 | No issues.
91 |  | Hawera | Yes | 27.9 | 27 | 31 | 32 | 35 | 35 | 35 | 36 | 36 | 37 | 37 | Peak load at Hawera is forecast to exceed the capacity of the supply transformer by winter 2030.
92 |  | Hawera 110 kV (Whareroa) | N/A | 28.4344 | 76.7851 | 76.7851 | 116.6777 | 116.6777 | 116.6777 | 116.6777 | 116.6777 | 116.6777 | 134.6133 | 134.6133 | Fonterra has feeders connected directly to the Hawera 110 kV bus; their capacity is not reported in the TPR . The TPR reports the gross demand forecast instead of net, excluding contribution from embedded generation. Fonterra has advised 60 MW, 30 MW and 18 MW load increases in 2026, 2029 and 2035, respectively.
93 |  | Hawera (Kupe) | No | 11 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | No capacity issues. A single 110/33 kV, 30 MVA supply transformer (T3) supplies the Beach Energy Kupe load, resulting in n security.
94 |  | Kapuni | N/A | 8.37 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | Kapuni load and generation is connected to the grid through a single 110 kV circuit (owned by Nova Energy) which is tee-connected to the 110 kV Opunake–Stratford–2 circuit, resulting in n security.The capacity of the assets owned by Nova Energy is not reported in the TPR. The TPR reports the gross demand forecast instead of net, excluding contribution from embedded generation.
95 |  | Marton | Yes | 24.27 | 27 | 28 | 28 | 29 | 29 | 30 | 30 | 30 | 31 | 31 | Load is forecast to exceed n-1 capacity by summer 2026
96 |  | Motunui | Yes | 12.2 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | No issues.
97 |  | Opunake | Yes | 11.2554 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | No issues.
98 |  | Stratford 33 kV | Yes | 41.3 | 28 | 28 | 28 | 29 | 29 | 29 | 30 | 30 | 30 | 30 | No issues.
99 |  | Taumarunui | Yes | 9.6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | Two 220/55 kV traction transformers at Taumarunui supply the KiwiRail North Island Main Trunk railway line. The two transformers are normally operated split, each providing n security to a portion of the railway line. The average transformer loading is low, with high levels of peak load occurring for only a few minutes at a time. Therefore, we do not assess the capacity of traction transformers in the TPR.
100 |  | Waverley | No | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | No capacity issues. A single 110/11 kV, 10 MVA transformer supplies load at Waverley resulting in n security
101 |  | Whanganui | No | 37.7 | 33 | 33 | 34 | 35 | 36 | 24 | 24 | 25 | 25 | 25 | Peak load at Whanganui already exceeds the n-1 capacity of the supply transformers . Capacity is limited by equipment other than the supply transformer(s). Powerco has advised 10.7 MW load shift from Whanganui to Brunswick in 2032.
102 |  | Fernhill | No | 70.6217 | 72 | 73 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | Peak load at Fernhill has exceeded the n-1 capacity of the smaller transformer (T2) since 2023. The branch n-1 capacity limit on the larger transformer (T3) is forecast to be exceeded in 2034. The T3 capacity is limited by equipment other than the supply transformer(s).
103 |  | Redclyffe | Yes | 76.55 | 91 | 93 | 96 | 98 | 100 | 102 | 104 | 106 | 108 | 110 | No issues.
104 |  | Tuai | N/A | 60.3292 | 76 | 78 | 80 | 82 | 84 | 85 | 86 | 87 | 87 | 88 | Eastland Networks owns the 110 kV feeders at Tuai
105 |  | Tauhara | No | 53.8 | -22.1952 | -21.6048 | -17.3173 | -16.7212 | -16.0381 | -15.4833 | -10.9516 | -10.2818 | -9.749 | -9.3214 | No capacity issues. The load at Tauhara is supplied through a single 220/33 kV, 70 MVA transformer, resulting in n security. The TPR reports the gross demand forecast instead of net, excluding contribution from embedded generation. Unison has advised 15 MW of new heavy industrial load at Tauhara in 2026.
106 |  | Whakatu | Yes | 84.1833 | 101 | 102 | 103 | 104 | 105 | 105 | 106 | 106 | 106 | 106 | No issues.
107 |  | Whirinaki | Yes | 57.4 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | No issues.
108 |  | Central Park 11 kV | Yes | 21.4467 | 25 | 25 | 26 | 27 | 27 | 28 | 28 | 28 | 28 | 28 | No issues.
109 |  | Central Park 33 kV | Yes | 133.675 | 170 | 172 | 174 | 178 | 180 | 182 | 186 | 188 | 189 | 189 | Peak load at Central Park for the combined 33 kV and 11 kV load is forecast to exceed the combined n-1 capacity of the transformers from winter 2032 . Central Park 33 kV has multiple step loads from expected public transport electrification upgrades and several new buildings planned.
110 |  | Gracefield | Yes | 63.85 | 73 | 74 | 76 | 78 | 79 | 79 | 80 | 80 | 82 | 82 | Peak load at Gracefield is forecast to exceed the n 1 capacity of the supply transformers from winter 2028
111 |  | Greytown | Yes | 15.6273 | 15 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | 16 | 16 | No issues.
112 |  | Haywards 11 kV | Yes | 20.1 | 24 | 25 | 25 | 26 | 26 | 26 | 26 | 27 | 27 | 27 | No issues.
113 |  | Haywards 33 kV | Yes | 21.3 | 29 | 30 | 31 | 32 | 33 | 34 | 34 | 35 | 36 | 37 | Peak load at Haywards 33 kV is forecast to exceed the n-1 capacity of the supply transformers from winter 2037 . Capacity is limited by equipment other than the supply transformer(s).
114 |  | Kaiwharawhara | Yes | 29.7222 | 31 | 32 | 32 | 35 | 35 | 35 | 36 | 36 | 36 | 36 | Kaiwharawhara peak load is forecast to exceed the n 1 capacity of the supply transformers from winter 2033. Capacity is limited by equipment other than the supply transformer(s).
115 |  | Masterton | Yes | 51.5448 | 51 | 56 | 57 | 60 | 61 | 62 | 62 | 63 | 63 | 64 | No issues.
116 |  | Melling 11 kV | Yes | 25.2385 | 30 | 30 | 30 | 33 | 34 | 34 | 34 | 34 | 34 | 34 | The 11 kV peak load is forecast to exceed the n-1 capacity of the supply transformers from winter 2030
117 |  | Melling 33 kV | Yes | 37.2444 | 39 | 40 | 41 | 42 | 43 | 43 | 44 | 44 | 44 | 44 | No issues.
118 |  | Paraparaumu | Yes | 64.84 | 72 | 74 | 75 | 77 | 78 | 80 | 81 | 82 | 84 | 85 | No issues.
119 |  | Pauatahanui | Yes | 20.975 | 22 | 22 | 22 | 22 | 23 | 23 | 23 | 23 | 23 | 23 | Peak load at Pāuatahanui is forecast to slightly exceed the n-1 capacity of the supply transformers from winter 2035
120 |  | Takapu Rd | Yes | 103.9 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 116 | 117 | 117 | Peak load at Takapu Road is forecast to exceed the n-1 capacity of the supply transformers from winter 2028
121 |  | Upper Hutt | Yes | 32 | 36 | 38 | 38 | 38 | 39 | 39 | 40 | 40 | 40 | 41 | No issues.
122 |  | Wilton | Yes | 54.5525 | 53 | 54 | 54 | 55 | 55 | 56 | 56 | 56 | 56 | 56 | No issues.
123 |  | Blenheim | Yes | 72.2111 | 85 | 91 | 93 | 96 | 97 | 99 | 100 | 101 | 102 | 102 | No issues. Marlborough Lines advised ~10 MW of industrial load increase between 2026 and 2029.
124 |  | Brightwater | N/A | N/A | 0.8 | 32 | 33 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | Nework Tasman requested a new 220/33 kV Brightwater GXP to offload their Stoke 33 kV network. From 2028, the new Brightwater GXP is expected to be live. Network Tasman has advised 29 MW load shift from Stoke 33 kV to Brightwater in 2028.
125 |  | Kikiwa | No | 3.2437 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | No issues. The Kikiwa load is normally supplied from the 11 kV tertiary winding of the Kikiwa–T1 interconnecting transformer, normally energised from the 220 kV side only and with the 110 kV side open. There is a backup supply from the T2 interconnecting transformer. Transferring the load between T1 and T2 requires a short interruption to the load.
126 |  | Stoke 33 kV | Yes | 139.3625 | 144 | 116 | 117 | 119 | 121 | 122 | 123 | 128 | 129 | 129 | Peak load at Stoke 33 kV is forecast to exceed the n-1 capacity of the supply transformers during winter 2026 and 2027 . Capacity is limited by equipment other than the supply transformer(s). Network Tasman has advised 29 MW load shift from Stoke 33 kV to Brightwater in 2028. Stoke 33 kV load includes supply to the Network Tasman and Nelson Electricity networks.
127 |  | Stoke 66 kV | Yes | 49.6992 | 14.3131 | 15.0229 | 19.9034 | 20.5847 | 21.3021 | 21.9049 | 22.4812 | 22.9917 | 23.4353 | 23.7456 | Peak load at Stoke 66 kV is forecast to exceed the n-1 branch capacity of the supply transformers from winter 2034, with no generation from Cobb. The TPR reports the gross demand forecast instead of net, excluding contribution from embedded generation
128 |  | Arthur's Pass | No | 2.6736 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.4 | 0.4 | 0.4 | No capacity issues. A single 66/11 kV, 3 MVA transformer supplies load at Arthur’s Pass, resulting in n security.
129 |  | Atarau | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Atarau grid exit point was decommissioned on June 2023. The substation was dismantled in 2025.
130 |  | Castle Hill | No | 0.6 | 0.7 | 0.7 | 0.7 | 0.8 | 0.8 | 0.8 | 0.8 | 0.9 | 0.9 | 0.9 | No capacity issues. A single 66/11 kV, 3.8 MVA transformer supplies load at Castle Hill, resulting in n security.
131 |  | Dobson | Yes | 8.9 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 16 | 16 | 16 | No issues.
132 |  | Greymouth | N/A | 13.1664 | 15 | 15 | 15 | 16 | 16 | 17 | 17 | 17 | 18 | 18 | Westpower owns the supply transformers at Greymouth.
133 |  | Hokitika | N/A | 19.07 | 14.959 | 15.3686 | 15.7383 | 16.1243 | 16.5572 | 16.9509 | 17.3392 | 17.7161 | 18.0729 | 18.381 | Westpower owns the supply transformers at Hokitika. Peak load at Hokitika is forecast to exceed the voltage stability limit from 2035. The TPR reports the gross demand forecast instead of net, excluding contribution from embedded generation
134 |  | Kumara | N/A | 3.9179 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | Kumara load is supplied via a single 66/11 kV supply transformer, resulting in n security. The supply transformer is owned by Westpower and is not reported in the TPR
135 |  | Murchison | No | 2.6 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | No capacity issues. Murchison is supplied by a single 110/11 kV, 10 MVA transformer resulting in n security.
136 |  | Otira | No | 0.77 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | 0.6 | No capacity issues. Otira is supplied by a single 66/11 kV, 2.5 MVA transformer, resulting in n security.
137 |  | Reefton | N/A | 7.1 | 18 | 18 | 18 | 18 | 19 | 19 | 19 | 20 | 20 | 20 | The supply transformers at Reefton are owned by Westpower and are not reported in the TPR. Westpower advised 8 MW load increase from heavy industry at Reefton in 2027.
138 |  | Robertson Street | N/A | 11.4 | 13 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | The supply transformers at Robertson Street are owned by Buller Electricity and are not reported in the TPR. Robertson Street (owned by Buller Electricity) is connected to the grid at Orowaiti.
139 |  | Ashburton 66 kV | Yes | 165.9524 | 191 | 194 | 196 | 199 | 202 | 204 | 205 | 211 | 213 | 214 | No issues.
140 |  | Ashley - 11 kV (MainPower) | Yes | 12.8618 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | No issues. Planned load shifts as advised by MainPower from Kaiapoi 11 kV: 2.25 MW to Ashley 11 kV (MainPower) in 2026. Planned load shifts as advised by MainPower from Southbrook 66 kV: 0.7 MW to Ashley 11 kV (MainPower) in 2026. Planned load shifts as advised by MainPower from Ashley 11 kV (MainPower): 3.25 MW to Ashley 66 kV in 2027.
141 |  | Ashley - 11 kV (Daiken) | Yes | 7.325 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | No issues.
142 |  | Ashley - MainPower 66 kV | N/A | N/A | 15 | 15 | 16 | 20 | 22 | 26 | 27 | 29 | 30 | 31 | This is a new connection. Mainpower will have feeders directly connected to the Ashley 66 kV bus from 2027. Planned load shifts as advised by MainPower from Ashley 11 kV (MainPower): 3.25 MW to Ashley 66 kV in 2027. Planned load shifts as advised by MainPower from Southbrook 66 kV to Ashley 66 kV: 6.85 MW, 2.5 MW and 2.5 MW in 2027, 2030 and 2032, respectively. Planned load shifts as advised by MainPower from Kaiapoi 11 kV: 3.75 MW to Ashley 66 kV in 2027.
143 |  | Bromley 66 kV | Yes | 220.78 | 159 | 198 | 202 | 208 | 233 | 239 | 244 | 249 | 254 | 258 | Peak load at Bromley is forecast to exceed the n-1 capacity of the supply transformers from winter 2031. Planned load shifts as advised by Orion from Bromley 66 kV: 31.3 MW to Islington 66 kV in 2038. Orion has advised 23 MW load growth in 2031 at Bromley 66 kV from commercial and industrial development. Planned load shifts as advised by Orion from Islington 66 kV: 29.1 MW and 31.3 MW to Bromley 66 kV in 2028 and 2038, respectively.
144 |  | Coleridge | No | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | No capacity issues. A single 66/11 kV, 2.5 MVA transformer supplies the load at Coleridge, resulting in n security.
145 |  | Culverden 33 kV | Yes | 18.0475 | 22 | 22 | 23 | 24 | 24 | 25 | 25 | 26 | 26 | 27 | The combined 33 kV and 66 kV peak load at Culverden is forecast to exceed the n-1 capacity of the supply transformers from summer 2029 .
146 |  | Culverden 66 kV | No | 6.2128 | 8 | 8 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 12 | No capacity issues. A single 33/66 kV, 20 MVA transformer supplies the 66 kV load, resulting in n security.
147 |  | Hororata 33 kV | No | 20.8 | 21 | 22 | 22 | 22 | 22 | 22 | 22 | 23 | 24 | 24 | Peak load on the Hororata 33 kV bus already exceeds the n-1 capacity of the supply transformers. Capacity is limited by equipment other than the supply transformer(s).
148 |  | Hororata 66 kV | N/A | 17.1517 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 19 | 19 | 19 | Orion owns the 66 kV feeders at Hororata.
149 |  | Islington 33 kV | Yes | 81.4583 | 84 | 88 | 90 | 94 | 104 | 107 | 109 | 111 | 114 | 117 | Peak load at Islington 33 kV is forecast to exceed the n-1 capacity of the supply transformers from winter 2032 . Capacity is limited by equipment other than the supply transformer(s). Planned load shifts as advised by Orion from Islington 33 kV: 1.5 MW to Islington 66 kV in 2033.
150 |  | Islington 66 kV | N/A | 445.725 | 483 | 480 | 493 | 512 | 533 | 551 | 570 | 586 | 604 | 618 | Orion owns the 66 KV feeders at Islington. Planned load shifts as advised by Orion from Bromley 66 kV: 31.3 MW to Islington 66 kV in 2038. Planned load shifts as advised by Orion from Islington 33 kV: 1.5 MW to Islington 66 kV in 2033. Planned load shifts as advised by Orion from Islington 66 kV: 29.1 MW and 31.3 MW to Bromley 66 kV in 2028 and 2038, respectively.
151 |  | Kaiapoi | Yes | 30.1 | 31 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 35 | Peak load at Kaiapoi is forecast to exceed the n-1 capacity of the supply transformers from winter 2039. Capacity is limited by equipment other than the supply transformer(s). Planned load shifts as advised by MainPower from Kaiapoi 11 kV: 2.25 MW to Ashley 11 kV (MainPower) in 2026. Planned load shifts as advised by MainPower from Kaiapoi 11 kV: 3.75 MW to Ashley 66 kV in 2027.
152 |  | Kimberley | N/A | 15.8 | 16 | 16 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | Orion owns the supply transformers at Kimberley.
153 |  | Norwood | Yes | 36.5646 | 38 | 37 | 38 | 38 | 39 | 40 | 40 | 41 | 42 | 42 | No issues.
154 |  | Southbrook 66 kV | N/A | 53.4667 | 55 | 57 | 64 | 63 | 62 | 64 | 66 | 68 | 69 | 71 | Mainpower owns the 66 kV feeders at Southbrook. Planned load shifts as advised by MainPower from Southbrook 66 kV: 0.7 MW to Ashley 11 kV (MainPower) in 2026. Planned load shifts as advised by MainPower from Southbrook 66 kV to Ashley 66 kV: 6.85 MW, 2.5 MW and 2.5 MW in 2027, 2030 and 2032, respectively
155 |  | Waipara 33 kV | No | 8.7 | 9 | 10 | 10 | 11 | 11 | 12 | 12 | 13 | 13 | 13 | Peak load at Waipara 33 kV is forecast to exceed the n-1 capacity of the supply transformers from 2034 . Capacity is limited by equipment other than the supply transformer(s). A single 66/33 kV, 16 MVA transformer supplies 33 kV load at Waipara, resulting in n security.
156 |  | Waipara 66 kV | N/A | 11.6 | 9 | 9 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | Mainpower owns the 66 kV feeders at Waipara
157 |  | Albury | No | 4.4 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 7 | No capacity issues. A single 110/11 kV, 20 MVA transformer supplies the load at Albury resulting in n security.
158 |  | Bells Pond | N/A | 14.8 | 17 | 17 | 18 | 18 | 18 | 19 | 19 | 19 | 20 | 20 | Alpine Energy owns the supply transformers at Bells Pond. Bells Pond is connected via a single 110 kV tee connection to the Oamaru–Studholme–Bells Pond–Waitaki–2 circuit providing 34/34 MVA (summer/winter) capacity, resulting in n security. No transmission capacity issues.
159 |  | Black Point | N/A | 16.3 | 17 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | No issues. Network Waitaki owns the supply transformers at Black Point. Black Point is connected via a single 110 kV Tee connection to the Oamaru–Black Point–Waitaki–1 circuit providing 44/44 MVA (summer/winter) capacity, resulting in n security.
160 |  | North Otago Grid Exit Point | N/A |  | 0 | 0 | 0.1 | 10 | 10 | 21 | 22 | 22 | 22 | 23 | This is a planned new GXP by Network Waitaki which is in the investigation phase. Advised by Network Waitaki: 9 MW and 5 MW load shift from Oamaru to North Otago GXP in 2030 and 2032, respectively. The North Otago grid exit point is not committed at the time of publication.
161 |  | Oamaru | Yes | 44.7456 | 50 | 52 | 54 | 51 | 52 | 52 | 52 | 53 | 53 | 54 | The peak load at Oamaru is forecast to exceed the n-1 circuit capacity from summer 2026, and the voltage stability limit from summer 2027 until summer 2029, and then from 2040. The n-1 transformer capacity limit will also be exceeded from summer 2027 until summer 2029. Capacity is limited by equipment other than the supply transformer(s). Advised by Network Waitaki: 9 MW and 5 MW load shift from Oamaru to North Otago GXP in 2030 and 2032, respectively. The North Otago grid exit point is not committed at the time of publication.
162 |  | Studholme | No | 15 | 20 | 21 | 21 | 22 | 22 | 23 | 23 | 24 | 24 | 24 | The peak load at Studholme already exceeds the n-1 capacity of the supply transformers, and from summer 2027 the n capacity is forecast to exceed.
163 |  | Tekapo A | No | 6.0921 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | Peak load at Tekapo A is forecast to exceed the continuous rating of T1 in 2040. Capacity is limited by equipment other than the supply transformer(s). A single 110/11 kV, 35 MVA transformer (T6) in series with a single 33/11 kV, 10 MVA transformer (T1) supplies load at Tekapo, resulting in n security.
164 |  | Temuka | No | 58.9 | 71 | 87 | 89 | 91 | 92 | 94 | 95 | 96 | 97 | 97 | The peak load at Temuka already exceeds the n-1 supply transformer capacity in summer, is forecast to exceed the n-1 circuit capacity from summer 2026, is forecast to exceed the n-1 voltage stability limit from sumer 2030, and is forecast to exceed the n capacity of the supply transformers from summer 2035. Advised by Alpine Energy: 11 MW truck charging and 4 MW heat pumps at Fonterra Clandeboye in 2028.
165 |  | Timaru | Yes | 67.2667 | 87 | 89 | 91 | 94 | 96 | 98 | 99 | 101 | 103 | 104 | The peak load at Timaru is forecast to exceed the continuous capacity of two supply transformers in service from 2028. Capacity is limited by equipment other than the supply transformer(s)
166 |  | Twizel | Yes | 7.9913 | 9 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 12 | 12 | No issues.
167 |  | Waitaki | N/A | 12.7169 | 14 | 14 | 14 | 14 | 14 | 10 | 11 | 11 | 11 | 11 | No issues. Network Waitaki is normally supplied through an 11/33 kV, 20 MVA step up transformer owned by Network Waitaki. There is also a lower capacity alternate supply through an 11/33 kV, 5.5 MVA step up transformer (T28) owned by Transpower that is too small to supply the peak load and normally has no load connected to it. Advised by Network Waitaki: 5 MW load shift from Waitaki to North Otago grid exit point in 2032.
168 |  | Balclutha | Yes | 31.35 | 41 | 42 | 43 | 44 | 44 | 45 | 45 | 45 | 46 | 46 | Peak load at Balclutha is forecast to exceed the n-1 capacity of the supply transformers from shoulder season 2027
169 |  | Brydone | Yes | 11.1 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | No issues.
170 |  | Clyde | Yes | 12.0459 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 28 | 29 | 29 | Peak load at Clyde is forecast to exceed the n-1 capacity of the supply transformers from summer 2032. Capacity is limited by equipment other than the supply transformer(s)
171 |  | Cromwell | Yes | 51.22 | 79 | 84 | 88 | 91 | 98 | 101 | 103 | 105 | 107 | 109 | Peak load at Cromwell 33 kV is forecast to exceed the 33 kV cable rating from winter 2026 and the n-1 capacity of the transformers’ 33 kV winding from winter 2027 . Capacity is limited by equipment other than the supply transformer(s). Aurora advised a 12 MW load increase from Bendigo Mine at Cromwell in 2027.
|  | Edendale | No | 50.4017 | 35 | 35 | 36 | 36 | 37 | 38 | 50 | 50 | 50 | 51 | Formerly Edendale 33 kV. Peak load at Edendale is already exceeding the n-1 capacity of the supply transformers. PowerNet advised a 20 MW load increase from Fonterra’ milk boiler electrification in 2026 and a 10 MW load increase from meat processing in 2033 at Edendale 33 kV. The 20 MW load from Fonterra’s electric boiler will be shifted to the new Puna Awa GXP in late 2027.
173 |  | Puna Awa | N/A | N/A | 83 | 83 | 83 | 83 | 83 | 83 | 83 | 92 | 92 | 92 | Formerly Edendale 220 kV. PowerNet requested a new Puna Awa GXP to enable electrification and resolve n-1 supply capacity issues at Edendale. Puna Awa is committed and is expected to be commissioned by 2027. PowerNet advised an 83 MW load increase from Fonterra Edendale in 2027 at the new Puna Awa GXP. About 20 MW of that load is the transfer of Fonterra Edendale’s first electric boiler from the Edendale 33 kV GXP.
174 |  | Frankton | Yes | 82.5935 | 93 | 112 | 118 | 122 | 126 | 129 | 132 | 136 | 139 | 141 | Peak load at Frankton is forecast to exceed the n-1 capacity of the Cromwell–T5 110 kV winding, followed by the 110 kV Cromwell–Frankton circuits from winter 2028. The Frankton supply capacity will also be limited in future by the Cromwell transformers’ 110 kV and 220 kV winding capacities from about winter 2028 About 10 MW load increase at Frankton in 2028 due to residential and commercial development.
175 |  | Gore | Yes | 58.0067 | 47 | 53 | 54 | 55 | 56 | 57 | 58 | 60 | 60 | 61 | No issues.
176 |  | Halfway Bush | Yes | 120.4578 | 129 | 133 | 140 | 144 | 146 | 148 | 149 | 150 | 152 | 153 | Assuming no contribution from the embedded generators, the peak load at Halfway Bush is forecast to exceed the n-1 capacity of the supply transformers from winter 2027.
177 |  | Invercargill 33 kV | Yes | 108.2571 | 133 | 140 | 145 | 146 | 149 | 152 | 154 | 156 | 157 | 164 | Formerly "Invercargill", name changed due to new 66 kV load at Invercargill .Peak load at Invercargill is forecast to exceed the n-1 capacity of the supply transformers from winter 2028. About 10 MW load increase at Invercargill 33 kV in 2026, mainly from industrial sector and transport
178 |  | Invercargill 66 kV | No | 32.4 | 30 | 30 | 30 | 30 | 60 | 60 | 60 | 60 | 60 | 60 | New 66 kV load connected in early 2026. No issues. One 220/66 kV transformer will supply the Invercargill 66 kV load, providing a nominal installed capacity of 120 MVA, resulting in n security. PowerNet advised a 30 MW load increase from electric boiler addition in 2031 at Invercargill 66 kV.
179 |  | Naseby | Yes | 32.5767 | 31 | 32 | 33 | 34 | 34 | 35 | 35 | 35 | 36 | 36 | No issues.
180 |  | North Makarewa | Yes | 61.5364 | 64 | 65 | 80 | 82 | 84 | 94 | 96 | 97 | 98 | 99 | Assuming no local generation at White Hill wind farm, peak load at North Makarewa is forecast to exceed the n-1 capacity of the supply transformers from summer 2026 .
181 |  | South Dunedin | Yes | 72.2 | 80 | 81 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 89 | No issues.
182 |  | Tiwai | N/A | 590.85 | 585 | 585 | 585 | 635 | 635 | 635 | 635 | 635 | 635 | 635 | New Zealand Aluminium Smelter (NZAS) owns the 220 kV feeders connected directly to the Tiwai 220 kV bus and their capacity is not reported in the TPR. The restart of Reduction Line 4 at Tiwai Point aluminium smelter in 2030 was announced after we finished our load forecast update. The 50 MW load increase is not included in all TPR studies, but is noted where this may impact an issue.
183 |  | GXPs Total |  | 8737.4683 | 9301.9262 | 9658.0588 | 10063.4649 | 10389.6083 | 10750.5514 | 11021.5867 | 11252.5895 | 11360.7789 | 11735.1968 | 11853.8527
184 |  | *Insert additional rows and update calculation of totals as needed
185
186 | G3(ii): Current Connection Capacity vs Actual and Forecast Injection
187 |  | Not required from disclosure year 2026
188
189 | G3(iii): Anticipatory Connection Asset capacity
|  |  | CY |  |  | Forecast Anticipatory capacity (MVA)
191 |  | Grid Injection point (generator location if embedded) | Total Capacity (MVA) | Opening Anticipatory capacity (MVA) | Closing Anticipatory capacity (MVA) | CY+1 | CY+2 | CY+3 | CY+4 | CY+5 | CY+6 | CY+7 | CY+8 | CY+9 | CY+10 | Comments on Capacity
192 |  | No Anticipatory connection asset to report. | [14 empty] | Required from disclosure year 2026
193 | [16 empty] | Required from disclosure year 2026
194 | [16 empty] | Required from disclosure year 2026
195 | [16 empty] | Required from disclosure year 2026
196 | [16 empty] | Required from disclosure year 2026
197 |  | GIPs Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Required from disclosure year 2026
198 |  | *Insert additional rows and update calculation of totals as needed
199
200

## G4. Quality Grid Outputs
[11 empty] | Transpower |  | Disclosure Date |  | 2026-10-23
SCHEDULE G4: QUALITY OF SUPPLY: GRID OUTPUTS AND PERFORMANCE MEASURES | [12 empty] | Disclosure Year (year ended) |  | 2026-06-30
ref
5 | G4(i): Grid Output Historical and Forecast Measures and Targets
6
7 |  | Grid Output Measure - Quality | Actual performance |  |  |  |  | CY Target | CY Target Achieved | Forecast Performance
8 |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY |  | (Yes/No) | CY+1 | CY+2 | CY+3 | CY+4 | CY+5
9 |  | Number of loss of supply events greater than 0.05 system minutes | 9 | 13 | 9 | 9 | 8 | None | None | None | None | None | None | None
10 |  | Number of loss of supply events greater than 1 system minute | 0 | 1 | 1 | 2 | 3 | None | None | None | None | None | None | None
11 |  | Unplanned HVAC circuit unavailability (%) | 0.337% | 0.494% | 0.06% | 0.034% | 0.078% | None | None | None | None | None | None | None
12 |  | Unplanned HVDC bi-pole unavailability (%)* | 1.264% | 0.05% | 0.066% | 0.646% | 0.492% | None | None | None | None | None | None | None
13 |  | Total impact of interruptions (measured in system minutes) | 3.28 | 334.46 | 2.53 | 5.77 | 7.43 | None | None | None | None | None | None | None
14 |  | *No target currently specified
15 |  | The number of loss of supply for the above quality measures relate to unplanned loss of supply events.
16 |  | The total impact of interruptions for the earliest year shown was reporting both planned and unplanned. It has now been fixed.
17 | G4(ii): Grid Connection Point Performance Measures
18
19
20 |  | Point of Service Performance - Demand | No target currently specified. The Point of Service code and description have been used to identify the locations.
21 | [5 empty] | Number of Interruptions |  |  |  | Unserved energy % X100
22 |  |  | Point of Service |  |  | CY-2 Actual | CY-1 Actual | CY Actual | 5 year average | CY-2 Actual | CY-1 Actual | CY Actual | 5 year average
23 |  |  | ABY011S1 | Albury 11 kV POS S 1 |  | 3 | 1 | 0 | 1 | 10.6106 | 95.7394 | 0 | 22.8681
24 |  |  | ALB033S1 | Albany 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 |  |  | ALB110S1 | Albany 110 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 |  |  | APS011S1 | Arthurs Pass 11 kV POS S 1 |  | 3 | 3 | 1 | 1.8 | 6.1035 | 4.6091 | 0.53624 | 3.167
27 |  |  | ARI110S2 | Arapuni 110 kV POS S 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 |  |  | ASB066SA | Ashburton 66 kV POS S |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 |  |  | ASY011S1 | Ashley 11 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 |  |  | ATI220S1 | Atiamuri 220 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 |  |  | BAL033S1 | Balclutha 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 |  |  | BDE011S1 | Brydone 11 kV POS S 1 |  | 1 | 0 | 0 | 0.2 | 1.4543 | 0 | 0 | 0.29085
33 |  |  | BDE011S2 | Brydone 11 kV POS S 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 |  |  | BLN033S1 | Blenheim 33 kV POS S 1 |  | 0 | 0 | 1 | 0.2 | 0 | 0 | 2.6122 | 0.52244
35 |  |  | BOB110S1 | Bombay 110 kV POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.086309
36 |  |  | BPD110S1 | Bells Pond 110 kV POS S 1 |  | 1 | 2 | 1 | 0.8 | 1.528 | 1.7385 | 0.76062 | 0.80541
37 |  |  | BPE033S1 | Bunnythorpe 33 kV POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.078203
38 |  |  | BPE055SA | Bunnythorpe 55 kV POS S |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 |  |  | BPT110S1 | Black Point 110 kV POS S 1 |  | 2 | 3 | 0 | 1 | 1.9648 | 0.70982 | 0 | 0.53491
40 |  |  | BRB033S1 | Bream Bay 33 kV POS S 1 |  | 1 | 0 | 0 | 0.2 | 2.3133 | 0 | 0 | 0.46266
41 |  |  | BRK033S1 | Brunswick 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 |  |  | BRY066SA | Bromley 66 kV POS S |  | 1 | 0 | 0 | 0.2 | 0.11256 | 0 | 0 | 0.022511
43 |  |  | CBG011S1 | Cambridge 11 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 |  |  | CLH011S1 | Castle Hill 11 kV POS S 1 |  | 3 | 3 | 1 | 1.8 | 9.2648 | 4.8334 | 0.21828 | 3.3796
45 |  |  | CML033S1 | Cromwell 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 |  |  | COL011S1 | Coleridge 11 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 |  |  | CPK011S1 | Central Park 11 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 |  |  | CPK033S1 | Central Park 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 |  |  | CST033S1 | Carrington Street 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 |  |  | CUL033S1 | Culverden 33 kV POS S 1 |  | 0 | 0 | 2 | 0.4 | 0 | 0 | 1.1305 | 0.2261
51 |  |  | CUL066S1 | Culverden 66 kV POS S 1 |  | 0 | 0 | 1 | 0.2 | 0 | 0 | 0.24619 | 0.049239
52 |  |  | CYD033S1 | Clyde 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 |  |  | DOB033S1 | Dobson 33 kV POS S 1 |  | 0 | 0 | 1 | 0.4 | 0 | 0 | 4.8881 | 1.2957
54 |  |  | DVK011S1 | Dannevirke 11 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 |  |  | EDG033S1 | Edgecumbe 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 |  |  | EDN033S1 | Edendale 33 kV POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.38782
57 |  |  | FHL033S1 | Fernhill 33 kV POS S 1 |  | 0 | 1 | 1 | 0.8 | 0 | 2.0997 | 1.1224 | 1.1909
58 |  |  | FKN033S1 | Frankton 33 kV (A) POS S 1 |  | 1 | 0 | 1 | 0.4 | 0.057267 | 0 | 0.13454 | 0.038361
59 |  |  | FKN033S2 | Frankton 33 kV (B) POS S 2 |  | 0 | 0 | 1 | 0.2 | 0 | 0 | 0.13563 | 0.027127
60 |  |  | GFD033S1 | Gracefield 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 |  |  | GLN033SA | Glenbrook 33 kV (B) POS S |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 |  |  | GLN033S3 | Glenbrook 33 kV (A) POS S 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 |  |  | GOR033S1 | Gore 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 |  |  | GYM066S1 | Greymouth 66 kV POS S 1 |  | 0 | 0 | 1 | 0.6 | 0 | 0 | 2.3586 | 0.89714
65 |  |  | GYT033S1 | Greytown 33 kV POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.49637
66 |  |  | HAM011S1 | Hamilton 11 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 |  |  | HAM033S1 | Hamilton 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 |  |  | HAM033S2 | Hamilton 33kV POS S 2 |  | - | - | 0 | 0 | - | - | 0 | 0
69 |  |  | HAM055SA | Hamilton 55 kV POS S |  | 1 | 0 | 0 | 0.2 | 0.018206 | 0 | 0 | 0.0036411
70 |  |  | HAY011S1 | Haywards 11 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 |  |  | HAY033S1 | Haywards 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 |  |  | HEN033S1 | Henderson 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 |  |  | HEP033S1 | Hepburn Road 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 |  |  | HIN033S1 | Hinuera 33 kV POS S 1 |  | 0 | 2 | 0 | 0.6 | 0 | 0.53041 | 0 | 0.60441
75 |  |  | HKK066S1 | Hokitika 66 kV POS S 1 |  | 0 | 1 | 0 | 0.6 | 0 | 1.0543 | 0 | 1.1773
76 |  |  | HLY033SA | Huntly 33 kV POS S |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 |  |  | HOB110S1 | Hobson Street 110 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 |  |  | HOR033S1 | Hororata 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 |  |  | HOR066S1 | Hororata 66 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 |  |  | HTI033S1 | Hangatiki 33 kV POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.77829
81 |  |  | HTI110S1 | Hangatiki 110 kV POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.64118
82 |  |  | HTU033S1 | Hautapu 33kV POS S 1 |  | - | 0 | 1 | 0.5 | - | 0 | 0.59795 | 0.29897
83 |  |  | HUI033S1 | Huirangi 33 kV POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.37488
84 |  |  | HWA033S1 | Hawera 33 kV (A) POS S 1 |  | 0 | 1 | 0 | 0.2 | 0 | 0.4879 | 0 | 0.09758
85 |  |  | HWA033S2 | Hawera 33 kV (B) POS S 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 |  |  | HWB033S1 | Halfway Bush 33 kV (A) POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 |  |  | HWB033S2 | Halfway Bush 33 (B) kV POS S 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 |  |  | INV033S1 | Invercargill 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 |  |  | INV066S1 | Invercargill 66 kV POS S 1 |  | - | - | 0 | 0 | - | - | 0 | 0
90 |  |  | ISL033S1 | Islington 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 |  |  | ISL066S1 | Islington 66 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 |  |  | KAI011S1 | Kaiapoi 11 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 |  |  | KAW011S1 | Kawerau 11 kV (A) POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 |  |  | KAW011S2 | Kawerau 11 kV POS S 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 |  |  | KBY066SA | Kimberley 66 kV POS S |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 |  |  | KIK011S1 | Kikiwa 11 kV POS S 1 |  | 0 | 0 | 1 | 0.6 | 0 | 0 | 3.1965 | 4.9622
97 |  |  | KIN011SA | Kinleith 11 kV POS SA |  | 0 | 1 | 0 | 0.2 | 0 | 0.23629 | 0 | 0.047259
98 |  |  | KIN011SB | Kinleith 11 kV POS SB |  | 0 | 0 | 0 | 0 | - | - | 0 | 0
99 |  |  | KIN033S1 | Kinleith 33 kV POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.064442
100 |  |  | KMO033S1 | Kaitemako 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 |  |  | KOE110S1 | Kaikohe 110 kV POS S 1 |  | 1 | 0 | 0 | 0.2 | 144.2917 | 0 | 0 | 28.8583
102 |  |  | KPA110S1 | Kaponga Tee 110 kV POS S1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 |  |  | KPU066S1 | Kopu 66 kV POS S 1 |  | 1 | 0 | 1 | 0.6 | 1.0971 | 0 | 0.17256 | 1.1089
104 |  |  | KUM066S1 | Kumara 66 kV POS S 1 |  | 0 | 0 | 0 | 0.6 | 0 | 0 | 0 | 1.2636
105 |  |  | KWA011S1 | Kaiwharawhara 11 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 |  |  | LFD110S1 | Lichfield 110 kV POS S 1 |  | 1 | 0 | 0 | 0.2 | 0.099267 | 0 | 0 | 0.019853
107 |  |  | LTN033S1 | Linton 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 |  |  | MAT110S1 | Matahina 110 kV (A) POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 |  |  | MCH011S1 | Murchison 11 kV POS S 1 |  | 0 | 1 | 1 | 0.8 | 0 | 3.3091 | 12.6971 | 5.4642
110 |  |  | MGM033S1 | Mangamaire 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 |  |  | MHO033S1 | Mangahao 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 |  |  | MLG011S1 | Melling 11 kV POS S 1 |  | 0 | 0 | 1 | 0.4 | 0 | 0 | 0.80171 | 0.43775
113 |  |  | MLG033S1 | Melling 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 |  |  | MNG033S1 | Mangere 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 |  |  | MNG110S1 | Mangere 110 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 |  |  | MNI011SA | Motunui 11 kV POS S |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 |  |  | MNI011S3 | Motunui 11 kV POS S 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 |  |  | MPE110S1 | Maungatapere 110 kV POS S 1 |  | 1 | 0 | 0 | 0.2 | 1.1638 | 0 | 0 | 0.23276
119 |  |  | MST033S1 | Masterton 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 |  |  | MTM033S1 | Mt Maunganui 33 kV POS S 1 |  | 0 | 0 | 1 | 0.2 | 0 | 0 | 2.4009 | 0.48018
121 |  |  | MTN033S1 | Marton 33 kV POS S 1 |  | 0 | 0 | 1 | 0.2 | 0 | 0 | 0.011965 | 0.002393
122 |  |  | MTO033S1 | Maungaturoto 33 kV POS S 1 |  | 0 | 2 | 0 | 0.6 | 0 | 4.0827 | 0 | 0.84829
123 |  |  | MTR033S1 | Mataroa 33 kV POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.11408
124 |  |  | NMA033S1 | North Makarewa 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 |  |  | NPK033S1 | National Park 33 kV POS S 1 |  | 0 | 0 | 1 | 1 | 0 | 0 | 0.18985 | 0.47751
126 |  |  | NSY033S1 | Naseby 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 |  |  | NWD066S1 | Norwood 66 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 |  |  | OAM033S1 | Oamaru 33 kV POS S 1 |  | 0 | 1 | 0 | 0.2 | 0 | 1.4339 | 0 | 0.28679
129 |  |  | OKN011S2 | Ohakune 11 kV (A) POS S 2 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.098495
130 |  |  | OKN011S1 | Ohakune 11 kV (B) POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.18683
131 |  |  | ONG033S1 | Ongarue 33 kV POS S 1 |  | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 | 0.51519
132 |  |  | OPK033S1 | Opunake 33 kV POS S 1 |  | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 | 0.84922
133 |  |  | ORO110S1 | Orowaiti Tee 110 kV POS S 1 |  | 2 | 0 | 1 | 1 | 0.57376 | 0 | 2.5012 | 0.84967
134 |  |  | OTA022S1 | Otahuhu 22 kV (A) POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 |  |  | OTI011S1 | Otira 11 kV POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0
136 |  |  | OWH011S1 | Owhata 11 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 |  |  | PAK033S1 | Pakuranga 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 |  |  | PAO110S1 | Piako 110 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 |  |  | PEN022S1 | Penrose 22 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 |  |  | PEN025S1 | Penrose 25 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 |  |  | PEN033S1 | Penrose 33 kV (A) POS S 1 |  | 1 | 0 | 0 | 0.2 | 0.12268 | 0 | 0 | 0.024536
142 |  |  | PEN033S2 | Penrose 33 kV (B) POS S 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 |  |  | PEN110S1 | Penrose 110 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 |  |  | PNI033S1 | Pauatahanui 33 kV POS S 1 |  | 1 | 0 | 0 | 0.6 | 0.93832 | 0 | 0 | 0.37653
145 |  |  | PRM033S1 | Paraparaumu 33 kV POS S 1 |  | 0 | 1 | 0 | 0.2 | 0 | 0.10122 | 0 | 0.020245
146 |  |  | RDF033S1 | Redclyffe 33 kV POS S 1 |  | 0 | 1 | 1 | 0.8 | 0 | 1.9783 | 1.0599 | 39.7201
147 |  |  | RFN110SA | Reefton 110 kV POS S |  | 1 | 0 | 1 | 0.6 | 0.41096 | 0 | 4.8587 | 1.2944
148 |  |  | ROS022S1 | Mount Roskill 22 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 |  |  | ROS110S1 | Mount Roskill 110 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 |  |  | ROT011S1 | Rotorua 11 kV POS S 1 |  | 0 | 1 | 0 | 0.2 | 0 | 1.0656 | 0 | 0.21311
151 |  |  | ROT033S1 | Rotorua 33 kV POS S 1 |  | 0 | 1 | 0 | 0.2 | 0 | 1.4581 | 0 | 0.29162
152 |  |  | SBK066S1 | Southbrook 66 kV POS S1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 |  |  | SDN033S1 | South Dunedin 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 |  |  | SFD033S1 | Stratford 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 |  |  | STK033S1 | Stoke 33 kV (A) POS S 1 |  | 0 | 0 | 1 | 0.2 | 0 | 0 | 2.1571 | 0.43141
156 |  |  | STK066S1 | Stoke 66 kV POS S 1 |  | 0 | 0 | 1 | 0.2 | 0 | 0 | 18.5354 | 3.7071
157 |  |  | STU011S1 | Studholme 11 kV POS S 1 |  | 0 | 1 | 1 | 0.4 | 0 | 2.5285 | 0.53109 | 0.61193
158 |  |  | SVL033S1 | Silverdale 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 |  |  | SWN025S1 | Southdown 25 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 |  |  | TAB033S1 | Tauhara 33 kV POS S 1 |  | 0 | 1 | 0 | 0.33333 | 0 | 26.3405 | 0 | 8.7802
161 |  |  | TAK033S1 | Takanini 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 |  |  | TGA011S1 | Tauranga 11 kV POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.51283
163 |  |  | TGA033S1 | Tauranga 33 kV POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.30512
164 |  |  | TIM011S1 | Timaru 11 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 |  |  | TKA033S1 | Tekapo A 33 kV POS S 1 |  | 0 | 2 | 1 | 2 | 0 | 35.487 | 1.1775 | 8.5906
166 |  |  | TKR033S1 | Takapu Road 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 |  |  | TKU033S1 | Tokaanu 33 kV (A) POS S 1 |  | 1 | 0 | 0 | 0.2 | 0.49224 | 0 | 0 | 0.098448
168 |  |  | TMI033S1 | Te Matai 33 kV POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.21575
169 |  |  | TMK033S1 | Temuka 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 |  |  | TMN055SA | Taumarunui 55 kV POS S |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 |  |  | TMU011SA | Te Awamutu 11 kV POS S |  | 2 | 0 | 1 | 0.6 | 0.16787 | 0 | 0.39478 | 0.11253
172 |  |  | TNG055SA | Tangiwai 55 kV POS S |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 |  |  | TRK011S1 | Tarukenga 11 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 |  |  | TUI110S2 | Tuai 110 kV POS S2 |  | 0 | 1 | 1 | 0.8 | 0 | 1.6876 | 1.3589 | 2.4426
175 |  |  | TWC220S1 | Tararua Wind Central 220 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 |  |  | TWH033S1 | Te Kowhai 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 |  |  | TWI220S1 | Tiwai 220 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 |  |  | TWZ033S1 | Twizel 33 kV (A) POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.085584
179 |  |  | TWZ033S3 | Twizel 33 kV (B) POS S 3 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 |  |  | UHT033S1 | Upper Hutt 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 |  |  | WAI011S1 | Waiotahe 11 kV POS S 1 |  | 0 | 1 | 1 | 0.4 | 0 | 0.29491 | 31.2185 | 6.3027
182 |  |  | WAI033S1 | Waiotahe 33 kV POS S 1 |  | - | - | 1 | 1 | - | - | 46.7627 | 46.7627
183 |  |  | WAI050S1 | Waiotahe 50 kV POS S 1 |  | 1 | 1 | 0 | 0.4 | 0.35904 | 0.23777 | 0 | 0.11936
184 |  |  | WDV011S1 | Woodville 11 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 |  |  | WEL033S1 | Wellsford 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 |  |  | WGN033S1 | Whanganui 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 |  |  | WHI011SA | Whirinaki 11 kV POS S |  | 0 | 1 | 1 | 0.6 | 0 | 1.7596 | 2.0853 | 207.7929
188 |  |  | WHU033S1 | Waihou 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 |  |  | WIL033S1 | Wilton 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 |  |  | WIR033S1 | Wiri 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 |  |  | WKO033S1 | Waikino 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 |  |  | WPR033S1 | Waipara 33 kV POS S 1 |  | 0 | 1 | 0 | 0.2 | 0 | 0.33665 | 0 | 0.067329
193 |  |  | WPR066S1 | Waipara 66 kV POS S 1 |  | 0 | 1 | 0 | 0.2 | 0 | 0.34678 | 0 | 0.069356
194 |  |  | WPW011S1 | Waipawa 11 kV POS S 1 |  | 0 | 0 | 1 | 0.6 | 0 | 0 | 4.2943 | 2.1275
195 |  |  | WPW033S1 | Waipawa 33 kV POS S 1 |  | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 | 0.58223
196 |  |  | WRD033S1 | Wairau Road 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 |  |  | WRK033S1 | Wairakei 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 |  |  | WTK011S2 | Waitaki 11kV POS S 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 |  |  | WTK033S1 | Waitaki 33 kV POS S 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 |  |  | WTU033S1 | Whakatu 33 kV POS S 1 |  | 0 | 1 | 1 | 0.6 | 0 | 1.2501 | 0.80137 | 19.5691
201 |  |  | WVY011S1 | Waverley 11 kV POS S 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 0.1433
202 |  |  | An update on the data has been done since last year's report. This has affected some numbers for KPA110S1.
203 |  |  | *Insert additional rows as needed
204
205 |  | Point of Service Performance - Injection
206 | [5 empty] | Number of Interruptions |  |  |  | Duration in minutes
207 |  |  | Point of Service |  |  | CY-2 Actual | CY-1 Actual | CY Actual | 5 year average | CY-2 Actual | CY-1 Actual | CY Actual | 5 year average
208 |  |  | ARA220I1 | Aratiatia 220 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 |  |  | ARG110I1 | Argyle 110 kV POS I 1 |  | 0 | 3 | 2 | 2.2 | 0 | 20 | 203 | 112.2
210 |  |  | ARI110I1 | Arapuni 110 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 |  |  | AVI220I1 | Aviemore 220 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 |  |  | BEN220I1 | Benmore 220 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 |  |  | BRB033I1 | Bream Bay 33 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 |  |  | BWK110I1 | Berwick 110 kV POS I 1 |  | 1 | 1 | 3 | 1.8 | 96 | 3 | 35 | 59.4
215 |  |  | COL066I1 | Coleridge 66 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 |  |  | CYD220I1 | Clyde 220 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 |  |  | DVK011I2 | Dannevirke 11kV POS I 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 |  |  | GLN033I1 | Glenbrook 33 kV POS I 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 10.6
219 |  |  | GLN033I2 | Glenbrook 33 kV POS I 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 |  |  | HLY220I1 | Huntly 220 kV POS I 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 32.8
221 |  |  | HRP220I1 | Harapaki 220 kV POS I 1 |  | 0 | 1 | 1 | 0.4 | 0 | 133 | 73 | 41.2
222 |  |  | HWA110I1 | Hawera 110 kV (A) POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 |  |  | HWA110I2 | Hawera 110 kV (B) POS I 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 |  |  | JRD110I1 | Junction Road 110 kV POS I 1 |  | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 | 3.6
225 |  |  | KAW110I1 | Kawerau 110 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 |  |  | KAW220I1 | Kawerau 220 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 |  |  | KIW220I1 | Kaiwera Downs 220kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 |  |  | KPO110I1 | Karapiro 110 kV POS I 1 |  | 0 | 1 | 0 | 0.2 | 0 | 35 | 0 | 7
229 |  |  | LTN220I1 | Linton 220 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 |  |  | MAN220I1 | Manapouri 220 kV POS I 1 |  | 0 | 0 | 0 | 0.4 | 0 | 0 | 0 | 4858.2
231 |  |  | MAT110I2 | Matahina 110 kV (B) POS I 2 |  | 0 | 1 | 0 | 0.2 | 0 | 131 | 0 | 26.2
232 |  |  | MHO033I2 | Mangahao 33 kV POS I 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 |  |  | MKE110I1 | McKee 110 kV POS I 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 3
234 |  |  | MTI220I1 | Maraetai 220 kV POS I 1 |  | 2 | 1 | 0 | 0.6 | 412 | 158 | 0 | 114
235 |  |  | NAP220I1 | Nga Awa Purua 220 kV POS I 1 |  | 0 | 1 | 0 | 0.2 | 0 | 549 | 0 | 109.8
236 |  |  | NAP220I2 | Nga Awa Purua 220 kV POS I 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 |  |  | OHA220I1 | Ohau A 220 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 |  |  | OHB220I1 | Ohau B 220 kV POS I 1 |  | 0 | 0 | 0 | 0.8 | 0 | 0 | 0 | 23.6
239 |  |  | OHC220I1 | Ohau C 220 kV POS I 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 5.6
240 |  |  | OHG110I1 | Ohangai 110 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 |  |  | OHK220I1 | Ohakuri 220 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 |  |  | OKI220I1 | Ohaaki 220 kV POS I 1 |  | 0 | 0 | 0 | 0.2 | 0 | 0 | 0 | 7.4
243 |  |  | PPI220I1 | Poihipi 220 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 |  |  | ROT110I1 | Rotorua 110 kV POS I 1 |  | 0 | 2 | 0 | 0.4 | 0 | 650 | 0 | 130
245 |  |  | ROX110I1 | Roxburgh 110 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 |  |  | ROX220I1 | Roxburgh 220 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 |  |  | RPO220I1 | Rangipo 220 kV POS I 1 |  | 1 | 1 | 0 | 1.4 | 14 | 205 | 0 | 475.8
248 |  |  | SFD220I1 | Stratford 220 kV POS I 1 |  | 0 | 0 | 1 | 0.2 | 0 | 0 | 67 | 13.4
249 |  |  | TAB220I1 | Tauhara 220 kV POS I 1 |  | 0 | 1 | 0 | 0.2 | 0 | 102 | 0 | 20.4
250 |  |  | THI220I1 | Te Mihi 220 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 |  |  | TKA011I1 | Tekapo A 11 kV POS I 1 |  | 2 | 2 | 3 | 2.8 | 8 | 1795 | 310 | 500
252 |  |  | TKB220I1 | Tekapo B 220 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 |  |  | TKU220I1 | Tokaanu 220 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 |  |  | TUI110I1 | Tuai 110 kV POS I 1 |  | 0 | 1 | 1 | 0.8 | 0 | 97 | 127 | 101.2
255 |  |  | WAI033I1 | Waiotahe 33 kV POS I 1 |  | 0 | 1 | 4 | 1 | 0 | 25 | 1635 | 332
256 |  |  | WDV110I1 | Woodville - Te Apiti Wind Farm 110 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 |  |  | WHI220I1 | Whirinaki 220 kV POS I 1 |  | 0 | 1 | 1 | 0.6 | 0 | 80 | 117 | 6367.6
258 |  |  | WHU110I1 | Waihou 110 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 |  |  | WKM220I1 | Whakamaru 220 kV POS I 1 |  | 0 | 0 | 1 | 0.4 | 0 | 0 | 116 | 82.6
260 |  |  | WPA220I1 | Waipapa 220 kV POS I 1 |  | 2 | 0 | 1 | 0.6 | 1449 | 0 | 330 | 355.8
261 |  |  | WRK220I1 | Wairakei 220 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 |  |  | WTK011I1 | Waitaki 11 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
263 |  |  | WVY110I1 | Waverley 110 kV POS I 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 |  |  | WWD110I1 | West Wind 110 kV POS I 1 |  | 0 | 0 | 1 | 1 | 0 | 0 | 9 | 142
265 |  |  | An update on the data has been done since last year's report. This has affected some numbers for BRB033I1.
*Insert additional rows as needed
267
268 | G4(iii): Unplanned Interruption Causes
269
270 |  | Cause of interruption | Annual Performance (System Minutes) |  |  |  |  | Significant Events (System Minutes) |  |  |  |  | Underlying Events (System Minutes)
271 |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY | CY-4 | CY-3 | CY-2 | CY-1 | CY | CY-4 | CY-3 | CY-2 | CY-1 | CY
272 |  | Transpower Unplanned
273 |  | Environment | 2.03 | 333.47 | 0.11 | 2.74 | 6.41 | 0 | 331.99 | 0 | 2.47 | 6.29 | 2.03 | 1.48 | 0.11 | 0.27 | 0.12
274 |  | Equipment | 0.9 | 0.62 | 0.23 | 0.49 | 0.84 | 0 | 0 | 0 | 0 | 0 | 0.9 | 0.62 | 0.23 | 0.49 | 0.84
275 |  | Human error | 0.31 | 0.2 | 2.02 | 0.42 | 0.06 | 0 | 0 | 1.55 | 0 | 0 | 0.31 | 0.2 | 0.47 | 0.42 | 0.06
276 |  | Miscellaneous | 0 | 0 | 0.07 | 1.75 | 0.04 | 0 | 0 | 0 | 1.72 | 0 | 0 | 0 | 0.07 | 0.03 | 0.04
277 |  | Not Known | 0.04 | 0.16 | 0.09 | 0.38 | 0.09 | 0 | 0 | 0 | 0 | 0 | 0.04 | 0.16 | 0.09 | 0.38 | 0.09
278 |  | Total Unplanned | 3.28 | 334.45 | 2.52 | 5.78 | 7.44 | 0 | 331.99 | 1.55 | 4.19 | 6.29 | 3.28 | 2.46 | 0.97 | 1.59 | 1.15
279
280 |  | Transpower Planned | 2.76 | 1.24 | 1.82 | 1.75 | 35.75 | 0 | 0 | 0 | 0 | 34.45 | 2.76 | 1.24 | 1.82 | 1.75 | 1.3
281
282 |  | Total Transpower Planned and Unplanned | 6.04 | 335.69 | 4.34 | 7.53 | 43.19 | 0 | 331.99 | 1.55 | 4.19 | 40.74 | 6.04 | 3.7 | 2.79 | 3.34 | 2.45
283
284

## G5. Quality interconnection
[9 empty] | Transpower |  | Disclosure Date |  | 2026-10-23
SCHEDULE G5: QUALITY OF SUPPLY: INTERCONNECTION ASSETS | [10 empty] | Disclosure Year (year ended) |  | 2026-06-30
ref
5 | G5(i): Interconnection Asset Report
6
7 | Asset | Type* | Asset Category | Sub Cat | Planned Unavailability % | Unplanned Unavailability % | Number Planned Interruptions | Planned Unserved Energy MWh | Number Unplanned Interruptions | Unplanned Unserved Energy MWh | Number of Outages <1 Min | Number of Interruptions <1 min | Measures Exceeded (plan/Unplan) ? | Incidents Affecting Performance | Steps Being Taken To Improve Performance | IDENT
8 | Index Measures for Asset Category |  | CCT | 110 | 1.67 | 0.07 | 0.08 | 0.5 | 0.28 | 10.45 | None Apply | None Apply
9 | ARI-BOB-1 | I | CCT | 110 | 93.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
10 | ARI-HAM-1 | I | CCT | 110 | 8.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
11 | ARI-HAM-2 | I | CCT | 110 | 11.51 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
12 | ARI-HTI-1 | I | CCT | 110 | 0.76 | 0 | 0 | 0 | 1 | 8.36 | 5 | 0 | N/Y | 20-Feb-2026: ARI-HTI-1 trip & A/R, Y-E, cause unknown area, no patrol. LOS at TMU as COPS operated at TMU. | No further action. | SN26042
13 | ARI-HTI-ONG-1 | I | CCT | 110 | 3.71 | 1.96 | 0 | 0 | 0 | 0 | 5 | 0 | Y/Y | Planned Outage /
14 | [13 empty] | 14-Oct-2025: ARI-HTI-ONG-1 tripped for a Bph-E fault, trees came down on landslide caused by heavy rain and flood. These trees, made mobile by the landslip, severed conductors in span ARI-ONG-B0194-0195-10. Line was patrolled via helicopter. Bph conductor was repaired. | Trees that came down were cleared and affected conductor repaired. | SN25150
15 | [13 empty] | 13-Nov-2025: ARI-HTI-ONG-1 tripped for a red phase to yellow phase fault, caused by gale force winds. Strong winds resulted in a tree falling on these conductors. Service provider repaired two broken conductors and re-instated the span from 195 to 196 using helicopter. | 2 broken conductors on ARI-ONG-B0195-0196-10 were replaced. Fallen trees were removed. | SN25167
16 | [13 empty] | 03-Dec-2025: ARI-HTI-ONG-1 trip & A/R, except at ONG, for a three phase fault, probably caused by a lightning strike. SDTF recorded a lightning strike close to ARI-ONG-B0140-10. No line patrol. No interruption of supply. | No further action. | SN25183
17 | [13 empty] | 06-May-2026: ONG-CB-92 RFS for a low SF6 gas pressure alarm which was a false alarm caused by an inverted SCADA point. ONG-RTO-1 circuit section of ARI-HTI-ONG-1 was also RFS. | SCADA point mapping corrected. | SN26066
18 | ARI-KIN-1 | I | CCT | 110 | 0.37 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N/N | Planned Outage /
19 | ARI-KIN-2 | I | CCT | 110 | 0.76 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N/N | Planned Outage /
20 | ATU-DOB-1 | I | CCT | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
21 | ATU-RFN-IGH-1 | I | CCT | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
22 | BAL-GOR-1 | B | CCT | 110 | 2.04 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Y/N | Planned Outage /
23 | BAL-HWB-1 | B | CCT | 110 | 5.06 | 0.38 | 0 | 0 | 0 | 0 | 2 | 0 | Y/Y | Planned Outage /
24 | [13 empty] | 29-Oct-2025: BAL-BWK-1 section of BAL-BWK-HWB-1 RFS STPP for line repairs after storm | Tree removed from line and broken conductor was replaced. | SS25103
25 | BDE-EDN-1 | B | CCT | 110 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
26 | BDE-GOR-1 | B | CCT | 110 | 0.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
27 | BLN-KIK-1 | I | CCT | 110 | 7.48 | 0.01 | 0 | 0 | 0 | 0 | 5 | 1 | Y/N | Planned Outage /
28 | BLN-STK-1 | I | CCT | 110 | 0.99 | 0.02 | 0 | 0 | 0 | 0 | 1 | 0 | N/N | Planned Outage /
29 | BLN-STK-2 | I | CCT | 110 | 0 | 0.02 | 0 | 0 | 0 | 0 | 2 | 0 | N/N
30 | BOB-HAM-1 | I | CCT | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
31 | BOB-HAM-2 | I | CCT | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
32 | BPE-MTN-WGN-1 | B | CCT | 110 | 1.19 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
33 | BPE-MTN-WGN-2 | B | CCT | 110 | 4.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
34 | BPE-MTR-1 | I | CCT | 110 | 0.08 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | N/Y | 15-Feb-2026: BPE-MTR-1 tripped for red to blue phase fault, caused by gale-force winds that felled trees onto 3 phase conductors in span BPE-ONG-A0148-0149-10. Copper conductor had snapped & was repaired. Note planned outage to BPE-MTR-1 for project work started on 23/2/2026 at 07:00 | Cleared all access tracks and trees along the circuit corridor. Damaged conductors were repaired. | SN26038
35 | BPE-WDV-1 | I | CCT | 110 | 1.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
36 | BPE-WDV-2 | I | CCT | 110 | 2.24 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
37 | CPK-WIL-1 | B | CCT | 110 | 0.3 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
38 | CPK-WWD-WIL-2 | B | CCT | 110 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
39 | CPK-WWD-WIL-3 | B | CCT | 110 | 2.58 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
40 | CST-HUI-1 | I | CCT | 110 | 3.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
41 | CST-HUI-2 | I | CCT | 110 | 3.77 | 0.37 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
42 | [13 empty] | 13-Oct-2025: HUI-CB-848 failed to close in an attempt to RTS HUI-BS-220 at the end of a planned outage. The issue was traced to a sticky mech box mechanism which has been attributed to corrosion, we have lubricated the mechanism, but the intention is to recondition the mech box | The issue was traced to a sticking mechanism within the mechanism box caused by corrosion. The affected points were lubricated without disassembly. The circuit breaker was operated several times until it opened and closed freely. The mechanism box is scheduled for refurbishment as part of a planned project by July 2027. | SN25148
43 | [13 empty] | 16-Dec-2025: CST-DS-94 failed to close on blue phase, CST-HUI-2 RFS for repairs | Pipe work was adjusted to get the switch fully aligned. Tested the switch is working. | SN25197
44 | [13 empty] | 19-Apr-2026: CST-HUI-2 RFS to isolate CST-CB-62 which went mid-position when it attempted to A/R after CST-SFD-3 tripped for a red phase to earth fault. | Circuit breaker pole replaced. | SN26056
45 | CST-JRD-SFD-1 | B | CCT | 110 | 1.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
46 | CST-MNI-1 | I | CCT | 110 | 1.24 | 0.09 | 0 | 0 | 0 | 0 | 0 | 0 | N/Y | 16-Dec-2025: CST-DS-94 failed to close on blue phase, CST-MNI-1 RFS for repairs | Pipe work was adjusted to get the switch fully aligned. Tested the switch is working. | SN25197
47 | [13 empty] | 19-Apr-2026: CST-MNI-1 RFS to isolate CST-CB-62 which went mid-position when it attempted to A/R after CST-SFD-3 tripped for a red phase to earth fault. | Circuit breaker pole replaced. | SN26056
48 | CST-NPL-1 | I | CCT | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
49 | CST-NPL-2 | I | CCT | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
50 | CST-SFD-1 | I | CCT | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
51 | CST-SFD-2 | I | CCT | 110 | 8.26 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
52 | CST-SFD-3 | I | CCT | 110 | 6.08 | 3.38 | 0 | 0 | 0 | 0 | 1 | 0 | Y/Y | Planned Outage /
53 | [13 empty] | 16-Dec-2025: CST-DS-94 failed to close on blue phase, CST-SFD-3 RFS for repairs | Pipe work was adjusted to get the switch fully aligned. Tested the switch is working. | SN25197
54 | [13 empty] | 19-Apr-2026: CST-SFD-3 delayed RTS when CST-CB-62 went mid-position when attempted to A/R after CST-SFD-3 tripped for a red phase to earth fault. CB62 failed to close via a remote close command. Blue phase pole was faulty. All three poles were replaced. | Circuit breaker pole replaced. | SN26056
55 | DOB-RFN-IGH-1 | I | CCT | 110 | 5.53 | 0.01 | 0 | 0 | 1 | 12.87 | 2 | 0 | Y/Y | Planned Outage /
56 | [13 empty] | 23-Oct-2025: ISL-KIK-1 trip and A/R, BPh-earth fault, cause strong winds, no patrol. Upper SI LOS, LOS to RFN to Westpower. Note RFN T3 still O/S from DOB-RFN-IGH2 trip of 21/10/25 (see SS25092) | Post event inspections have occurred using drones and service providers to identify defects. Information has been supplied to inform an investigation to look at options to improve the performance/resilience of ISL-KIK-A and B assets to high wind events. This investigation project is being generated within the system, and will be prioritised within the work plan. | SS25104
57 | DOB-RFN-IGH-2 | I | CCT | 110 | 2.1 | 2.99 | 0 | 0 | 0 | 0 | 4 | 0 | Y/Y | Planned Outage /
58 | [13 empty] | 21-Oct-2025: DOB-RFN-IGH-2 tripped, A/R, tripped, cause heavy rain and strong winds, LOS at RFN, pole 68 in the river, broken conductors span 67 - 68, broken insulators str 65,66,67, 68 | Pole 68 was removed and pole 67 was replaced with a taller pole. With the pole removed the conductor now totally spans the river. | SS25092
59 | [13 empty] | 17-Nov-2025: DOB-RFN-IGH-2 RFS for conductor repair work, DOB T11 RFS, LOS at RFN. Conductor has separated from insulator string. | Replaced broken insulators. | SS25112
60 | EDG-KAW-1 | I | CCT | 110 | 3.19 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
61 | EDG-KAW-2 | I | CCT | 110 | 1.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
62 | EDG-OWH-2 | B | CCT | 110 | 0.99 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | N/N | Planned Outage /
63 | EDN-INV-1 | I | CCT | 110 | 2.35 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
64 | FHL-RDF-1 | I | CCT | 110 | 5.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
65 | FHL-RDF-2 | I | CCT | 110 | 6.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
66 | FHL-TUI-1 | I | CCT | 110 | 1.58 | 0.04 | 0 | 0 | 0 | 0 | 1 | 0 | N/N | Planned Outage /
67 | FHL-WPW-1 | I | CCT | 110 | 2.13 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Y/N | Planned Outage /
68 | FHL-WPW-2 | I | CCT | 110 | 1.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
69 | GOR-ROX-1 | I | CCT | 110 | 4.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
70 | HAM-KPO-1 | I | CCT | 110 | 4.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
71 | HAM-KPO-2 | I | CCT | 110 | 3.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
72 | HAY-TKR-1 | I | CCT | 110 | 1.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
73 | HAY-TKR-2 | I | CCT | 110 | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
74 | HAY-UHT-1 | I | CCT | 110 | 2.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
75 | HAY-UHT-2 | I | CCT | 110 | 0.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
76 | HEN-HEP-1 | I | CCT | 110 | 1.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
77 | HEN-HEP-2 | I | CCT | 110 | 1.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
78 | HEN-HEP-3 | I | CCT | 110 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
79 | HEN-HEP-4 | I | CCT | 110 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
80 | HEN-MPE-1 | I | CCT | 110 | 22.8 | 0.06 | 0 | 0 | 0 | 0 | 5 | 0 | Y/N | Planned Outage /
81 | HEN-MPE-2 | I | CCT | 110 | 23.66 | 0.02 | 0 | 0 | 0 | 0 | 6 | 0 | Y/N | Planned Outage /
82 | HEP-ROS-1 | I | CCT | 110 | 3.27 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
83 | HEP-ROS-2 | I | CCT | 110 | 6.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
84 | HOR-KBY-ISL-1 | B | CCT | 110 | 5.81 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | Y/N | Planned Outage /
85 | HOR-KBY-ISL-2 | B | CCT | 110 | 12.33 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Y/N | Planned Outage /
86 | HUI-MNI-1 | I | CCT | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
87 | HWA-SFD-1 | I | CCT | 110 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
88 | HWA-WVY-1 | I | CCT | 110 | 2.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
89 | HWB-ROX-1 | I | CCT | 110 | 4.04 | 4.3 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
90 | [13 empty] | 18-Feb-2026: HWB-CT-CT552 red phase had an oil leak and NGOC was advised on 18/2/2026 at 1755. HWB-ROX-1 RTS delayed. HWB-CT-CT552 red phase was replaced with a new CT. | Leaking current transformer was replaced after engineering advice. | SS26015
91 | HWB-ROX-2 | I | CCT | 110 | 5.06 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Y/N | Planned Outage /
92 | IGH-KIK-1 | I | CCT | 110 | 2.65 | 0.03 | 0 | 0 | 0 | 0 | 1 | 1 | Y/N | Planned Outage /
93 | IGH-KIK-2 | B | CCT | 110 | 3.14 | 0.03 | 0 | 0 | 0 | 0 | 3 | 0 | Y/N | Planned Outage /
94 | IGH-ROB-1 | B | CCT | 110 | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
95 | IGH-ROB-2 | B | CCT | 110 | 4.27 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
96 | KIK-STK-3 | I | CCT | 110 | 1.15 | 0.38 | 0 | 0 | 0 | 0 | 1 | 0 | N/Y | 13-Jul-2025: KIK-STK-3 RFS on a STPP to fell trees as there was a landslip adjacent to the circuit in span KIK-STK-B0187-0188. Risk of trees slipping into MAD of line (Bph conductor). | Outage taken to clear the trees moving towards the circuit. | SS25058
97 | [13 empty] | 23-Oct-2025: KIK-STK-3 RFS for supply restoration after ISL-KIK-1 trip and A/R, BPh-earth fault, cause strong winds, no patrol, Upper SI LOS | Post event inspections have occurred using drones and service providers to identify defects. Information has been supplied to inform an investigation to look at options to improve the performance/resilience of ISL-KIK-A and B assets to high wind events. This investigation project is being generated within the system, and will be prioritised within the work plan. | SS25104
98 | [13 empty] | 30-Apr-2026: KIK-STK-3 RFS to fell a tree growing too close to the line | KIK-STK-3 was removed from service to remove tree that was growing too close. | SS26029
99 | KIN-TRK-1 | I | CCT | 110 | 1.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
100 | KIN-TRK-2 | I | CCT | 110 | 2.01 | 0.07 | 0 | 0 | 0 | 0 | 1 | 0 | Y/Y | Planned Outage /
101 | [13 empty] | 27-Nov-2025: KIN-TRK-2 RFS to replace shot up insulators on ARI-EDG-B0092-10, caused by human error by third party, the public. | The damaged insulators on all phases were replaced. | SN25174
102 | KMO-MTM-1 | I | CCT | 110 | 0.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
103 | KMO-MTM-TGA-2 | B | CCT | 110 | 2.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
104 | KMO-TGA-1 | B | CCT | 110 | 0.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
105 | KMO-TMI-1 | I | CCT | 110 | 4.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
106 | KPO-TMU-1 | I | CCT | 110 | 8.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
107 | MDN-MPE-1 | I | CCT | 110 | 2.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
108 | MDN-MPE-2 | I | CCT | 110 | 2.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
109 | MGM-MST-1 | I | CCT | 110 | 6.76 | 0.46 | 0 | 0 | 0 | 0 | 1 | 0 | Y/Y | Planned Outage /
110 | [13 empty] | 23-Oct-2025: MGM-MST-1 trip & A/R, blue phase to earth fault, cause strong winds, later RFS as structures MGM-MST-A0010-10 and MGM-MST-A0114-10 were leaning at an acute angle to the road / ground. Pole 114 had snapped off at the base. Both hard wood poles were replaced and a guy wire was added to new pole 114 | Poles replaced and guy wire installed. | SN25153
111 | MGM-WDV-1 | I | CCT | 110 | 4.01 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
112 | MNG-OTA-1 | I | CCT | 110 | 1.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
113 | MNG-OTA-2 | I | CCT | 110 | 0.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
114 | MNG-ROS-1 | I | CCT | 110 | 0.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
115 | MNG-ROS-2 | I | CCT | 110 | 3.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
116 | MNI-MKE-SFD-1 | B | CCT | 110 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N/N | Planned Outage /
117 | MST-UHT-1 | I | CCT | 110 | 1.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
118 | MST-UHT-2 | I | CCT | 110 | 1.23 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
119 | MTR-OKN-1 | I | CCT | 110 | 0.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
120 | OAM-BPT-WTK-1 | B | CCT | 110 | 1.2 | 0 | 1 | 16.64 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
121 | OAM-STU-BPD-WTK-2 | B | CCT | 110 | 1.21 | 0.01 | 0 | 0 | 1 | 4.18 | 0 | 1 | N/Y | 04-May-2026: OAM-STU-BPD-WTK2 tripped, cause unknown - suspected to have been a bird strike. BPD T1's CB442 & BPD T2's CB482 RFS. LOS to Alpine Energy Ltd at BPD. | OAM-STU-BPD-WTK-2 was energised successfully. Bird mitigation trials underway. | SS26030
122 | OKN-NPK-ONG-1 | B | CCT | 110 | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
123 | OPK-SFD-1 | B | CCT | 110 | 3.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
124 | OTA-PEN-2 | I | CCT | 110 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
125 | OTA-ROS-1 | I | CCT | 110 | 3.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
126 | OTA-ROS-2 | I | CCT | 110 | 5.21 | 1.64 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
127 | [13 empty] | 11-Nov-2025: ROS-CB-82's blue phase pole was leaking SF6 gas from the top so OTA-ROS-2 RFS to repair ROS-CB-82. Replacement pole from BPE. To be installed on 18/11/2025. | Removed the circuit breaker pole with leaks and installed a new pole. | SN25165
128 | [13 empty] | 15-Mar-2026: OTA-ROS2 tripped for a yellow phase to earth caused by a balloon at structure PEN-ROS-A0005. | No further action. | SN26046
129 | OTA-WIR-1 | B | CCT | 110 | 2.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
130 | OTA-WIR-2 | B | CCT | 110 | 1.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
131 | RDF-TUI-1 | I | CCT | 110 | 5.72 | 0.19 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
132 | [13 empty] | 14-Sep-2025: TUI-CB-162 spring not charged alarm preventing a close, delayed RTS of RDF-TUI-1 - planned outage | Spring not charged, alarm was reset. | SN25134
133 | [13 empty] | 28-Oct-2025: RDF-TUI-1 RFS, only RDF-CB-52 manually opened, to restore supply following HRP-TAB-1 & WHI-WRK-1 tripped, LOS to Hawkes Bay, probably caused by lightning. There have been changes to RDF 110kV bus and its bays so RDF-CB-52 is now RDF-CB-CB232. | No further action. | SN25160
134 | RDF-TUI-2 | I | CCT | 110 | 6.9 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
135 | STU-TIM-1 | I | CCT | 110 | 1.79 | 0 | 0 | 0 | 1 | 3.59 | 2 | 1 | Y/Y | Planned Outage /
136 | [13 empty] | 16-Dec-2025: STU-TIM-1 trip at STU 72, no A/R, protection mal-operation at STU during ASB-TIM-TWZ-1 and 2 trippings. Total LOS to STU. | Protection design currently under review. | SS25132
137 | TKR-WIL-1 | I | CCT | 110 | 5.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
138 | TKR-WIL-2 | I | CCT | 110 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
139 | TMI-OWH-TRK-1 | B | CCT | 110 | 6.34 | 0.04 | 0 | 0 | 0 | 0 | 3 | 0 | Y/N | Planned Outage /
140 | WDV-DVK-WPW-1 | I | CCT | 110 | 2.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
141 | WDV-DVK-WPW-2 | I | CCT | 110 | 3.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
142 | WGN-WVY-1 | I | CCT | 110 | 14.13 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Y/N | Planned Outage /
143
144 | Asset | Type* | Asset Category | Sub Cat | Planned Unavailability % | Unplanned Unavailability % | Number Planned Interruptions | Planned Unserved Energy MWh | Number Unplanned Interruptions | Unplanned Unserved Energy MWh | Number of Outages <1 Min | Number of Interruptions <1 min | Measures Exceeded (plan/Unplan) ? | Incidents Affecting Performance | Steps Being Taken To Improve Performance | IDENT
145 | Index Measures for Asset Category |  | CCT | 220 | 0.88 | 0.05 | 0 | 0 | 0.13 | 9.87 | None Apply | None Apply
146 | ALB-HEN-3 | I | CCT | 220 | 4.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
147 | ALB-HPI-1 | B | CCT | 220 | 3.6 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
148 | ALB-SVL-2 | B | CCT | 220 | 4.27 | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
149 | [13 empty] | 02-Jun-2026: SVL-TF-T2 tripped via protection 2's differential residual earth fault function, protection maloperated, this incident was caused by an incorrect protection setting which will be changed during an outage to T2. There was no primary fault to T2. ALB-SVL-2 also trip for SVL-P-TF-T2 incorrect setting | Protection setting has been changed. | SN26082
150 | [13 empty] | 04-Jun-2026: SVL-TF-T2 tripped via protection 2's differential residual earth fault function, protection maloperated, this incident was caused by an incorrect protection setting which will be changed during an outage to T2. There was no primary fault to T2. ALB-SVL-2 also trip for SVL-P-TF-T2 incorrect setting | Protection setting has been changed. | SN26106
151 | ALB-WRD-4 | I | CCT | 220 | 18.04 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
152 | ASB-BRY-1 | B | CCT | 220 | 1.73 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
153 | ASB-ISL-1 | B | CCT | 220 | 3.95 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
154 | ASB-TIM-TWZ-1 | I | CCT | 220 | 1.6 | 0.05 | 0 | 0 | 0 | 0 | 3 | 0 | Y/Y | Planned Outage /
155 | [13 empty] | 23-Aug-2025: OPI-TWZ-1 section of ASB-TIM-TWZ-1 RFS to remove bird's nest from above TIM-DS-64 | Birds nest was removed from disconnector. Bird proofing was installed. | SS25067
156 | ASB-TIM-TWZ-2 | I | CCT | 220 | 1.19 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | Y/N | Planned Outage /
157 | ATI-OHK-1 | I | CCT | 220 | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
158 | ATI-TRK-1 | I | CCT | 220 | 0.07 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | N/N | Planned Outage /
159 | ATI-TRK-2 | I | CCT | 220 | 0.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
160 | ATI-WKM-1 | I | CCT | 220 | 0.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
161 | AVI-BEN-1 | I | CCT | 220 | 0.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
162 | AVI-BEN-2 | I | CCT | 220 | 2.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
163 | AVI-WTK-1 | I | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
164 | BEN-OHB-1 | B | CCT | 220 | 0.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
165 | BEN-OHC-2 | B | CCT | 220 | 2.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
166 | BEN-TWZ-1 | I | CCT | 220 | 2.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
167 | BPE-BRK-1 | I | CCT | 220 | 1.99 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
168 | BPE-BRK-2 | I | CCT | 220 | 1.57 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Y/N | Planned Outage /
169 | BPE-LTN-2 | I | CCT | 220 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
170 | BPE-LTN-WIL-1 | I | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
171 | BPE-PRM-HAY-1 | B | CCT | 220 | 3.86 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Y/N | Planned Outage /
172 | BPE-PRM-HAY-2 | B | CCT | 220 | 1.23 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
173 | BPE-TKU-1 | B | CCT | 220 | 1.85 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Y/N | Planned Outage /
174 | BPE-TKU-2 | B | CCT | 220 | 28.39 | 0.02 | 0 | 0 | 0 | 0 | 4 | 0 | Y/N | Planned Outage /
175 | BPE-TNG-1 | B | CCT | 220 | 2.25 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Y/N | Planned Outage /
176 | BPE-TWC-LTN-1 | B | CCT | 220 | 0.66 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N/N | Planned Outage /
177 | BPE-WIL-1 | I | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
178 | BRB-HPI-1 | B | CCT | 220 | 9.96 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
179 | BRB-MDN-1 | B | CCT | 220 | 1.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
180 | BRK-OHG-1 | I | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
181 | BRK-SFD-1 | I | CCT | 220 | 5.18 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Y/N | Planned Outage /
182 | BRK-SFD-2 | I | CCT | 220 | 4.27 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
183 | BRK-SFD-3 | I | CCT | 220 | 9.53 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Y/N | Planned Outage /
184 | BRY-ISL-1 | B | CCT | 220 | 3.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
185 | CYD-CML-TWZ-1 | I | CCT | 220 | 0.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
186 | CYD-CML-TWZ-2 | I | CCT | 220 | 1.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
187 | CYD-ROX-1 | I | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
188 | CYD-ROX-2 | I | CCT | 220 | 0.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
189 | DRY-BOB-HLY-1 | B | CCT | 220 | 1.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
190 | DRY-BOB-HLY-2 | B | CCT | 220 | 1.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
191 | DRY-OTA-1 | B | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
192 | DRY-TAK-OTA-1 | B | CCT | 220 | 11.86 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
193 | DRY-TAK-OTA-2 | B | CCT | 220 | 9.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
194 | EDG-KAW-3 | I | CCT | 220 | 2.41 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | Y/N | Planned Outage /
195 | EDG-TRK-1 | I | CCT | 220 | 5.35 | 0 | 0 | 0 | 0 | 0 | 2 | 10 | Y/N | Planned Outage /
196 | EDG-TRK-2 | I | CCT | 220 | 6.06 | 0 | 0 | 0 | 0 | 0 | 5 | 10 | Y/N | Planned Outage /
197 | HAM-OHW-1 | I | CCT | 220 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
198 | HAM-WKM-1 | I | CCT | 220 | 4.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
199 | HAY-WIL-LTN-1 | I | CCT | 220 | 9.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
200 | HAY-WIL-LTN-2 | I | CCT | 220 | 11.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
201 | HEN-HPI-1 | I | CCT | 220 | 5.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
202 | HEN-OTA-1 | I | CCT | 220 | 3.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
203 | HEN-SWN-1 | I | CCT | 220 | 3.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
204 | HLY-OHW-1 | I | CCT | 220 | 0.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
205 | HLY-OHW-2 | I | CCT | 220 | 1.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
206 | HLY-OTA-2 | B | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
207 | HLY-SFD-1 | I | CCT | 220 | 5.78 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Y/N | Planned Outage /
208 | HLY-TWH-1 | B | CCT | 220 | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
209 | HOB-PEN-1 | I | CCT | 220 | 1.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
210 | HOB-WRD-1 | I | CCT | 220 | 2.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
211 | HPI-MDN-1 | I | CCT | 220 | 5.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
212 | HRP-RDF-1 | I | CCT | 220 | 0.78 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
213 | HRP-TAB-1 | I | CCT | 220 | 1.55 | 0.01 | 0 | 0 | 5 | 209.34 | 0 | 0 | Y/Y | Planned Outage /
214 | [13 empty] | 28-Oct-2025: HRP-TAB-1 & WHI-WRK-1 tripped, LOS to Hawkes Bay. Probable cause lightning, LOS at WTU to UNN. | No further action. | SN25160
215 | HWB-SDN-1 | B | CCT | 220 | 2.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
216 | HWB-TMH-1 | B | CCT | 220 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
217 | INV-MAN-2 | B | CCT | 220 | 3.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
218 | INV-NMA-1 | B | CCT | 220 | 1.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
219 | INV-ROX-1 | I | CCT | 220 | 3.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
220 | INV-ROX-2 | I | CCT | 220 | 5.03 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Y/N | Planned Outage /
221 | INV-TWI-1 | I | CCT | 220 | 5.54 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
222 | INV-TWI-2 | I | CCT | 220 | 4.9 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
223 | ISL-KIK-1 | I | CCT | 220 | 5.29 | 0.03 | 0 | 0 | 9 | 339.49 | 1 | 0 | Y/Y | Planned Outage /
224 | [13 empty] | 23-Oct-2025: ISL-KIK-1 trip and A/R, BPh-earth fault, cause strong winds, no patrol. Upper SI LOS, LOS to STK 66kV to Network Tasman. | Post event inspections have occurred using drones and service providers to identify defects. Information has been supplied to inform an investigation to look at options to improve the performance/resilience of ISL-KIK-A and B assets to high wind events. This investigation project is being generated within the system, and will be prioritised within the work plan. | SS25104
225 | [13 empty] | 09-Oct-2025: ISL-KIK-1 RFS as tower climber reported at twr 88. The maintenance contractor confirmed at tower 88 that there was no tower climber and no damage to Transpower equipment. The maintenance contractor also inspected both sides of tower 88 and found nothing. | No further action. | SS25087
226 | ISL-LIV-1 | I | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
227 | ISL-NWD-1 | I | CCT | 220 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
228 | ISL-TKB-1 | B | CCT | 220 | 1.9 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Y/N | Planned Outage /
229 | ISL-WPR-CUL-KIK-2 | B | CCT | 220 | 2.09 | 0.07 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
230 | [13 empty] | 21-Oct-2025: ISL-WPR-CUL-KIK-2 tripped for a BPh to earth fault, strong winds. No patrol was carried out before cct RTS | Post event inspections have occurred using drones and service providers to identify defects. Information has been supplied to inform an investigation to look at options to improve the performance/resilience of ISL-KIK-A and B assets to high wind events. This investigation project is being generated within the system, and will be prioritised within the work plan. | SS25095
231 | [13 empty] | 23-Oct-2025: ISL-WPR-CUL-KIK-2 tripped for a BPh to earth fault, strong winds. Patrol found no cause. | Post event inspections have occurred using drones and service providers to identify defects. Information has been supplied to inform an investigation to look at options to improve the performance/resilience of ISL-KIK-A and B assets to high wind events. This investigation project is being generated within the system, and will be prioritised within the work plan. | SS25096
232 | [13 empty] | 23-Oct-2025: ISL-WPR-CUL-KIK-2 tripped for a BPh to earth fault, strong winds. Patrol found no cause. | Post event inspections have occurred using drones and service providers to identify defects. Information has been supplied to inform an investigation to look at options to improve the performance/resilience of ISL-KIK-A and B assets to high wind events. This investigation project is being generated within the system, and will be prioritised within the work plan. | SS25097
233 | [13 empty] | 27-Oct-2025: ISL-WPR-CUL-KIK-2 tripped for a RPh to earth fault, strong winds. no patrol | Circuit was returned to service. Post event inspections have occurred using drones and service providers to identify defects. Information has been supplied to inform an investigation to look at options to improve the performance/resilience of ISL-KIK-A and B assets to high wind events. This investigation project is being generated within the system, and will be prioritised within the work plan. | SS25107
234 | ISL-WPR-CUL-KIK-3 | B | CCT | 220 | 5.65 | 0.02 | 0 | 0 | 3 | 8.25 | 0 | 0 | Y/Y | Planned Outage /
235 | [13 empty] | 23-Oct-2025: ISL-WPR-CUL-KIK-3 tripped, R-E fault, cause strong winds, no patrol. LOS at CUL. Load backfed via WPR. | Post event inspections have occurred using drones and service providers to identify defects. Information has been supplied to inform an investigation to look at options to improve the performance/resilience of ISL-KIK-A and B assets to high wind events. This investigation project is being generated within the system, and will be prioritised within the work plan. | SS25102
236 | [13 empty] | 31-Aug-2025: ISL-WPR-CUL-KIK-3 tripped, R-E fault, cause unknown , no patrol | Investigation on KIK-CB-322 is ongoing, root cause has not been established. No further action. | SS25072
237 | [13 empty] | 23-Oct-2025: ISL-WPR-CUL-KIK-3 tripped, R-E fault, cause strong winds, no patrol | Post event inspections have occurred using drones and service providers to identify defects. Information has been supplied to inform an investigation to look at options to improve the performance/resilience of ISL-KIK-A and B assets to high wind events. This investigation project is being generated within the system, and will be prioritised within the work plan. | SS25099
238 | [13 empty] | 23-Oct-2025: ISL-WPR-CUL-KIK-3 tripped, R-E fault, cause strong winds, no patrol. LOS CUL, ISL-WPR-CUL-KIK-2 O/S until 0957. | Post event inspections have occurred using drones and service providers to identify defects. Information has been supplied to inform an investigation to look at options to improve the performance/resilience of ISL-KIK-A and B assets to high wind events. This investigation project is being generated within the system, and will be prioritised within the work plan. | SS25105
239 | [13 empty] | 20-Dec-2025: ISL-WPR-CUL-KIK-3 tripped, R-E fault, probable cause lightning, no patrol. SDTF recorded two lightning strikes at 1921:29 close to span 5 to 6 on ISL-KIK-B line. | No further action. | SS25135
240 | KAW-OHK-1 | I | CCT | 220 | 3.39 | 0.03 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
241 | KIK-STK-1 | I | CCT | 220 | 3.73 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
242 | KIK-STK-2 | I | CCT | 220 | 1.57 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
243 | KIW-GOR-NMA-1 | B | CCT | 220 | 506.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
244 | KIW-TMH-1 | B | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
245 | KMO-TRK-1 | I | CCT | 220 | 0.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N/N | Planned Outage /
246 | KMO-TRK-2 | I | CCT | 220 | 0.76 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | N/N | Planned Outage /
247 | LIV-NSY-1 | I | CCT | 220 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
248 | LIV-NWD-1 | I | CCT | 220 | 0 | 1.32 | 0 | 0 | 0 | 0 | 11 | 0 | N/Y | 07-Jul-2025: LIV-NWD-1 tripped, A/R at LIV CB42 only, NWD CB232 remained open, blue phase to earth fault, cause unknown, no patrol. | No further action. | SS25055
249 | LIV-WTK-1 | I | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
250 | MAN-NMA-1 | B | CCT | 220 | 2.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
251 | MAN-NMA-2 | B | CCT | 220 | 0.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
252 | MAN-NMA-3 | B | CCT | 220 | 3.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
253 | NMA-GOR-TMH-1 | I | CCT | 220 | 5.45 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
254 | NMA-GOR-TMH-2 | I | CCT | 220 | 1.44 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
255 | NMA-TWI-1 | B | CCT | 220 | 2.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
256 | NMA-TWI-2 | B | CCT | 220 | 2.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
257 | NPL-SFD-1 | I | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
258 | NPL-SFD-2 | I | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
259 | NSY-ROX-1 | I | CCT | 220 | 0.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
260 | OHB-TWZ-3 | B | CCT | 220 | 0.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
261 | OHC-TWZ-4 | B | CCT | 220 | 0.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
262 | OHG-SFD-1 | I | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
263 | OHK-WRK-1 | I | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | N/N
264 | OHW-OTA-1 | I | CCT | 220 | 5.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
265 | OHW-OTA-2 | I | CCT | 220 | 5.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
266 | OHW-WKM-1 | I | CCT | 220 | 5.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
267 | OTA-HTU-WKM-1 | I | CCT | 220 | 2.53 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
268 | OTA-HTU-WKM-2 | I | CCT | 220 | 4.4 | 0.01 | 0 | 0 | 1 | 2.69 | 3 | 0 | Y/Y | Planned Outage /
269 | [13 empty] | 22-Nov-2025: OTA-HTU-WKM-2 tripped for a yellow phase to earth fault, cause unknown. HTU-TF-T2 tripped for circuit fault. A patrol of the circuit on 23/11/2025 found no fault. | No further action. Improvements underway for Spatial Distance To Fault information with Real Time Systems team. | SN25173
270 | OTA-PAK-3 | I | CCT | 220 | 2.6 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
271 | OTA-PAK-4 | I | CCT | 220 | 2.68 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
272 | OTA-PEN-5 | I | CCT | 220 | 4.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
273 | OTA-PEN-6 | I | CCT | 220 | 2.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
274 | OTA-SWN-1 | I | CCT | 220 | 1.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
275 | OTA-WKM-1 | I | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
276 | OTA-WKM-2 | I | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
277 | PAK-PEN-3 | I | CCT | 220 | 1.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
278 | PAK-WKM-1 | I | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
279 | PAK-WKM-2 | I | CCT | 220 | 93.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
280 | RDF-WHI-1 | I | CCT | 220 | 1.13 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
281 | RDF-WRK-1 | I | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
282 | ROX-TMH-1 | I | CCT | 220 | 0.67 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | N/N | Planned Outage /
283 | ROX-TMH-2 | I | CCT | 220 | 1.06 | 0.06 | 0 | 0 | 0 | 0 | 5 | 0 | Y/Y | Planned Outage /
284 | [13 empty] | 01-Oct-2025: ROX-TMH-2 tripped, A/R twice and tripped for a R-Y phase fault, clashing, cause strong winds | No further action. | SS25085
285 | RPO-TNG-1 | B | CCT | 220 | 1.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
286 | RPO-WRK-1 | B | CCT | 220 | 1.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
287 | SDN-TMH-1 | B | CCT | 220 | 2.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
288 | SFD-TMN-1 | I | CCT | 220 | 1.2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
289 | TAB-WRK-1 | I | CCT | 220 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
290 | THI-WKM-1 | B | CCT | 220 | 0.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
291 | THI-WRK-1 | B | CCT | 220 | 0.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
292 | TKB-TWZ-1 | B | CCT | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
293 | TKU-WKM-1 | B | CCT | 220 | 1.76 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
294 | TKU-WKM-2 | B | CCT | 220 | 35.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
295 | TMN-TWH-1 | B | CCT | 220 | 1.18 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
296 | WHI-WRK-1 | I | CCT | 220 | 1.87 | 0.02 | 0 | 0 | 5 | 209.34 | 1 | 0 | Y/Y | Planned Outage /
297 | [13 empty] | 28-Oct-2025: HRP-TAB-1 & WHI-WRK-1 tripped, LOS to Hawkes Bay. Probable cause lightning, LOS at WTU to UNN. | No further action. | SN25160
298 | WKM-WRK-1 | I | CCT | 220 | 1.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
299
300 | Asset | Type* | Asset Category | Sub Cat | Planned Unavailability % | Unplanned Unavailability % | Number Planned Interruptions | Planned Unserved Energy MWh | Number Unplanned Interruptions | Unplanned Unserved Energy MWh | Number of Outages <1 Min | Number of Interruptions <1 min | Measures Exceeded (plan/Unplan) ? | Incidents Affecting Performance | Steps Being Taken To Improve Performance | IDENT
301 | Index Measures for Asset Category |  | CCT | 66 | 1.25 | 0.08 | 0.14 | 0.46 | 1.31 | 1.88 | None Apply | None Apply
302 | ASY-SBK-1 | B | CCT | 66 | 2.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
303 | ASY-WPR-1 | B | CCT | 66 | 0.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
304 | COL-HOR-2 | I | CCT | 66 | 1.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
305 | COL-HOR-3 | I | CCT | 66 | 2.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
306 | COL-OTI-1 | I | CCT | 66 | 9.33 | 0.06 | 0 | 0 | 2 | 0.12 | 11 | 20 | Y/Y | Planned Outage /
307 | [13 empty] | 27-Nov-2025: COL-OTI-1 tripped, A/R, tripped, strong winds, Yph to Bph fault cause environmental - gale force winds. Patrol of the circuit found no fault. LOS to Orion at APS and at CLH. | Currently investigating improvement options. | SS25118
308 | [13 empty] | 24-Jun-2026: COL-OTI-1 trip & A/R, Yph-E fault, cause unknown. Momentary LOS at CLH and APS. No cct patrol. | No further action. | SS26040
309 | COL-OTI-2 | I | CCT | 66 | 7.88 | 0.03 | 0 | 0 | 0 | 0 | 9 | 0 | Y/N | Planned Outage /
310 | DOB-GYM-1 | I | CCT | 66 | 2.62 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
311 | GYM-KUM-1 | I | CCT | 66 | 4 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
312 | HKK-KUM-1 | B | CCT | 66 | 1.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
313 | HKK-OTI-2 | B | CCT | 66 | 9.2 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
314 | ISL-SBK-1 | I | CCT | 66 | 10.3 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Y/N | Planned Outage /
315 | ISL-SBK-2 | I | CCT | 66 | 8.11 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
316 | KUM-OTI-1 | B | CCT | 66 | 6.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
317 | SBK-WPR-1 | I | CCT | 66 | 1.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
318
319 | Asset | Type* | Asset Category | Sub Cat | Planned Unavailability % | Unplanned Unavailability % | Number Planned Interruptions | Planned Unserved Energy MWh | Number Unplanned Interruptions | Unplanned Unserved Energy MWh | Number of Outages <1 Min | Number of Interruptions <1 min | Measures Exceeded (plan/Unplan) ? | Incidents Affecting Performance | Steps Being Taken To Improve Performance | IDENT
320 | Index Measures for Asset Category |  | Shunt | CAP_HV | 0.81 | 1.33 | 0 | 0 | 0.02 | 0.03 | None Apply | None Apply
321 | ALB-CAPS-C1 | I | Shunt | CAP_HV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
322 | ALB-CAPS-C2 | I | Shunt | CAP_HV | 0.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
323 | HAM-CAPS-C1 | I | Shunt | CAP_HV | 3.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
324 | HAM-CAPS-C2 | I | Shunt | CAP_HV | 1.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
325 | HEN-CAPS-C1 | I | Shunt | CAP_HV | 2.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
326 | HEP-CAPS-C11 | I | Shunt | CAP_HV | 0.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
327 | HEP-CAPS-C12 | I | Shunt | CAP_HV | 0.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
328 | HEP-CAPS-C13 | I | Shunt | CAP_HV | 0.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
329 | ISL-CAPS-C14 | I | Shunt | CAP_HV | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
330 | ISL-CAPS-C15 | I | Shunt | CAP_HV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
331 | ISL-CAPS-C16 | I | Shunt | CAP_HV | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | N/Y | 01-Jul-2025: ISL-CAPS-C16 unavailable for service, blown fuses, broken insulators, cause unknown, still investigated, accidentally found. C16 was already out of service prior to incident. Nilay Chauhan RTS ISL-CAPS-C16 in 2027. | The service kits for the ISL-CAPS-C16 circuit breaker are being verified for completeness and suitability. After the circuit breaker issue is resolved, new insulators will be installed and tested on C16. | SS25042
332 | ISL-CAPS-C21 | I | Shunt | CAP_HV | 2.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
333 | ISL-CAPS-C22 | I | Shunt | CAP_HV | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
334 | ISL-CAPS-C25 | I | Shunt | CAP_HV | 2.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
335 | ISL-CAPS-C26 | I | Shunt | CAP_HV | 3.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
336 | ISL-CAPS-C27 | I | Shunt | CAP_HV | 0.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
337 | MTM-CAPS-C1 | I | Shunt | CAP_HV | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
338 | NMA-CAPS-C1 | I | Shunt | CAP_HV | 5.05 | 3.96 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
339 | [13 empty] | 06-Nov-2025: NMA-CAPS-C1 RFS to replace blown capacitor cans (x2). Can 55 and can 59 on yellow phase were replaced | Blown capacitor cans were replaced. | SS25113
340 | NMA-CAPS-C3 | I | Shunt | CAP_HV | 5.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
341 | OHW-CAPS-C1 | I | Shunt | CAP_HV | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
342 | OHW-CAPS-C2 | I | Shunt | CAP_HV | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
343 | OTA-CAPS-C11 | I | Shunt | CAP_HV | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
344 | OTA-CAPS-C12 | I | Shunt | CAP_HV | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
345 | OTA-CAPS-C29 | I | Shunt | CAP_HV | 4.33 | 11.75 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
346 | [13 empty] | 17-Nov-2025: OTA-CAPS-C29 and OTA-REA-29, unavailable for service, conductor hanging from insulator | The hanging conductor was removed. Hot spot on R29 was repaired and serviced. Testing done before C29 was returned to service. | SN25170
347 | [13 empty] | 19-Jan-2026: OTA-CAPS-C29 and OTA-REA-29 tripped via C29's Dif Earth fault after RPC close, caused by equipment failure. Four faulty capacitor cans and Bph reactor replaced per Ben Thornton | Faulty capacitor cans and faulty reactors were replaced. | SN26017
348 | OTA-CAPS-C30 | I | Shunt | CAP_HV | 2.4 | 17.35 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
349 | [13 empty] | 12-Feb-2026: OTA-CAPS-C30 tripped when OTA-CB-1422 tripped on close. CB1422 failed to latch closed and this was caused by worn anvils in its closing mechanism. | Spring tension was re-tuned and circuit breaker returned to service. This issue was traced to a specific model where the manufacturer provided incorrect spring tensions. A service instruction has been published to undertake further testing and detuning as necessary. Additional spares have been procured. | SN26025
350 | OTA-CAPS-C31 | I | Shunt | CAP_HV | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
351 | PEN-CAPS-C1 | I | Shunt | CAP_HV | 2.91 | 39.3 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
352 | [13 empty] | 06-Aug-2025: PEN-CAP-C1 tripped via neutral unbalance protection, caused by equipment failure. Five internal fuses blown on Y2. Three capacitor cans and HV terminations replaced. | 3 capacitors replaced as well as high voltage terminations. Relay was modified. | SN25108
353 | [13 empty] | 11-Nov-2025: PEN-CAP-C1 tripped via neutral unbalance protection due to five faulty capacitor cans. Five cans were replaced | Tested all capacitor cans. The leaky and failed cans were replaced. | SN25166
354 | [13 empty] | 11-Dec-2025: PEN-CAPS-C1 tripped via neutral unbalance, caused by equipment failure. Four faulty capacitor cans were replaced, and two capacitor cans were swapped. | Faulty capacitor cans replaced. | SN25196
355 | [13 empty] | 25-Mar-2026: PEN-CAPS-C1 tripped via neutral unbalance, caused by equipment failure. 5 faulty capacitor cans were replaced. No capacitor cans were swapped. | Faulty capacity cans were replaced. | SN26047
356 | PEN-CAPS-C11 | I | Shunt | CAP_HV | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
357 | PEN-CAPS-C12 | I | Shunt | CAP_HV | 0.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
358 | PEN-CAPS-C13 | I | Shunt | CAP_HV | 0.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
359 | PEN-CAPS-C14 | I | Shunt | CAP_HV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
360 | SBK-CAPS-C11 | I | Shunt | CAP_HV | 0.82 | 0.87 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
361 | TGA-CAPS-C11 | I | Shunt | CAP_HV | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
362 | TMU-CAPS-C1 | I | Shunt | CAP_HV | 0 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
363 | TMU-CAPS-C2 | I | Shunt | CAP_HV | 0 | 1.06 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
364
365 | Asset | Type* | Asset Category | Sub Cat | Planned Unavailability % | Unplanned Unavailability % | Number Planned Interruptions | Planned Unserved Energy MWh | Number Unplanned Interruptions | Unplanned Unserved Energy MWh | Number of Outages <1 Min | Number of Interruptions <1 min | Measures Exceeded (plan/Unplan) ? | Incidents Affecting Performance | Steps Being Taken To Improve Performance | IDENT
366 | Index Measures for Asset Category |  | Shunt | CAP_LV | 0.81 | 1.33 | 0 | 0 | 0.02 | 0.03 | None Apply | None Apply
367 | BAL-CAPS-C1 | I | Shunt | CAP_LV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
368 | BAL-CAPS-C2 | I | Shunt | CAP_LV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
369 | BLN-CAPS-C1 | I | Shunt | CAP_LV | 0.24 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
370 | BLN-CAPS-C2 | I | Shunt | CAP_LV | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
371 | BLN-CAPS-C3 | I | Shunt | CAP_LV | 0.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
372 | BLN-CAPS-C4 | I | Shunt | CAP_LV | 0.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
373 | BRY-CAPS-C5A | I | Shunt | CAP_LV | 1.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
374 | BRY-CAPS-C7A | I | Shunt | CAP_LV | 1.71 | 2.78 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
375 | [13 empty] | 05-Aug-2025: BRY-DS-2004 hot spots on all phases as identified by Thermovision checks so forced outage to BRY-CAPS-C7A. Contacts were serviced. | Contacts pressure and alignment were checked. Contacts were serviced and all phases retested. | SS25061
376 | [13 empty] | 07-Mar-2026: BRY-TF-T7 trip via REF, BRY-CAPS-C7A, BRY-REA-C7A also trip, caused by a second earth point on the secondary wiring of T7's Neutral Current Transformer. | Additional earthing point removed. | SS26018
377 | GYM-CAPS-C1 | I | Shunt | CAP_LV | 0.33 | 1.34 | 0 | 0 | 0 | 0 | 0 | 0 | N/Y | 25-Oct-2025: GYM-CAPs C1,C2,C3 RFS, faulty load break switch LB1 and LB2 | The contacts had welded together. These have been forced open and inspected to ensure they were not damaged. LB1 and LB2 were tested before returning to service. | SS25106
378 | GYM-CAPS-C2 | I | Shunt | CAP_LV | 0.89 | 1.34 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
379 | [13 empty] | 25-Oct-2025: GYM-CAPs C1,C2,C3 RFS, faulty load break switch LB1 and LB2 | The contacts had welded together. These have been forced open and inspected to ensure they were not damaged. LB1 and LB2 were tested before returning to service. | SS25106
380 | GYM-CAPS-C3 | I | Shunt | CAP_LV | 0.89 | 1.34 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
381 | [13 empty] | 25-Oct-2025: GYM-CAPs C1,C2,C3 RFS, faulty load break switch LB1 and LB2 | The contacts had welded together. These have been forced open and inspected to ensure they were not damaged. LB1 and LB2 were tested before returning to service. | SS25106
382 | HKK-CAPS-C7 | I | Shunt | CAP_LV | 0.23 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
383 | HKK-CAPS-C8 | I | Shunt | CAP_LV | 0.23 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
384 | HKK-CAPS-C9 | I | Shunt | CAP_LV | 0.23 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
385 | KTA-CAPS-C1 | I | Shunt | CAP_LV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
386 | KTA-CAPS-C11 | I | Shunt | CAP_LV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
387 | KTA-CAPS-C21 | I | Shunt | CAP_LV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
388 | KTA-CAPS-C31 | I | Shunt | CAP_LV | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
389 | ONG-CAPS-C1 | I | Shunt | CAP_LV | 1.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
390 | STK-CAPS-C31 | I | Shunt | CAP_LV | 0.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
391 | STK-CAPS-C32 | I | Shunt | CAP_LV | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
392 | STK-CAPS-C33 | I | Shunt | CAP_LV | 1.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
393 | STK-CAPS-C34 | I | Shunt | CAP_LV | 3.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
394
395 | Asset | Type* | Asset Category | Sub Cat | Planned Unavailability % | Unplanned Unavailability % | Number Planned Interruptions | Planned Unserved Energy MWh | Number Unplanned Interruptions | Unplanned Unserved Energy MWh | Number of Outages <1 Min | Number of Interruptions <1 min | Measures Exceeded (plan/Unplan) ? | Incidents Affecting Performance | Steps Being Taken To Improve Performance | IDENT
396 | Index Measures for Asset Category |  | Shunt | Filter | 1.03 | 1.71 | 0 | 0 | 0 | 0 | None Apply | None Apply
397 | S1.20DB72-FB5 | I | Shunt | Filter | 8.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
398 | S1.20DB74-FB6 | I | Shunt | Filter | 8.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
399 | S1.20DB80-FB7 | I | Shunt | Filter | 8.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
400 | S1.WA-Z1.FB4 | I | Shunt | Filter | 3.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
401 | S1.WA-Z2.FB3 | I | Shunt | Filter | 3.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
402 | S4.10DC96-FB6 | I | Shunt | Filter | 9.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
403 | S4.10DC98-FB5 | I | Shunt | Filter | 5.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
404 | S4.10DC98.A-FB5A | I | Shunt | Filter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
405 | S4.10DC98.A-FB5B | I | Shunt | Filter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
406 | S4.10E04-FB7 | I | Shunt | Filter | 0 | 7.9 | 0 | 0 | 0 | 0 | 0 | 0 | N/Y | 09-Oct-2025: HAY-FB-7 tripped faulty control card | Faulty control card was replaced. | SN25144
407 | S4.10E22-FB8 | I | Shunt | Filter | 0.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
408 | S4.WA-Z1.FB4 | I | Shunt | Filter | 4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
409 | S4.WA-Z1.Z1.FB4A | I | Shunt | Filter | 0.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
410 | S4.WA-Z1.Z2.FB4B | I | Shunt | Filter | 0 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
411 | S4.WA-Z2.FB3 | I | Shunt | Filter | 4.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
412 | S4.WA-Z2.Z1.FB3A | I | Shunt | Filter | 0 | 0.03 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
413 | S4.WA-Z2.Z2.FB3B | I | Shunt | Filter | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
414
415 | Asset | Type* | Asset Category | Sub Cat | Planned Unavailability % | Unplanned Unavailability % | Number Planned Interruptions | Planned Unserved Energy MWh | Number Unplanned Interruptions | Unplanned Unserved Energy MWh | Number of Outages <1 Min | Number of Interruptions <1 min | Measures Exceeded (plan/Unplan) ? | Incidents Affecting Performance | Steps Being Taken To Improve Performance | IDENT
416 | Index Measures for Asset Category |  | Shunt | REA | 1.33 | 0.31 | 0 | 0 | 0 | 0 | None Apply | None Apply
417 | HAY-REA-R1 | I | Shunt | REA | 0.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
418 | ISL-REA-R492 | I | Shunt | REA | 1.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
419 | KIK-REA-R182 | I | Shunt | REA | 0.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
420 | OTA-REA-R472 | I | Shunt | REA | 2.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
421 | PAK-REA-R562 | I | Shunt | REA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
422 | PAK-REA-R582 | I | Shunt | REA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
423 | PEN-REA-862 | I | Shunt | REA | 1.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
424 | WRD-REA-R182 | I | Shunt | REA | 2.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
425
426 | Asset | Type* | Asset Category | Sub Cat | Planned Unavailability % | Unplanned Unavailability % | Number Planned Interruptions | Planned Unserved Energy MWh | Number Unplanned Interruptions | Unplanned Unserved Energy MWh | Number of Outages <1 Min | Number of Interruptions <1 min | Measures Exceeded (plan/Unplan) ? | Incidents Affecting Performance | Steps Being Taken To Improve Performance | IDENT
427 | Index Measures for Asset Category |  | Shunt | SCM | 2 | 1 | 0 | 0 | 0 | 0 | None Apply | None Apply
428 | HAY-SC1 | I | Shunt | SCM | 5.97 | 0.44 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
429 | HAY-SC10 | I | Shunt | SCM | 1.21 | 3.93 | 0 | 0 | 0 | 0 | 0 | 0 | N/Y | 02-Dec-2025: HAY-SC10 & HAY-TF-T10 RFS to investigate rotor earth fault. Rotor earth leakage brush on the exciter end was sticky and was replaced. Pony motor brushes were worn and were replaced | Found the issue to with shaft earthing. Wiring has been corrected to resolve the issue. | SN25194
430 | HAY-SC2 | I | Shunt | SCM | 9.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
431 | HAY-SC3 | I | Shunt | SCM | 90.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
432 | HAY-SC4 | I | Shunt | SCM | 89.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
433 | HAY-SC7 | I | Shunt | SCM | 1.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
434 | HAY-SC8 | I | Shunt | SCM | 5.03 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
435 | HAY-SC9 | I | Shunt | SCM | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | N/Y | 01-Jul-2025: HAY-SC9 & T9 RFS as SC9 was making an abnormal noise. | The planned refurbishment of the machine was brought forward and condenser disassembled. This work is in progress. | SN25077
436
437 | Asset | Type* | Asset Category | Sub Cat | Planned Unavailability % | Unplanned Unavailability % | Number Planned Interruptions | Planned Unserved Energy MWh | Number Unplanned Interruptions | Unplanned Unserved Energy MWh | Number of Outages <1 Min | Number of Interruptions <1 min | Measures Exceeded (plan/Unplan) ? | Incidents Affecting Performance | Steps Being Taken To Improve Performance | IDENT
438 | Index Measures for Asset Category |  | Shunt | SVC | 0.82 | 0.04 | 0 | 0 | 0 | 0 | None Apply | None Apply
439 | ALB-SVC-7 | I | Shunt | SVC | 0.71 | 1.97 | 0 | 0 | 0 | 0 | 0 | 0 | N/Y | 18-Oct-2025: ALB-SVC-7 tripped when CB822 was closed due to two blown thyristors. The thyristors were replaced | ALB-TF-T8 was returned to service restoring supply to ALB-SVC-7 via LS8. Maintenance in October will inspect UPS and review alarm logs to help confirm UPS is not cause of trippings. | SN25147
440 | [13 empty] | 11-Feb-2026: ALB-SVC-7 tripped, no cause found possibly UPS problem | LVAC stability problem under investigation. | SN26024
441 | HAM-STC-3 | I | Shunt | SVC | 3.52 | 0.11 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
442 | [13 empty] | 02-Mar-2026: HAM-STC-3 & HAM-TF-T3 tripped cause unknown. "VCU Cell condition fault, yellow phase, trip". Alarms reset and STC3 RTS. | Fibre patch leads and SPF modules changed. Fault corrected following reboot | SN26044
443 | [13 empty] | 15-Jun-2026: HAM-STC-3 & HAM-TF-T3 RFS to repair a water leak on STC3's Denim cooling system, caused by equipment failure. | New bottles were supplied by manufacturer as replacement for defective resin bottles. | SN26087
444 | [13 empty] | 30-Jun-2026: HAM-STC-3 failed to start, unavailable for service, due to valve control unit offline and not alarming. HAM-TF-T3 was also RFS for this fault. A remote reset of valve control unit resolved this fault so that HAM-STC-3 could be restarted. | A remote reset of valve control unit resolved this fault. Manufacturer provided updates for Human Machine Interface/ control system. | SN26096
445 | ISL-SVC-3 | I | Shunt | SVC | 1.94 | 0.09 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
446 | [13 empty] | 16-Aug-2025: ISL-SVC-3 RFS due to thyristor valve problems. Hitachi technician changed out the light guide to the thyristor middle stack 4th from the bottom left-hand side as you stand looking at it | Technician changed out the light guide to thyristor middle stack. | SS25064
447 | ISL-SVC-9 | I | Shunt | SVC | 0.59 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
448 | KIK-STC-2 | I | Shunt | SVC | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
449 | MDN-STC-5 | I | Shunt | SVC | 1.98 | 0.21 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
450 | [13 empty] | 04-Feb-2026: MDN-CB-2702 failed to close on RTS of STC-5, Interlock not properly lined up, delayed RTS of STC-5 and LS5B | Programme for servicing indoor switchgear has been put together. This is planned to be implemented in the next 9 months. | SN26021
451 | MDN-STC-6 | I | Shunt | SVC | 3.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
452 | OTA-STC-15 | I | Shunt | SVC | 0.34 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | N/Y | 22-Jul-2025: OTA-STC-15 and OTA-TF-T15 tripped when contractor employed by Transpower tested fire alarm. 5 WHYS has been requested by Tim Williams | Fire panel witing improvements done. Future subcontractors to be used need to be suitably competent. | SN25098
453 | [13 empty] | 09-Sep-2025: OTA-STC-15 and OTA-TF-T15 tripped during fire alarm testing | Wiring improvements done at OTA. Subcontractors pre-qualification in placed for those working on Transpower fire alam systems. Additional site specific training being provided to specific fire technicians working on fire alarm systems at OTA and HAM. | SN25129
454 | PEN-STC-1 | I | Shunt | SVC | 4.18 | 0.33 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
455 | [13 empty] | 16-Aug-2025: PEN-STC-1A and 1B tripped due to overvoltage trips for feeder fault on CB2342 | Lockout relays were reset. | SN25114
456 | [13 empty] | 10-Dec-2025: PEN-STC-1A and 1B tripped due to human error an incorrect cable was cut | The cut cores were jointed and finished with an external PVC insulating cover to prevent moisture ingress. | SN25192
457 | S4.10DB66-STC31 | I | Shunt | SVC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
458 | S4.10J01-STC31 | I | Shunt | SVC | 0.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
459
460 | Asset | Type* | Asset Category | Sub Cat | Planned Unavailability % | Unplanned Unavailability % | Number Planned Interruptions | Planned Unserved Energy MWh | Number Unplanned Interruptions | Unplanned Unserved Energy MWh | Number of Outages <1 Min | Number of Interruptions <1 min | Measures Exceeded (plan/Unplan) ? | Incidents Affecting Performance | Steps Being Taken To Improve Performance | IDENT
461 | Index Measures for Asset Category |  | TF | 110/066 | 2.25 | 0.02 | 0 | 0 | 0 | 0 | None Apply | None Apply
462 | DOB-TF-T11 | I | TF | 110/066 | 2.27 | 2.99 | 0 | 0 | 0 | 0 | 4 | 0 | Y/Y | Planned Outage /
463 | [13 empty] | 21-Oct-2025: DOB-RFN-IGH-2 and DOB-TF-T11 tripped, A/R, tripped cause heavy rain and strong winds, LOS at RFN, broken conductors span 67 - 68 and 68 - 69, broken insulators str 65,66,67, 68 | Pole 68 was removed and pole 67 was replaced with a taller pole. With the pole removed the conductor now totally spans the river. | SS25092
464 | [13 empty] | 17-Nov-2025: DOB-RFN-IGH-2 RFS for conductor repair work, DOB T11 RFS, LOS at RFN. Conductor has separated from insulator string. | Replaced broken insulators. | SS25112
465 | DOB-TF-T12 | I | TF | 110/066 | 5.53 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Y/N | Planned Outage /
466
467 | Asset | Type* | Asset Category | Sub Cat | Planned Unavailability % | Unplanned Unavailability % | Number Planned Interruptions | Planned Unserved Energy MWh | Number Unplanned Interruptions | Unplanned Unserved Energy MWh | Number of Outages <1 Min | Number of Interruptions <1 min | Measures Exceeded (plan/Unplan) ? | Incidents Affecting Performance | Steps Being Taken To Improve Performance | IDENT
468 | Index Measures for Asset Category |  | TF | 220/066 | 0.66 | 0.02 | 0 | 0 | 0 | 0 | None Apply | None Apply
469 | ISL-TF-T3 | I | TF | 220/066 | 1.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
470 | ISL-TF-T6 | I | TF | 220/066 | 3.07 | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | Y/Y | Planned Outage /
471 | [13 empty] | 02-Jun-2026: ISL-CB-502 failed to close via SCADA or locally on RTS of T6 after a planned outage for maintenance. POW relays was blocking the closing. POW relay was turned off and on and then CB502 closed successfully. | POW was reset. | SS26033
472 | ISL-TF-T7 | I | TF | 220/066 | 0.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
473 | ISL-TF-T8 | I | TF | 220/066 | 437.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
474 | WPR-TF-T12 | I | TF | 220/066 | 0.13 | 2.71 | 0 | 0 | 0 | 0 | 0 | 0 | N/Y | 21-Oct-2025: WPR T12 tripped with ISL-WPR-CUL-KIK2. but then CB172 failed to close so T12 now on fault with CB172, burned out close coil | Post event inspections have occurred using drones and service providers to identify defects. Information has been supplied to inform an investigation to look at options to improve the performance/resilience of ISL-KIK-A and B assets to high wind events. This investigation project is being generated within the system, and will be prioritised within the work plan. | SS25095
475 | WPR-TF-T13 | I | TF | 220/066 | 6.78 | 0.01 | 0 | 0 | 0 | 0 | 3 | 0 | Y/N | Planned Outage /
476
477 | Asset | Type* | Asset Category | Sub Cat | Planned Unavailability % | Unplanned Unavailability % | Number Planned Interruptions | Planned Unserved Energy MWh | Number Unplanned Interruptions | Unplanned Unserved Energy MWh | Number of Outages <1 Min | Number of Interruptions <1 min | Measures Exceeded (plan/Unplan) ? | Incidents Affecting Performance | Steps Being Taken To Improve Performance | IDENT
478 | Index Measures for Asset Category |  | TF | 220/110 | 1.56 | 0.06 | 0.03 | 0.1 | 0.02 | 0.72 | None Apply | None Apply
479 | BOB-TF-T4 | I | TF | 220/110 | 1.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
480 | BOB-TF-T5 | I | TF | 220/110 | 1.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
481 | BPE-TF-T2 | I | TF | 220/110 | 0.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
482 | BPE-TF-T3 | I | TF | 220/110 | 0.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
483 | EDG-TF-T5 | I | TF | 220/110 | 11.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
484 | EDG-TF-T6 | I | TF | 220/110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N
485 | GOR-TF-T11 | I | TF | 220/110 | 6.98 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
486 | GOR-TF-T12 | I | TF | 220/110 | 1.44 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | N/N | Planned Outage /
487 | HAM-TF-T6 | I | TF | 220/110 | 1.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
488 | HAM-TF-T9 | I | TF | 220/110 | 1.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
489 | HAY-TF-T1 | I | TF | 220/110 | 0.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
490 | HAY-TF-T2 | I | TF | 220/110 | 1.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
491 | HAY-TF-T5 | I | TF | 220/110 | 1.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
492 | HEN-TF-T1 | I | TF | 220/110 | 1.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
493 | HEN-TF-T5 | I | TF | 220/110 | 3.26 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
494 | HWB-TF-T6 | I | TF | 220/110 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
495 | INV-TF-T1 | I | TF | 220/110 | 2.35 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
496 | KAW-TF-T12 | I | TF | 220/110 | 1.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
497 | KIK-TF-T1 | B | TF | 220/110 | 0.93 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
498 | KIK-TF-T2 | B | TF | 220/110 | 1.15 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
499 | KMO-TF-T2 | I | TF | 220/110 | 1.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
500 | KMO-TF-T4 | I | TF | 220/110 | 0.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
501 | MDN-TF-T5 | I | TF | 220/110 | 1.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
502 | MDN-TF-T6 | I | TF | 220/110 | 0.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
503 | OTA-TF-T3 | I | TF | 220/110 | 1.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
504 | OTA-TF-T4 | I | TF | 220/110 | 1.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
505 | OTA-TF-T5 | I | TF | 220/110 | 1.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
506 | PEN-TF-T10 | I | TF | 220/110 | 8.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
507 | PEN-TF-T6 | I | TF | 220/110 | 1.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
508 | RDF-TF-T3 | I | TF | 220/110 | 16.51 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Y/N | Planned Outage /
509 | RDF-TF-T4 | I | TF | 220/110 | 9.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
510 | ROX-TF-T10 | I | TF | 220/110 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
511 | SFD-TF-T10 | I | TF | 220/110 | 2.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Y/N | Planned Outage /
512 | SFD-TF-T9 | I | TF | 220/110 | 0.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
513 | STK-TF-T7 | I | TF | 220/110 | 1.21 | 0.01 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
514 | TIM-TF-T5 | I | TF | 220/110 | 2.4 | 0.05 | 0 | 0 | 0 | 0 | 3 | 0 | Y/N | Planned Outage /
515 | TIM-TF-T8 | I | TF | 220/110 | 1.89 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | Y/N | Planned Outage /
516 | TRK-TF-T2 | I | TF | 220/110 | 1.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
517 | TRK-TF-T3 | I | TF | 220/110 | 0.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
518 | WIL-TF-T8 | I | TF | 220/110 | 1.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
519 | WTK-TF-T23 | I | TF | 220/110 | 1.21 | 0.01 | 0 | 0 | 1 | 4.18 | 0 | 0 | N/Y | 04-May-2026: WTK-TF-T23 tripped for OAM-STU-BPD-WTK2 fault, LOS. | OAM-STU-BPD-WTK-2 was energised successfully. Bird mitigation trials underway. | SS26030
520 | WTK-TF-T24 | I | TF | 220/110 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | N/N | Planned Outage /
521
522 | Asset | Type* | Asset Category | Sub Cat | Planned Unavailability % | Unplanned Unavailability % | Number Planned Interruptions | Planned Unserved Energy MWh | Number Unplanned Interruptions | Unplanned Unserved Energy MWh | Number of Outages <1 Min | Number of Interruptions <1 min | Measures Exceeded (plan/Unplan) ? | Incidents Affecting Performance | Steps Being Taken To Improve Performance | IDENT
523 | Index Measures for Asset Category |  | HVDC | HVDC | 1.56 | 0.06 | 0.03 | 0.1 | 0.02 | 0.72 | None Apply | None Apply
524 | HVDC-BIPOLE |  | HVDC | HVDC | 2.13 | 0.49 | 0 | 0 | 0 | 0 | - | - | Y/Y
525 | HVDC-POLE2 |  | HVDC | HVDC | 2.65 | 0.36 | 0 | 0 | 0 | 0 | - | - | Y/Y | 11-Jul-2025: HVDC BiPole as HVDC Pole2 reduction to 100%, Pole 3 reduction to 10% HVDC run back to 70MW from 180MW caused by a human error incident, an operations error | Operator training was reinforced and dispatch procedure document for HAY bus removal has been updated. | SH25010
526 | [13 empty] | 16-Sep-2025: HVDC Pole 2 unplanned outage to fix an indication fault preventing deblock. | Faulty cable replaced. | SH25011
527 | [13 empty] | 23-Oct-2025: HVDC Pole 2 tripped and stayed out. | There was fire under the lines (under tower 956). No damage found during inspection. No further action. | SH25007
528 | [13 empty] | 23-Oct-2025: HVDC Pole 2 went to reduced voltage. Forced outage. | There was fire under the lines (under tower 956). No damage found during inspection. No further action. | SH25007
529 | [13 empty] | 23-Oct-2025: HVDC Pole 3, BEN-HAY-1 tripped. Note HVDC Pole 2 had tripped earlier at 09:21:52. HVDC Pole 3 tripped, possibly fire nearby at Hamner Springs | There was fire under the lines (under tower 956). No damage found during inspection. No further action. | SH25008
530 | [13 empty] | 23-Oct-2025: HVDC Pole 2 tripped and restarted at reduced voltage | There was fire under the lines (under tower 956). No damage found during inspection. No further action. | SH25008
531 | [13 empty] | 23-Oct-2025: HVDC Pole 2 reduced voltage | There was fire under the lines (under tower 956). No damage found during inspection. No further action. | SH25012
532 | [13 empty] | 17-Nov-2025: HVDC Biplole reduced capability, Human error at Wilton T8, CT wired reverse polarity. Forced outage. | Panel labelling corrected and drawings as-built. Quality alert issued. | SH25009
533 | [13 empty] | 15-Feb-2026: BEN-HAY-2 tripped, HVDC Pole 2 restarted in reduced voltage. Fault locator indicated tower 4 near OTB. | Salt buildup on insulator and bushing were removed by washing. | SH26009
534 | [13 empty] | 23-Apr-2026: HVDC Pole 2 operating at reduced voltage due to flashovers at tower 1506 Hakana Bay (Port Underwood). Left in reduced voltage overnight, at full voltage got 5X fault restarts. SP reported corona noise, suspect salt contamination from prior southerly storm. Drone inspection 24th, faulty insulator | Insulators replaced on both poles at this tower. | SH26004
535 | [13 empty] | 24-Apr-2026: HVDC Pole 2 operating at reduced voltage due to flashovers at tower 1506 Hakana Bay (Port Underwood), suspect salt contamination. Forced outage. | Insulators replaced on both poles at this tower. | SH26008
536 | [13 empty] | 25-Apr-2026: HVDC Pole 2 operating at reduced voltage due to flashovers at tower 1506 Hakana Bay (Port Underwood). Left in reduced voltage overnight, at full voltage got 5X fault restarts. SP reported corona noise, suspect salt contamination from prior southerly storm. Drone inspection 24th, faulty insulator. | Insulators replaced on both poles at this tower. | SH26007
537 | [13 empty] | 27-Jun-2026: HVDC Pole 2 (BEN-HAY 2) was blocked, when it tried to start it tripped and was restarted on reduced voltage caused by adverse weather, strong winds, fog and light snow. Snow on towers in the South Island. | No further action. | SH26010
538 | HVDC-POLE3 |  | HVDC | HVDC | 1.76 | 0.59 | 0 | 0 | 0 | 0 | - | - | Y/Y | 11-Jul-2025: HVDC BiPole as HVDC Pole2 reduction to 100%, Pole 3 reduction to 10% HVDC run back to 70MW from 180MW caused by a human error incident, an operations error | Operator training was reinforced and dispatch procedure document for HAY bus removal has been updated. | SH25010
539 | [13 empty] | 25-Sep-2025: HVDC Pole 3 unplanned outage for valve warning ground fault due to faulty Bph delta bushing on T25. | The test tap box was inspected, repaired and moisture dried out. Circuit board was also dried out. | SH25006
540 | [13 empty] | 21-Oct-2025: HVDC Pole 3 reduced voltage, BEN-HAY-A faulted, spans 1498-1500, gale force winds blew conductor into pine trees | No further action. | SH25005
541 | [13 empty] | 23-Oct-2025: Continuation of HVDC Pole 3 because Pole 2 returned to service | There was fire under the lines (under tower 956). No damage found during inspection. No further action. | SH25008
542 | [13 empty] | 23-Oct-2025: HVDC Pole 3, BEN-HAY-1 tripped. Note HVDC Pole 2 had tripped earlier at 09:21:52. HVDC Pole 3 tripped, possibly fire nearby at Hamner Springs | There was fire under the lines (under tower 956). No damage found during inspection. No further action. | SH25008
543 | [13 empty] | 17-Nov-2025: HVDC Biplole reduced capability, Human error at Wilton T8, CT wired reverse polarity. Forced outage. | Panel labelling corrected and drawings as-built. Quality alert issued. | SH25009
544 | [13 empty] | 04-Feb-2026: HVDC pole 3 tripped for BEN T30B cooling loss of 24V power supply | 24V supplies in all Pole 3 converter transformers at HAY and BEN have been made redundant (previously non-redundant). | SH26001
545 | [13 empty] | 15-Feb-2026: HVDC Pole 3 tripped via Pole 3 220kV Connection Differential Protection due to a metal flashing that shorted out a 220kV connection on HAY-TF-T25's yellow phase unit. It was a yellow phase to ground fault. | Loose flashings have been removed. Flashings changed to alternative fasteners. There is also increased maintenance inspections on this. | SH26002
546 | [13 empty] | 18-Apr-2026: HVDC Pole 3 unplanned outage to open and close disconnector 3336 to check indication after Midpos alarms | Disconnector exercised and mech box inspection/ terminals tightened. | SH26006
547 | [13 empty] | 21-Apr-2026: HVDC Pole 3 tripped for HAY Pole 3 valve cooling fault caused by low flow. Cold water temperature 15 deg Celsius due to cold ambient temperature. Normally water temp at 40 deg Celsius when pole is running. Cold water thicker so flow rate reduced a bit then it hit the abnormal flow alarm level | Alarm settings on flow meter were changed to resolve the issue. | SH26003
548 | [13 empty] | 26-Apr-2026: HVDC Pole 3 tripped, unplanned outage, due to faulty valve base electronics at Haywards | Insulators replaced on both poles at this tower. Control card tested and replaced. | SH26005
549
550 | (1) Transpower’s asset management systems include plans and processes to maintain performance of all our assets, and to minimise the impact of events on customers and end-consumers. Events mentioned in this report will have been dealt with according to these plans and processes whether or not a specific response is given here.
551 | (2) Actions provided in the report are based on current available information.
552
553
554

## G6. Asset Health and Age
[8 empty] | Transpower |  | Disclosure Date |  | 2026-10-23
SCHEDULE G6: ASSET HEALTH AND AGE | [9 empty] | Disclosure Year (year ended) |  | 2026-06-30
Disclosure of line items not required from disclosure year 2026 onward are specified in column CJ.
ref
5 |  | G6(i): Asset Health | [17 empty] | Not required from disclosure year 2026 | Not required from disclosure year 2026 | Not required from disclosure year 2026 | Not required from disclosure year 2026 | Not required from disclosure year 2026 | Required from disclosure year 2026 | [8 empty] | Agreed approach: Grid Base Refurbishment and Replacement projects. Actuals CY -2 (2023/24) to CY (2025/26). Proposal for reset period = RCP4 Proposal R&R CY-2 (2023/24) to CY+6 (2031/32) | [11 empty] | Grid Enhancement and Development (E&D) projects. Our RCP4 expenditure proposal included an envelope allowance for but costings were high-level and did not include numbers of assets. Agreed Approach: input actuals for Base E&D and approved MCPs only; No Proposal deliverables as the detailed scope was not known | [11 empty] | Disposals of individual assets are not always recorded in our system at this level of detail. We have therefore assumed that for every asset replacement there is a corresponding disposal. | [11 empty] | Agreed approach: Actuals Divestments if any: Proposal: only if known or referred to in proposal
6 | [8 empty] | Total Number of Assets CY | Asset Age | [8 empty] | Asset Health | Asset Health/Remaining Expected Life | [15 empty] | Asset Replacement/Refurbishment/Development/Enhancement of Existing Assets | [12 empty] | Asset Additions | [11 empty] | Asset Disposal | [11 empty] | Asset Divestments | [8 empty] | Assumptions and Comments
7 |  |  | Some rows below have been added by Transpower in order to provide aggregate asset health numbers. Those rows have been coloured green. | [21 empty] | Asset Health Distribution % of assets in AHI category | [8 empty] | Actual |  |  | Forecast from Expenditure Proposal for Reset Period | [8 empty] | Actual |  |  | Forecast from Expenditure Proposal for Reset Period | [8 empty] | Actual |  |  | Forecast from Expenditure Proposal for Reset Period | [8 empty] | Actual |  |  | Forecast from Expenditure Proposal for Reset Period
8 |  | Category | Asset Category | Voltage | Asset Class 1 | Asset Class 2 | Units | Notes on Units of measure |  | 1-5 years | 6-10 years | 11-15 years | 16-20 years | 21-30 years | 31-40 years | 41-50 years | 50 + years | Unknown Age | Asset health accuracy | Due now | 0-2 years | 2-7 years | 7-12 years | 12 + years | Not Scored | 0 ≤ AHI < 4 | 4 ≤ AHI < 5 | 5 ≤ AHI < 6 | 6 ≤ AHI < 7 | 7 ≤ AHI < 8 | 8 ≤ AHI < 9 | 9 ≤ AHI < 9.5 | 9.5 ≤ AHI | CY-2 | CY-1 | CY | CY-2 | CY-1 | CY | CY+1 | CY+2 | CY+3 | CY+4 | CY+5 | CY+6 | CY-2 | CY-1 | CY | CY-2 | CY-1 | CY | CY+1 | CY+2 | CY+3 | CY+4 | CY+5 | CY+6 | CY-2 | CY-1 | CY | CY-2 | CY-1 | CY | CY+1 | CY+2 | CY+3 | CY+4 | CY+5 | CY+6 | CY-2 | CY-1 | CY | CY-2 | CY-1 | CY | CY+1 | CY+2 | CY+3 | CY+4 | CY+5 | CY+6
9 |  | HVDC | Converter Station/Cable Stations/Electrode Stations | HVDC | Power Transformers HVDC Converter |  | No of Tranaformer banks |  | 4 |  |  | 2 |  |  | 2 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 |  |  |  |  | HV Outdoor Circuit Breakers HVDC |  | No. of breakers |  | 39 | 2 | 4 | 27 | 1 | 1 | 4 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0
11 |  |  |  |  | Thyristor Valves and Control HVDC |  | No. of quadrivalves (valve stacks) |  | 12 |  |  | 6 |  |  | 6 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 |  |  |  |  | HVDC Capacitors Banks / Filter Banks |  | No. of HVDC capacitors banks and filter banks |  | 115 |  |  | 60 |  |  | 51 |  |  | 4 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 |  |  |  |  | HVDC Reactors |  | No. of standalone reactors |  | 112 |  |  | 50 | 14 |  | 48 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 |  |  |  |  | HVDC Disconnectors |  | No. of disconnectors |  | 40 |  |  | 11 | 4 | 2 | 23 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 |  |  |  |  | HVDC Earthswitches |  | No. of earthswitches |  | 69 |  |  | 21 | 5 | 2 | 41 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 |  |  |  |  | HVDC Standalone Current Transformers and Current Transducers |  | No. of transformers |  | 112 | 26 | 0 | 45 | 14 |  | 27 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 |  |  |  |  | HVDC Voltage Transformers (CVTs and VTs) and Voltage Dividers |  | No. of transformers |  | 53 | 9 | 1 | 31 | 7 |  | 5 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 |  |  |  |  | Cables HVDC submarine cables and terminations |  | Kilometres of cable |  | 3x40km | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 |  |  |  |  | Cable Fibre Optic Submarine |  | Kilometres of cable |  | 3x40km | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 |  | HVDC | HVDC submarine cables | [21 empty] | 0% | 65.57% | 29.51% | 3.279% | 1.639% | 0% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 |  | AC Stations | Power Transformers | 220 | Interconnector | Single Phase | No. of transformer banks | Primary voltage 220 kV | 8 | [7 empty] | 8 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | [5 empty] | Three Phase | No. of transformers |  | 45 | 4 | 8 | 8 | 9 | 6 | 8 |  | 2 | [16 empty] | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 |  |  |  |  | Supply | Single Phase | No. of transformer banks |  | 7 | [6 empty] | 1 | 6 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | [5 empty] | Three Phase | No. of transformers |  | 82 | 10 | 5 | 12 | 12 | 9 | 10 | 16 | 8 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 3 | 0 | 1 | 0 | 0 | 0
25 |  |  |  | 110 | Interconnector | Single Phase | No. of transformer banks | Primary voltage 110 kV | 0 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | [5 empty] | Three Phase | No. of transformers |  | 3 |  | 2 |  | 1 | [20 empty] | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
27 |  |  |  |  | Supply | Single Phase | No. of transformer banks |  | 35 | [7 empty] | 35 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | [5 empty] | Three Phase | No. of transformers |  | 111 | 8 | 14 | 16 | 17 | 29 | 7 | 13 | 7 | [16 empty] | 0 | 2 | 3 | 0 | 4 | 4 | 2 | 0 | 6 | 2 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 4 | 4 | 2 | 0 | 6 | 2 | 0 | 5 | 0 | 0 | 0
29 |  |  |  | 66 & 50 | Supply | Single Phase | No. of transformer banks |  | 2 | [7 empty] | 2 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | [5 empty] | Three Phase | No. of transformers |  | 13 |  |  | 2 | 3 | 2 |  | 5 | 1 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0
31 |  |  |  | Various | Other (33 & below, Earthing, Local Service) |  | No. of transformers |  | 313 | 46 | 49 | 55 | 46 | 37 | 26 | 28 | 25 | 1 | [15 empty] | 3 | 163 | 3 | 10 | 6 | 7 | 3 | 2 | 2 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 163 | 3 | 10 | 6 | 7 | 3 | 2 | 2 | 0 | 0 | 3 | 0 | 0 | 0
32 |  | AC Stations | Power Transformers | ALL | [20 empty] | 0% | 54.71% | 2.432% | 15.81% | 10.03% | 13.07% | 1.824% | 0.6079% | 1.52% | 0 | 0 | 0 | 10 | 12 | 11 | 7 | 2 | 8 | 8 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 12 | 11 | 7 | 2 | 8 | 8 | 0 | 11 | 0 | 0 | 0
33 |  | AC Stations | Switchyards | Various |  |  | No. of switchyards |  | 327 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 |  | AC Stations | Switchyard Roofs and Fences | ALL | [20 empty] | 0% | 89.17% | 4.6% | 3.468% | 1.132% | 1.628% | 0% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 |  | AC Stations | Outdoor Circuit Breakers | 220 | SF6 | SF6 | No. of 3 phase sets | There are situations where there are connections to only 2 phases but for the purpose of recording these will be counted as a three phase set | 540 | 41 | 15 | 55 | 136 | 142 | 101 | 50 | [17 empty] | 3 | 0 | 1 | 3 | 2 | 2 | 6 | 0 | 1 | 1 | 15 | 14 | 1 | 0 | 2 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 3 | 2 | 2 | 6 | 0 | 1 | 1 | 15 | 14 | 0 | 0 | 0
36 |  |  |  | 110 | Bulk Oil |  | No. of 3 phase sets |  | 5 | [7 empty] | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 |  |  |  |  | SF6 |  | No. of 3 phase sets |  | 522 | 12 | 69 | 78 | 82 | 180 | 92 | 9 | [17 empty] | 0 | 0 | 4 | 0 | 4 | 14 | 7 | 6 | 21 | 12 | 2 | 10 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 14 | 7 | 6 | 21 | 12 | 2 | 10 | 0 | 0 | 0
38 |  |  |  | 66 & 50 | Bulk Oil |  | No. of 3 phase sets |  | 18 | [7 empty] | 18 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 |  |  |  |  | Minimium Oil |  | No. of 3 phase sets |  | 0 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 |  |  |  |  | SF6 |  | No. of 3 phase sets |  | 83 |  | 7 | 16 | 7 | 29 | 16 | 8 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 |  |  |  |  | Vacuum |  | No. of 3 phase sets |  | 0 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 |  |  |  | 33,22,11 | Vacuum |  | No. of 3 phase sets |  | 15 | 1 | 2 | 3 | 4 |  | 5 | [18 empty] | 0 | 0 | 0 | 3 | 22 | 3 | 10 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 22 | 3 | 10 | 9 | 1 | 0 | 0 | 0 | 0 | 0 | 0
43 |  |  |  |  | Bulk Oil |  | No. of 3 phase sets |  | 24 | [6 empty] | 13 | 9 | 2 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 |  |  |  |  | Minimum Oil |  | No. of 3 phase sets |  | 1 | [7 empty] | 1 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 |  |  |  |  | SF6 |  | No. of 3 phase sets |  | 70 | 2 | 10 | 12 | 22 | 14 | 10 | [18 empty] | 6 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0
46 |  | AC Stations | Outdoor Circuit Breakers | ALL | [20 empty] | 0.148% | 79.87% | 7.254% | 7.772% | 3.553% | 1.11% | 0.07402% | 0.2221% | 0% | 0 | 0 | 0 | 6 | 28 | 19 | 37 | 22 | 23 | 15 | 17 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 28 | 19 | 37 | 22 | 23 | 15 | 17 | 25 | 0 | 0 | 0
47 |  | AC Stations | Indoor Switchgear | 220 | SF6 |  | No. of 3 phase sets | For the Indoor switch gear the 3 phase sets includes the disconnectors , earthswitches, and integral instrument transformers | 43 |  |  | 12 |  |  |  | 31 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 |  |  |  | 110 | SF6 |  | No. of 3 phase sets |  | 9 | [6 empty] | 9 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 |  |  |  | 33,22,11 | Bulk Oil |  | No. of 3 phase sets |  | 10 | [7 empty] | 10 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 |  |  |  |  | Minimum Oil |  | No. of 3 phase sets |  | 0 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 |  |  |  |  | SF6 |  | No. of 3 phase sets |  | 98 | 1 |  | 3 | 6 | 73 | 10 | 5 | [17 empty] | 0 | 41 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 0 | 3 | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 11 | 0 | 0 | 0 | 0
52 |  |  |  |  | Vacuum |  | No. of 3 phase sets |  | 897 | 38 | 213 | 324 | 124 | 198 | [19 empty] | 0 | 0 | 0 | 11 | 12 | 5 | 1 | 7 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 12 | 5 | 1 | 7 | 19 | 0 | 0 | 0 | 0 | 0 | 0
53 |  |  |  | Various | Other (Airblast/Airbreak) |  | No. of 3 phase sets |  | 13 | [6 empty] | 13 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 |  | AC Stations | Indoor Switchgear | ALL | [20 empty] | 0% | 86.26% | 0.7477% | 10.84% | 1.869% | 0% | 0.2804% | 0% | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 |  | AC Stations | Reactive Power | 220 | Reactors |  | No.of 3 phase sets of standalone reactors | Theses are standalone power reactors that are not part of capacitor or filter banks, Statcoms or SVCs | 20 | 4 |  | 3 | 4 | 5 | 4 | [18 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 |  |  |  | 110 | Reactors |  | No. 3 phase sets of standalone reactors |  | 21 |  | 5 |  | 5 | 8 | 3 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 |  |  |  | 66 | Reactors |  | No. 3 phase sets of standalone reactors |  | 4 |  |  |  | 1 |  | 3 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 |  |  |  | <66 | Reactors |  | No. 3 phase sets of standalone reactors |  | 78 | 7 | 1 | 17 | 18 | 22 | 10 | 2 |  | 1 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0
59 |  | AC Stations | Reactive Power |  | Reactors( all) | [19 empty] | 0.5988% | 67.66% | 6.188% | 8.184% | 8.383% | 5.788% | 1.796% | 0.1996% | 1.198% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 |  |  |  |  | Capacitors | [28 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 |  | AC Stations | Reactive Power | 220 | Capacitor Banks / Filter Banks |  | No of Capacitor Banks and Filter Banks | Excludes the Capacitor Banks and Filter banks which are part of the HVDC installations | 14 |  |  |  | 5 | 3 | 6 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 0 | 0
62 |  |  |  | 110 | Capacitor Banks / Filter Banks |  | No of Capacitor Banks and Filter Banks |  | 17 |  | 4 |  | 9 | 1 | 3 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
63 |  |  |  | 66 | Capacitor Banks / Filter Banks |  | No of Capacitor Banks and Filter Banks |  | 4 |  |  |  | 1 |  | 3 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 |  |  |  | < 66 | Capacitor Banks / Filter Banks |  | No of Capacitor Banks and Filter Banks |  | 62 |  | 1 | 18 | 18 | 17 | 7 |  |  | 1 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 |  | AC Stations | Reactive Power |  | Capacitors (all) | [19 empty] | 0% | 68.03% | 7.388% | 8.102% | 3.653% | 8.54% | 0.2923% | 0.01624% | 3.978% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 |  | AC and DC Stations | Reactive Power |  | Synchronous Condensers |  | No of Synchronous Condensers including all associated equipment | This includes all asoociated equipment such as cooling, excitaion systems etc | 8 | [7 empty] | 8 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0
67 |  |  |  |  | STATCOMs |  | No. of Statcoms | This includes all associated equipment such as transformers reactors, capacitors , cooling systems, controls etc | 8 | [8 empty] | 8 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 |  |  |  |  | Static Var Compensators ( SVC) |  | No. of SVCs | This includes all associated equipment such as transformers reactors, capacitors , cooling systems, controls etc | 3 |  |  |  | 1 |  |  |  |  | 2 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 |  | AC Stations | Instrument Transformers ( Standalone) | 220 | CT |  | No. of 3 phase sets standalone transformers | There are situations where there are connections to only 2 phases but for the purpose of recording these will be counted as a three phase set | 574 | 74 | 49 | 105 | 111 | 115 | 62 | 55 | 3 | [16 empty] | 4 | 10 | 21 | 10 | 10 | 43 | 17 | 7 | 2 | 9 | 22 | 7 | 2 | 0 | 3 | 2 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 10 | 21 | 10 | 10 | 43 | 17 | 7 | 2 | 9 | 22 | 7 | 0 | 0 | 0
70 |  |  |  |  | VT |  | No. of 3 phase sets standalone transformers |  | 12 | 3 |  | 3 | 4 |  |  | 2 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 |  |  |  |  | CVT |  | No. of 3 phase sets standalone transformers |  | 301 | 30 | 35 | 50 | 36 | 122 | 26 | 2 | [17 empty] | -3 | 0 | 0 | 1 | 2 | 4 | 1 | 15 | 0 | 0 | 5 | 1 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -3 | 0 | 0 | 1 | 2 | 4 | 1 | 15 | 0 | 0 | 5 | 1 | 0 | 0 | 0
72 |  |  |  | 110 | CT |  | No. of 3 phase sets standalone transformers |  | 462 | 21 | 98 | 27 | 44 | 160 | 86 | 25 |  | 1 | [15 empty] | 2 | 3 | 7 | 6 | 4 | 25 | 6 | 9 | 13 | 18 | 5 | 7 | 2 | 1 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 7 | 6 | 4 | 25 | 6 | 9 | 13 | 18 | 5 | 7 | 0 | 0 | 0
73 |  |  |  |  | VT |  | No. of 3 phase sets standalone transformers |  | 187 | 13 | 29 | 20 | 26 | 72 | 19 | 6 |  | 2 | [15 empty] | 4 | 1 | 1 | 5 | 1 | 7 | 3 | 3 | 6 | 8 | 1 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 1 | 1 | 5 | 1 | 7 | 3 | 3 | 6 | 8 | 1 | 3 | 0 | 0 | 0
74 |  |  |  |  | CVT |  | No. of 3 phase sets standalone transformers |  | 30 | 4 | 1 |  | 2 | 7 | 3 | 13 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 |  |  |  | 66 & 50 | CT |  | No. of 3 phase sets standalone transformers |  | 83 | 4 | 18 | 14 | 2 | 13 | 25 | 7 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 13 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 13 | 0 | 0 | 0 | 2 | 0 | 0 | 0
76 |  |  |  |  | VT |  | No. of 3 phase sets standalone transformers |  | 45 | 6 | 5 | 9 | 8 | 7 | 2 | 8 | [17 empty] | 0 | 1 | 1 | 0 | 1 | 2 | 4 | 2 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 2 | 4 | 2 | 0 | 3 | 2 | 0 | 0 | 0 | 0
77 |  |  |  | 33 & below | CT |  | No. of 3 phase sets standalone transformers |  | 245 | 54 | 63 | 13 | 45 | 54 | 7 | 2 | 1 | 6 | [15 empty] | 5 | 0 | 2 | 0 | 2 | 0 | 0 | 6 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 2 | 0 | 2 | 0 | 0 | 6 | 1 | 1 | 1 | 0 | 0 | 0 | 0
78 |  |  |  |  | VT |  | No. of 3 phase sets standalone transformers |  | 181 | 18 | 36 | 49 | 14 | 46 | 13 | 2 | 2 | 1 | [15 empty] | 0 | 1 | 2 | 0 | 3 | 3 | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 0 | 3 | 3 | 4 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0
79 |  |  |  |  | CVT |  | No. of 3 phase sets standalone transformers |  | 1 |  |  |  | 1 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 |  |  |  | Other | VT |  | No. of 3 phase sets standalone transformers |  | 0 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 |  | AC Stations | Instrument Transformers ( Standalone) | ALL | [20 empty] | 0.1697% | 76.81% | 5.378% | 12.2% | 3.767% | 1.103% | 0.3054% | 0.2545% | 0.01697% | 0 | 0 | 0 | 22 | 23 | 84 | 39 | 57 | 22 | 41 | 36 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 23 | 84 | 39 | 57 | 22 | 41 | 36 | 20 | 0 | 0 | 0
82 |  | AC Stations | Disconnectors (standalone) | 220 |  |  | No. of 3 phase sets | There are situations where there are connections to only 2 phases but for the purpose of recording these will be counted as a three phase set | 1503 | 29 | 10 | 184 | 169 | 152 | 235 | 304 | 390 | 30 | [15 empty] | 0 | 0 | 1 | 0 | 1 | 4 | 7 | 4 | 5 | 1 | 1 | 1 | 1 | 0 | 20 | 1 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 4 | 7 | 4 | 5 | 1 | 1 | 1 | 0 | 0 | 0
83 |  |  |  | 110 |  |  | No. of 3 phase sets |  | 944 | 4 | 19 | 28 | 110 | 215 | 57 | 113 | 321 | 77 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 3 | 7 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 3 | 7 | 1 | 1 | 1 | 0 | 0 | 0
84 |  |  |  | 66 & 50 |  |  | No. of 3 phase sets |  | 209 | 5 | 5 | 10 | 6 | 45 | 21 | 18 | 91 | 8 | [15 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0
85 |  |  |  | 33,22,11 |  |  | No. of 3 phase sets |  | 520 | 40 | 46 | 129 | 85 | 45 | 6 | 67 | 58 | 44 | [15 empty] | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0
86 |  |  |  | Other |  |  | No. of 3 phase sets |  | 1 |  |  | 1
87 |  | AC Stations | Disconnectors - all | [21 empty] | 0.6371% | 51.96% | 7.518% | 6.021% | 7.232% | 9.302% | 10.83% | 2.708% | 3.791% | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 1 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
88 |  | AC Stations | Earth Switches (standalone) | 220 |  |  | No. of 3 phase sets | There are situations where there are connections to only 2 phases but for the purpose of recording these will be counted as a three phase set | 821 | 75 | 14 | 187 | 169 | 37 | 89 | 166 | 84 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 1 | 0 | 0 | 0
89 |  |  |  | 110 |  |  | No. of 3 phase sets |  | 413 | 27 | 65 | 42 | 74 | 65 | 26 | 63 | 49 | 2 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
90 |  |  |  | 66 & 50 |  |  | No. of 3 phase sets |  | 67 | 4 | 7 | 16 | 5 | 13 | 13 | 3 | 6 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0
91 |  |  |  | 33,22,11 |  |  | No. of 3 phase sets |  | 445 | 43 | 18 | 156 | 74 | 76 | 20 | 41 | 14 | 3 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 |  |  |  | Unknown |  |  | No. of 3 phase sets |  | 38 | 5 | 14 | 13 | 3 |  |  |  | 1 | 2 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 |  | AC Stations | Earthswitch - all | [21 empty] | 0.3563% | 70.55% | 5.819% | 3.682% | 3.147% | 4.335% | 8.848% | 0.4751% | 2.791% | 5 | 0 | 0 | 0 | 0 | 6 | 9 | 8 | 12 | 3 | 8 | 7 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 6 | 9 | 8 | 12 | 3 | 8 | 7 | 0 | 0 | 0
94 | New Line | AC Stations | Disconnectors & Earth Switches | Replacements are often combined - have added combined deliverables into this line |  |  |  | For replacements only | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 |  | AC Stations | Power Cables greater than 1 km | 220 | Paper Insulated (oil filled) |  | Metres of cable (circuit length) |  | 0 | [24 empty] | 40 | 0 | 1 | 40 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 1 | 40 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 |  |  |  |  | XLPE |  | Metres of cable (circuit length) |  | 62875 |  | 4623 | 58252 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 |  |  |  | 110 | Paper Insulated (oil filled) |  | Metres of cable (circuit length) |  | 0 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 |  |  |  |  | XLPE |  | Metres of cable (circuit length) |  | 16797 |  | 4500 | 2634 | 7983 | 750 | 930 | [18 empty] | 0 | 0 | 0 | 3292 | 1816 | 5123 | 3132 | 1594 | 2410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3292 | 1816 | 5123 | 3132 | 1594 | 2410 | 0 | 0 | 0 | 0 | 0 | 0
99 |  |  |  | 66 & 50 | XLPE |  | Metres of cable (circuit length) |  | 2234 |  |  | 2234 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 |  | AC Stations | Power Cables 1 km or less | 220 | Paper Insulated (oil filled) |  | No of circuits |  | 7 | [6 empty] | 7 | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 |  |  |  |  | XLPE |  | No of circuits |  | 12 |  | 2 | 1 | 9 | [20 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 |  |  |  | 110 | Paper Insulated (oil filled) |  | No of circuits |  | 0 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 |  |  |  |  | XLPE |  | No of circuits |  | 30 | 1 | 9 | 3 | 6 | 4 | 7 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 |  |  |  | 66 & 50 | XLPE |  | No of circuits |  | 9 |  | 2 | 4 | 1 |  | 2 | [18 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 |  |  |  | 33,22,11 | Paper Insulated |  | No of circuits |  | 21 | [6 empty] | 20 | 1 | [16 empty] | 2176 | 75 | 766 | 27103 | 75131 | 0 | 0 | 0 | 0 | 360 | 360 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2176 | 75 | 766 | 27103 | 75131 | 0 | 0 | 0 | 0 | 360 | 360 | 360 | 0 | 0 | 0
106 |  |  |  |  | XLPE |  | No of circuits |  | 698 | 98 | 146 | 209 | 85 | 113 | 29 | 2 | 1 | 15 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 |  |  |  | Unknown | XLPE |  | No of circuits |  | 23 | 11 | 1 | 4 |  | 4 | 2 |  | 1 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 |  | AC Stations | Power Cables | Solid (excludes pressurised cables) | [20 empty] | 2.477% | 96.91% | 0.4619% | 0.126% | 0% | 0.021% | 0% | 0% | 0% | 0 | 4 | 0 | 1 | 2 | 2 | 1 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 2 | 2 | 1 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0
109 |  | Secondary Systems | Revenue Metering |  |  |  | No. of meters |  | 403 | 384 | 17 | 1 | 1 | [20 empty] | 7 | 14 | 7 | 11 | 9 | 18 | 15 | 24 | 11 | 21 | 26 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 14 | 7 | 11 | 9 | 18 | 15 | 24 | 11 | 21 | 26 | 13 | 0 | 0 | 0
110 |  | Secondary Systems | Bus Protection Scheme | 220/110/66/33 | Bus Zone Protection Scheme (Incl CB fail) |  | No. of protection schemes |  | 261 | 21 | 65 | 76 | 56 | 28 | 12 | 2 | 1 | [16 empty] | 10 | 6 | 10 | 14 | 7 | 10 | 11 | 11 | 6 | 23 | 22 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 6 | 10 | 14 | 7 | 10 | 11 | 11 | 6 | 23 | 22 | 18 | 0 | 0 | 0
111 |  |  |  |  | Bus Coupler Protection Scheme |  | No. of protection schemes |  | 136 | 11 | 31 | 21 | 17 | 37 | 18 |  |  | 1 | [15 empty] | 3 | 22 | 1 | 4 | 0 | 5 | 18 | 11 | 1 | 24 | 11 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 22 | 1 | 4 | 0 | 5 | 18 | 11 | 1 | 24 | 11 | 9 | 0 | 0 | 0
112 |  |  |  |  | Arc Flash Detection Scheme |  | No. of protection schemes |  | 93 | 5 | 34 | 36 | 15 | 2 |  |  |  | 1 | [15 empty] | 20 | 21 | 4 | 52 | 12 | 52 | 63 | 33 | 26 | 20 | 15 | 57 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 21 | 4 | 52 | 12 | 52 | 63 | 33 | 26 | 20 | 15 | 57 | 0 | 0 | 0
113 |  | Secondary Systems | Line Protection Scheme | 220/110/66/33 |  |  | No. of protection schemes |  | 642 | 37 | 151 | 186 | 175 | 83 | 8 | 2 | [17 empty] | 11 | 1094 | 11 | 22 | 15 | 17 | 29 | 10 | 10 | 20 | 10 | 19 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 1094 | 11 | 22 | 15 | 17 | 29 | 10 | 10 | 20 | 10 | 19 | 0 | 0 | 0
114 |  | Secondary Systems | Transformer Protection Scheme | 220/110/66 |  |  | No. of protection schemes |  | 332 | 38 | 90 | 86 | 86 | 30 | 1 |  |  | 1 | [15 empty] | 22 | 10 | 13 | 33 | 44 | 35 | 25 | 40 | 14 | 77 | 51 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 10 | 13 | 33 | 44 | 35 | 25 | 40 | 14 | 77 | 51 | 58 | 0 | 0 | 0
115 |  | Secondary Systems | Feeder Protection Scheme | 33/22/11 |  |  | No. of protection schemes | Includes all voltages | 933 | 132 | 277 | 318 | 115 | 85 |  |  | 1 | 5 | [15 empty] | 0 | 1 | 1 | 1 | 2 | 2 | 8 | 4 | 3 | 3 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 8 | 4 | 3 | 3 | 1 | 0 | 0 | 0 | 0
116 |  | Secondary Systems | Special Protection Scheme | 33/22/11 |  |  | No. of protection schemes | Includes all voltages | 42 | 8 | 7 | 7 | 11 | 6 | 2 |  |  | 1 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 |  | Secondary Systems | Protection Relays | ALL | [20 empty] | 0% | 44.09% | 15.25% | 13.86% | 12.59% | 5.444% | 4.595% | 1.004% | 3.166% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 |  | Secondary Systems | Batteries & DC Systems | [30 empty] | 214 | 20 | 589 | 47 | 25 | 8 | 26 | 18 | 32 | 29 | 30 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 214 | 20 | 589 | 47 | 25 | 8 | 26 | 18 | 32 | 29 | 30 | 43 | 0 | 0 | 0
119 |  | Secondary Systems | Battery Banks | 125 VDC |  |  | No. of banks |  | 371 | 145 | 208 | 12 | 1 |  |  |  |  | 5 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 |  | Secondary Systems | Battery Banks | 24 and 48 VDC |  |  | No. of banks |  | 330 | 234 | 93 | 1 | [5 empty] | 2 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 |  | Secondary Systems | Battery Banks | ALL | [20 empty] | 3.166% | 35.09% | 33.25% | 11.61% | 10.82% | 1.847% | 0% | 0% | 4.222% | 213 | 46 | 24 | 60 | 29 | 19 | 30 | 13 | 5 | 12 | 10 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 213 | 46 | 24 | 60 | 29 | 19 | 30 | 13 | 5 | 12 | 10 | 21 | 0 | 0 | 0
122 |  | Secondary Systems | Battery Chargers | 125 VDC |  |  | No. of chargers |  | 374 | 167 | 85 | 58 | 49 | 10 |  |  |  | 5 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 |  | Secondary Systems | Battery Chargers | 24 and 48 VDC |  |  | No. of chargers |  | 299 | 44 | 42 | 81 | 129 |  | 1 |  |  | 2 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 |  | Secondary Systems | Battery Chargers | ALL | [20 empty] | 4.521% | 61.44% | 6.649% | 6.915% | 10.37% | 5.585% | 3.191% | 0.5319% | 0.7979% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 |  | Secondary Systems | SubstationTelemetry Systems |  | RTU |  | No. of RTUs |  | 6 |  |  | 2 | 4 | [20 empty] | 11 | 11 | 2 | 29 | 12 | 4 | 57 | 56 | 29 | 35 | 47 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 11 | 2 | 29 | 12 | 4 | 57 | 56 | 29 | 35 | 47 | 60 | 0 | 0 | 0
126 |  |  |  |  | SMS Platform |  |  |  | 246 | 77 | 124 | 45 | [21 empty] | 1 | 5 | 5 | 4 | 10 | 6 | 13 | 44 | 11 | 9 | 4 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 5 | 4 | 10 | 6 | 13 | 44 | 11 | 9 | 4 | 33 | 0 | 0 | 0
127 |  |  |  |  | GPS Clocks |  | No. of GPS clocks |  | 208 | 51 | 124 | 33 | [21 empty] | 53 | 9 | 1 | 55 | 8 | 50 | 51 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 9 | 1 | 55 | 8 | 50 | 51 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0
128 |  |  |  |  | Human Machine Interface (HMI) |  | No. of HMI's |  | 218 | 171 | 46 | [6 empty] | 1 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 |  | Transmission Lines | Tower | 400 | Single Cct Lattice Steel Tower or Monopole | Unpainted | No of Structures |  | 6 |  |  | 6 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | [5 empty] | Painted | No of Structures |  | 0 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 |  |  |  |  | Double Cct Lattice Steel Tower or Monopole | Unpainted | No of Structures |  | 412 |  |  | 412 | [21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | [5 empty] | Painted | No of Structures |  | 0 | [24 empty] | 83 | 151 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 264 | 87 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 151 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 264 | 87 | 88 | 0 | 0 | 0
133 |  |  |  | 220 | Single Cct Lattice Steel Tower or Monopole | Unpainted | No of Structures |  | 5563 | 1 | 2 | 6 | 1 |  | 2 | 32 | 5519 | [16 empty] | 83 | 43 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 136 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 43 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 136 | 139 | 0 | 0 | 0
134 | [5 empty] | Painted | No of Structures |  | 1965 |  | 9 | 23 |  | 1 |  | 2 | 1930 | [16 empty] | 126 | 105 | 47 | 178 | 237 | 242 | 263 | 227 | 270 | 75 | 99 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126 | 105 | 47 | 178 | 237 | 242 | 263 | 227 | 270 | 75 | 99 | 101 | 0 | 0 | 0
135 |  |  |  |  | Double Cct Lattice Steel Tower or Monopole | Unpainted | No of Structures |  | 4989 | 3 |  | 109 | 8 | 6 | 678 | 1759 | 2418 | 8 | [15 empty] | 83 | 103 | 98 | 145 | 141 | 160 | 128 | 144 | 129 | 125 | 154 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 103 | 98 | 145 | 141 | 160 | 128 | 144 | 129 | 125 | 154 | 158 | 0 | 0 | 0
136 | [5 empty] | Painted | No of Structures |  | 2498 |  |  | 2 | 2 | 2 | 52 | 707 | 1733 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 |  |  |  |  | Triple Circuit Steel Tower | Unpainted | No of Structures |  | 0 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | [5 empty] | Painted | No of Structures |  | 4 | [6 empty] | 4 | [17 empty] | 20 | 4 | 36 | 53 | 25 | 78 | 50 | 65 | 66 | 30 | 31 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 4 | 36 | 53 | 25 | 78 | 50 | 65 | 66 | 30 | 31 | 31 | 1 | 0 | 0
139 |  |  |  | 110/66 | Single Cct Lattice Steel Tower or Monopole | Unpainted | No of Structures |  | 1375 |  |  |  |  | 1 |  | 45 | 1329 | [16 empty] | 14 | 15 | 0 | 106 | 59 | 41 | 66 | 53 | 69 | 11 | 48 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 15 | 0 | 106 | 59 | 41 | 66 | 53 | 69 | 11 | 48 | 49 | 0 | 0 | 0
140 | [5 empty] | Painted | No of Structures |  | 143 | [6 empty] | 67 | 76 | [16 empty] | 33 | 21 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 21 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 13 | 13 | 0 | 0 | 0
141 |  |  |  |  | Double Cct Steel Tower or Monopole | Unpainted | No of Structures |  | 3176 |  |  | 1 | 2 | 2 |  | 286 | 2885 | [16 empty] | 72 | 69 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 69 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 21 | 21 | 0 | 0 | 0
142 | [5 empty] | Painted | No of Structures |  | 1646 |  |  | 1 |  |  |  | 263 | 1382 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 |  |  |  |  | Triple Circuit Steel Tower | Unpainted | No of Structures |  | 1 | [7 empty] | 1 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | [5 empty] | Painted | No of Structures |  | 2 | [7 empty] | 2 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 |  |  |  |  | Quad Circuit Steel Tower | Unpainted | No of Structures |  | 0 | [24 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | [5 empty] | Painted | No of Structures |  | 2 | [7 empty] | 2 | [16 empty] | 2 | 0 | 0 | 2 | 2 | 0 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 2 | 0 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0
147 |  |  |  | 350 kV HVDC | Single/Double Cct Steel Tower or monopole | Unpainted | No of Structures |  | 1462 |  |  | 88 |  |  | 1 |  | 1373 | [16 empty] | 0 | 13 | -1 | 0 | 10 | 0 | 2 | 25 | 2 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | -1 | 0 | 10 | 0 | 2 | 25 | 2 | 15 | 0 | 0 | 0 | 0 | 0
148 | [5 empty] | Painted | No of Structures |  | 186 | [5 empty] | 96 |  | 90 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 |  |  |  | HVDC Electrode Line | Single/Double Cct Steel Tower or monopole | Unpainted | No of Structures |  | 11 | [7 empty] | 11 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | [5 empty] | Painted | No of Structures |  | 7 | [7 empty] | 7
151 |  |  |  | Unknown | Single/Double Cct Steel Tower or monopole | Unpainted | No of Structures |  | 10 | [8 empty] | 10 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | [5 empty] | Painted | No of Structures |  | 0 | [24 empty] | 6 | 20 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 3 | 4 | 6 | 3 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 20 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0
153 |  | Transmission Lines | Tower Protective Coating | ALL | [20 empty] | 0.04268% | 47.76% | 8.988% | 8.356% | 14% | 11.74% | 4.976% | 1.396% | 2.74% | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 |  | Transmission Lines | Tower Foundation |  | Concrete foundation |  | No of Structures |  | 9395 | 36 | 18 | 131 | 9 | 2 |  |  | 3 | 9196 | [15 empty] | 138 | 94 | 53 | 205 | 187 | 141 | 193 | 141 | 143 | 182 | 142 | 142 | 0 | 121 | 161 | 0 | 121 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 94 | 53 | 205 | 187 | 141 | 193 | 141 | 143 | 182 | 142 | 142 | 0 | 0 | 0
155 |  |  |  |  | Buried Steel Grillage |  | No of Structures |  | 8196 | 92 | 16 | 25 | 27 |  |  |  |  | 8036 | [15 empty] | 125 | 16 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 110 | 110 | 0 | 7 | 2 | 0 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 16 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 110 | 110 | 67 | 0 | 0
156 |  |  |  |  | Concrete Encased Grillage |  | No of Structures |  | 5287 | 1086 | 1478 | 2012 | 708 |  |  | 1 | 2 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 |  |  |  |  | Other |  | No of Structures |  | 553 | 13 | 2 | 21 | 2 |  |  | 26 | 1 | 488 | [15 empty] | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 |  |  |  |  | Unknown |  | No of Structures |  | 72 | 3 |  | 3 | [5 empty] | 66 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 |  | Transmission Lines | Tower Foundation | Grillage | [20 empty] | 0% | 28.4% | 19.68% | 20.57% | 15% | 10.51% | 4.468% | 0.8499% | 0.5221% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 |  | Transmission Lines | Tower Foundation | Non-grillage | [20 empty] | 0.06377% | 98.49% | 0.4336% | 0.6568% | 0.2041% | 0.05739% | 0.05739% | 0.02551% | 0.00638% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 |  | Transmission Lines | Conductor |  | Copper |  | Circuit Kilometres |  | 1853 | 4 | 1 |  |  |  | 0 | 0 | 1848 | [16 empty] | 78 | 19 | 39 | 78 | 11 | 8 | 83 | 0 | 1 | 133 | 0 | 0 | 4 | 0 | 174 | 4 | 0 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 19 | 39 | 78 | 11 | 8 | 83 | 0 | 1 | 133 | 0 | 0 | 8960 | 0 | 0
162 |  |  |  |  | AAAC |  | Circuit Kilometres |  | 859 |  | 1 | 692 | 107 | 32 |  | 23 | 4 | [16 empty] | 0 | 0 | 0 | 44 | 44 | 0 | 53 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 44 | 0 | 53 | 14 | 0 | 0 | 0 | 0 | 1015 | 0 | 0
163 |  |  |  |  | ACSR |  | Circuit Kilometres |  | 13656 | 208 | 404 | 255 | 145 | 897 | 988 | 2117 | 8642 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 |  |  |  |  | Earthwire |  | Circuit Kilometres |  | 3365 | 73 | 66 | 303 | 155 | 224 | 10 | 670 | 1864 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 |  |  |  |  | OPGW ( includes areaial communications cables) |  | Circuit Kilometres | Count of Assets | 1657 | 6 | 11 | 697 | 34 | 221 | 14 | 329 | 345 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 |  |  |  |  | Other |  | Circuit Kilometres |  | 14 |  | 2 | 5 |  |  |  |  | 7 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 |  | Transmission Lines | Conductor | ALL | [20 empty] | 0.00731% | 59.54% | 12.89% | 22.69% | 3.811% | 0.4982% | 0.4573% | 0.05238% | 0.05063% | 4 | 22 | 3 | 16 | 4 | 12 | 14 | 14 | 22 | 37 | 12 | 12 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 22 | 3 | 16 | 4 | 12 | 14 | 14 | 22 | 37 | 12 | 12 | 0 | 0 | 0
168 |  | Transmission Lines | Earthwire | ALL | [20 empty] | 0.0021% | 43.93% | 6.447% | 17.32% | 19.31% | 8.098% | 2.704% | 0.239% | 1.948% | 18 | 116 | 62 | 12 | 127 | 134 | 133 | 135 | 123 | 132 | 110 | 110 | 17 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 116 | 62 | 12 | 127 | 134 | 133 | 135 | 123 | 132 | 110 | 110 | 0 | 0 | 0
169 |  | Transmission Lines | Pole |  | Single Pole (steel) |  | No of Structures |  | 639 | 369 | 91 | 27 | 47 | 34 | 3 | 2 | 66 | [16 empty] | 67 | 137 | 109 | 22 | 197 | 122 | 129 | 134 | 144 | 135 | 112 | 112 | 16 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 137 | 109 | 22 | 197 | 122 | 129 | 134 | 144 | 135 | 112 | 112 | 66 | 0 | 0
170 |  |  |  |  | Single Pole (wood/concrete) |  | No of Structures |  | 6624 | 170 | 184 | 258 | 1109 | 1392 | 1979 | 502 | 1010 | 20 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 |  |  |  |  | Pi-Pole (wood/concrete/steel) |  | No of Structures |  | 5880 | 582 | 450 | 357 | 681 | 1774 | 566 | 573 | 892 | 5 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 |  |  |  |  | Unclassified |  | No of Structures |  | 62 | 9 |  | 6 | 9 | 14 | 6 | 3 | 7 | 8 | [15 empty] | 0 | 0 | 0 | 136.65 | 196.65 | 166.8 | 177 | 189.45 | 204.75 | 241 | 231 | 251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 136.65 | 196.65 | 166.8 | 177 | 189.45 | 204.75 | 241 | 231 | 251 | 0 | 0 | 0
173 |  | Transmission Lines | Pole | ALL | [20 empty] | 0% | 79.9% | 1.689% | 5.673% | 8.514% | 3.454% | 0.356% | 0.00757% | 0.409% | 710 | 809 | 569 | 774.35 | 1114.35 | 945.2 | 1003 | 1073.55 | 1160.25 | 1205 | 1157 | 1256 | 91 | 204 | 201 | 91 | 204 | 201 | 0 | 0 | 0 | 0 | 0 | 0 | 710 | 809 | 569 | 774.35 | 1114.35 | 945.2 | 1003 | 1073.55 | 1160.25 | 1205 | 1157 | 1256 | 65 | 0 | 0
174 |  | Transmission Lines | Insulators |  | Composite |  | No. of insulator circuits sets |  | 10593 | 561 | 1043 | 1070 | 3837 | 2811 | 234 | 297 | 679 | 61 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 |  |  |  |  | Glass and Porcelain |  | No. of insulator circuits sets |  | 41547 | 4559 | 3882 | 2854 | 2880 | 3962 | 4904 | 3562 | 14938 | 6 | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 |  |  |  |  | Unknown |  | No. of insulator circuits sets |  | 680 | 306 | 129 | 220 | 8 | 5 | 1 | 1 | 10 | [16 empty] | 414 | 237 | 438 | 44 | 337 | 475 | 475 | 475 | 475 | 475 | 475 | 475 | 15 | 57 | 51 | 15 | 57 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 414 | 237 | 438 | 44 | 337 | 475 | 475 | 475 | 475 | 475 | 475 | 475 | 3 | 0 | 0
177 |  | Transmission Lines | Insulators | ALL | [20 empty] | 0.216% | 65.92% | 4.899% | 10.85% | 11.08% | 4.677% | 1.271% | 0.591% | 0.4982% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 |  | Transmission Lines | Attachment Points | ALL |  |  |  |  | 64449 | 4319 | 3058 | 2994 | 377 | 1264 | 1659 | 8303 | 42443 | 32 | [6 empty] | 0.0299% | 41.27% | 5.145% | 17.53% | 24.15% | 7.661% | 1.613% | 0.5362% | 2.063% | 0.20055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.20055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179
180
181 |  | G6(ii): Transmission Line Terrain factor and Corrosion Zones
182 |  |  | Corrosion Zones |  |  | Route length ( kM)
183 |  |  |  | Extreme |  | 114
184 |  |  |  | Very Severe |  | 863
185 |  |  |  | Severe |  | 1624
186 |  |  |  | Moderate |  | 5571
187 |  |  |  | Low |  | 1469
188 |  |  |  | Benign |  | 687
189 |  |  |  | Unknown |  | 26
190
191 |  |  | Terrain |  |  | Route length ( kM)
192 |  |  |  | Flat |  | n/a
193 |  |  |  | Hilly |  | n/a
194 |  |  |  | Mountainous |  | n/a
195 |  |  |  | Rolling |  | n/a
196 |  |  |  | Steep |  | n/a
197 |  |  |  | Urban |  | n/a
198 |  |  |  | Note: these terrain attributes are associated by Transpower with tower foundations, not on spans which have lengths.
Please note:
Some rows above have been added by Transpower to complete the data set. Those rows have been coloured orange.

## G7. AMMAT
[13 empty] | Transpower |  | Disclosure Date |  | 2026-10-23
SCHEDULE G7: ASSET MANAGEMENT MATURITY ASSESSMENT TOOL (AMMAT) | [14 empty] | Disclosure Year (year ended) |  | 2026-06-30
ref
5 |  | Question No. (See note 1) | Function | Question | Column1 | Column2 | Maturity Level 0 | Maturity Level 1 | Maturity Level 2 | Maturity Level 3 | Maturity Level 4 | Why | Who | Record/documented Information | User Guidance | Evidence—Summary | Score
6 |  | 3 | Asset management policy | To what extent has an asset management policy been documented, authorised and communicated? |  |  | The organisation does not have a documented asset management policy. | The organisation has an asset management policy, but it has not been authorised by top management, or it is not influencing the management of the assets. | The organisation has an asset management policy, which has been authorised by top management, but it has had limited circulation. It may be in use to influence development of strategy and planning but its effect is limited. | The asset management policy is authorised by top management, is widely and effectively communicated to all relevant employees and stakeholders, and used to make these persons aware of their asset related obligations. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Widely used AM practice standards require an organisation to document, authorise and communicate its asset management policy (eg, as required in PAS 55 para 4.2 i). A key pre-requisite of any robust policy is that the organisation's top management must be seen to endorse and fully support it. Also vital to the effective implementation of the policy, is to tell the appropriate people of its content and their obligations under it. Where an organisation outsources some of its asset-related activities, then these people and their organisations must equally be made aware of the policy's content. Also, there may be other stakeholders, such as regulatory authorities and shareholders who should be made aware of it. | Top management. The management team that has overall responsibility for asset management. | The organisation's asset management policy, its organisational strategic plan, documents indicating how the asset management policy was based upon the needs of the organisation and evidence of communication. | Asset Management Policy | Transpower's Asset Management Policy has been endorsed by Top Management and is consistent with Transpower's Statement of Corporate Intent, corporate policies, and the requirements of ISO:55001. The Asset Management Policy guides Transpower’s asset management strategies and plans, and is widely communicated to stakeholders, employees, and the public. | 3
7 |  | 10 | Asset management strategy | What has the organisation done to ensure that its asset management strategy is consistent with other appropriate organisational policies and strategies, and the needs of stakeholders? |  |  | The organisation has not considered the need to ensure that its asset management strategy is appropriately aligned with the organisation's other organisational policies and strategies or with stakeholder requirements. OR The organisation does not have an asset management strategy. | The need to align the asset management strategy with other organisational policies and strategies as well as stakeholder requirements is understood and work has started to identify the linkages or to incorporate them in the drafting of asset management strategy. | Some of the linkages between the long-term asset management strategy and other organisational policies, strategies and stakeholder requirements are defined but the work is fairly well advanced but still incomplete. | All linkages are in place and evidence is available to demonstrate that, where appropriate, the organisation's asset management strategy is consistent with its other organisational policies and strategies. The organisation has also identified and considered the requirements of relevant stakeholders. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | In setting an organisation's asset management strategy, it is important that it is consistent with any other policies and strategies that the organisation has and has taken into account the requirements of relevant stakeholders. This question examines to what extent the asset management strategy is consistent with other organisational policies and strategies (eg, as required by PAS 55 para 4.3.1 b) and has taken account of stakeholder requirements as required by PAS 55 para 4.3.1 c). Generally, this will take into account the same polices, strategies and stakeholder requirements as covered in drafting the asset management policy but at a greater level of detail. | Top management. The organisation's strategic planning team. The management team that has overall responsibility for asset management. | The organisation's asset management strategy document and other related organisational policies and strategies. Other than the organisation's strategic plan, these could include those relating to health and safety, environmental, etc. Results of stakeholder consultation. | Grid Business Strategic Asset Management Plan (SAMP) | Transpower's Grid Business Strategic Asset Management Plan (SAMP) has been endorsed by Top Management and is aligned with Transpower's corporate strategy and objectives. The SAMP guides the development of the asset strategies, the asset management plan, and operational plans. | 3
8 |  | 11 | Asset management strategy | In what way does the organisation's asset management strategy take account of the lifecycle of the assets, asset types and asset systems over which the organisation has stewardship? |  |  | The organisation has not considered the need to ensure that its asset management strategy is produced with due regard to the lifecycle of the assets, asset types or asset systems that it manages. OR The organisation does not have an asset management strategy. | The need is understood, and the organisation is drafting its asset management strategy to address the lifecycle of its assets, asset types and asset systems. | The long-term asset management strategy takes account of the lifecycle of some, but not all, of its assets, asset types and asset systems. | The asset management strategy takes account of the lifecycle of all of its assets, asset types and asset systems. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Good asset stewardship is the hallmark of an organisation compliant with widely used AM standards. A key component of this is the need to take account of the lifecycle of the assets, asset types and asset systems. (For example, this requirement is recognised in 4.3.1 d) of PAS 55). This question explores what an organisation has done to take lifecycle into account in its asset management strategy. | Top management. People in the organisation with expert knowledge of the assets, asset types, asset systems and their associated life-cycles. The management team that has overall responsibility for asset management. Those responsible for developing and adopting methods and processes used in asset management | The organisation's documented asset management strategy and supporting working documents. | Asset Class Strategies | When establishing the asset management strategy for each of the asset class strategies Transpower has considered the asset-related risk, the physical condition of the assets, age profile, flexibility and suitability of the assets and their intended use. Other items that have been considered are asset type, criticality, resilience, and historical asset related information such as reliability, maintenance records and operational performance. In terms of the asset lifecycle, in addition to age and condition assessment, Transpower considers growth and customer demand such as electrification to check if the asset is able to meet the present and expected service need of our customers. | 3
9 |  | 26 | Asset management plan(s) | How does the organisation establish and document its asset management plan(s) across the life cycle activities of its assets and asset systems? |  |  | The organisation does not have an identifiable asset management plan(s) covering asset systems and critical assets. | The organisation has asset management plan(s) but they are not aligned with the asset management strategy and objectives and do not take into consideration the full asset life cycle (including asset creation, acquisition, enhancement, utilisation, maintenance decommissioning and disposal). | The organisation is in the process of putting in place comprehensive, documented asset management plan(s) that cover all life cycle activities, clearly aligned to asset management objectives and the asset management strategy. | Asset management plan(s) are established, documented, implemented and maintained for asset systems and critical assets to achieve the asset management strategy and asset management objectives across all life cycle phases. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | The asset management strategy need to be translated into practical plan(s) so that all parties know how the objectives will be achieved. The development of plan(s) will need to identify the specific tasks and activities required to optimize costs, risks and performance of the assets and/or asset system(s), when they are to be carried out and the resources required. | The management team with overall responsibility for the asset management system. Operations, maintenance and engineering managers. | The organisation's asset management plan(s). | Asset Management Plan | The Asset Management Plan is reviewed annually, and this process takes into consideration the requirements of the: - Asset Management Policy - Corporate policies (including Risk Management Policy) -Grid Business Strategic Asset Management Plan (SAMP) and asset management objectives - Asset Class Strategies and objectives - Financial and resource capabilities or constraints - Legal, regulatory, statutory and other asset management requirements The overall strategies for managing an asset class across its lifecycle are documented in the respective Asset Class Strategies. | 3
10 |  | 27 | Asset management plan(s) | How has the organisation communicated its plan(s) to all relevant parties to a level of detail appropriate to the receiver's role in their delivery? |  |  | The organisation does not have plan(s) or their distribution is limited to the authors. | The plan(s) are communicated to some of those responsible for delivery of the plan(s). OR Communicated to those responsible for delivery is either irregular or ad-hoc. | The plan(s) are communicated to most of those responsible for delivery but there are weaknesses in identifying relevant parties resulting in incomplete or inappropriate communication. The organisation recognises improvement is needed as is working towards resolution. | The plan(s) are communicated to all relevant employees, stakeholders and contracted service providers to a level of detail appropriate to their participation or business interests in the delivery of the plan(s) and there is confirmation that they are being used effectively. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Plans will be ineffective unless they are communicated to all those, including contracted suppliers and those who undertake enabling function(s). The plan(s) need to be communicated in a way that is relevant to those who need to use them. | The management team with overall responsibility for the asset management system. Delivery functions and suppliers. | Distribution lists for plan(s). Documents derived from plan(s) which detail the receivers role in plan delivery. Evidence of communication. | Asset Management Plan, Transmission Planning Report, Customer Engagement Plans | The Asset Management Plan (as part of the annual Integrated Transmission Plan) is annually distributed to Transpower's stakeholders, regulatory bodies, finance team, communications team, and all asset and engineering teams across the business. The Asset Management Plan is also available for all employees, customers and members of the public on Transpower's website. Transpower’s Customer Engagement Plans outline the approach to our engagement with each of our connected customers, including the communication of investments, service levels, asset management plans, works delivery plan and outage plans. | 3
11 |  | 29 | Asset management plan(s) | How are designated responsibilities for delivery of asset plan actions documented? |  |  | The organisation has not documented responsibilities for delivery of asset plan actions. | Asset management plan(s) inconsistently document responsibilities for delivery of plan actions and activities and/or responsibilities and authorities for implementation inadequate and/or delegation level inadequate to ensure effective delivery and/or contain misalignments with organisational accountability. | Asset management plan(s) consistently document responsibilities for the delivery of actions but responsibility/authority levels are inappropriate/ inadequate, and/or there are misalignments within the organisation. | Asset management plan(s) consistently document responsibilities for the delivery actions and there is adequate detail to enable delivery of actions. Designated responsibility and authority for achievement of asset plan actions is appropriate. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | The implementation of asset management plan(s) relies on (1) actions being clearly identified, (2) an owner allocated and (3) that owner having sufficient delegated responsibility and authority to carry out the work required. It also requires alignment of actions across the organisation. This question explores how well the plan(s) set out responsibility for delivery of asset plan actions. | The management team with overall responsibility for the asset management system. Operations, maintenance and engineering managers. If appropriate, the performance management team. | The organisation's asset management plan(s). Documentation defining roles and responsibilities of individuals and organisational departments. | Grid Business Asset Management System Framework | Designated responsibilities for delivery of the AMP are documented and set out in the Grid Business Asset Management System Framework. The EGM Grid Development has overall responsibility for preparation, drafting and implementation of the AMP. The EGMs Grid Delivery and Operations have responsibility for the Delivery of the plan and operation of the assets. Responsibilities are also documented in employee position descriptions, and contracts with our service providers and consultants. | 3
12 |  | 31 | Asset management plan(s) | What has the organisation done to ensure that appropriate arrangements are made available for the efficient and cost effective implementation of the plan(s)? (Note this is about resources and enabling support) |  |  | The organisation has not considered the arrangements needed for the effective implementation of plan(s). | The organisation recognises the need to ensure appropriate arrangements are in place for implementation of asset management plan(s) and is in the process of determining an appropriate approach for achieving this. | The organisation has arrangements in place for the implementation of asset management plan(s) but the arrangements are not yet adequately efficient and/or effective. The organisation is working to resolve existing weaknesses. | The organisation's arrangements fully cover all the requirements for the efficient and cost effective implementation of asset management plan(s) and realistically address the resources and timescales required, and any changes needed to functional policies, standards, processes and the asset management information system. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | It is essential that the plan(s) are realistic and can be implemented, which requires appropriate resources to be available and enabling mechanisms in place. This question explores how well this is achieved. The plan(s) not only need to consider the resources directly required and timescales, but also the enabling activities, including for example, training requirements, supply chain capability and procurement timescales. | The management team with overall responsibility for the asset management system. Operations, maintenance and engineering managers. If appropriate, the performance management team. If appropriate, the performance management team. Where appropriate the procurement team and service providers working on the organisation's asset-related activities. | The organisation's asset management plan(s). Documented processes and procedures for the delivery of the asset management plan. | Grid Works Plan, Outage Plan, Transpower Grid Delivery Works Planning Process | The Grid Works Plan and the Outage Plan provide a forecast of work and outage requirements for the grid. The Grid Works Plan is a rolling two-year plan derived from the Asset Management Plan. A two year work planning process is initiated annually in collaboration with our service providers, so that work can be planned and scheduled in more detail. These two-year plans and schedules are key inputs to the annual outage planning process which is managed by our operations division. | 3
13 |  | 33 | Contingency planning | What plan(s) and procedure(s) does the organisation have for identifying and responding to incidents and emergency situations and ensuring continuity of critical asset management activities? |  |  | The organisation has not considered the need to establish plan(s) and procedure(s) to identify and respond to incidents and emergency situations. | The organisation has some ad-hoc arrangements to deal with incidents and emergency situations, but these have been developed on a reactive basis in response to specific events that have occurred in the past. | Most credible incidents and emergency situations are identified. Either appropriate plan(s) and procedure(s) are incomplete for critical activities or they are inadequate. Training/ external alignment may be incomplete. | Appropriate emergency plan(s) and procedure(s) are in place to respond to credible incidents and manage continuity of critical asset management activities consistent with policies and asset management objectives. Training and external agency alignment is in place. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Widely used AM practice standards require that an organisation has plan(s) to identify and respond to emergency situations. Emergency plan(s) should outline the actions to be taken to respond to specified emergency situations and ensure continuity of critical asset management activities including the communication to, and involvement of, external agencies. This question assesses if, and how well, these plan(s) triggered, implemented and resolved in the event of an incident. The plan(s) should be appropriate to the level of risk as determined by the organisation's risk assessment methodology. It is also a requirement that relevant personnel are competent and trained. | The manager with responsibility for developing emergency plan(s). The organisation's risk assessment team. People with designated duties within the plan(s) and procedure(s) for dealing with incidents and emergency situations. | The organisation's plan(s) and procedure(s) for dealing with emergencies. The organisation's risk assessments and risk registers. | Asset Management Plan, Business continuity plans, Preparedness Plans | Transpower’s planning and response to network/asset failures and system emergency events is underpinned by our obligations as a lifeline utility with special post event functions under the CDEM (Civil Defense and Emergency Management) Act and EIPC (Electricity Industry Participation Code). To meet these obligations Transpower has plans and resources in place to coordinate with national and regional civil defence event management plans. Readiness plans are developed, maintained, rehearsed, and reviewed when enacted. This also includes plans for corporate business continuity, grid operations, high risk outages and specific failure plans. To meet our Readiness plan objectives requires Transpower to maintain a significant value of strategic spares for critical asset failures and urgent replacement and repairs. Budgets to meet our readiness plans are contained within our AMP. Emergency response and restoration contingency budgets are also set in the AMP, the risk policies are outlined in the AMP. Contingency budgets are set aside each year to cover unforeseen emergency works. Also, improvement opportunities are tracked via the Major Hazard Risk reviews. Transpower also applies the Coordinated Incident Management System (CIMS) used by NEMA. | 3
14 |  | 37 | Structure, authority and responsibilities | What has the organisation done to appoint member(s) of its management team to be responsible for ensuring that the organisation's assets deliver the requirements of the asset management strategy, objectives and plan(s)? |  |  | Top management has not considered the need to appoint a person or persons to ensure that the organisation's assets deliver the requirements of the asset management strategy, objectives and plan(s). | Top management understands the need to appoint a person or persons to ensure that the organisation's assets deliver the requirements of the asset management strategy, objectives and plan(s). | Top management has appointed an appropriate people to ensure the assets deliver the requirements of the asset management strategy, objectives and plan(s) but their areas of responsibility are not fully defined and/or they have insufficient delegated authority to fully execute their responsibilities. | The appointed person or persons have full responsibility for ensuring that the organisation's assets deliver the requirements of the asset management strategy, objectives and plan(s). They have been given the necessary authority to achieve this. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | In order to ensure that the organisation's assets and asset systems deliver the requirements of the asset management policy, strategy and objectives responsibilities need to be allocated to appropriate people who have the necessary authority to fulfil their responsibilities. (This question, relates to the organisation's assets eg, para b), s 4.4.1 of PAS 55, making it therefore distinct from the requirement contained in para a), s 4.4.1 of PAS 55). | Top management. People with management responsibility for the delivery of asset management policy, strategy, objectives and plan(s). People working on asset-related activities. | Evidence that managers with responsibility for the delivery of asset management policy, strategy, objectives and plan(s) have been appointed and have assumed their responsibilities. Evidence may include the organisation's documents relating to its asset management system, organisational charts, job descriptions of post-holders, annual targets/objectives and personal development plan(s) of post-holders as appropriate. | Grid Business Asset Management System Framework, Grid Management Operating System (MOS) | The grid business asset management system framework, together with the grid management operating system, detail the roles and responsibilities for the management of the asset management functions so that the grid business can meet the objectives of the business. | 3
15 |  | 40 | Structure, authority and responsibilities | What evidence can the organisation's top management provide to demonstrate that sufficient resources are available for asset management? |  |  | The organisation's top management has not considered the resources required to deliver asset management. | The organisations top management understands the need for sufficient resources but there are no effective mechanisms in place to ensure this is the case. | A process exists for determining what resources are required for its asset management activities and in most cases these are available but in some instances resources remain insufficient. | An effective process exists for determining the resources needed for asset management and sufficient resources are available. It can be demonstrated that resources are matched to asset management requirements. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Optimal asset management requires top management to ensure sufficient resources are available. In this context the term 'resources' includes manpower, materials, funding and service provider support. | Top management. The management team that has overall responsibility for asset management. Risk management team. The organisation's managers involved in day-to-day supervision of asset-related activities, such as frontline managers, engineers, foremen and chargehands as appropriate. | Evidence demonstrating that asset management plan(s) and/or the process(es) for asset management plan implementation consider the provision of adequate resources in both the short and long term. Resources include funding, materials, equipment, services provided by third parties and personnel (internal and service providers) with appropriate skills competencies and knowledge. | Grid Works Plan | Transpower understands the need to provide enough resources; a budget has been allocated for resources such as staff, material, equipment, and services from third parties. Transpower endeavours to align the staffing, the structure, and skills with the AMP to ensure effective and efficient implementation. The resource needs are reviewed throughout the planning and programming processes. Our processes include internal and external workforce planning to support the growth in work forecast over the next 15 years and is also a key consideration in our regulatory funding applications and procurement. Moreover, Transpower assessed impacts from decarbonisation and electrification and identified the increase and resource requirements as part of its RCP4 submission, and these impacts are regularly reviewed. | 3
16 |  | 42 | Structure, authority and responsibilities | To what degree does the organisation's top management communicate the importance of meeting its asset management requirements? |  |  | The organisation's top management has not considered the need to communicate the importance of meeting asset management requirements. | The organisations top management understands the need to communicate the importance of meeting its asset management requirements but does not do so. | Top management communicates the importance of meeting its asset management requirements but only to parts of the organisation. | Top management communicates the importance of meeting its asset management requirements to all relevant parts of the organisation. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Widely used AM practice standards require an organisation to communicate the importance of meeting its asset management requirements such that personnel fully understand, take ownership of, and are fully engaged in the delivery of the asset management requirements (eg, PAS 55 s 4.4.1 g). | Top management. The management team that has overall responsibility for asset management. People involved in the delivery of the asset management requirements. | Evidence of such activities as road shows, written bulletins, workshops, team talks and management walk-abouts would assist an organisation to demonstrate it is meeting this requirement of PAS 55. | Internal website - recorded archive of weekly and monthly roadshows as well as regular staff newsletters/updates. | Top management communicate the importance of meeting its asset management requirements during weekly CEO & EGM updates, and two-monthly management roadshow. The tracking against service performance measures and safety is always the first item discussed before reporting other Asset Management metrics. | 3
17 |  | 45 | Outsourcing of asset management activities | Where the organisation has outsourced some of its asset management activities, how has it ensured that appropriate controls are in place to ensure the compliant delivery of its organisational strategic plan, and its asset management policy and strategy? |  |  | The organisation has not considered the need to put controls in place. | The organisation controls its outsourced activities on an ad-hoc basis, with little regard for ensuring for the compliant delivery of the organisational strategic plan and/or its asset management policy and strategy. | Controls systematically considered but currently only provide for the compliant delivery of some, but not all, aspects of the organisational strategic plan and/or its asset management policy and strategy. Gaps exist. | Evidence exists to demonstrate that outsourced activities are appropriately controlled to provide for the compliant delivery of the organisational strategic plan, asset management policy and strategy, and that these controls are integrated into the asset management system | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Where an organisation chooses to outsource some of its asset management activities, the organisation must ensure that these outsourced process(es) are under appropriate control to ensure that all the requirements of widely used AM standards (eg, PAS 55) are in place, and the asset management policy, strategy objectives and plan(s) are delivered. This includes ensuring capabilities and resources across a time span aligned to life cycle management. The organisation must put arrangements in place to control the outsourced activities, whether it be to external providers or to other in-house departments. This question explores what the organisation does in this regard. | Top management. The management team that has overall responsibility for asset management. The manager(s) responsible for the monitoring and management of the outsourced activities. People involved with the procurement of outsourced activities. The people within the organisations that are performing the outsourced activities. The people impacted by the outsourced activity. | The organisation's arrangements that detail the compliance required of the outsourced activities. For example, this this could form part of a contract or service level agreement between the organisation and the suppliers of its outsourced activities. Evidence that the organisation has demonstrated to itself that it has assurance of compliance of outsourced activities. | Service Agreements with Service Providers and Engineering Consultants | Asset management tasks are outsourced to external providers, including engineering design, service delivery (asset inspections and maintenance) and construction. These contracts were retendered in 2022 establishing a more effective contracting and engagement model ensuring an all of business approach. These contracts also include formal requirements for agreed self-audit programmes, and regular reviews of contract requirements are undertaken. The Partnering Charter has created a collaborative culture with the external providers and performance is reviewed during various meetings which include representatives from multiple levels of the organisation from Executive General Managers to operational staff. The performance metrics are also linked to the incentive scheme with the Service Providers. Auditing of external providers is ongoing and provides valuable insight into work practice improvements. | 3
18 |  | 48 | Training, awareness and competence | How does the organisation develop plan(s) for the human resources required to undertake asset management activities - including the development and delivery of asset management strategy, process(es), objectives and plan(s)? |  |  | The organisation has not recognised the need for assessing human resources requirements to develop and implement its asset management system. | The organisation has recognised the need to assess its human resources requirements and to develop a plan(s). There is limited recognition of the need to align these with the development and implementation of its asset management system. | The organisation has developed a strategic approach to aligning competencies and human resources to the asset management system including the asset management plan but the work is incomplete or has not been consistently implemented. | The organisation can demonstrate that plan(s) are in place and effective in matching competencies and capabilities to the asset management system including the plan for both internal and contracted activities. Plans are reviewed integral to asset management system process(es). | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | There is a need for an organisation to demonstrate that it has considered what resources are required to develop and implement its asset management system. There is also a need for the organisation to demonstrate that it has assessed what development plan(s) are required to provide its human resources with the skills and competencies to develop and implement its asset management systems. The timescales over which the plan(s) are relevant should be commensurate with the planning horizons within the asset management strategy considers e.g. if the asset management strategy considers 5, 10 and 15 year time scales then the human resources development plan(s) should align with these. Resources include both 'in house' and external resources who undertake asset management activities. | Senior management responsible for agreement of plan(s). Managers responsible for developing asset management strategy and plan(s). Managers with responsibility for development and recruitment of staff (including HR functions). Staff responsible for training. Procurement officers. Contracted service providers. | Evidence of analysis of future work load plan(s) in terms of human resources. Document(s) containing analysis of the organisation's own direct resources and contractors resource capability over suitable timescales. Evidence, such as minutes of meetings, that suitable management forums are monitoring human resource development plan(s). Training plan(s), personal development plan(s), contract and service level agreements. | People Strategy | Contractors Service Provider/ Field Workers Transpower is a registered Private Training Enterprise (PTE) developing and delivering compliance and trade training to contracted Service Provider and subcontractor field workers who work on Transpower transmission assets. Grid Skills train all our Service Providers in the core competencies required to work on our assets (i.e. tower climbing, substation maintainer). Service Providers provide workforce plans annually to demonstrate they have the right number of people with the right skills to deliver work to plan | 3
19 |  | 49 | Training, awareness and competence | How does the organisation identify competency requirements and then plan, provide and record the training necessary to achieve the competencies? |  |  | The organisation does not have any means in place to identify competency requirements. | The organisation has recognised the need to identify competency requirements and then plan, provide and record the training necessary to achieve the competencies. | The organisation is the process of identifying competency requirements aligned to the asset management plan(s) and then plan, provide and record appropriate training. It is incomplete or inconsistently applied. | Competency requirements are in place and aligned with asset management plan(s). Plans are in place and effective in providing the training necessary to achieve the competencies. A structured means of recording the competencies achieved is in place. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Widely used AM standards require that organisations to undertake a systematic identification of the asset management awareness and competencies required at each level and function within the organisation. Once identified the training required to provide the necessary competencies should be planned for delivery in a timely and systematic way. Any training provided must be recorded and maintained in a suitable format. Where an organisation has contracted service providers in place then it should have a means to demonstrate that this requirement is being met for their employees. (eg, PAS 55 refers to frameworks suitable for identifying competency requirements). | Senior management responsible for agreement of plan(s). Managers responsible for developing asset management strategy and plan(s). Managers with responsibility for development and recruitment of staff (including HR functions). Staff responsible for training. Procurement officers. Contracted service providers. | Evidence of an established and applied competency requirements assessment process and plan(s) in place to deliver the required training. Evidence that the training programme is part of a wider, co-ordinated asset management activities training and competency programme. Evidence that training activities are recorded and that records are readily available (for both direct and contracted service provider staff) e.g. via organisation wide information system or local records database. | Progression Pathways and Competence Frameworks | Transpower has a progression pathway for engineers, project managers and asset planners. Managers are responsible for workforce planning to ensure that the skills and resources required to meet the business needs now and in the future are meet including team succession planning. This workforce planning is underpinned by progression pathways and the quarterly performance process undertaken with members of the staff. This ensures all teams have a suitable mix of experience, skills, etc to successfully deliver their work programme, and to actively grow the next generation of staff. There is a competency framework for Project Management, Asset Management and for Grid Operators. Asset management training plans have been established for asset management roles and related training courses established, including an asset management fundamentals course. | 3
20 |  | 50 | Training, awareness and competence | How does the organization ensure that persons under its direct control undertaking asset management related activities have an appropriate level of competence in terms of education, training or experience? |  |  | The organization has not recognised the need to assess the competence of person(s) undertaking asset management related activities. | Competency of staff undertaking asset management related activities is not managed or assessed in a structured way, other than formal requirements for legal compliance and safety management. | The organization is in the process of putting in place a means for assessing the competence of person(s) involved in asset management activities including contractors. There are gaps and inconsistencies. | Competency requirements are identified and assessed for all persons carrying out asset management related activities - internal and contracted. Requirements are reviewed and staff reassessed at appropriate intervals aligned to asset management requirements. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | A critical success factor for the effective development and implementation of an asset management system is the competence of persons undertaking these activities. organisations should have effective means in place for ensuring the competence of employees to carry out their designated asset management function(s). Where an organisation has contracted service providers undertaking elements of its asset management system then the organisation shall assure itself that the outsourced service provider also has suitable arrangements in place to manage the competencies of its employees. The organisation should ensure that the individual and corporate competencies it requires are in place and actively monitor, develop and maintain an appropriate balance of these competencies. | Managers, supervisors, persons responsible for developing training programmes. Staff responsible for procurement and service agreements. HR staff and those responsible for recruitment. | Evidence of a competency assessment framework that aligns with established frameworks such as the asset management Competencies Requirements Framework (Version 2.0); National Occupational Standards for Management and Leadership; UK Standard for Professional Engineering Competence, Engineering Council, 2005. | Grid Skills Learner Pathways | Everyone working on Transpower assets must be deemed competent. Transpower Employees Transpower employees who access Transpower sites are signed off for access by a Regional Service Manager upon the successful completion of training. Transpower's strategy to overcome the skills shortage is to encourage personnel development and training of current employees. Transpower has a programme to attract engineering graduates through an engineering graduate programme. All staff have training and development plans which are agreed with their manager. Contractors Service Provider/ Field Workers Service Specification defines the minimum training and competency requirements for Transpower field work. Training is also aligned to required industry regulations and codes of practice. Transpower Grid Skills holds NZQA programme approval and accreditation for the following training; Substation Maintainer, Line Mechanic, Tower Structure Maintainer and Power Technician. Where NZQA qualifications are not used Grid Skills develops and assures training through the Grid Skills Quality Management System. On successful completion of required training courses and acquiring suitable field experience, field workers are deemed competent by their employer based on that employers’ competency processes which are audited by Transpower as part of its regular Service Provider audit process. | 3
21 |  | 53 | Communication, participation and consultation | How does the organisation ensure that pertinent asset management information is effectively communicated to and from employees and other stakeholders, including contracted service providers? |  |  | The organisation has not recognised the need to formally communicate any asset management information. | There is evidence that the pertinent asset management information to be shared along with those to share it with is being determined. | The organisation has determined pertinent information and relevant parties. Some effective two way communication is in place but as yet not all relevant parties are clear on their roles and responsibilities with respect to asset management information. | Two way communication is in place between all relevant parties, ensuring that information is effectively communicated to match the requirements of asset management strategy, plan(s) and process(es). Pertinent asset information requirements are regularly reviewed. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Widely used AM practice standards require that pertinent asset management information is effectively communicated to and from employees and other stakeholders including contracted service providers. Pertinent information refers to information required in order to effectively and efficiently comply with and deliver asset management strategy, plan(s) and objectives. This will include for example the communication of the asset management policy, asset performance information, and planning information as appropriate to contractors. | Top management and senior management representative(s), employee's representative(s), employee's trade union representative(s); contracted service provider management and employee representative(s); representative(s) from the organisation's Health, Safety and Environmental team. Key stakeholder representative(s). | Asset management policy statement prominently displayed on notice boards, intranet and internet; use of organisation's website for displaying asset performance data; evidence of formal briefings to employees, stakeholders and contracted service providers; evidence of inclusion of asset management issues in team meetings and contracted service provider contract meetings; newsletters, etc. | Grid Management Operating System (MOS), Customer Engagement Plan | The grid management operating system documents the communication mechanisms between the asset management functions at Transpower. Transpower’s Customer Engagement Plans document communication between Transpower and its connected customers. The plans includes six principles of engagement including the maintenance of transparent and collaborative engagement, communication channels and engagement plans, including an annual customer engagement survey. Every two years, Transpower conducts a wider stakeholder engagement survey. Transpower consults with customers on their desired level of service as part of the five yearly regulatory reset. This results in a set of service performance measures, which are proposed to the Commerce Commission for approval. Transpower’s Management Operating System The grid business asset management system framework, together with the grid management operating system, detail the roles and responsibilities for the communication of asset management information between employees as well as external providers. The TPR (Transmission Planning Report) is published annually and sets out our plan for the enhancement and development of the network over the next 15 years. TPR Envision is publically available and uses GIS mapping interface to make it easier for customers and interested parties to understand the grid plans. | 3
22 |  | 59 | Asset Management System documentation | What documentation has the organisation established to describe the main elements of its asset management system and interactions between them? |  |  | The organisation has not established documentation that describes the main elements of the asset management system. | The organisation is aware of the need to put documentation in place and is in the process of determining how to document the main elements of its asset management system. | The organisation in the process of documenting its asset management system and has documentation in place that describes some, but not all, of the main elements of its asset management system and their interaction. | The organisation has established documentation that comprehensively describes all the main elements of its asset management system and the interactions between them. The documentation is kept up to date. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Widely used AM practice standards require an organisation maintain up to date documentation that ensures that its asset management systems (ie, the systems the organisation has in place to meet the standards) can be understood, communicated and operated. (eg, s 4.5 of PAS 55 requires the maintenance of up to date documentation of the asset management system requirements specified throughout s 4 of PAS 55). | The management team that has overall responsibility for asset management. Managers engaged in asset management activities. | The documented information describing the main elements of the asset management system (process(es)) and their interaction. | Grid Business Asset Management System Framework, Grid Management Operating System (MOS) | Transpower's asset management system is well documented through its grid business asset management system framework, grid management operating system and the supporting information on its intranet. | 3
23 |  | 62 | Information management | What has the organisation done to determine what its asset management information system(s) should contain in order to support its asset management system? |  |  | The organisation has not considered what asset management information is required. | The organisation is aware of the need to determine in a structured manner what its asset information system should contain in order to support its asset management system and is in the process of deciding how to do this. | The organisation has developed a structured process to determine what its asset information system should contain in order to support its asset management system and has commenced implementation of the process. | The organisation has determined what its asset information system should contain in order to support its asset management system. The requirements relate to the whole life cycle and cover information originating from both internal and external sources. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Effective asset management requires appropriate information to be available. Widely used AM standards therefore require the organisation to identify the asset management information it requires in order to support its asset management system. Some of the information required may be held by suppliers. The maintenance and development of asset management information systems is a poorly understood specialist activity that is akin to IT management but different from IT management. This group of questions provides some indications as to whether the capability is available and applied. Note: To be effective, an asset information management system requires the mobilisation of technology, people and process(es) that create, secure, make available and destroy the information required to support the asset management system. | The organisation's strategic planning team. The management team that has overall responsibility for asset management. Information management team. Operations, maintenance and engineering managers | Details of the process the organisation has employed to determine what its asset information system should contain in order to support its asset management system. Evidence that this has been effectively implemented. | Asset Information Strategy | Transpower has determined what its asset management information system should contain based on our current and future needs, the increasing requirements from various regulatory bodies, the safety management system requirements, as well as the intellectual knowledge of staff. Transpower has an established data and analytics operating model to ensure asset information is, and continues to be, fit for purpose and of demonstrated value to asset management. This role is supported by a dedicated Asset Data Product Owner role, in the Asset Information team, to specify new asset data products. | 3
24 |  | 63 | Information management | How does the organisation maintain its asset management information system(s) and ensure that the data held within it (them) is of the requisite quality and accuracy and is consistent? |  |  | There are no formal controls in place or controls are extremely limited in scope and/or effectiveness. | The organisation is aware of the need for effective controls and is in the process of developing an appropriate control process(es). | The organisation has developed a controls that will ensure the data held is of the requisite quality and accuracy and is consistent and is in the process of implementing them. | The organisation has effective controls in place that ensure the data held is of the requisite quality and accuracy and is consistent. The controls are regularly reviewed and improved where necessary. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | The response to the questions is progressive. A higher scale cannot be awarded without achieving the requirements of the lower scale. This question explores how the organisation ensures that information management meets widely used AM practice requirements (eg, s 4.4.6 (a), (c) and (d) of PAS 55). | The management team that has overall responsibility for asset management. Users of the organisational information systems. | The asset management information system, together with the policies, procedure(s), improvement initiatives and audits regarding information controls. | Grid Asset Information Framework | Transpower uses Maximo as its key asset information system, and this is supplemented by other asset information systems such as Geospatial, Drawings, and Photos management systems. Asset Information is considered a critical control for managing risk, and therefore we regularly assess how well the control is operating and identify and deliver continuous improvement activities. To ensure the quality and consistency of data, processes are developed and applied such that data for newly build assets is captured and validated against standards before it is entered into our core system Maximo. For some asset classes, data is reviewed by Subject Matter Experts prior to load. Transpower’s enterprise-wide Data & Analytics modernisation programme has rolled out Snowflake which supporst improved Data Quality dashboards and reporting on asset data completeness and conformance to standards for review and action. Transpower Grid Delivery Quality and Compliance teams conduct real time processes for the verification of asset capability information, and conduct process, documentation, and data audits. A field mobility app (“Matai”) is used by field workers to streamline the collection of Asset Condition Assessment (CA) information. This has improved data quality by removing manual paper-based recording and office-based data entry which are prone to transcription errors. It also allows the data to be validated and corrected if necessary at the point of entry. It also provides a mechanism for trusted field staff to populate data that is missing (or correct existing data). | 3
25 |  | 64 | Information management | How has the organisation's ensured its asset management information system is relevant to its needs? |  |  | The organisation has not considered the need to determine the relevance of its management information system. At present there are major gaps between what the information system provides and the organisations needs. | The organisation understands the need to ensure its asset management information system is relevant to its needs and is determining an appropriate means by which it will achieve this. At present there are significant gaps between what the information system provides and the organisations needs. | The organisation has developed and is implementing a process to ensure its asset management information system is relevant to its needs. Gaps between what the information system provides and the organisations needs have been identified and action is being taken to close them. | The organisation's asset management information system aligns with its asset management requirements. Users can confirm that it is relevant to their needs. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Widely used AM standards need not be prescriptive about the form of the asset management information system, but simply require that the asset management information system is appropriate to the organisations needs, can be effectively used and can supply information which is consistent and of the requisite quality and accuracy. | The organisation's strategic planning team. The management team that has overall responsibility for asset management. Information management team. Users of the organisational information systems. | The documented process the organisation employs to ensure its asset management information system aligns with its asset management requirements. Minutes of information systems review meetings involving users. | Grid Asset Information Framework | Transpower's asset management information system is reviewed and aligned to current asset management requirements, it also aligns with the increasing regulatory and safety management requirements. Transpower includes in the annual business plan a budget for continual improvement of asset information. Maximo and Geospatial systems are part of a regular ICT lifecycle refresh schedule to ensure the systems continue to be well supported. A Photos and Multimedia platform collects and manages this content to align with changing technology and data collection practices. The Digital Engineering programme has delivered a new 3D model management system to improve management (and provide efficiencies) of detailed substation engineering models throughout the works delivery lifecycle. A new vegetation management system ihas been delivered. | 3
26 |  | 69 | Risk management process(es) | How has the organisation documented process(es) and/or procedure(s) for the identification and assessment of asset and asset management related risks throughout the asset life cycle? |  |  | The organisation has not considered the need to document process(es) and/or procedure(s) for the identification and assessment of asset and asset management related risks throughout the asset life cycle. | The organisation is aware of the need to document the management of asset related risk across the asset lifecycle. The organisation has plan(s) to formally document all relevant process(es) and procedure(s) or has already commenced this activity. | The organisation is in the process of documenting the identification and assessment of asset related risk across the asset lifecycle but it is incomplete or there are inconsistencies between approaches and a lack of integration. | Identification and assessment of asset related risk across the asset lifecycle is fully documented. The organisation can demonstrate that appropriate documented mechanisms are integrated across life cycle phases and are being consistently applied. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Risk management is an important foundation for proactive asset management. Its overall purpose is to understand the cause, effect and likelihood of adverse events occurring, to optimally manage such risks to an acceptable level, and to provide an audit trail for the management of risks. Widely used standards require the organisation to have process(es) and/or procedure(s) in place that set out how the organisation identifies and assesses asset and asset management related risks. The risks have to be considered across the four phases of the asset lifecycle (eg, para 4.3.3 of PAS 55). | The top management team in conjunction with the organisation's senior risk management representatives. There may also be input from the organisation's Safety, Health and Environment team. Staff who carry out risk identification and assessment. | The organisation's risk management framework and/or evidence of specific process(es) and/ or procedure(s) that deal with risk control mechanisms. Evidence that the process(es) and/or procedure(s) are implemented across the business and maintained. Evidence of agendas and minutes from risk management meetings. Evidence of feedback in to process(es) and/or procedure(s) as a result of incident investigation(s). Risk registers and assessments. | Transpower Corporate Risk Policy, Transpower Risk Management Guidelines | Transpower has identified critical risks and critical controls, and developed risk bowties to cover all aspects of its asset management activities. Bowties and the associated critical controls are aligned and integrated into the Asset Management System Framework. Bowties are reviewed at regular intervals to ensure they reflect any changes in the operating environment. Asset Health and Asset Criticality frameworks provide a view of asset failure risk. Our resilience strategy describes our known threats and major hazards, together with our strategic approaches and key objectives to managing a resilient grid. We are delivering the RCP4 proactive resilience programmes to manage these risks. | 3
27 |  | 79 | Use and maintenance of asset risk information | How does the organisation ensure that the results of risk assessments provide input into the identification of adequate resources and training and competency needs? |  |  | The organisation has not considered the need to conduct risk assessments. | The organisation is aware of the need to consider the results of risk assessments and effects of risk control measures to provide input into reviews of resources, training and competency needs. Current input is typically ad-hoc and reactive. | The organisation is in the process ensuring that outputs of risk assessment are included in developing requirements for resources and training. The implementation is incomplete and there are gaps and inconsistencies. | Outputs from risk assessments are consistently and systematically used as inputs to develop resources, training and competency requirements. Examples and evidence is available. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Widely used AM standards require that the output from risk assessments are considered and that adequate resource (including staff) and training is identified to match the requirements. It is a further requirement that the effects of the control measures are considered, as there may be implications in resources and training required to achieve other objectives. | Staff responsible for risk assessment and those responsible for developing and approving resource and training plan(s). There may also be input from the organisation's Safety, Health and Environment team. | The organisations risk management framework. The organisation's resourcing plan(s) and training and competency plan(s). The organisation should be able to demonstrate appropriate linkages between the content of resource plan(s) and training and competency plan(s) to the risk assessments and risk control measures that have been developed. | Bowties, Control Self Assessments | The critical control assessment reviews are used to inform improvement actions and include controls for specialist skills and competency. The major hazard reviews are used to inform investment and contingency planning (including the spares policy). Transpower monitors the external technical and scientific environment and as it changes, for example, changing risks due to climate change, we incorporate that knowledge in our assets impacts. Asset Health and/or Asset Criticality are used to inform investment plans to replace or refurbish assets, and the prioritisation of defects. | 3
28 |  | 82 | Legal and other requirements | What procedure does the organisation have to identify and provide access to its legal, regulatory, statutory and other asset management requirements, and how is requirements incorporated into the asset management system? |  |  | The organisation has not considered the need to identify its legal, regulatory, statutory and other asset management requirements. | The organisation identifies some its legal, regulatory, statutory and other asset management requirements, but this is done in an ad-hoc manner in the absence of a procedure. | The organisation has procedure(s) to identify its legal, regulatory, statutory and other asset management requirements, but the information is not kept up to date, inadequate or inconsistently managed. | Evidence exists to demonstrate that the organisation's legal, regulatory, statutory and other asset management requirements are identified and kept up to date. Systematic mechanisms for identifying relevant legal and statutory requirements. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | In order for an organisation to comply with its legal, regulatory, statutory and other asset management requirements, the organisation first needs to ensure that it knows what they are (eg, PAS 55 specifies this in s 4.4.8). It is necessary to have systematic and auditable mechanisms in place to identify new and changing requirements. Widely used AM standards also require that requirements are incorporated into the asset management system (e.g. procedure(s) and process(es)) | Top management. The organisations regulatory team. The organisation's legal team or advisors. The management team with overall responsibility for the asset management system. The organisation's health and safety team or advisors. The organisation's policy making team. | The organisational processes and procedures for ensuring information of this type is identified, made accessible to those requiring the information and is incorporated into asset management strategy and objectives | Asset Management Policy | Transpower's Asset Management Policy requires compliance with all relevant laws and regulations when undertaking asset management activities. These include compliance with the Health and Safety at Work Act 2015, Commerce Act 1986 (Input Methodologies, Information Disclosures and individual price-quality path), the Electricity Industry Act 2010 (EIPC 2010) and the Resource Management Act 1991. Transpower's asset management processes such as the Decision Framework, Asset Health and MCP Approval have all been developed to be consistent with these requirements. | 3
29 |  | 88 | Life Cycle Activities | How does the organisation establish implement and maintain process(es) for the implementation of its asset management plan(s) and control of activities across the creation, acquisition or enhancement of assets. This includes design, modification, procurement, construction and commissioning activities? |  |  | The organisation does not have process(es) in place to manage and control the implementation of asset management plan(s) during activities related to asset creation including design, modification, procurement, construction and commissioning. | The organisation is aware of the need to have process(es) and procedure(s) in place to manage and control the implementation of asset management plan(s) during activities related to asset creation including design, modification, procurement, construction and commissioning but currently do not have these in place (note: procedure(s) may exist but they are inconsistent/incomplete). | The organisation is in the process of putting in place process(es) and procedure(s) to manage and control the implementation of asset management plan(s) during activities related to asset creation including design, modification, procurement, construction and commissioning. Gaps and inconsistencies are being addressed. | Effective process(es) and procedure(s) are in place to manage and control the implementation of asset management plan(s) during activities related to asset creation including design, modification, procurement, construction and commissioning. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Life cycle activities are about the implementation of asset management plan(s) i.e. they are the "doing" phase. They need to be done effectively and well in order for asset management to have any practical meaning. As a consequence, widely used standards (eg, PAS 55 s 4.5.1) require organisations to have in place appropriate process(es) and procedure(s) for the implementation of asset management plan(s) and control of lifecycle activities. This question explores those aspects relevant to asset creation. | Asset managers, design staff, construction staff and project managers from other impacted areas of the business, e.g. Procurement | Documented process(es) and procedure(s) which are relevant to demonstrating the effective management and control of life cycle activities during asset creation, acquisition, enhancement including design, modification, procurement, construction and commissioning. | Asset Planning Decision Framework, Options Assessment Approach, Works Delivery Frameworks | The asset lifecycle functions are described in Transpower's Asset Management System Framework. The asset planning decision framework and delivery frameworks document these functions in more detail and provide effective management and control of activities during planning decision-making, engineering design, procurement, resource management and the acquisition and commissioning of assets. | 3
30 |  | 91 | Life Cycle Activities | How does the organisation ensure that process(es) and/or procedure(s) for the implementation of asset management plan(s) and control of activities during maintenance (and inspection) of assets are sufficient to ensure activities are carried out under specified conditions, are consistent with asset management strategy and control cost, risk and performance? |  |  | The organisation does not have process(es)/procedure(s) in place to control or manage the implementation of asset management plan(s) during this life cycle phase. | The organisation is aware of the need to have process(es) and procedure(s) in place to manage and control the implementation of asset management plan(s) during this life cycle phase but currently do not have these in place and/or there is no mechanism for confirming they are effective and where needed modifying them. | The organisation is in the process of putting in place process(es) and procedure(s) to manage and control the implementation of asset management plan(s) during this life cycle phase. They include a process for confirming the process(es)/procedure(s) are effective and if necessary carrying out modifications. | The organisation has in place process(es) and procedure(s) to manage and control the implementation of asset management plan(s) during this life cycle phase. They include a process, which is itself regularly reviewed to ensure it is effective, for confirming the process(es)/ procedure(s) are effective and if necessary carrying out modifications. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Having documented process(es) which ensure the asset management plan(s) are implemented in accordance with any specified conditions, in a manner consistent with the asset management policy, strategy and objectives and in such a way that cost, risk and asset system performance are appropriately controlled is critical. They are an essential part of turning intention into action (eg, as required by PAS 55 s 4.5.1). | Asset managers, operations managers, maintenance managers and project managers from other impacted areas of the business | Documented procedure for review. Documented procedure for audit of process delivery. Records of previous audits, improvement actions and documented confirmation that actions have been carried out. | Work Management Manual, Service specifications and Standard Maintenance Procedures | The asset lifecycle functions are described in Transpower's Asset Management System Framework. The work management manual and delivery frameworks document these functions in more detail and provide effective management and control of activities during maintenance decision-making, procurement, resource management, reliability engineering and maintenance delivery. The Work Management Manual outlines the maintenance process from work identification and planning through to delivery of work, commercial control, and continual improvement. Service specifications and Standard Maintenance Procedures detail when and how to perform maintenance activities. | 3
31 |  | 95 | Performance and condition monitoring | How does the organisation measure the performance and condition of its assets? |  |  | The organisation has not considered how to monitor the performance and condition of its assets. | The organisation recognises the need for monitoring asset performance but has not developed a coherent approach. Measures are incomplete, predominantly reactive and lagging. There is no linkage to asset management objectives. | The organisation is developing coherent asset performance monitoring linked to asset management objectives. Reactive and proactive measures are in place. Use is being made of leading indicators and analysis. Gaps and inconsistencies remain. | Consistent asset performance monitoring linked to asset management objectives is in place and universally used including reactive and proactive measures. Data quality management and review process are appropriate. Evidence of leading indicators and analysis. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Widely used AM standards require that organisations establish implement and maintain procedure(s) to monitor and measure the performance and/or condition of assets and asset systems. They further set out requirements in some detail for reactive and proactive monitoring, and leading/lagging performance indicators together with the monitoring or results to provide input to corrective actions and continual improvement. There is an expectation that performance and condition monitoring will provide input to improving asset management strategy, objectives and plan(s). | A broad cross-section of the people involved in the organisation's asset-related activities from data input to decision-makers, i.e. an end-to end assessment. This should include contactors and other relevant third parties as appropriate. | Functional policy and/or strategy documents for performance or condition monitoring and measurement. The organisation's performance monitoring frameworks, balanced scorecards etc. Evidence of the reviews of any appropriate performance indicators and the action lists resulting from these reviews. Reports and trend analysis using performance and condition information. Evidence of the use of performance and condition information shaping improvements and supporting asset management strategy, objectives and plan(s). | Asset Health Framework | Condition: Transpower publishes condition-based asset health internally and to the regulator on an annual basis. The asset health models utilise condition data, are a strong leading indicator for performance and are used as an input into planning decision framework. Performance monitoring: Transpower has service measures on grid performance that are reported monthly and incentivised by the regulator. The data collected for this also provides performance related asset class strategic objectives to be measured. | 3
32 |  | 99 | Investigation of asset-related failures, incidents and nonconformities | How does the organisation ensure responsibility and the authority for the handling, investigation and mitigation of asset-related failures, incidents and emergency situations and non conformances is clear, unambiguous, understood and communicated? |  |  | The organisation has not considered the need to define the appropriate responsibilities and the authorities. | The organisation understands the requirements and is in the process of determining how to define them. | The organisation are in the process of defining the responsibilities and authorities with evidence. Alternatively there are some gaps or inconsistencies in the identified responsibilities/authorities. | The organisation have defined the appropriate responsibilities and authorities and evidence is available to show that these are applied across the business and kept up to date. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Widely used AM standards require that the organisation establishes implements and maintains process(es) for the handling and investigation of failures incidents and non-conformities for assets and sets down a number of expectations. Specifically this question examines the requirement to define clearly responsibilities and authorities for these activities, and communicate these unambiguously to relevant people including external stakeholders if appropriate. | The organisation's safety and environment management team. The team with overall responsibility for the management of the assets. People who have appointed roles within the asset-related investigation procedure, from those who carry out the investigations to senior management who review the recommendations. Operational controllers responsible for managing the asset base under fault conditions and maintaining services to customers. Contractors and other third parties as appropriate. | Process(es) and procedure(s) for the handling, investigation and mitigation of asset-related failures, incidents and emergency situations and non conformances. Documentation of assigned responsibilities and authority to employees. Job Descriptions, Audit reports. Common communication systems i.e. all Job Descriptions on Internet etc. | Operational Event Management Guidelines, Grid Management Operating System (MOS) | Transpower’s grid management operating system (MOS) ensures ongoing evaluation, management review and improvement of asset management activities. Real time operational event management and fault response activities are well managed by grid asset controllers, service delivery managers, and operational engineering teams, with supporting frameworks well embedded for incident, investigation management, and corrective actions to address root cause. Planned maintenance, corrective maintenance, defect management, risk assessment, prioritization, problem, cause, remedy, and application of five whys are in place to prevent, and where required, manage asset failures. Asset performance and reliability is assessed and guidelines for service providers and engineering teams are in place for minimising repeat faults (Root Cause Analysis), and asset feedback is provided to asset portfolio owners as inputs into long term planning and mitigations. | 3
33 |  | 105 | Audit | What has the organisation done to establish procedure(s) for the audit of its asset management system (process(es))? |  |  | The organisation has not recognised the need to establish procedure(s) for the audit of its asset management system. | The organisation understands the need for audit procedure(s) and is determining the appropriate scope, frequency and methodology(s). | The organisation is establishing its audit procedure(s) but they do not yet cover all the appropriate asset-related activities. | The organisation can demonstrate that its audit procedure(s) cover all the appropriate asset-related activities and the associated reporting of audit results. Audits are to an appropriate level of detail and consistently managed. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | This question seeks to explore what the organisation has done to comply with the standard practice AM audit requirements (eg, the associated requirements of PAS 55 s 4.6.4 and its linkages to s 4.7). | The management team responsible for its asset management procedure(s). The team with overall responsibility for the management of the assets. Audit teams, together with key staff responsible for asset management. For example, Asset Management Director, Engineering Director. People with responsibility for carrying out risk assessments | The organisation's asset-related audit procedure(s). The organisation's methodology(s) by which it determined the scope and frequency of the audits and the criteria by which it identified the appropriate audit personnel. Audit schedules, reports etc. Evidence of the procedure(s) by which the audit results are presented, together with any subsequent communications. The risk assessment schedule or risk registers. | Transpower Risk Policy, Transpower Risk Management Guidelines | Transpower utilises the three lines of assurance approach which includes a combination of audits, assessments, self-assessments, and reviews. An annual corporate risk and assurance work plan incorporates third line independent assurance of key corporate and asset management processes. Quality Assurance second line assurance activity is in place and aligned to the Transpower risk and assurance framework and integrates with health and safety assurance activities. Audits involving documented criteria are conducted as part of an annual assurance programme to test and verify that Transpower requirements are being met. Minimum requirements and processes for assurance and self-audit programmes for external providers is in place. Management systems of external providers and selected relevant Transpower business functions involved in asset management lifecycle from design through to disposal are audited biennially. Critical control self-assessment rounds are run biannually to evaluate the effectiveness of key asset management functions and processes. Grid performance metrics are externally audited annually, and regulatory compliance reports provided. | 3
34 |  | 109 | Corrective & Preventative action | How does the organisation instigate appropriate corrective and/or preventive actions to eliminate or prevent the causes of identified poor performance and non conformance? |  |  | The organisation does not recognise the need to have systematic approaches to instigating corrective or preventive actions. | The organisation recognises the need to have systematic approaches to instigating corrective or preventive actions. There is ad-hoc implementation for corrective actions to address failures of assets but not the asset management system. | The need is recognized for systematic instigation of preventive and corrective actions to address root causes of non compliance or incidents identified by investigations, compliance evaluation or audit. It is only partially or inconsistently in place. | Mechanisms are consistently in place and effective for the systematic instigation of preventive and corrective actions to address root causes of non compliance or incidents identified by investigations, compliance evaluation or audit. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Having investigated asset related failures, incidents and non-conformances, and taken action to mitigate their consequences, an organisation is required to implement preventative and corrective actions to address root causes. Incident and failure investigations are only useful if appropriate actions are taken as a result to assess changes to a businesses risk profile and ensure that appropriate arrangements are in place should a recurrence of the incident happen. Widely used AM standards also require that necessary changes arising from preventive or corrective action are made to the asset management system. | The management team responsible for its asset management procedure(s). The team with overall responsibility for the management of the assets. Audit and incident investigation teams. Staff responsible for planning and managing corrective and preventive actions. | Analysis records, meeting notes and minutes, modification records. Asset management plan(s), investigation reports, audit reports, improvement programmes and projects. Recorded changes to asset management procedure(s) and process(es). Condition and performance reviews. Maintenance reviews | National Event Review Group, Reliability Management Strategy | The grid asset management system framework manages day to day operational events and incidents. Event and incident management ensures return to normal operating mode or restoration of service, through application of required actions. Events and incidents are investigated at a level based on incident severity and targets the identification of recommendations to address contributory factors and elimination of root causes. Investigations, poor performance or non-conformance of national significance are elevated to the National Event Review Group (NERG) by regional Event Review Group’s (ERG’s) and control room Operational Review Group (ORG). NERG conducts a management review into findings, contributory factors, and identified root cause(s) and will endorse and formalise corrective actions for management and monitoring. The NERG governs the Transpower problem and investigation management (RESOLVE) Process. A Reliability Advisory Group enables the grid business to realise the benefits of reliability engineering through the implementation of the Reliability Management Strategy, applying a coordinated approach to reliability engineering principles across its asset management functions. For instance, Transpower operational engineering has increased online monitoring of SF6 gas compartments which enables a more proactive response. | 3
35 |  | 113 | Continual Improvement | How does the organisation achieve continual improvement in the optimal combination of costs, asset related risks and the performance and condition of assets and asset systems across the whole life cycle? |  |  | The organisation does not consider continual improvement of these factors to be a requirement, or has not considered the issue. | A Continual Improvement ethos is recognised as beneficial, however it has just been started, and or covers partially the asset drivers. | Continuous improvement process(es) are set out and include consideration of cost risk, performance and condition for assets managed across the whole life cycle but it is not yet being systematically applied. | There is evidence to show that continuous improvement process(es) which include consideration of cost risk, performance and condition for assets managed across the whole life cycle are being systematically applied. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | Widely used AM standards have requirements to establish, implement and maintain process(es)/procedure(s) for identifying, assessing, prioritising and implementing actions to achieve continual improvement. Specifically there is a requirement to demonstrate continual improvement in optimisation of cost risk and performance/condition of assets across the life cycle. This question explores an organisation's capabilities in this area—looking for systematic improvement mechanisms rather that reviews and audit (which are separately examined). | The top management of the organisation. The manager/team responsible for managing the organisation's asset management system, including its continual improvement. Managers responsible for policy development and implementation. | Records showing systematic exploration of improvement. Evidence of new techniques being explored and implemented. Changes in procedure(s) and process(es) reflecting improved use of optimisation tools/techniques and available information. Evidence of working parties and research. | Grid Management Operating System (MOS) | Transpower’s grid management operating system (MOS) ensures ongoing evaluation, management review and improvement of asset management activities. Asset management objectives, delivery progress against the Asset Management Plan and the performance and condition of the assets are monitored, managed and reviewed. Opportunities to improve the asset management system are identified, prioritised, and implemented. | 3
36 |  | 115 | Continual Improvement | How does the organisation seek and acquire knowledge about new asset management related technology and practices, and evaluate their potential benefit to the organisation? |  |  | The organisation makes no attempt to seek knowledge about new asset management related technology or practices. | The organisation is inward looking, however it recognises that asset management is not sector specific and other sectors have developed good practice and new ideas that could apply. Ad-hoc approach. | The organisation has initiated asset management communication within sector to share and, or identify 'new' to sector asset management practices and seeks to evaluate them. | The organisation actively engages internally and externally with other asset management practitioners, professional bodies and relevant conferences. Actively investigates and evaluates new practices and evolves its asset management activities using appropriate developments. | The organisation's process(es) surpass the standard required to comply with requirements set out in a recognised standard. The assessor is advised to note in the Evidence section why this is the case and the evidence seen. | One important aspect of continual improvement is where an organisation looks beyond its existing boundaries and knowledge base to look at what 'new things are on the market'. These new things can include equipment, process(es), tools, etc. An organisation which does this (eg, by the PAS 55 s 4.6 standards) will be able to demonstrate that it continually seeks to expand its knowledge of all things affecting its asset management approach and capabilities. The organisation will be able to demonstrate that it identifies any such opportunities to improve, evaluates them for suitability to its own organisation and implements them as appropriate. This question explores an organisation's approach to this activity. | The top management of the organisation. The manager/team responsible for managing the organisation's asset management system, including its continual improvement. People who monitor the various items that require monitoring for 'change'. People that implement changes to the organisation's policy, strategy, etc. People within an organisation with responsibility for investigating, evaluating, recommending and implementing new tools and techniques, etc. | Research and development projects and records, benchmarking and participation knowledge exchange professional forums. Evidence of correspondence relating to knowledge acquisition. Examples of change implementation and evaluation of new tools, and techniques linked to asset management strategy and objectives. | CIGRE Library EEA Papers Asset Management Council membership ITAMS Benchmarking Study | Transpower acquires knowledge about new asset management related technology and practices by researching international papers and standards to identify benchmarks for asset management practices, as well as sending engineering staff on conferences and forums to gain knowledge of new and innovative asset management techniques and practices. Transpower is a corporate member of the Asset Management Council, with many staff holding memberships, attending webinars and contributing to the operation of the NZ Chapter. Transpower also actively engages in industry discussions with other transmission and networking companies, professional bodies, and regulatory bodies about what comprises the best asset management system, technology, and practices, including participation in an international benchmarking study for Transmission companies (ITAMS). Transpower’s strategies and plans, such as the strategic asset management plan and asset class strategies are periodically reviewed, to incorporate the above. Currently, Transpower is involved or holds a membership with CEATI in North America, CIGRE, Asset Management Council (Australia), EEA, JiCable, Network users’ groups e.g., switchgear users’ group, HVDC users’ group. | 3
37
| Note1 | The question numbers refer to te review clauses in pas 55 assesement methodology

## G8. AMMAT Results
[5 empty] | Transpower | Disclosure Date | 2026-10-23
SCHEDULE G8: AMMAT RESULTS SUMMARY | [5 empty] | Disclosure Year (year ended) | 2026-06-30
ref
5
6 | Question | Function | Score
7 | 3 | Asset management policy | 3
8 | 10 | Asset management strategy | 3
9 | 11 | Asset management strategy | 3
10 | 26 | Asset management plan(s) | 3
11 | 27 | Asset management plan(s) | 3
12 | 29 | Asset management plan(s) | 3
13 | 31 | Asset management plan(s) | 3
14 | 33 | Contingency planning | 3
15 | 37 | Structure, authority and responsibilities | 3
16 | 40 | Structure, authority and responsibilities | 3
17 | 42 | Structure, authority and responsibilities | 3
18 | 45 | Outsourcing of asset management activities | 3
19 | 48 | Training, awareness and competence | 3
20 | 49 | Training, awareness and competence | 3
21 | 50 | Training, awareness and competence | 3
22 | 53 | Communication, participation and consultation | 3
23 | 59 | Asset Management System documentation | 3
24 | 62 | Information management | 3
25 | 63 | Information management | 3
26 | 64 | Information management | 3
27 | 69 | Risk management process(es) | 3
28 | 79 | Use and maintenance of asset risk information | 3
29 | 82 | Legal and other requirements | 3
30 | 88 | Life Cycle Activities | 3
31 | 91 | Life Cycle Activities | 3
32 | 95 | Performance and condition monitoring | 3
33 | 99 | Investigation of asset-related failures, incidents and nonconformities | 3
34 | 105 | Audit | 3
35 | 109 | Corrective & Preventative action | 3
36 | 113 | Continual Improvement | 3
37 | 115 | Continual Improvement | 3
38
39 |  | Overall average score | 3
40
41 | Focus | Assessment Area | Assessment Area Average | Questions
42 | Process | Asset strategy and delivery | 3 | 10, 11, 26, 33, 69, 91 and 109
43 | Process | Documentation, controls and review | 3 | 45, 59, 82, 88, 95, 105 and 113
44 | Process | Systems, integration and information management | 3 | 31, 62, 63 and 64
45 | Process | Communication and participation | 3 | 3, 27, 42 and 53
46 | People | Structure, capability and authority | 3 | 29, 37, 99 and 115
47 | People | Competency and training | 3 | 40, 48, 49, 50 and 79
48
49
50
51
52
53
54
55
56
57
58
59
60
61

## SO1. System Operator
|  |  |  | Transpower |  | Disclosure Date |  | 2026-10-23
SCHEDULE SO1: SYSTEM OPERATOR | [5 empty] | Disclosure Year (year ended) |  | 2026-06-30
ref
5 | SO1(i): Return on Investment
6 | [6 empty] | CY | CY
7 | [6 empty] | ($000) | ($000)
8 |  | Operating surplus/(deficit) |  |  |  |  | 23113617.4487
9 | less | Assets purchased or commissioned |  |  |  |  | 16627441.8719
10 | less | Tax payable |  |  |  |  | 3146298.0432
11 |  | Notional cash flows for the year | [5 empty] | 3339877.5336
12
13 |  | Opening fixed assets | [5 empty] | -36972908.0921
14
15 |  | Closing fixed assets |  |  |  |  | 39215178.1182
16 | plus | Lost assets |  |  |  |  | 0
17 | less | Found assets |  |  |  |  | 0
18 |  | Adjusted closing fixed assets | [5 empty] | 39215178.1182
19
20
21 |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
22 |  | Vanilla ROI |  | 10.96% | 10.3% | 10.09% | 8.448% | 15.78%
23
24 |  | Leverage (%) | ` | 42% | 42% | 42% | 42% | 41%
25 |  | Cost of debt (%) |  | 2.79% | 5.31% | 5.94% | 6.23% | 5.44%
26 |  | Corporate tax rate (%) |  | 28% | 28% | 28% | 28% | 28%
27
28 |  | Post-tax ROI |  | 10.63% | 9.673% | 9.394% | 7.715% | 15.16%
29
30 | SO1(ii): Regulatory Profit
31 |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
32 |  |  |  | ($000) | ($000) | ($000) | ($000) | ($000)
33 |  | Total revenue |  | 41590965.45 | 46454101.75 | 49355603.28 | 50300674.07 | 55736832.01
34
35 | less | Operating expenditure |  | 23122371.3924 | 25690107.234 | 27975450.0197 | 31569482.7198 | 32623214.5613
36
37 |  | Operating surplus/(deficit) |  | 18468594.0576 | 20763994.516 | 21380153.2603 | 18731191.3502 | 23113617.4487
38
39 | less | Total depreciation |  | 12253928.4572 | 14060800.3666 | 14564829.1823 | 12926940.5185 | 14385171.8458
40
41 |  | Regulatory profit/(loss) before tax |  | 6214665.6004 | 6703194.1495 | 6815324.078 | 5804250.8318 | 8728445.6029
42
43 | less | Tax payable |  | 1182820.7676 | 1671588.5127 | 2165300 | 2517854.5388 | 3146298.0432
44
45 |  | Regulatory profit/(loss) after tax |  | 5031844.8328 | 5031605.6368 | 4650024.078 | 3286396.293 | 5582147.5597
46
47 | SO1(iii): Revenue
48 |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
49 |  | Revenue |  | ($000) | ($000) | ($000) | ($000) | ($000)
50 |  | System operator service provider agreement revenue - operating |  | 27162644.04 | 28884630.68 | 30691110.5 | 31305160 | 35654912.35
|  | System operator service provider agreement revenue - capital |  | 13735212 | 16797069.51 | 17857031 | 18121508 | 19159981.31
52 |  | Technical services advisory revenue |  | 693109.41 | 772401.56 | 807461.78 | 874006.07 | 921938.35
53 |  | Other gains /(losses) (provide details)
54 |  | Total revenue |  | 41590965.45 | 46454101.75 | 49355603.28 | 50300674.07 | 55736832.01
55
56 |  |  |  | CY+1 | CY+2 | CY+3 | CY+4 | CY+5
57 |  | Revenue forecast |  | ($000) | ($000) | ($000) | ($000) | ($000)
58 |  | System operator service provider agreement revenue - operating |  | 36341741 | 36883232.5687 | 38093361.3148 | 38660952.3984 | 39237000.5891
59 |  | System operator service provider agreement revenue - capital |  | 20038236.2283 | 17570052.3586 | 20296533.2278 | 20296533.2278 | 20296533.2278
60 |  | Technical services advisory revenue |  | 1004426.04 | 340486.8656 | 345594.1686 | 350778.0811 | 356039.7523
61 |  | Other gains /(losses) (provide details)
62 |  | Total forecast revenue |  | 57384403.2683 | 54793771.7929 | 58735488.7112 | 59308263.7073 | 59889573.5693
63
64 |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
65 |  | Actual vs. forecast |  | ($000) | ($000) | ($000) | ($000) | ($000)
66 |  | Historical forecast revenue |  | 41605327.1785 | 45725705.1703 | 49007369.4837 | 49900000 | 55520772.2559
67 |  | Actual revenue |  | 41590965.45 | 46454101.75 | 49355603.28 | 50300674.07 | 55736832.01
68 |  | Variance ($) |  | 14361.7285 | -728396.5797 | -348233.7963 | -400674.07 | -216059.7541
69 |  | Variance (%) |  | 0.03452% | -1.593% | -0.7106% | -0.803% | -0.3892%
70
71 | SO1(iv): Operating Expenditure
72 |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
73 |  | Operating expenditure |  | ($000) | ($000) | ($000) | ($000) | ($000)
74 |  | Operating Costs |  | 17571503.4853 | 19632397.7569 | 19868533.0981 | 21922013.3498 | 23539344.6444
75 |  | IT Operations |  | 5004667.6871 | 5223221.7371 | 6784151.6016 | 7918589.6899 | 7745747.5869
76 |  | Investigation Expenses |  | 546200.22 | 834487.74 | 1322765.32 | 1728879.68 | 1338122.33
77 |  | [spare line]
78 |  | [spare line]
79 |  | Other opex
80 |  | Total operating expenditure |  | 23122371.3924 | 25690107.234 | 27975450.0197 | 31569482.7198 | 32623214.5613
81 |  | *Insert additional rows and update calculation of totals as needed
82 |  |  |  | CY+1 | CY+2 | CY+3 | CY+4 | CY+5
83 |  | Operating expenditure forecast |  | ($000) | ($000) | ($000) | ($000) | ($000)
84 |  | Operating Costs |  | 25725812.8733 | 26137986.9543 | 26660678.6303 | 27193595.508 | 27737634.9841
85 |  | IT Operations |  | 7570332.151 | 7149098.5153 | 7295512.0529 | 7441422.2939 | 7612054.1071
86 |  | Investigation Expenses |  | 1908013 | 1975793.1002 | 2015308.9622 | 2055615.1415 | 2096727.4443
87 |  | [spare line]
88 |  | [spare line]
89 |  | Other opex
90 |  | Total forecast operating expenditure |  | 35204158.0243 | 35262878.5698 | 35971499.6455 | 36690632.9434 | 37446416.5356
91 |  | *Insert additional rows and update calculation of totals as needed
92 |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
93 |  | Actual vs. forecast operating expenditure |  | ($000) | ($000) | ($000) | ($000) | ($000)
94 |  | Historical forecast operating expenditure |  | 22671947.9047 | 25491613.7738 | 29044368.2283 | 32201612.9489 | 32441792.3916
95 |  | Actual operating expenditure |  | 23122371.3924 | 25690107.234 | 27975450.0197 | 31569482.7198 | 32623214.5613
96 |  | Variance ($) |  | -450423.4877 | -198493.4601 | 1068918.2086 | 632130.2291 | -181422.1697
97 |  | Variance (%) |  | -1.987% | -0.7787% | 3.68% | 1.963% | -0.5592%
98
99
100 | SO1(v): Capital Expenditure: Commissioned capex
101 |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
102 |  | Capital expenditure |  | ($000) | ($000) | ($000) | ($000) | ($000)
103 |  | Buildings and grounds |  | 6639.36 | 391027.3536 | 0 | 1.4552e-11 | 38984.697
104 |  | IT market systems |  | 6089981.5 | 6995709.0063 | 5552200.14 | 5984932.6282 | 16366713.5846
105 |  | IT market changes |  | 7208918.18 | 8087265 | 364421 | 0 | 0
106 |  | Other |  | 2404137 | 1019183.823 | 0 | 1543.7968 | 221743.5903
107
108 |  | Capital Expenditure |  | 15709676.04 | 16493185.1829 | 5916621.14 | 5986476.425 | 16627441.8719
109 |  | *Insert additional rows and update calculation of totals as needed
110 |  |  |  | CY+1 | CY+2 | CY+3 | CY+4 | CY+5
111 |  | Capital expenditure forecast |  | ($000) | ($000) | ($000) | ($000) | ($000)
112 |  | Buildings and grounds |  | 124800 | 6020281.8 | 0 | 0 | 31704.4
113 |  | IT market systems |  | 15877664.36 | 10504422.56 | 21976209.2 | 18498512.74 | 12613634.8
114 |  | IT market changes |  | 1048619 | 3453765 | 0 | 0 | 0
115 |  | Other |  | 1339414.99 | 295726.84 | 308962.06 | 320056.86 | 1865930.78
116
117 |  | Total forecast capital expenditure |  | 18390498.35 | 20274196.2 | 22285171.26 | 18818569.6 | 14511269.98
118 |  | *Insert additional rows and update calculation of totals as needed
119 |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
120 |  | Actual vs. forecast capital expenditure |  | ($000) | ($000) | ($000) | ($000) | ($000)
121 |  | Historical forecast capital expenditure |  | 18216151.9 | 19564292.44 | 10164024.16 | 11124953.87 | 20343323.33
122 |  | Actual capital expenditure |  | 15709676.04 | 16493185.1829 | 5916621.14 | 5986476.425 | 16627441.8719
123 |  | Variance ($) |  | 2506475.86 | 3071107.2571 | 4247403.02 | 5138477.445 | 3715881.4581
124 |  | Variance (%) |  | 13.76% | 15.7% | 41.79% | 46.19% | 18.27%
125
126 | SO1(vi): Fixed Assets: RAB equivalent values
127 |  |  |  | CY-4 | CY-3 | CY-2 | CY-1 | CY
128 |  |  |  | ($000) | ($000) | ($000) | ($000) | ($000)
129 |  | Opening fixed assets |  | 46673447.8287 | 50129195.4115 | 52561580.2279 | 43913372.1856 | 36972908.0921
130 | plus | Found assets
131 | less | Disposed assets
132 | less | Lost assets
133 | plus | Assets purchased or commissioned |  | 15709676.04 | 16493185.1829 | 5916621.14 | 5986476.425 | 16627441.8719
134 | less | Total depreciation |  | 12253928.4572 | 14060800.3666 | 14564829.1823 | 12926940.5185 | 14385171.8458
135 | plus | Adjustment resulting from asset allocation
136 |  | Closing fixed assets |  | 3455747.5828 | 52561580.2279 | 43913372.1856 | 36972908.0921 | 39215178.1182
137
138

## Drop down boxes (hidden)
Drop down boxes and Categories
dd_YesNo
Yes
No
[Select one]
dd_opexsalescapex
Transmission revenues
Insurance and other
Opex
Base capex
Major capex
Other assets (IP, etc)
Assets acquired
Assets disposed
Investments
Debt issue
Loan
[Select one]
Grid R&R
Grid E&D
IST
Business Support
AC Stations
Protection and Metering
HVDC Stations
Transmission Lines
Grid E&D
Transmission Systems
Asset Management Systems
Grid Operations
Telecommunications & Network
Corporate Systems
IST Shared Services
Security Services
Other
Office buildings and facilities
Spares and inventory
Properties